## Budget
MOFARREH MARZOUQ AL-HARBI & PARTNERS CO. LTD.
Baseline Budget Rev. 0 EFFECTIVE BUDGET LEVLE ( 4 )
*Key Legend
|  | Project name: WO# | [19 empty] | Pay Item level |  |  | Project Duration:
|  | Project No.: WO# | [19 empty] | Activity Level |  |  | Notice to proceed date:
|  | Client: | [19 empty] | Resource Level |  |  | Currency: SAR
1e-19
Item Type | BOQ Item No. | BOQ Description | Unit | Original BOQ |  |  |  |  | Effective BOQ | [11 empty] | Cost Code | Resources | [7 empty] | Remaining Budget Breakdown Category
|  |  |  | Original QTY | Original Selling |  | Original Budget |  | QTY |  |  |  |  | Effective Selling |  | Effective Budget | [5 empty] | Res./Act. | Res. Category | Res./Act. Unit | Resource Rate (SR) | Resource Productivity (MH/UNIT) | Res./Act. Budget (SR) | Res./Act. QTY | Total Cost
[5 empty] | Selling Rate | Contract Amount | Budget Rate | Budget Amount | Revised QTY | Effective QTY | Executed QTY upto Dec-25 | Remaining QTY upto Dec-25 | Remaining % | Effective Selling Rate | Effective Contract Amount | Effective Budget Rate | ETC | AC upto Dec-25 | Revised Budget Amount | Actual Rate | [9 empty] | Machinery | Material | Manpower | SC | Total
|  | Total Budget |  | 1 |  | 233776076.7635 |  | 158202758.6881 | [6 empty] | 233776076.7635 |  | 158202758.6881 | 0 | 158202758.6881
|  | Indirect Budget |  | 1 |  | 0 |  | 37202526.9595 | [6 empty] | 0 |  | 37202526.9595 | 0 | 37202526.9595
| IND01 | Indirect Labour Cost | Ea | 1 |  |  | 19627660 | 19627660 | 1 | 1 |  | 1 |  |  |  | 19627660 | 19627660 |  | 19627660
| IND02 | Staff Cars | Ea | 1 |  |  | 2192647 | 2192647 | 1 | 1 |  | 1 |  |  |  | 2192647 | 2192647 |  | 2192647
| IND03 | Fuel for Staff Cars | Ea | 1 |  |  | 593611.5 | 593611.5 | 1 | 1 |  | 1 |  |  |  | 593611.5 | 593611.5 |  | 593611.5
| IND04 | Indirect Equipment Cost | Ea | 1 |  |  | 2736630 | 2736630 | 1 | 1 |  | 1 |  |  |  | 2736630 | 2736630 |  | 2736630
| IND05 | Fuel for Indirect Equip. | Ea | 1 |  |  | 1262384.5 | 1262384.5 | 1 | 1 |  | 1 |  | 0 | 0 | 1262384.5 | 1262384.5 |  | 1262384.5
| IND06 | Camp Cost (Food and Accommodation) | Ea | 1 |  |  | 4174002 | 4174002 | 1 | 1 |  | 1 |  |  |  | 4174002 | 4174002 |  | 4174002
| IND07 | Mobilization | Ea | 1 |  |  | 546000 | 546000 | 1 | 1 |  | 1 |  |  |  | 546000 | 546000 |  | 546000
| IND08 | Demobilization | Ea | 1 |  |  | 54600 | 54600 | 1 | 1 |  | 1 |  |  |  | 54600 | 54600 |  | 54600
| IND09 | General Tools | Ea | 1 |  |  | 108100 | 108100 | 1 | 1 |  | 1 |  |  |  | 108100 | 108100 |  | 108100
| IND10 | Project Running Cost | Ea | 1 |  |  | 519000 | 519000 | 1 | 1 |  | 1 |  |  |  | 519000 | 519000 |  | 519000
| IND11 | Waste Management | Ea | 1 |  |  | 893600 | 893600 | 1 | 1 |  | 1 |  |  |  | 893600 | 893600 |  | 893600
| IND12 | Safety, Medical & Traffic Control | Ea | 1 |  |  | 514091 | 514091 | 1 | 1 |  | 1 |  |  |  | 514091 | 514091 |  | 514091
| IND13 | Lab Testing & Project Services | Ea | 1 |  |  | 288000 | 288000 | 1 | 1 |  | 1 |  |  |  | 288000 | 288000 |  | 288000
| IND14 | Survey Expenses | Ea | 1 |  |  | 50000 | 50000 | 1 | 1 |  | 1 |  |  |  | 50000 | 50000 |  | 50000
| IND15 | Security Expenses | Ea | 1 |  |  | 720000 | 720000 | 1 | 1 |  | 1 |  |  |  | 720000 | 720000 |  | 720000
| IND16 | Design Services | Ea | 1 |  |  | 0 | 0 | 1 | 1 |  | 1 |  |  |  | 0 | 0 |  | 0
| IND17 | Warrantee Period Maintenance Cost | Ea | 1 |  |  | 584440.1919 | 584440.1919 | 1 | 1 |  | 1 |  |  |  | 584440.1919 | 584440.1919 |  | 584440.1919
| IND18 | Program Overhead | Ea | 1 |  |  | 2337760.7676 | 2337760.7676 | 1 | 1 |  | 1 |  |  |  | 2337760.7676 | 2337760.7676 |  | 2337760.7676
|  | Direct Budget |  |  |  | 233776076.7635 |  | 121000231.7286 | [6 empty] | 233776076.7635 |  | 121000231.7286 | 0 | 121000231.7286 | [9 empty] | 121000231.7286 | 219500 | 219500 | 219500 | 219500 | 878000
General items | 1 | Preparing, installing and setting up site offices | sum | 0.1 | 617230 | 61723 | 925000 | 92500 | 0.1 | 0.1 |  | 0.1 | 100% | 617230 | 61723 | 925000 | 92500 |  | 92500 | [7 empty] | 925000 | 0.1 | 92500 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 0.1 | 0.1 |  | 0.1 | [9 empty] | Setting up site offices (Remining Works) |  | LS | 925000 |  | 925000 | 0.1 | 92500 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply and applying Electric connections | SC | LS | 25000 | 0.1 | 250000 | 1 | 25000
[22 empty] | Supply and applying Mechnical connections | SC | LS | 35000 | 0.1 | 350000 | 1 | 35000
[22 empty] | Supply and Apply Plants with the Soil Mix | SC | LS | 10000 | 0.1 | 100000 | 1 | 10000
[22 empty] | Supply AC Unit | Material | LS | 13000 | 0.1 | 130000 | 1 | 13000
[22 empty] | Supply cabines Doors | Material | LS | 6500 | 0.1 | 65000 | 1 | 6500
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.001 | 17000 | 100 | 1700
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.001 | 13000 | 100 | 1300
General items | 2 | Maintaining and maintaining site offices | days | 294 | 2374 | 697956 | 153.0612 | 45000 | 294 | 294 |  | 294 | 100% | 2374 | 697956 | 153.0612 | 45000 |  | 45000 | [7 empty] | 153.0612 | 294 | 45000 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 294 | 294 |  | 294 | [9 empty] | Maintenance of Offices (Remining Works) |  | LS | 153.0612 |  | 153.0612 | 294 | 45000 | 0 | 0 | 0 | 0 | 0
[22 empty] | Maintaining the Offices Floor and slabs | SC | LS | 25000 | 294 | 85.034 | 1 | 25000
[22 empty] | Maintaining the Offices Wall Paints | SC | LS | 11000 | 294 | 37.415 | 1 | 11000
[22 empty] | Supply and apply furnitures | SC | LS | 9000 | 294 | 30.6122 | 1 | 9000
General items | 3 | Soil testing equipment | sum | 0.3 | 12588 | 3776.4 | 94000 | 28200 | 0.3 | 0.3 |  | 0.3 | 100% | 12588 | 3776.4 | 94000 | 28200 |  | 28200 | [7 empty] | 94000 | 0.3 | 28200 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 0.3 | 0.3 |  | 0.3 | [9 empty] | Soil testing equipment |  | LS | 94000 |  | 94000 | 0.3 | 28200 | 0 | 0 | 0 | 0 | 0
[22 empty] | Soil testing equipment | SC | LS | 94000 | 1 | 94000 | 0.3 | 28200
General items | 4 | Asphalt testing equipment | sum | 0.5 | 8812 | 4406 | 112800 | 56400 | 0.5 | 0.5 |  | 0.5 | 100% | 8812 | 4406 | 112800 | 56400 |  | 56400 | [7 empty] | 112800 | 0.5 | 56400 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 0.5 | 0.5 |  | 0.5 | [9 empty] | Asphalt testing equipment |  | LS | 112800 |  | 112800 | 0.5 | 56400 | 0 | 0 | 0 | 0 | 0
[22 empty] | Asphalt testing equipment | SC | LS | 112800 | 1 | 112800 | 0.5 | 56400
General items | 5 | Concrete testing equipment | sum | 0.3 | 10070 | 3021 | 94000 | 28200 | 0.3 | 0.3 |  | 0.3 | 100% | 10070 | 3021 | 94000 | 28200 |  | 28200 | [7 empty] | 94000 | 0.3 | 28200 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 0.3 | 0.3 |  | 0.3 | [9 empty] | Concrete testing equipment |  | LS | 94000 |  | 94000 | 0.3 | 28200 | 0 | 0 | 0 | 0 | 0
[22 empty] | Concrete testing equipment | SC | LS | 94000 | 1 | 94000 | 0.3 | 28200
General items | 6 | Providing four (4) laboratory workers for the duration of the project | sum | 0.3 | 1727084 | 518125.2 | 2000000 | 600000 | 0.3 | 0.3 |  | 0.3 | 100% | 1727084 | 518125.2 | 2000000 | 600000 |  | 600000 | [7 empty] | 2000000 | 0.3 | 600000 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 0.3 | 0.3 |  | 0.3 | [9 empty] | Lab Technicians |  | LS | 2000000 |  | 2000000 | 0.3 | 600000 | 0 | 0 | 0 | 0 | 0
[22 empty] | Hiring Two Technicians with Vechicle | SC | Months | 25000 | 0.0125 | 2000000 | 24 | 600000
General items | 7 | Computers and surveying devices | sum | 0.3 | 314702 | 94410.6 | 100000 | 30000 | 0.3 | 0.3 |  | 0.3 | 100% | 314702 | 94410.6 | 100000 | 30000 |  | 30000 | [7 empty] | 100000 | 0.3 | 30000 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 0.3 | 0.3 |  | 0.3 | [9 empty] | Computers and surveying devices |  | LS | 100000 |  | 100000 | 0.3 | 30000 | 0 | 0 | 0 | 0 | 0
[22 empty] | Computers and surveying devices | SC | LS | 100000 | 1 | 100000 | 0.3 | 30000
Earthworks - Roads
Roads | 8 | Cleaning and removing weeds, trees and roots | m² | 4547.23 | 4 | 18188.92 | 0.46125 | 2097.4262 | 4547.23 | 4547.23 |  | 4547.23 | 100% | 4 | 18188.92 | 0.46125 | 2097.4262 |  | 2097.4262 | [7 empty] | 0.46125 | 4547.23 | 2097.4262 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 4547.23 | 4547.23 |  | 4547.23 | [9 empty] | Site Clearance with disposal |  | M² | 0.46125 |  | 0.46125 | 4547.23 | 2097.4262 | 0 | 0 | 0 | 0 | 0
[22 empty] | Grader | Machinery | HR | 90.4 | 600 | 0.15067 | 7.5787 | 685.116
[22 empty] | Fuel | Material | LTR | 1.76 | 28.5714 | 0.0616 | 159.1531 | 280.1094
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 1224 | 0.053595 | 3.7151 | 243.7078
[22 empty] | Fuel | Material | LTR | 1.76 | 136 | 0.012941 | 33.4355 | 58.8465 | [5 empty] | 122 | 1220
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 408 | 0.11765 | 11.1452 | 534.9682
[22 empty] | Fuel | Material | LTR | 1.76 | 40.8 | 0.043137 | 111.4517 | 196.155
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 600 | 0.021667 | 7.5787 | 98.5233
Roads | 9 | Precast Curbstone type (K1-D) | m | 9616 | 79 | 759664 | 45 | 432720 | 9616 | 9616 |  | 9616 | 100% | 79 | 759664 | 45 | 432720 |  | 432720 | [7 empty] | 45 | 9616 | 432720 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 9616 | 9616 |  | 9616 | [9 empty] | Supply & Install Curbstone |  | M | 45 |  | 45 | 9616 | 432720 | 0 | 0 | 0 | 0 | 0
[22 empty] | Curbstone Supply | Material | LM | 18 | 1 | 18 | 9616 | 173088
[22 empty] | Curbstone Installation | SC | LM | 27 | 1 | 27 | 9616 | 259632
local road |  | Bituminous construction - Local Roads
local road | 1 | Bituminous foundation layer (MC 1) | m² | 142.28 | 5 | 711.4 | 3.45 | 490.866 | 142.28 | 142.28 |  | 142.28 | 100% | 5 | 711.4 | 3.45 | 490.866 |  | 490.866 | [7 empty] | 3.45 | 142.28 | 490.866 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 142.28 | 142.28 |  | 142.28 | [9 empty] | MC1 Works |  | M² | 3.45 |  | 3.45 | 142.28 | 490.866 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply MC1 | Material | Ton | 2450 | 1000 | 2.45 | 0.14228 | 348.586
[22 empty] | Spray MC1 | SC | M² | 1 | 1 | 1 | 142.28 | 142.28
local road | 2 | Bituminous base layer (Grade 1 - Class A) with a thickness of 70 mm after compaction | m³ | 46.3824 | 1007 | 46707.0768 | 585.6 | 27161.5334 | 46.3824 | 46.3824 |  | 46.3824 | 100% | 1007 | 46707.0768 | 585.6 | 27161.5334 |  | 27161.5334 | [7 empty] | 585.6 | 46.3824 | 27161.5334 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 46.3824 | 46.3824 |  | 46.3824 | [9 empty] | Binder Course Works 70 mm |  | M³ | 585.6 |  | 585.6 | 46.3824 | 27161.5334 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Asphalt Binder Course | Material | Ton | 200 | 0.41667 | 480 | 111.3178 | 22263.552
[22 empty] | Asphalt Transportation 0-60 KM | SC | Ton | 19 | 0.41667 | 45.6 | 111.3178 | 2115.0374
[22 empty] | Apply Asphalt Binder Course 7 CM | SC | M² | 4.2 | 0.07 | 60 | 662.6057 | 2782.944
local road | 3 | The upper surface layer of bituminous concrete with a thickness of 50 mm after compaction (Grade 1 - Class A), including the adhesive layer (R.C). | m³ | 72.55 | 1007 | 73057.85 | 802.6889 | 58235.0789 | 72.55 | 72.55 |  | 72.55 | 100% | 1007 | 73057.85 | 802.6889 | 58235.0789 |  | 58235.0789 | [7 empty] | 802.6889 | 72.55 | 58235.0789 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 72.55 | 72.55 |  | 72.55 | [9 empty] | Wearing Course Works 50 mm |  | M³ | 802.6889 |  | 802.6889 | 72.55 | 58235.0789 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply RC2 | Material | Ton | 2550 | 45 | 56.6667 | 1.6122 | 4111.1667
[22 empty] | Asphalt Transportation 0-60 KM | SC | Ton | 19 | 45 | 0.42222 | 1.6122 | 30.6322
[22 empty] | Spray RC2 | SC | M² | 1 | 0.05 | 20 | 1451 | 1451
[22 empty] | Supply bituminous concrete 50 mm | Material | Ton | 250 | 0.41667 | 600 | 174.12 | 43530
[22 empty] | Asphalt Transportation 0-60 KM | SC | Ton | 19 | 0.41667 | 45.6 | 174.12 | 3308.28
[22 empty] | Apply Asphalt Wearing Course 3-5 CM | SC | M² | 4 | 0.05 | 80 | 1451 | 5804
local road |  | Curbstone
local road |  | Precast cold storage works include pouring foundation concrete on site, (concrete base and hunching), cement mortar, reinforcement, excavation, backfilling, compaction, painting, disposal of waste, and completing the work as required in accordance with the standards of the competent authorities, specifications and design plans. | [34 empty] | Original Pay item
local road | 4 | Precast Curbstone type (K1-D) | m | 237.75 | 72 | 17118 | 45 | 10698.75 | 237.75 | 237.75 |  | 237.75 | 100% | 72 | 17118 | 45 | 10698.75 |  | 10698.75 | [7 empty] | 45 | 237.75 | 10698.75 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 237.75 | 237.75 |  | 237.75 | [9 empty] | Supply & Install Curbstone |  | M | 45 |  | 45 | 237.75 | 10698.75 | 0 | 0 | 0 | 0 | 0
[22 empty] | Curbstone Supply | Material | LM | 18 | 1 | 18 | 237.75 | 4279.5
[22 empty] | Curbstone Installation | SC | LM | 27 | 1 | 27 | 237.75 | 6419.25
Manholes and pipework accessories-Telecom 7
Ducts
Terms of services protected by concrete in trenches, including excavation in all types of soil, backfilling, the use of other materials for backfilling, compaction, waste disposal work, concrete works, casting, protective covers, warning tapes, restoring the object to its origin, testing, and all requirements of the various authorities, specifications, and designs.
Telecom 7 | 1 | Expresses (8 outlets), diameter 50 mm | m | 44441.45 | 215 | 9554911.75 | 178.1678 | 7918036.0004 | 44441.45 | 44441.45 |  | 44441.45 | 100% | 215 | 9554911.75 | 178.1678 | 7918036.0004 |  | 7918036.0004 | [7 empty] | 178.1678 | 44441.45 | 7918036.0004 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 44441.45 | 44441.45 |  | 44441.45 | [9 empty] | Excavate & Disposal ( W= 1.7 M * d= 1 ) |  | M | 7.9527 |  | 7.9527 | 44441.45 | 353431.5933 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 58.8235 | 0.952 | 755.5046 | 42308.2604
[22 empty] | Fuel | Material | LTR | 1.76 | 4.2017 | 0.41888 | 10577.0651 | 18615.6346
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 12 | 4 | 3703.4542 | 177765.8
[22 empty] | Fuel | Material | LTR | 1.76 | 1.2 | 1.4667 | 37034.5417 | 65180.7933
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 58.8235 | 0.816 | 755.5046 | 36264.2232
[22 empty] | Fuel | Material | LTR | 1.76 | 5.8824 | 0.2992 | 7555.0465 | 13296.8818
[9 empty] | 44441.45 | 44441.45 |  | 44441.45 | [9 empty] | Duct bank |  | M | 160.34 |  | 160.34 | 44441.45 | 7125742.093 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 3.5714 | 70 | 12443.606 | 3110901.5
[22 empty] | UPVC Pipe 50 mm | Material | M | 4 | 0.125 | 32 | 355531.6 | 1422126.4
[22 empty] | UPVC Fitting 50 mm | Material | M | 2 | 0.125 | 16 | 355531.6 | 711063.2
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 3.5714 | 42 | 12443.606 | 1866540.9
[22 empty] | Skilled Labor | Manpower | HR | 17 | 50 | 0.34 | 888.829 | 15110.093
[9 empty] | 44441.45 | 44441.45 |  | 44441.45 | [9 empty] | Backfilling |  | M | 9.8751 |  | 9.8751 | 44441.45 | 438862.314 | 0 | 0 | 0 | 0 | 0
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 70.4225 | 0.93152 | 631.0686 | 41398.0995
[22 empty] | Fuel | Material | LTR | 1.76 | 7.8247 | 0.22493 | 5679.6173 | 9996.1265
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 14.3662 | 3.3412 | 3093.4735 | 148486.7271
[22 empty] | Fuel | Material | LTR | 1.76 | 1.4366 | 1.2251 | 30934.7348 | 54445.1333
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 35.2113 | 1.0224 | 1262.1372 | 45436.9385
[22 empty] | Fuel | Material | LTR | 1.76 | 3.9124 | 0.44986 | 11359.2346 | 19992.2529
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 42.3529 | 1.1333 | 1049.312 | 50366.9767
[22 empty] | Fuel | Material | LTR | 1.76 | 4.2353 | 0.41556 | 10493.1201 | 18467.8914
[22 empty] | Plate Compactor | Machinery | HR | 23 | 25 | 0.92 | 1777.658 | 40886.134
[22 empty] | Fuel | Material | LTR | 1.76 | 8.3333 | 0.2112 | 5332.974 | 9386.0342
Telecom 7 | 2 | Road crossing ferries (8 exit) | m | 3346.3551 | 435 | 1455664.4902 | 304.7893 | 1019933.3577 | 3346.3551 | 3346.3551 |  | 3346.3551 | 100% | 435 | 1455664.4902 | 304.7893 | 1019933.3577 |  | 1019933.3577 | [7 empty] | 304.7893 | 3346.3551 | 1019933.3577 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 3346.3551 | 3346.3551 |  | 3346.3551 | [9 empty] | Excavate & Disposal ( W= 1.7 M * d= 1 ) |  | M | 8.5743 |  | 8.5743 | 3346.3551 | 28692.5414 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 47.0588 | 1.19 | 71.11 | 3982.1626
[22 empty] | Fuel | Material | LTR | 1.76 | 3.3613 | 0.5236 | 995.5407 | 1752.1516
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 12 | 4 | 278.8629 | 13385.4206
[22 empty] | Fuel | Material | LTR | 1.76 | 1.2 | 1.4667 | 2788.6293 | 4907.9876
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 47.0588 | 1.02 | 71.11 | 3413.2823
[22 empty] | Fuel | Material | LTR | 1.76 | 4.7059 | 0.374 | 711.1005 | 1251.5368
[9 empty] | 3346.3551 | 3346.3551 |  | 3346.3551 | [9 empty] | Duct bank |  | M | 286.34 |  | 286.34 | 3346.3551 | 958195.3337 | 0 | 0 | 0 | 0 | 0
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 3.5714 | 98 | 936.9794 | 327942.8047
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 44.6429 | 56 | 74.9584 | 187395.8884
[22 empty] | UPVC Pipe 50 mm | Material | M | 4 | 0.125 | 32 | 26770.8412 | 107083.3648
[22 empty] | UPVC Fitting 50 mm | Material | M | 2 | 0.125 | 16 | 26770.8412 | 53541.6824
[22 empty] | Trench RC Concrete workmanship | SC | M³ | 300 | 3.5714 | 84 | 936.9794 | 281093.8326
[22 empty] | Skilled Labor | Manpower | HR | 17 | 50 | 0.34 | 66.9271 | 1137.7608
[9 empty] | 3346.3551 | 3346.3551 |  | 3346.3551 | [9 empty] | Backfilling |  | M | 9.8751 |  | 9.8751 | 3346.3551 | 33045.4826 | 0 | 0 | 0 | 0 | 0
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 70.4225 | 0.93152 | 47.5182 | 3117.1967
[22 empty] | Fuel | Material | LTR | 1.76 | 7.8247 | 0.22493 | 427.6642 | 752.689
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 14.3662 | 3.3412 | 232.9326 | 11180.7631
[22 empty] | Fuel | Material | LTR | 1.76 | 1.4366 | 1.2251 | 2329.3256 | 4099.6131
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 35.2113 | 1.0224 | 95.0365 | 3421.3135
[22 empty] | Fuel | Material | LTR | 1.76 | 3.9124 | 0.44986 | 855.3284 | 1505.3779
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 42.3529 | 1.1333 | 79.0112 | 3792.5358
[22 empty] | Fuel | Material | LTR | 1.76 | 4.2353 | 0.41556 | 790.1116 | 1390.5965
[22 empty] | Plate Compactor | Machinery | HR | 23 | 25 | 0.92 | 133.8542 | 3078.6467
[22 empty] | Fuel | Material | LTR | 1.76 | 8.3333 | 0.2112 | 401.5626 | 706.7502
Telecom 7 |  | Street Fiber Cabin Foundations (FDH)
Fiber cabin foundations for streets, including protection columns, earthworks, concrete works, pipe connections, paving, etc., in accordance with the requirements, specifications, and plans of the competent authority (telecommunications companies providing the service must provide fiber cabins)
Telecom 7 |  | SP1 | Unit |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
Telecom 7 |  | Manholes |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
Telecom 7 |  | Communications manholes include excavation, backfilling, waste disposal, dewatering, concrete foundations, walls, supports, formwork, construction works, waterproofing, covers, frames, etc., in accordance with the procedures of the concerned authorities, specifications and plans. |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
Telecom 7 | 3 | Manhole 2000x1000x1000 | nr | 437 | 14980 | 6546260 | 8034.0793 | 3510892.6515 | 437 | 437 |  | 437 | 100% | 14980 | 6546260 | 8034.0793 | 3510892.6515 |  | 3510892.6515 | [7 empty] | 8034.0793 | 437 | 3510892.6515 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 437 | 437 |  | 437 | [9 empty] | Excavate & Disposal (3*2*1.5) |  | Ea | 48.7868 |  | 48.7868 | 437 | 21319.8213 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 8.8889 | 6.3 | 49.1625 | 2753.1
[22 empty] | Fuel | Material | LTR | 1.76 | 0.63492 | 2.772 | 688.275 | 1211.364
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 2.2667 | 21.1765 | 192.7941 | 9254.1176
[22 empty] | Fuel | Material | LTR | 1.76 | 0.22667 | 7.7647 | 1927.9412 | 3393.1765
[22 empty] | Plate Compactor | Machinery | HR | 23 | 8.3333 | 2.76 | 52.44 | 1206.12
[22 empty] | Fuel | Material | LTR | 1.76 | 2.7778 | 0.6336 | 157.32 | 276.8832
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 8.8889 | 5.4 | 49.1625 | 2359.8
[22 empty] | Fuel | Material | LTR | 1.76 | 0.88889 | 1.98 | 491.625 | 865.26
[9 empty] | 437 | 437 |  | 437 | [9 empty] | Plain Concrete 30 cm |  | Ea | 403.2 |  | 403.2 | 437 | 176198.4 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 0.99206 | 252 | 440.496 | 110124
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 0.99206 | 151.2 | 440.496 | 66074.4
[9 empty] | 437 | 437 |  | 437 | [9 empty] | Manhole Installation |  | Ea | 7484 |  | 7484 | 437 | 3270508 | 0 | 0 | 0 | 0 | 0
[22 empty] | Precast Insulated Manhole 2*1*1 | Material | Ea | 7450 | 1 | 7450 | 437 | 3255650
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.5 | 34 | 874 | 14858
[9 empty] | 437 | 437 |  | 437 | [9 empty] | Backfilling 6 M³ & Compaction |  | Ea | 98.0925 |  | 98.0925 | 437 | 42866.4302 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.16667 | 60 | 2622 | 26220
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 16.6667 | 3.936 | 26.22 | 1720.032
[22 empty] | Fuel | Material | LTR | 1.76 | 1.8519 | 0.9504 | 235.98 | 415.3248
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 3.4 | 14.1176 | 128.5294 | 6169.4118
[22 empty] | Fuel | Material | LTR | 1.76 | 0.34 | 5.1765 | 1285.2941 | 2262.1176
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 8.3333 | 4.32 | 52.44 | 1887.84
[22 empty] | Fuel | Material | LTR | 1.76 | 0.92593 | 1.9008 | 471.96 | 830.6496
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 10 | 4.8 | 43.7 | 2097.6
[22 empty] | Fuel | Material | LTR | 1.76 | 1 | 1.76 | 437 | 769.12
[22 empty] | Plate Compactor | Machinery | HR | 23 | 25 | 0.92 | 17.48 | 402.04
[22 empty] | Fuel | Material | LTR | 1.76 | 8.3333 | 0.2112 | 52.44 | 92.2944
PTW8 |  | HDPE pipe, HDPE, PE 100, SDR 11, for (PN 16) rod |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
PTW8 |  | Supply, installation, connection, testing and operation of high-density polyethylene (HDPE) pipes in designated trenches, including excavation, backfilling, compaction, disposal of waste, warning tapes, dewatering and washing in accordance with the procedures of the concerned authority, specifications and plans (backfill work under and around the pipe is measured individually) |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
PTW8 |  | Pipes with an outer diameter of 200 mm at a depth of less than 1.5 m | m | 4087.2533 | 252 | 1029987.8253 | 128.1661 | 523847.1597 | 4087.2533 | 4087.2533 |  | 4087.2533 | 100% | 252 | 1029987.8253 | 128.1661 | 523847.1597 |  | 523847.1597 | [7 empty] | 128.1661 | 4087.2533 | 523847.1597 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 4087.2533 | 4087.2533 |  | 4087.2533 | [9 empty] | Excavation ( W= 1.0 & d= 1.5 ) |  | M | 7.5827 |  | 7.5827 | 4087.2533 | 30992.5356 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 66.6667 | 0.84 | 61.3088 | 3433.2928
[22 empty] | Fuel | Material | LTR | 1.76 | 4.7619 | 0.3696 | 858.3232 | 1510.6488
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 13.6 | 3.5294 | 300.5333 | 14425.5998
[22 empty] | Fuel | Material | LTR | 1.76 | 1.36 | 1.2941 | 3005.3333 | 5289.3866
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 81.7451 | 1880.1365
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 245.2352 | 431.6139
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 66.6667 | 0.72 | 61.3088 | 2942.8224
[22 empty] | Fuel | Material | LTR | 1.76 | 6.6667 | 0.264 | 613.088 | 1079.0349
[9 empty] | 4087.2533 | 4087.2533 |  | 4087.2533 | [9 empty] | Pipe Laying & Protection |  | M | 115.5833 |  | 115.5833 | 4087.2533 | 472418.3577 | 0 | 0 | 0 | 0 | 0
[22 empty] | 200 mm solid HDPE Pipe DR 11 | Material | M | 50 | 1 | 50 | 4087.2533 | 204362.6637
[22 empty] | 200 mm HDPE Pipe Installation | SC | M | 25 | 1 | 25 | 4087.2533 | 102181.3319
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 10 | 25 | 408.7253 | 102181.3319
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 10 | 15 | 408.7253 | 61308.7991
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 13.6242 | 2384.2311
[9 empty] | 4087.2533 | 4087.2533 |  | 4087.2533 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 4087.2533 | 20436.2664 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 4087.2533 | 20436.2664
PTW8 |  | Pipes with an outer diameter of 200 mm at a depth of 1.5 - 2.00 m | m | 173.5416 | 263 | 45641.4474 | 130.5051 | 22648.0681 | 173.5416 | 173.5416 |  | 173.5416 | 100% | 263 | 45641.4474 | 130.5051 | 22648.0681 |  | 22648.0681 | [7 empty] | 130.5051 | 173.5416 | 22648.0681 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 173.5416 | 173.5416 |  | 173.5416 | [9 empty] | Excavation ( W= 1.0 & d= 2.0 ) |  | M | 9.9218 |  | 9.9218 | 173.5416 | 1721.8405 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 50 | 1.12 | 3.4708 | 194.3666
[22 empty] | Fuel | Material | LTR | 1.76 | 3.5714 | 0.4928 | 48.5917 | 85.5213
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 10.2 | 4.7059 | 17.0139 | 816.6665
[22 empty] | Fuel | Material | LTR | 1.76 | 1.02 | 1.7255 | 170.1388 | 299.4444
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 3.4708 | 79.8291
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 10.4125 | 18.326
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 50 | 0.96 | 3.4708 | 166.6
[22 empty] | Fuel | Material | LTR | 1.76 | 5 | 0.352 | 34.7083 | 61.0867
[9 empty] | 173.5416 | 173.5416 |  | 173.5416 | [9 empty] | Pipe Laying & Protection |  | M | 115.5833 |  | 115.5833 | 173.5416 | 20058.5195 | 0 | 0 | 0 | 0 | 0
[22 empty] | 200 mm solid HDPE Pipe DR 11 | Material | M | 50 | 1 | 50 | 173.5416 | 8677.0813
[22 empty] | 200 mm HDPE Pipe Installation | SC | M | 25 | 1 | 25 | 173.5416 | 4338.5406
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 10 | 25 | 17.3542 | 4338.5406
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 10 | 15 | 17.3542 | 2603.1244
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.57847 | 101.2326
[9 empty] | 173.5416 | 173.5416 |  | 173.5416 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 173.5416 | 867.7081 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 173.5416 | 867.7081
PTW8 |  | Pipes with an outer diameter of 200 mm at a depth of 2.0 - 2.5 m | m | 66.7141 | 278 | 18546.5267 | 167.8441 | 11197.5755 | 66.7141 | 66.7141 |  | 66.7141 | 100% | 278 | 18546.5267 | 167.8441 | 11197.5755 |  | 11197.5755 | [7 empty] | 167.8441 | 66.7141 | 11197.5755 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 66.7141 | 66.7141 |  | 66.7141 | [9 empty] | Excavation ( W= 1.0 & d= 2.5 ) |  | M | 47.2608 |  | 47.2608 | 66.7141 | 3152.964 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 40 | 1.4 | 1.6679 | 93.3998
[22 empty] | Fuel | Material | LTR | 1.76 | 2.8571 | 0.616 | 23.3499 | 41.0959
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 8.16 | 5.8824 | 8.1758 | 392.436
[22 empty] | Fuel | Material | LTR | 1.76 | 0.816 | 2.1569 | 81.7575 | 143.8932
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 1.3343 | 30.6885
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 4.0028 | 7.045
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 40 | 1.2 | 1.6679 | 80.0569
[22 empty] | Fuel | Material | LTR | 1.76 | 4 | 0.44 | 16.6785 | 29.3542
[22 empty] | Steel Shoring D=2.5 M | Material | M | 35 | 1 | 35 | 66.7141 | 2334.9944
[9 empty] | 66.7141 | 66.7141 |  | 66.7141 | [9 empty] | Pipe Laying & Protection |  | M | 115.5833 |  | 115.5833 | 66.7141 | 7711.0409 | 0 | 0 | 0 | 0 | 0
[22 empty] | 200 mm solid HDPE Pipe DR 11 | Material | M | 50 | 1 | 50 | 66.7141 | 3335.7062
[22 empty] | 200 mm HDPE Pipe Installation | SC | M | 25 | 1 | 25 | 66.7141 | 1667.8531
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 10 | 25 | 6.6714 | 1667.8531
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 10 | 15 | 6.6714 | 1000.7119
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.22238 | 38.9166
[9 empty] | 66.7141 | 66.7141 |  | 66.7141 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 66.7141 | 333.5706 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 66.7141 | 333.5706
PTW8 |  | Pipes with an outer diameter of 225 mm at a depth of less than 1.5 m | m | 1467.4565 | 277 | 406485.4505 | 156.1661 | 229166.9039 | 1467.4565 | 1467.4565 |  | 1467.4565 | 100% | 277 | 406485.4505 | 156.1661 | 229166.9039 |  | 229166.9039 | [7 empty] | 156.1661 | 1467.4565 | 229166.9039 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 1467.4565 | 1467.4565 |  | 1467.4565 | [9 empty] | Excavation ( W= 1.0 & d= 1.5 ) |  | M | 7.5827 |  | 7.5827 | 1467.4565 | 11127.3256 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 66.6667 | 0.84 | 22.0118 | 1232.6635
[22 empty] | Fuel | Material | LTR | 1.76 | 4.7619 | 0.3696 | 308.1659 | 542.3719
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 13.6 | 3.5294 | 107.9012 | 5179.2582
[22 empty] | Fuel | Material | LTR | 1.76 | 1.36 | 1.2941 | 1079.0121 | 1899.0614
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 29.3491 | 675.03
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 88.0474 | 154.9634
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 66.6667 | 0.72 | 22.0118 | 1056.5687
[22 empty] | Fuel | Material | LTR | 1.76 | 6.6667 | 0.264 | 220.1185 | 387.4085
[9 empty] | 1467.4565 | 1467.4565 |  | 1467.4565 | [9 empty] | Pipe Laying & Protection |  | M | 143.5833 |  | 143.5833 | 1467.4565 | 210702.2958 | 0 | 0 | 0 | 0 | 0
[22 empty] | 225 mm solid HDPE Pipe DR 11 | Material | M | 75 | 1 | 75 | 1467.4565 | 110059.2375
[22 empty] | 225 mm HDPE Pipe Installation | SC | M | 28 | 1 | 28 | 1467.4565 | 41088.782
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 10 | 25 | 146.7457 | 36686.4125
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 10 | 15 | 146.7457 | 22011.8475
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 4.8915 | 856.0163
[9 empty] | 1467.4565 | 1467.4565 |  | 1467.4565 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 1467.4565 | 7337.2825 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 1467.4565 | 7337.2825
PTW8 |  | Pipes with an outer diameter of 225 mm at a depth of 1.5 - 2.00 m | m | 1179.5279 | 290 | 342063.091 | 158.5051 | 186961.1947 | 1179.5279 | 1179.5279 |  | 1179.5279 | 100% | 290 | 342063.091 | 158.5051 | 186961.1947 |  | 186961.1947 | [7 empty] | 158.5051 | 1179.5279 | 186961.1947 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 1179.5279 | 1179.5279 |  | 1179.5279 | [9 empty] | Excavation ( W= 1.0 & d= 2.0 ) |  | M | 9.9218 |  | 9.9218 | 1179.5279 | 11703.0075 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 50 | 1.12 | 23.5906 | 1321.0712
[22 empty] | Fuel | Material | LTR | 1.76 | 3.5714 | 0.4928 | 330.2678 | 581.2713
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 10.2 | 4.7059 | 115.64 | 5550.7195
[22 empty] | Fuel | Material | LTR | 1.76 | 1.02 | 1.7255 | 1156.3999 | 2035.2638
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 23.5906 | 542.5828
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 70.7717 | 124.5581
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 50 | 0.96 | 23.5906 | 1132.3468
[22 empty] | Fuel | Material | LTR | 1.76 | 5 | 0.352 | 235.9056 | 415.1938
[9 empty] | 1179.5279 | 1179.5279 |  | 1179.5279 | [9 empty] | Pipe Laying & Protection |  | M | 143.5833 |  | 143.5833 | 1179.5279 | 169360.5476 | 0 | 0 | 0 | 0 | 0
[22 empty] | 225 mm solid HDPE Pipe DR 11 | Material | M | 75 | 1 | 75 | 1179.5279 | 88464.5925
[22 empty] | 225 mm HDPE Pipe Installation | SC | M | 28 | 1 | 28 | 1179.5279 | 33026.7812
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 10 | 25 | 117.9528 | 29488.1975
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 10 | 15 | 117.9528 | 17692.9185
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 3.9318 | 688.0579
[9 empty] | 1179.5279 | 1179.5279 |  | 1179.5279 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 1179.5279 | 5897.6395 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 1179.5279 | 5897.6395
PTW8 |  | Pipes with an outer diameter of 225 mm at a depth of 2.0 - 2.5 m | m |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
PTW8 |  | Pipes with an outer diameter of 250 mm at a depth of less than 1.5 m | m | 1365.2587 | 307 | 419134.4209 | 178.1661 | 243242.7672 | 1365.2587 | 1365.2587 |  | 1365.2587 | 100% | 307 | 419134.4209 | 178.1661 | 243242.7672 |  | 243242.7672 | [7 empty] | 178.1661 | 1365.2587 | 243242.7672 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 1365.2587 | 1365.2587 |  | 1365.2587 | [9 empty] | Excavation ( W= 1.0 & d= 1.5 ) |  | M | 7.5827 |  | 7.5827 | 1365.2587 | 10352.3873 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 66.6667 | 0.84 | 20.4789 | 1146.8173
[22 empty] | Fuel | Material | LTR | 1.76 | 4.7619 | 0.3696 | 286.7043 | 504.5996
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 13.6 | 3.5294 | 100.3867 | 4818.5601
[22 empty] | Fuel | Material | LTR | 1.76 | 1.36 | 1.2941 | 1003.8667 | 1766.8054
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 27.3052 | 628.019
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 81.9155 | 144.1713
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 66.6667 | 0.72 | 20.4789 | 982.9863
[22 empty] | Fuel | Material | LTR | 1.76 | 6.6667 | 0.264 | 204.7888 | 360.4283
[9 empty] | 1365.2587 | 1365.2587 |  | 1365.2587 | [9 empty] | Pipe Laying & Protection |  | M | 165.5833 |  | 165.5833 | 1365.2587 | 226064.0864 | 0 | 0 | 0 | 0 | 0
[22 empty] | 250 mm solid HDPE Pipe DR 11 | Material | M | 95 | 1 | 95 | 1365.2587 | 129699.5765
[22 empty] | 250 mm HDPE Pipe Installation | SC | M | 30 | 1 | 30 | 1365.2587 | 40957.761
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 10 | 25 | 136.5259 | 34131.4675
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 10 | 15 | 136.5259 | 20478.8805
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 4.5509 | 796.4009
[9 empty] | 1365.2587 | 1365.2587 |  | 1365.2587 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 1365.2587 | 6826.2935 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 1365.2587 | 6826.2935
PTW8 |  | Pipes with an outer diameter of 250 mm at a depth of 1.5 - 2.00 m | m | 333.0246 | 325 | 108232.995 | 180.5051 | 60112.6407 | 333.0246 | 333.0246 |  | 333.0246 | 100% | 325 | 108232.995 | 180.5051 | 60112.6407 |  | 60112.6407 | [7 empty] | 180.5051 | 333.0246 | 60112.6407 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 333.0246 | 333.0246 |  | 333.0246 | [9 empty] | Excavation ( W= 1.0 & d= 2.0 ) |  | M | 9.9218 |  | 9.9218 | 333.0246 | 3304.1943 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 50 | 1.12 | 6.6605 | 372.9876
[22 empty] | Fuel | Material | LTR | 1.76 | 3.5714 | 0.4928 | 93.2469 | 164.1145
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 10.2 | 4.7059 | 32.6495 | 1567.1746
[22 empty] | Fuel | Material | LTR | 1.76 | 1.02 | 1.7255 | 326.4947 | 574.6307
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 6.6605 | 153.1913
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 19.9815 | 35.1674
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 50 | 0.96 | 6.6605 | 319.7036
[22 empty] | Fuel | Material | LTR | 1.76 | 5 | 0.352 | 66.6049 | 117.2247
[9 empty] | 333.0246 | 333.0246 |  | 333.0246 | [9 empty] | Pipe Laying & Protection |  | M | 165.5833 |  | 165.5833 | 333.0246 | 55143.3233 | 0 | 0 | 0 | 0 | 0
[22 empty] | 250 mm solid HDPE Pipe DR 11 | Material | M | 95 | 1 | 95 | 333.0246 | 31637.337
[22 empty] | 250 mm HDPE Pipe Installation | SC | M | 30 | 1 | 30 | 333.0246 | 9990.738
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 10 | 25 | 33.3025 | 8325.615
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 10 | 15 | 33.3025 | 4995.369
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 1.1101 | 194.2643
[9 empty] | 333.0246 | 333.0246 |  | 333.0246 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 333.0246 | 1665.123 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 333.0246 | 1665.123
PTW8 |  | Pipes with an outer diameter of 250 mm at a depth of 2.0 - 2.5 m | m | 65.052 | 344 | 22377.888 | 217.8441 | 14171.1976 | 65.052 | 65.052 |  | 65.052 | 100% | 344 | 22377.888 | 217.8441 | 14171.1976 |  | 14171.1976 | [7 empty] | 217.8441 | 65.052 | 14171.1976 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 65.052 | 65.052 |  | 65.052 | [9 empty] | Excavation ( W= 1.0 & d= 2.5 ) |  | M | 47.2608 |  | 47.2608 | 65.052 | 3074.4106 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 40 | 1.4 | 1.6263 | 91.0728
[22 empty] | Fuel | Material | LTR | 1.76 | 2.8571 | 0.616 | 22.7682 | 40.072
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 8.16 | 5.8824 | 7.9721 | 382.6588
[22 empty] | Fuel | Material | LTR | 1.76 | 0.816 | 2.1569 | 79.7206 | 140.3082
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 1.301 | 29.9239
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 3.9031 | 6.8695
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 40 | 1.2 | 1.6263 | 78.0624
[22 empty] | Fuel | Material | LTR | 1.76 | 4 | 0.44 | 16.263 | 28.6229
[22 empty] | Steel Shoring D=2.5 M | Material | M | 35 | 1 | 35 | 65.052 | 2276.82
[9 empty] | 65.052 | 65.052 |  | 65.052 | [9 empty] | Pipe Laying & Protection |  | M | 165.5833 |  | 165.5833 | 65.052 | 10771.527 | 0 | 0 | 0 | 0 | 0
[22 empty] | 250 mm solid HDPE Pipe DR 11 | Material | M | 95 | 1 | 95 | 65.052 | 6179.94
[22 empty] | 250 mm HDPE Pipe Installation | SC | M | 30 | 1 | 30 | 65.052 | 1951.56
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 10 | 25 | 6.5052 | 1626.3
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 10 | 15 | 6.5052 | 975.78
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.21684 | 37.947
[9 empty] | 65.052 | 65.052 |  | 65.052 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 65.052 | 325.26 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 65.052 | 325.26
PTW8 |  | Pipes with an outer diameter of 355 mm at a depth of 1.5 - 2.00 m | m | 1032.0554 | 1038 | 1071273.4533 | 289.5051 | 298785.2934 | 1032.0554 | 1032.0554 |  | 1032.0554 | 100% | 1038 | 1071273.4533 | 289.5051 | 298785.2934 |  | 298785.2934 | [7 empty] | 289.5051 | 1032.0554 | 298785.2934 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 1032.0554 | 1032.0554 |  | 1032.0554 | [9 empty] | Excavation ( W= 1.0 & d= 2.0 ) |  | M | 9.9218 |  | 9.9218 | 1032.0554 | 10239.8184 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 50 | 1.12 | 20.6411 | 1155.902
[22 empty] | Fuel | Material | LTR | 1.76 | 3.5714 | 0.4928 | 288.9755 | 508.5969
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 10.2 | 4.7059 | 101.1819 | 4856.7311
[22 empty] | Fuel | Material | LTR | 1.76 | 1.02 | 1.7255 | 1011.819 | 1780.8014
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 20.6411 | 474.7455
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 61.9233 | 108.985
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 50 | 0.96 | 20.6411 | 990.7731
[22 empty] | Fuel | Material | LTR | 1.76 | 5 | 0.352 | 206.4111 | 363.2835
[9 empty] | 1032.0554 | 1032.0554 |  | 1032.0554 | [9 empty] | Pipe Laying & Protection |  | M | 274.5833 |  | 274.5833 | 1032.0554 | 283385.1982 | 0 | 0 | 0 | 0 | 0
[22 empty] | 355 mm solid HDPE Pipe DR 11 | Material | M | 190 | 1 | 190 | 1032.0554 | 196090.5165
[22 empty] | 355 mm HDPE Pipe Installation | SC | M | 44 | 1 | 44 | 1032.0554 | 45410.4354
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 10 | 25 | 103.2055 | 25801.3838
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 10 | 15 | 103.2055 | 15480.8303
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 3.4402 | 602.0323
[9 empty] | 1032.0554 | 1032.0554 |  | 1032.0554 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 1032.0554 | 5160.2768 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 1032.0554 | 5160.2768
PTW8 |  | Pipes with an outer diameter of 355 mm at a depth of 2.0 - 2.50 m | m | 154.8347 | 1052 | 162886.157 | 326.8441 | 50606.8321 | 154.8347 | 154.8347 |  | 154.8347 | 100% | 1052 | 162886.157 | 326.8441 | 50606.8321 |  | 50606.8321 | [7 empty] | 326.8441 | 154.8347 | 50606.8321 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 154.8347 | 154.8347 |  | 154.8347 | [9 empty] | Excavation ( W= 1.0 & d= 2.5 ) |  | M | 47.2608 |  | 47.2608 | 154.8347 | 7317.6166 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 40 | 1.4 | 3.8709 | 216.7686
[22 empty] | Fuel | Material | LTR | 1.76 | 2.8571 | 0.616 | 54.1922 | 95.3782
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 8.16 | 5.8824 | 18.9748 | 910.7926
[22 empty] | Fuel | Material | LTR | 1.76 | 0.816 | 2.1569 | 189.7485 | 333.9573
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 3.0967 | 71.224
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 9.2901 | 16.3505
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 40 | 1.2 | 3.8709 | 185.8017
[22 empty] | Fuel | Material | LTR | 1.76 | 4 | 0.44 | 38.7087 | 68.1273
[22 empty] | Steel Shoring D=2.5 M | Material | M | 35 | 1 | 35 | 154.8347 | 5419.2162
[9 empty] | 154.8347 | 154.8347 |  | 154.8347 | [9 empty] | Pipe Laying & Protection |  | M | 274.5833 |  | 274.5833 | 154.8347 | 42515.0418 | 0 | 0 | 0 | 0 | 0
[22 empty] | 355 mm solid HDPE Pipe DR 11 | Material | M | 190 | 1 | 190 | 154.8347 | 29418.6025
[22 empty] | 355 mm HDPE Pipe Installation | SC | M | 44 | 1 | 44 | 154.8347 | 6812.729
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 10 | 25 | 15.4835 | 3870.8687
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 10 | 15 | 15.4835 | 2322.5212
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.51612 | 90.3203
[9 empty] | 154.8347 | 154.8347 |  | 154.8347 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 154.8347 | 774.1737 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 154.8347 | 774.1737
PTW8 |  | Pipes with an outer diameter of 355 mm at a depth of 2.5 - 3.0 m | m | 302.1924 | 1060 | 320323.9705 | 354.1832 | 107031.4777 | 302.1924 | 302.1924 |  | 302.1924 | 100% | 1060 | 320323.9705 | 354.1832 | 107031.4777 |  | 107031.4777 | [7 empty] | 354.1832 | 302.1924 | 107031.4777 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 302.1924 | 302.1924 |  | 302.1924 | [9 empty] | Excavation ( W= 1.0 & d= 3.0 ) |  | M | 74.5999 |  | 74.5999 | 302.1924 | 22543.5122 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 33.3333 | 1.68 | 9.0658 | 507.6833
[22 empty] | Fuel | Material | LTR | 1.76 | 2.381 | 0.7392 | 126.9208 | 223.3806
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 6.8 | 7.0588 | 44.4401 | 2133.123
[22 empty] | Fuel | Material | LTR | 1.76 | 0.68 | 2.5882 | 444.4006 | 782.1451
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 6.0438 | 139.0085
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 18.1315 | 31.9115
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 33.3333 | 1.44 | 9.0658 | 435.1571
[22 empty] | Fuel | Material | LTR | 1.76 | 3.3333 | 0.528 | 90.6577 | 159.5576
[22 empty] | Steel Shoring D>3.0 M | Material | M | 60 | 1 | 60 | 302.1924 | 18131.5455
[9 empty] | 302.1924 | 302.1924 |  | 302.1924 | [9 empty] | Pipe Laying & Protection |  | M | 274.5833 |  | 274.5833 | 302.1924 | 82977.0034 | 0 | 0 | 0 | 0 | 0
[22 empty] | 355 mm solid HDPE Pipe DR 11 | Material | M | 190 | 1 | 190 | 302.1924 | 57416.5608
[22 empty] | 355 mm HDPE Pipe Installation | SC | M | 44 | 1 | 44 | 302.1924 | 13296.4667
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 10 | 25 | 30.2192 | 7554.8106
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 10 | 15 | 30.2192 | 4532.8864
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 1.0073 | 176.2789
[9 empty] | 302.1924 | 302.1924 |  | 302.1924 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 302.1924 | 1510.9621 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 302.1924 | 1510.9621
PTW8 |  | Increased depth difference of 0.5 m for 355 mm diameter pipes | m |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
PTW8 |  | Increased depth difference of 1.0 m for 355 mm diameter pipes | m |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
PTW8 |  | Increased depth difference of 1.5 m for 355 mm diameter pipes | m |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
PTW8 |  | Increased depth difference of 2.0 m for 355 mm diameter pipes | m |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
PTW8 |  | Increased depth difference of 2.5 m for 355 mm diameter pipes | m |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
PTW8 |  | Increased depth difference of 3.0 m for 355 mm diameter pipes | m |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
PTW8 |  | Increased depth difference of 3.5 m for 355 mm diameter pipes | m |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
PTW8 |  | Pipes with an outer diameter of 560 mm at a depth of 1.5 - 2.0 m | m | 435.8991 | 1714 | 747131.0574 | 653.1446 | 284705.127 | 435.8991 | 435.8991 |  | 435.8991 | 100% | 1714 | 747131.0574 | 653.1446 | 284705.127 |  | 284705.127 | [7 empty] | 653.1446 | 435.8991 | 284705.127 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 435.8991 | 435.8991 |  | 435.8991 | [9 empty] | Excavation ( W= 1.56 & d= 2.0 ) |  | M | 15.1612 |  | 15.1612 | 435.8991 | 6608.7662 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 32.0513 | 1.7472 | 13.6001 | 761.6029
[22 empty] | Fuel | Material | LTR | 1.76 | 2.2894 | 0.76877 | 190.4007 | 335.1053
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 6.5385 | 7.3412 | 66.6669 | 3200.0122
[22 empty] | Fuel | Material | LTR | 1.76 | 0.65385 | 2.6918 | 666.6692 | 1173.3378
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 8.718 | 200.5136
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 26.1539 | 46.0309
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 32.0513 | 1.4976 | 13.6001 | 652.8025
[22 empty] | Fuel | Material | LTR | 1.76 | 3.2051 | 0.54912 | 136.0005 | 239.3609
[9 empty] | 435.8991 | 435.8991 |  | 435.8991 | [9 empty] | Pipe Laying & Protection |  | M | 632.9833 |  | 632.9833 | 435.8991 | 275916.8653 | 0 | 0 | 0 | 0 | 0
[22 empty] | 560 mm solid HDPE Pipe DR 11 | Material | M | 510 | 1 | 510 | 435.8991 | 222308.541
[22 empty] | 560 mm HDPE Pipe Installation | SC | M | 60 | 1 | 60 | 435.8991 | 26153.946
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 6.4103 | 39 | 68.0003 | 17000.0649
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 6.4103 | 23.4 | 68.0003 | 10200.0389
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 1.453 | 254.2745
[9 empty] | 435.8991 | 435.8991 |  | 435.8991 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 435.8991 | 2179.4955 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 435.8991 | 2179.4955
PTW8 |  | Pipes with an outer diameter of 560 mm at a depth of 2.0 - 2.50 m | m | 126.0561 | 1777 | 224001.6897 | 691.7935 | 87204.7868 | 126.0561 | 126.0561 |  | 126.0561 | 100% | 1777 | 224001.6897 | 691.7935 | 87204.7868 |  | 87204.7868 | [7 empty] | 691.7935 | 126.0561 | 87204.7868 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 126.0561 | 126.0561 |  | 126.0561 | [9 empty] | Excavation ( W= 1.56 & d= 2.5 ) |  | M | 53.8101 |  | 53.8101 | 126.0561 | 6783.0959 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 25.641 | 2.184 | 4.9162 | 275.3065
[22 empty] | Fuel | Material | LTR | 1.76 | 1.8315 | 0.96096 | 68.8266 | 121.1349
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 5.2308 | 9.1765 | 24.099 | 1156.7501
[22 empty] | Fuel | Material | LTR | 1.76 | 0.52308 | 3.3647 | 240.9896 | 424.1417
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 2.5211 | 57.9858
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 7.5634 | 13.3115
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 25.641 | 1.872 | 4.9162 | 235.977
[22 empty] | Fuel | Material | LTR | 1.76 | 2.5641 | 0.6864 | 49.1619 | 86.5249
[22 empty] | Steel Shoring D=2.5 M | Material | M | 35 | 1 | 35 | 126.0561 | 4411.9635
[9 empty] | 126.0561 | 126.0561 |  | 126.0561 | [9 empty] | Pipe Laying & Protection |  | M | 632.9833 |  | 632.9833 | 126.0561 | 79791.4104 | 0 | 0 | 0 | 0 | 0
[22 empty] | 560 mm solid HDPE Pipe DR 11 | Material | M | 510 | 1 | 510 | 126.0561 | 64288.611
[22 empty] | 560 mm HDPE Pipe Installation | SC | M | 60 | 1 | 60 | 126.0561 | 7563.366
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 6.4103 | 39 | 19.6648 | 4916.1879
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 6.4103 | 23.4 | 19.6648 | 2949.7127
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.42019 | 73.5327
[9 empty] | 126.0561 | 126.0561 |  | 126.0561 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 126.0561 | 630.2805 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 126.0561 | 630.2805
PTW8 |  | Pipes with an outer diameter of 560 mm at a depth of 2.5 - 3.0 m | m | 143.4339 | 1845 | 264635.6377 | 720.4424 | 103335.8959 | 143.4339 | 143.4339 |  | 143.4339 | 100% | 1845 | 264635.6377 | 720.4424 | 103335.8959 |  | 103335.8959 | [7 empty] | 720.4424 | 143.4339 | 103335.8959 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 143.4339 | 143.4339 |  | 143.4339 | [9 empty] | Excavation ( W= 1.56 & d= 3.0 ) |  | M | 82.459 |  | 82.459 | 143.4339 | 11827.4264 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 21.3675 | 2.6208 | 6.7127 | 375.9117
[22 empty] | Fuel | Material | LTR | 1.76 | 1.5263 | 1.1532 | 93.9779 | 165.4011
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 4.359 | 11.0118 | 32.9054 | 1579.4609
[22 empty] | Fuel | Material | LTR | 1.76 | 0.4359 | 4.0376 | 329.0544 | 579.1357
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 2.8687 | 65.9796
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 8.606 | 15.1466
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 21.3675 | 2.2464 | 6.7127 | 322.21
[22 empty] | Fuel | Material | LTR | 1.76 | 2.1368 | 0.82368 | 67.1271 | 118.1437
[22 empty] | Steel Shoring D>3.0 M | Material | M | 60 | 1 | 60 | 143.4339 | 8606.037
[9 empty] | 143.4339 | 143.4339 |  | 143.4339 | [9 empty] | Pipe Laying & Protection |  | M | 632.9833 |  | 632.9833 | 143.4339 | 90791.2998 | 0 | 0 | 0 | 0 | 0
[22 empty] | 560 mm solid HDPE Pipe DR 11 | Material | M | 510 | 1 | 510 | 143.4339 | 73151.3145
[22 empty] | 560 mm HDPE Pipe Installation | SC | M | 60 | 1 | 60 | 143.4339 | 8606.037
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 6.4103 | 39 | 22.3757 | 5593.924
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 6.4103 | 23.4 | 22.3757 | 3356.3544
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.47811 | 83.6698
[9 empty] | 143.4339 | 143.4339 |  | 143.4339 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 143.4339 | 717.1697 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 143.4339 | 717.1697
PTW8 |  | Increased depth difference of 1.0 m for 560 mm diameter pipes | m |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
PTW8 |  | Increased depth difference of 1.5 m for 560 mm diameter pipes | m |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
PTW8 |  | Increased depth difference of 2.0 m for 560 mm diameter pipes | m |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
PTW8 |  | Increased depth difference of 2.5 m for 560 mm diameter pipes | m |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
PTW8 |  | Increased depth difference of 3.0 m for 560 mm diameter pipes | m |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
PTW8 |  | Pipes with an outer diameter of 710 mm at a depth of 2.0 - 2.5 m | m | 577.7726 | 2605 | 1505097.623 | 1471.5478 | 850219.9708 | 577.7726 | 577.7726 |  | 577.7726 | 100% | 2605 | 1505097.623 | 1471.5478 | 850219.9708 |  | 850219.9708 | [7 empty] | 1471.5478 | 577.7726 | 850219.9708 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 577.7726 | 577.7726 |  | 577.7726 | [9 empty] | Excavation ( W= 1.71 & d= 2.5 ) |  | M | 55.5644 |  | 55.5644 | 577.7726 | 32103.5987 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 23.3918 | 2.394 | 24.6998 | 1383.1876
[22 empty] | Fuel | Material | LTR | 1.76 | 1.6708 | 1.0534 | 345.7969 | 608.6025
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 4.7719 | 10.0588 | 121.0773 | 5811.7126
[22 empty] | Fuel | Material | LTR | 1.76 | 0.47719 | 3.6882 | 1210.7735 | 2130.9613
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 11.5555 | 265.7754
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 34.6664 | 61.0128
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 23.3918 | 2.052 | 24.6998 | 1185.5894
[22 empty] | Fuel | Material | LTR | 1.76 | 2.3392 | 0.7524 | 246.9978 | 434.7161
[22 empty] | Steel Shoring D=2.5 M | Material | M | 35 | 1 | 35 | 577.7726 | 20222.041
[9 empty] | 577.7726 | 577.7726 |  | 577.7726 | [9 empty] | Pipe Laying & Protection |  | M | 1410.9833 |  | 1410.9833 | 577.7726 | 815227.5091 | 0 | 0 | 0 | 0 | 0
[22 empty] | 710 mm solid HDPE Pipe DR 11 | Material | M | 1222 | 1 | 1222 | 577.7726 | 706038.1172
[22 empty] | 710 mm HDPE Pipe Installation | SC | M | 120 | 1 | 120 | 577.7726 | 69332.712
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 5.848 | 42.75 | 98.7991 | 24699.7786
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 5.848 | 25.65 | 98.7991 | 14819.8672
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 1.9259 | 337.034
[9 empty] | 577.7726 | 577.7726 |  | 577.7726 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 577.7726 | 2888.863 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 577.7726 | 2888.863
PTW8 |  | Pipes with an outer diameter of 710 mm at a depth of 2.5 - 3.0 m | m | 3.8841 | 2690 | 10448.229 | 1500.5475 | 5828.2766 | 3.8841 | 3.8841 |  | 3.8841 | 100% | 2690 | 10448.229 | 1500.5475 | 5828.2766 |  | 5828.2766 | [7 empty] | 1500.5475 | 3.8841 | 5828.2766 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 3.8841 | 3.8841 |  | 3.8841 | [9 empty] | Excavation ( W= 1.71 & d= 3.0 ) |  | M | 84.5642 |  | 84.5642 | 3.8841 | 328.4557 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 19.4932 | 2.8728 | 0.19925 | 11.1582
[22 empty] | Fuel | Material | LTR | 1.76 | 1.3924 | 1.264 | 2.7896 | 4.9096
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 3.9766 | 12.0706 | 0.97674 | 46.8834
[22 empty] | Fuel | Material | LTR | 1.76 | 0.39766 | 4.4259 | 9.7674 | 17.1906
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 0.077682 | 1.7867
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 0.23305 | 0.41016
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 19.4932 | 2.4624 | 0.19925 | 9.5642
[22 empty] | Fuel | Material | LTR | 1.76 | 1.9493 | 0.90288 | 1.9925 | 3.5069
[22 empty] | Steel Shoring D>3.0 M | Material | M | 60 | 1 | 60 | 3.8841 | 233.046
[9 empty] | 3.8841 | 3.8841 |  | 3.8841 | [9 empty] | Pipe Laying & Protection |  | M | 1410.9833 |  | 1410.9833 | 3.8841 | 5480.4004 | 0 | 0 | 0 | 0 | 0
[22 empty] | 710 mm solid HDPE Pipe DR 11 | Material | M | 1222 | 1 | 1222 | 3.8841 | 4746.3702
[22 empty] | 710 mm HDPE Pipe Installation | SC | M | 120 | 1 | 120 | 3.8841 | 466.092
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 5.848 | 42.75 | 0.66418 | 166.0453
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 5.848 | 25.65 | 0.66418 | 99.6272
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.012947 | 2.2657
[9 empty] | 3.8841 | 3.8841 |  | 3.8841 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 3.8841 | 19.4205 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 3.8841 | 19.4205
PTW8 |  | Pipes with an outer diameter of 710 mm at a depth of 3.5 - 4.0 m | m | 88.4103 | 2777 | 245515.4031 | 1508.547 | 133371.0967 | 88.4103 | 88.4103 |  | 88.4103 | 100% | 2777 | 245515.4031 | 1508.547 | 133371.0967 |  | 133371.0967 | [7 empty] | 1508.547 | 88.4103 | 133371.0967 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 88.4103 | 88.4103 |  | 88.4103 | [9 empty] | Excavation ( W= 1.71 & d= 4.0 ) |  | M | 92.5637 |  | 92.5637 | 88.4103 | 8183.5854 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 14.6199 | 3.8304 | 6.0473 | 338.6468
[22 empty] | Fuel | Material | LTR | 1.76 | 1.0443 | 1.6854 | 84.6617 | 149.0046
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 2.9825 | 16.0941 | 29.6435 | 1422.8858
[22 empty] | Fuel | Material | LTR | 1.76 | 0.29825 | 5.9012 | 296.4345 | 521.7248
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 1.7682 | 40.6687
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 5.3046 | 9.3361
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 14.6199 | 3.2832 | 6.0473 | 290.2687
[22 empty] | Fuel | Material | LTR | 1.76 | 1.462 | 1.2038 | 60.4726 | 106.4319
[22 empty] | Steel Shoring D>3.0 M | Material | M | 60 | 1 | 60 | 88.4103 | 5304.618
[9 empty] | 88.4103 | 88.4103 |  | 88.4103 | [9 empty] | Pipe Laying & Protection |  | M | 1410.9833 |  | 1410.9833 | 88.4103 | 124745.4598 | 0 | 0 | 0 | 0 | 0
[22 empty] | 710 mm solid HDPE Pipe DR 11 | Material | M | 1222 | 1 | 1222 | 88.4103 | 108037.3866
[22 empty] | 710 mm HDPE Pipe Installation | SC | M | 120 | 1 | 120 | 88.4103 | 10609.236
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 5.848 | 42.75 | 15.1182 | 3779.5403
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 5.848 | 25.65 | 15.1182 | 2267.7242
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.2947 | 51.5727
[9 empty] | 88.4103 | 88.4103 |  | 88.4103 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 88.4103 | 442.0515 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 88.4103 | 442.0515
PTW8 |  | Increased depth difference of 1.5 m for 710 mm diameter pipes | m |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
PTW8 |  | Increased depth difference of 2.0 m for 710 mm diameter pipes | m |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
PTW8 |  | Increased depth difference of 2.5 m for 710 mm diameter pipes | m |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
PTW8 |  | Increased depth difference of 3.0 m for 710 mm diameter pipes | m |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
PTW8 |  | Increased depth difference of 3.5 m for 710 mm diameter pipes | m |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
PTW8 |  | Increased depth difference of 4.0 m for 710 mm diameter pipes | m |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
PTW8 |  | Supply and installation of accessories and installation parts for pipes in accordance with the procedures of the concerned authority, specifications and plans |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
PTW8 |  | HDPE High Density Polyethylene Pipe Fittings |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
PTW8 |  | Elbow 45°, diameter 200 mm. | nr | 23.7 | 1391 | 32966.7 | 320 | 7584 | 23.7 | 23.7 |  | 23.7 | 100% | 1391 | 32966.7 | 320 | 7584 |  | 7584 | [7 empty] | 320 | 23.7 | 7584 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 23.7 | 23.7 |  | 23.7 | [9 empty] | Supply & Install fittings |  | Ea | 320 |  | 320 | 23.7 | 7584 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Elbow 45°, diameter 200 mm | Material | Ea | 260 | 1 | 260 | 23.7 | 6162
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.5 | 34 | 47.4 | 805.8
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.5 | 26 | 47.4 | 616.2
PTW8 |  | Elbow 22.5°, diameter 250 mm. | nr | 1.78 | 1546 | 2751.88 | 372 | 662.16 | 1.78 | 1.78 |  | 1.78 | 100% | 1546 | 2751.88 | 372 | 662.16 |  | 662.16 | [7 empty] | 372 | 1.78 | 662.16 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 1.78 | 1.78 |  | 1.78 | [9 empty] | Supply & Install fittings |  | Ea | 372 |  | 372 | 1.78 | 662.16 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Elbow 22.5°, diameter 250 mm | Material | Ea | 312 | 1 | 312 | 1.78 | 555.36
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.5 | 34 | 3.56 | 60.52
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.5 | 26 | 3.56 | 46.28
PTW8 |  | Elbow 45°, diameter 250 mm. | nr | 11.6 | 1554 | 18026.4 | 395.4 | 4586.64 | 11.6 | 11.6 |  | 11.6 | 100% | 1554 | 18026.4 | 395.4 | 4586.64 |  | 4586.64 | [7 empty] | 395.4 | 11.6 | 4586.64 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 11.6 | 11.6 |  | 11.6 | [9 empty] | Supply & Install fittings |  | Ea | 395.4 |  | 395.4 | 11.6 | 4586.64 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Elbow 45°, diameter 250 mm | Material | Ea | 335.4 | 1 | 335.4 | 11.6 | 3890.64
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.5 | 34 | 23.2 | 394.4
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.5 | 26 | 23.2 | 301.6
PTW8 |  | Elbow 45°, diameter 355 mm. | nr | 25 | 1964 | 49100 | 895 | 22375 | 25 | 25 |  | 25 | 100% | 1964 | 49100 | 895 | 22375 |  | 22375 | [7 empty] | 895 | 25 | 22375 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 25 | 25 |  | 25 | [9 empty] | Supply & Install fittings |  | Ea | 895 |  | 895 | 25 | 22375 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Elbow 45°, diameter 355 mm | Material | Ea | 835 | 1 | 835 | 25 | 20875
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.5 | 34 | 50 | 850
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.5 | 26 | 50 | 650
PTW8 |  | 90° elbow, diameter 250 mm. | nr | 1.35 | 1554 | 2097.9 | 415 | 560.25 | 1.35 | 1.35 |  | 1.35 | 100% | 1554 | 2097.9 | 415 | 560.25 |  | 560.25 | [7 empty] | 415 | 1.35 | 560.25 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 1.35 | 1.35 |  | 1.35 | [9 empty] | Supply & Install fittings |  | Ea | 415 |  | 415 | 1.35 | 560.25 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply 90° elbow, diameter 250 mm | Material | Ea | 355 | 1 | 355 | 1.35 | 479.25
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.5 | 34 | 2.7 | 45.9
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.5 | 26 | 2.7 | 35.1
PTW8 |  | 90° elbow, diameter 355 mm. | nr | 1.5 | 1964 | 2946 | 1005.7143 | 1508.5714 | 1.5 | 1.5 |  | 1.5 | 100% | 1964 | 2946 | 1005.7143 | 1508.5714 |  | 1508.5714 | [7 empty] | 1005.7143 | 1.5 | 1508.5714 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 1.5 | 1.5 |  | 1.5 | [9 empty] | Supply & Install fittings |  | Ea | 1005.7143 |  | 1005.7143 | 1.5 | 1508.5714 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply 90° elbow, diameter 355 mm | Material | Ea | 920 | 1 | 920 | 1.5 | 1380
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.35 | 48.5714 | 4.2857 | 72.8571
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.35 | 37.1429 | 4.2857 | 55.7143
PTW8 |  | Elbow 45°, diameter 560 mm. | nr | 5.15 | 3436 | 17695.4 | 2050 | 10557.5 | 5.15 | 5.15 |  | 5.15 | 100% | 3436 | 17695.4 | 2050 | 10557.5 |  | 10557.5 | [7 empty] | 2050 | 5.15 | 10557.5 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 5.15 | 5.15 |  | 5.15 | [9 empty] | Supply & Install fittings |  | Ea | 2050 |  | 2050 | 5.15 | 10557.5 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Elbow 45°, diameter 560 mm | Material | Ea | 1950 | 1 | 1950 | 5.15 | 10042.5
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.3 | 56.6667 | 17.1667 | 291.8333
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.3 | 43.3333 | 17.1667 | 223.1667
PTW8 |  | Elbow 45°, diameter 710 mm. | nr | 4.3375 | 4821 | 20911.0875 | 3622 | 15710.425 | 4.3375 | 4.3375 |  | 4.3375 | 100% | 4821 | 20911.0875 | 3622 | 15710.425 |  | 15710.425 | [7 empty] | 3622 | 4.3375 | 15710.425 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 4.3375 | 4.3375 |  | 4.3375 | [9 empty] | Supply & Install fittings |  | Ea | 3622 |  | 3622 | 4.3375 | 15710.425 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Elbow 45°, diameter 710 mm | Material | Ea | 3472 | 1 | 3472 | 4.3375 | 15059.8
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.2 | 85 | 21.6875 | 368.6875
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.2 | 65 | 21.6875 | 281.9375
PTW8 |  | Elbow 90°, diameter 710 mm. | nr | 0.24 | 4821 | 1157.04 | 4350 | 1044 | 0.24 | 0.24 |  | 0.24 | 100% | 4821 | 1157.04 | 4350 | 1044 |  | 1044 | [7 empty] | 4350 | 0.24 | 1044 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 0.24 | 0.24 |  | 0.24 | [9 empty] | Supply & Install fittings |  | Ea | 4350 |  | 4350 | 0.24 | 1044 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Elbow 90°, diameter 710 mm | Material | Ea | 4200 | 1 | 4200 | 0.24 | 1008
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.2 | 85 | 1.2 | 20.4
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.2 | 65 | 1.2 | 15.6
PTW8 |  | Measurement difference between elbow 22.5, diameter 710 mm and elbow 45, diameter 710 mm | m | 0.35 | 4317 | 1510.95 | 3475 | 1216.25 | 0.35 | 0.35 |  | 0.35 | 100% | 4317 | 1510.95 | 3475 | 1216.25 |  | 1216.25 | [7 empty] | 3475 | 0.35 | 1216.25 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 0.35 | 0.35 |  | 0.35 | [9 empty] | Supply & Install fittings |  | Ea | 3475 |  | 3475 | 0.35 | 1216.25 | 0 | 0 | 0 | 0 | 0
[22 empty] | M diff 710 mm elbow 22.5 & elbow 45 | Material | Ea | 3325 | 1 | 3325 | 0.35 | 1163.75
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.2 | 85 | 1.75 | 29.75
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.2 | 65 | 1.75 | 22.75
PTW8 |  | T-shaped pipes made of high-density polyethylene (HDPE). |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
PTW8 |  | Tee size 200x200x200 mm | nr | 24.925 | 1850 | 46111.25 | 487 | 12138.475 | 24.925 | 24.925 |  | 24.925 | 100% | 1850 | 46111.25 | 487 | 12138.475 |  | 12138.475 | [7 empty] | 487 | 24.925 | 12138.475 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 24.925 | 24.925 |  | 24.925 | [9 empty] | Supply & Install fittings |  | Ea | 487 |  | 487 | 24.925 | 12138.475 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Tee size 200x200x200 mm | Material | Ea | 387 | 1 | 387 | 24.925 | 9645.975
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.3 | 56.6667 | 83.0833 | 1412.4167
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.3 | 43.3333 | 83.0833 | 1080.0833
PTW8 |  | Tee size 225x225x225 mm | nr | 0.9 | 2046 | 1841.4 | 529 | 476.1 | 0.9 | 0.9 |  | 0.9 | 100% | 2046 | 1841.4 | 529 | 476.1 |  | 476.1 | [7 empty] | 529 | 0.9 | 476.1 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 0.9 | 0.9 |  | 0.9 | [9 empty] | Supply & Install fittings |  | Ea | 529 |  | 529 | 0.9 | 476.1 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Tee size 225x225x225 mm | Material | Ea | 429 | 1 | 429 | 0.9 | 386.1
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.3 | 56.6667 | 3 | 51
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.3 | 43.3333 | 3 | 39
PTW8 |  | Tee size 250x250x200 mm | nr | 2.575 | 2242 | 5773.15 | 637 | 1640.275 | 2.575 | 2.575 |  | 2.575 | 100% | 2242 | 5773.15 | 637 | 1640.275 |  | 1640.275 | [7 empty] | 637 | 2.575 | 1640.275 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 2.575 | 2.575 |  | 2.575 | [9 empty] | Supply & Install fittings |  | Ea | 637 |  | 637 | 2.575 | 1640.275 | 0 | 0 | 0 | 0 | 0
[22 empty] | SupplyTee size 250x250x200 mm | Material | Ea | 537 | 1 | 537 | 2.575 | 1382.775
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.3 | 56.6667 | 8.5833 | 145.9167
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.3 | 43.3333 | 8.5833 | 111.5833
PTW8 |  | Tee size 250x250x225 mm | nr | 4.3 | 2462 | 10586.6 | 655 | 2816.5 | 4.3 | 4.3 |  | 4.3 | 100% | 2462 | 10586.6 | 655 | 2816.5 |  | 2816.5 | [7 empty] | 655 | 4.3 | 2816.5 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 4.3 | 4.3 |  | 4.3 | [9 empty] | Supply & Install fittings |  | Ea | 655 |  | 655 | 4.3 | 2816.5 | 0 | 0 | 0 | 0 | 0
[22 empty] | SupplyTee size 250x250x225 mm | Material | Ea | 555 | 1 | 555 | 4.3 | 2386.5
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.3 | 56.6667 | 14.3333 | 243.6667
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.3 | 43.3333 | 14.3333 | 186.3333
PTW8 |  | Tee size 250x250x250 mm | nr | 8.875 | 2700 | 23962.5 | 670 | 5946.25 | 8.875 | 8.875 |  | 8.875 | 100% | 2700 | 23962.5 | 670 | 5946.25 |  | 5946.25 | [7 empty] | 670 | 8.875 | 5946.25 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 8.875 | 8.875 |  | 8.875 | [9 empty] | Supply & Install fittings |  | Ea | 670 |  | 670 | 8.875 | 5946.25 | 0 | 0 | 0 | 0 | 0
[22 empty] | SupplyTee size 250x250x250 mm | Material | Ea | 570 | 1 | 570 | 8.875 | 5058.75
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.3 | 56.6667 | 29.5833 | 502.9167
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.3 | 43.3333 | 29.5833 | 384.5833
PTW8 |  | Tee size 355x355x200 mm | nr | 4.2875 | 2946 | 12630.975 | 1185 | 5080.6875 | 4.2875 | 4.2875 |  | 4.2875 | 100% | 2946 | 12630.975 | 1185 | 5080.6875 |  | 5080.6875 | [7 empty] | 1185 | 4.2875 | 5080.6875 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 4.2875 | 4.2875 |  | 4.2875 | [9 empty] | Supply & Install fittings |  | Ea | 1185 |  | 1185 | 4.2875 | 5080.6875 | 0 | 0 | 0 | 0 | 0
[22 empty] | SupplyTee size 355x355x200 mm | Material | Ea | 1065 | 1 | 1065 | 4.2875 | 4566.1875
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.25 | 68 | 17.15 | 291.55
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.25 | 52 | 17.15 | 222.95
PTW8 |  | Tee size 355x355x225 mm | nr | 2.35 | 3436 | 8074.6 | 1310 | 3078.5 | 2.35 | 2.35 |  | 2.35 | 100% | 3436 | 8074.6 | 1310 | 3078.5 |  | 3078.5 | [7 empty] | 1310 | 2.35 | 3078.5 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 2.35 | 2.35 |  | 2.35 | [9 empty] | Supply & Install fittings |  | Ea | 1310 |  | 1310 | 2.35 | 3078.5 | 0 | 0 | 0 | 0 | 0
[22 empty] | SupplyTee size 355x355x225 mm | Material | Ea | 1190 | 1 | 1190 | 2.35 | 2796.5
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.25 | 68 | 9.4 | 159.8
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.25 | 52 | 9.4 | 122.2
PTW8 |  | Tee size 355x355x250 mm | nr | 0.45 | 3575 | 1608.75 | 1335 | 600.75 | 0.45 | 0.45 |  | 0.45 | 100% | 3575 | 1608.75 | 1335 | 600.75 |  | 600.75 | [7 empty] | 1335 | 0.45 | 600.75 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 0.45 | 0.45 |  | 0.45 | [9 empty] | Supply & Install fittings |  | Ea | 1335 |  | 1335 | 0.45 | 600.75 | 0 | 0 | 0 | 0 | 0
[22 empty] | SupplyTee size 355x355x250 mm | Material | Ea | 1215 | 1 | 1215 | 0.45 | 546.75
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.25 | 68 | 1.8 | 30.6
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.25 | 52 | 1.8 | 23.4
PTW8 |  | Tee size 355x355x355 mm | nr | 13.9 | 3827 | 53195.3 | 1470 | 20433 | 13.9 | 13.9 |  | 13.9 | 100% | 3827 | 53195.3 | 1470 | 20433 |  | 20433 | [7 empty] | 1470 | 13.9 | 20433 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 13.9 | 13.9 |  | 13.9 | [9 empty] | Supply & Install fittings |  | Ea | 1470 |  | 1470 | 13.9 | 20433 | 0 | 0 | 0 | 0 | 0
[22 empty] | SupplyTee size 355x355x355 mm | Material | Ea | 1350 | 1 | 1350 | 13.9 | 18765
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.25 | 68 | 55.6 | 945.2
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.25 | 52 | 55.6 | 722.8
PTW8 |  | Tee size 560x560x250 mm | nr | 0.925 | 4142 | 3831.35 | 2845 | 2631.625 | 0.925 | 0.925 |  | 0.925 | 100% | 4142 | 3831.35 | 2845 | 2631.625 |  | 2631.625 | [7 empty] | 2845 | 0.925 | 2631.625 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 0.925 | 0.925 |  | 0.925 | [9 empty] | Supply & Install fittings |  | Ea | 2845 |  | 2845 | 0.925 | 2631.625 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Tee size 560x560x250 mm | Material | Ea | 2725 | 1 | 2725 | 0.925 | 2520.625
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.25 | 68 | 3.7 | 62.9
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.25 | 52 | 3.7 | 48.1
PTW8 |  | Tee size 560x560x355 mm | nr | 1.4125 | 4456 | 6294.1 | 3320 | 4689.5 | 1.4125 | 1.4125 |  | 1.4125 | 100% | 4456 | 6294.1 | 3320 | 4689.5 |  | 4689.5 | [7 empty] | 3320 | 1.4125 | 4689.5 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 1.4125 | 1.4125 |  | 1.4125 | [9 empty] | Supply & Install fittings |  | Ea | 3320 |  | 3320 | 1.4125 | 4689.5 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Tee size 560x560x355 mm | Material | Ea | 3200 | 1 | 3200 | 1.4125 | 4520
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.25 | 68 | 5.65 | 96.05
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.25 | 52 | 5.65 | 73.45
PTW8 |  | Tee size 560x560x560 mm | nr | 1.5 | 4632 | 6948 | 3670 | 5505 | 1.5 | 1.5 |  | 1.5 | 100% | 4632 | 6948 | 3670 | 5505 |  | 5505 | [7 empty] | 3670 | 1.5 | 5505 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 1.5 | 1.5 |  | 1.5 | [9 empty] | Supply & Install fittings |  | Ea | 3670 |  | 3670 | 1.5 | 5505 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Tee size 560x560x560 mm | Material | Ea | 3550 | 1 | 3550 | 1.5 | 5325
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.25 | 68 | 6 | 102
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.25 | 52 | 6 | 78
PTW8 |  | Tee size 710x710x200 mm | nr | 3.8 | 5010 | 19038 | 4350 | 16530 | 3.8 | 3.8 |  | 3.8 | 100% | 5010 | 19038 | 4350 | 16530 |  | 16530 | [7 empty] | 4350 | 3.8 | 16530 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 3.8 | 3.8 |  | 3.8 | [9 empty] | Supply & Install fittings |  | Ea | 4350 |  | 4350 | 3.8 | 16530 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Tee size 710x710x200 mm | Material | Ea | 4200 | 1 | 4200 | 3.8 | 15960
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.2 | 85 | 19 | 323
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.2 | 65 | 19 | 247
PTW8 |  | Tee size 710x710x250 mm | nr | 0.075 | 5324 | 399.3 | 4800 | 360 | 0.075 | 0.075 |  | 0.075 | 100% | 5324 | 399.3 | 4800 | 360 |  | 360 | [7 empty] | 4800 | 0.075 | 360 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 0.075 | 0.075 |  | 0.075 | [9 empty] | Supply & Install fittings |  | Ea | 4800 |  | 4800 | 0.075 | 360 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Tee size 710x710x250 mm | Material | Ea | 4650 | 1 | 4650 | 0.075 | 348.75
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.2 | 85 | 0.375 | 6.375
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.2 | 65 | 0.375 | 4.875
PTW8 |  | Tee size 710x710x355mm | nr |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
PTW8 |  | Tee size 710x710x560 mm | nr | 0.075 | 6332 | 474.9 | 5250 | 393.75 | 0.075 | 0.075 |  | 0.075 | 100% | 6332 | 474.9 | 5250 | 393.75 |  | 393.75 | [7 empty] | 5250 | 0.075 | 393.75 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 0.075 | 0.075 |  | 0.075 | [9 empty] | Supply & Install fittings |  | Ea | 5250 |  | 5250 | 0.075 | 393.75 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Tee size 710x710x560 mm | Material | Ea | 5100 | 1 | 5100 | 0.075 | 382.5
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.2 | 85 | 0.375 | 6.375
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.2 | 65 | 0.375 | 4.875
PTW8 |  | Tee size 710x710x710 mm | nr | 1.325 | 6976 | 9243.2 | 5650 | 7486.25 | 1.325 | 1.325 |  | 1.325 | 100% | 6976 | 9243.2 | 5650 | 7486.25 |  | 7486.25 | [7 empty] | 5650 | 1.325 | 7486.25 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 1.325 | 1.325 |  | 1.325 | [9 empty] | Supply & Install fittings |  | Ea | 5650 |  | 5650 | 1.325 | 7486.25 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Tee size 710x710x710 mm | Material | Ea | 5500 | 1 | 5500 | 1.325 | 7287.5
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.2 | 85 | 6.625 | 112.625
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.2 | 65 | 6.625 | 86.125
PTW8 |  | Size difference between a tee of 225x225x200 mm and a tee of 200x200x200 | m | 0.998 | 1964 | 1960.072 | 500 | 499 | 0.998 | 0.998 |  | 0.998 | 100% | 1964 | 1960.072 | 500 | 499 |  | 499 | [7 empty] | 500 | 0.998 | 499 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 0.998 | 0.998 |  | 0.998 | [9 empty] | Supply & Install fittings |  | Ea | 500 |  | 500 | 0.998 | 499 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Tee size 225x225x200 mm | Material | Ea | 400 | 1 | 400 | 0.998 | 399.2
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.3 | 56.6667 | 3.3267 | 56.5533
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.3 | 43.3333 | 3.3267 | 43.2467
PTW8 |  | Size difference between a tee of 560x560x200 mm and a tee of 200x200x200 | m | 0.325 | 4582 | 1489.15 | 2845 | 924.625 | 0.325 | 0.325 |  | 0.325 | 100% | 4582 | 1489.15 | 2845 | 924.625 |  | 924.625 | [7 empty] | 2845 | 0.325 | 924.625 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 0.325 | 0.325 |  | 0.325 | [9 empty] | Supply & Install fittings |  | Ea | 2845 |  | 2845 | 0.325 | 924.625 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Tee size 560x560x200 mm | Material | Ea | 2725 | 1 | 2725 | 0.325 | 885.625
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.25 | 68 | 1.3 | 22.1
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.25 | 52 | 1.3 | 16.9
PTW8 |  | Size difference between a tee of 560x560x200 mm and a tee of 225x225x225 | m |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
PTW8 |  | Size difference between a tee of 560x560x200 mm and a tee of 250x250x200 | m |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
PTW8 |  | Size difference between a tee of 560x560x200 mm and a tee of 250x250x225 mm | m |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
PTW8 |  | Size difference between a tee of 560x560x200 mm and a tee of 250x250x250 | m |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
PTW8 |  | Size difference between a tee of 560x560x200 mm and a tee of 355x355x200 mm | m |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
PTW8 |  | Size difference between a tee of 560x560x200 mm and a tee of 355x355x225 mm | m |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
PTW8 |  | Size difference between a tee of 560x560x200 mm and a tee of 355x355x250 mm | m |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
PTW8 |  | Size difference between a tee of 560x560x200 mm and a tee of 355x355x355 mm | m |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
PTW8 |  | Closed tube |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
PTW8 |  | 200 mm closed tube | nr | 104.075 | 598 | 62236.85 | 125 | 13009.375 | 104.075 | 104.075 |  | 104.075 | 100% | 598 | 62236.85 | 125 | 13009.375 |  | 13009.375 | [7 empty] | 125 | 104.075 | 13009.375 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 104.075 | 104.075 |  | 104.075 | [9 empty] | Supply & Install fittings |  | Ea | 125 |  | 125 | 104.075 | 13009.375 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply 200 mm closed tube | Material | Ea | 65 | 1 | 65 | 104.075 | 6764.875
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.5 | 34 | 208.15 | 3538.55
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.5 | 26 | 208.15 | 2705.95
PTW8 |  | Closed tube measuring 225 mm | nr | 19.825 | 657 | 13025.025 | 132 | 2616.9 | 19.825 | 19.825 |  | 19.825 | 100% | 657 | 13025.025 | 132 | 2616.9 |  | 2616.9 | [7 empty] | 132 | 19.825 | 2616.9 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 19.825 | 19.825 |  | 19.825 | [9 empty] | Supply & Install fittings |  | Ea | 132 |  | 132 | 19.825 | 2616.9 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply 225 mm closed tube | Material | Ea | 72 | 1 | 72 | 19.825 | 1427.4
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.5 | 34 | 39.65 | 674.05
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.5 | 26 | 39.65 | 515.45
PTW8 |  | Closed tube measuring 250 mm | nr | 17.3125 | 736 | 12742 | 164 | 2839.25 | 17.3125 | 17.3125 |  | 17.3125 | 100% | 736 | 12742 | 164 | 2839.25 |  | 2839.25 | [7 empty] | 164 | 17.3125 | 2839.25 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 17.3125 | 17.3125 |  | 17.3125 | [9 empty] | Supply & Install fittings |  | Ea | 164 |  | 164 | 17.3125 | 2839.25 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply 250 mm closed tube | Material | Ea | 89 | 1 | 89 | 17.3125 | 1540.8125
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.4 | 42.5 | 43.2812 | 735.7812
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.4 | 32.5 | 43.2812 | 562.6562
PTW8 |  | Closed tube measuring 355 mm | nr | 19.8 | 957 | 18948.6 | 385 | 7623 | 19.8 | 19.8 |  | 19.8 | 100% | 957 | 18948.6 | 385 | 7623 |  | 7623 | [7 empty] | 385 | 19.8 | 7623 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 19.8 | 19.8 |  | 19.8 | [9 empty] | Supply & Install fittings |  | Ea | 385 |  | 385 | 19.8 | 7623 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply 355 mm closed tube | Material | Ea | 310 | 1 | 310 | 19.8 | 6138
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.4 | 42.5 | 49.5 | 841.5
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.4 | 32.5 | 49.5 | 643.5
PTW8 |  | Closed tube measuring 560 mm | m | 8.45 | 1064 | 8990.8 | 895.7143 | 7568.7857 | 8.45 | 8.45 |  | 8.45 | 100% | 1064 | 8990.8 | 895.7143 | 7568.7857 |  | 7568.7857 | [7 empty] | 895.7143 | 8.45 | 7568.7857 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 8.45 | 8.45 |  | 8.45 | [9 empty] | Supply & Install fittings |  | Ea | 895.7143 |  | 895.7143 | 8.45 | 7568.7857 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply 560 mm closed tube | Material | Ea | 810 | 1 | 810 | 8.45 | 6844.5
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.35 | 48.5714 | 24.1429 | 410.4286
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.35 | 37.1429 | 24.1429 | 313.8571
PTW8 |  | Closed tube measuring 710 mm | nr |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
PTW8 |  | Art (J): Pipe works - fittings and valves (continued) |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
PTW8 |  | REDUCER Couplings / Tapers HDPE |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
PTW8 |  | Connector size 200*250 mm | nr | 1.75 | 0 | 0 | 0 | 0 | 1.75 | 1.75 |  | 1.75 | 100% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1.75
PTW8 |  | Connector size 225*250 mm | nr |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
PTW8 |  | Connector size 200*355 mm | nr | 5.275 | 0 | 0 | 0 | 0 | 5.275 | 5.275 |  | 5.275 | 100% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 5.275
PTW8 |  | Connector size 250*355 mm | nr | 4.35 | 0 | 0 | 0 | 0 | 4.35 | 4.35 |  | 4.35 | 100% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 4.35
PTW8 |  | Connector size 250*560 mm | nr | 0.8 | 0 | 0 | 0 | 0 | 0.8 | 0.8 |  | 0.8 | 100% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 0.8
PTW8 |  | Connector size 355*560 mm | nr | 0.425 | 0 | 0 | 0 | 0 | 0.425 | 0.425 |  | 0.425 | 100% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 0.425
PTW8 |  | Connector size 200*710 mm | nr | 1.65 | 0 | 0 | 0 | 0 | 1.65 | 1.65 |  | 1.65 | 100% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1.65
PTW8 |  | Connector size 355*710 mm | nr | 0.6 | 0 | 0 | 0 | 0 | 0.6 | 0.6 |  | 0.6 | 100% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 0.6
PTW8 |  | Connector size 560*710 mm | nr | 1.675 | 0 | 0 | 0 | 0 | 1.675 | 1.675 |  | 1.675 | 100% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1.675
PTW8 |  | Valves |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
PTW8 |  | Valves: Supply, installation, and testing of valves, including collars, flange connections, flange rates, and spacers, in addition to bolts, nuts, and all the work required for pipes inside the room, along with all accessories (columns) and ribbed bolts, according to the specifications and the required standards. |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
PTW8 |  | Gate Valves (Water Control Valve) Gate Valve |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
PTW8 |  | Shut-off valve on 200mm pipe | nr | 72.5 | 2946 | 213585 | 1544.8 | 111998 | 72.5 | 72.5 |  | 72.5 | 100% | 2946 | 213585 | 1544.8 | 111998 |  | 111998 | [7 empty] | 1544.8 | 72.5 | 111998 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 72.5 | 72.5 |  | 72.5 | [9 empty] | Supply & Install Valves |  | Ea | 1544.8 |  | 1544.8 | 72.5 | 111998 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Gate Valve 200 mm | Material | Ea | 1268 | 1 | 1268 | 72.5 | 91930
[22 empty] | Fitting and Accessories 200 | Material | Ea | 126.8 | 1 | 126.8 | 72.5 | 9193
[22 empty] | Installation Valve 200mm | SC | Ea | 150 | 1 | 150 | 72.5 | 10875
PTW8 |  | Shut-off valve on 225mm pipe | nr | 15.9 | 3390 | 53901 | 1857.2 | 29529.48 | 15.9 | 15.9 |  | 15.9 | 100% | 3390 | 53901 | 1857.2 | 29529.48 |  | 29529.48 | [7 empty] | 1857.2 | 15.9 | 29529.48 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 15.9 | 15.9 |  | 15.9 | [9 empty] | Supply & Install Valves |  | Ea | 1857.2 |  | 1857.2 | 15.9 | 29529.48 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Gate Valve 225 mm | Material | Ea | 1552 | 1 | 1552 | 15.9 | 24676.8
[22 empty] | Fitting and Accessories 225 | Material | Ea | 155.2 | 1 | 155.2 | 15.9 | 2467.68
[22 empty] | Installation Valve 225mm | SC | Ea | 150 | 1 | 150 | 15.9 | 2385
PTW8 |  | Shut-off valve on 250mm pipe | nr | 38.3 | 3792 | 145233.6 | 2020 | 77366 | 38.3 | 38.3 |  | 38.3 | 100% | 3792 | 145233.6 | 2020 | 77366 |  | 77366 | [7 empty] | 2020 | 38.3 | 77366 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 38.3 | 38.3 |  | 38.3 | [9 empty] | Supply & Install Valves |  | Ea | 2020 |  | 2020 | 38.3 | 77366 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Gate Valve 250 MM | Material | Ea | 1700 | 1 | 1700 | 38.3 | 65110
[22 empty] | Fitting and Accessories 250 | Material | Ea | 170 | 1 | 170 | 38.3 | 6511
[22 empty] | Installation Valve 250mm | SC | Ea | 150 | 1 | 150 | 38.3 | 5745
PTW8 |  | Butterfly Valves Water Control Valve |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
PTW8 |  | Shut-off valve on 355mm pipe | nr | 50.3 | 6218 | 312765.4 | 5205 | 261811.5 | 50.3 | 50.3 |  | 50.3 | 100% | 6218 | 312765.4 | 5205 | 261811.5 |  | 261811.5 | [7 empty] | 5205 | 50.3 | 261811.5 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 50.3 | 50.3 |  | 50.3 | [9 empty] | Supply & Install Valves |  | Ea | 5205 |  | 5205 | 50.3 | 261811.5 | 0 | 0 | 0 | 0 | 0
[22 empty] | Butterfly Valve for 355mm | Material | Ea | 4550 | 1 | 4550 | 50.3 | 228865
[22 empty] | Fitting and Accessories 355 | Material | Ea | 455 | 1 | 455 | 50.3 | 22886.5
[22 empty] | Installation Valve 355mm | SC | Ea | 200 | 1 | 200 | 50.3 | 10060
PTW8 |  | Shut-off valve on 560mm pipe | nr | 20 | 9328 | 186560 | 9325 | 186500 | 20 | 20 |  | 20 | 100% | 9328 | 186560 | 9325 | 186500 |  | 186500 | [7 empty] | 9325 | 20 | 186500 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 20 | 20 |  | 20 | [9 empty] | Supply & Install Valves |  | Ea | 9325 |  | 9325 | 20 | 186500 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Butterfly Valve 560 MM | Material | Ea | 8250 | 1 | 8250 | 20 | 165000
[22 empty] | Fitting and Accessories 560 | Material | Ea | 825 | 1 | 825 | 20 | 16500
[22 empty] | Installation Valve 560mm | SC | Ea | 250 | 1 | 250 | 20 | 5000
PTW8 |  | Shut-off valve on 710mm pipe | nr | 14.8 | 12273 | 181640.4 | 11675 | 172790 | 14.8 | 14.8 |  | 14.8 | 100% | 12273 | 181640.4 | 11675 | 172790 |  | 172790 | [7 empty] | 11675 | 14.8 | 172790 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 14.8 | 14.8 |  | 14.8 | [9 empty] | Supply & Install Valves |  | Ea | 11675 |  | 11675 | 14.8 | 172790 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Butterfly Valve 710 MM | Material | Ea | 10250 | 1 | 10250 | 14.8 | 151700
[22 empty] | Fitting and Accessories 710 | Material | Ea | 1025 | 1 | 1025 | 14.8 | 15170
[22 empty] | Installation Valve 710mm | SC | Ea | 400 | 1 | 400 | 14.8 | 5920
PTW8 |  | Wash-out chambers (cleaning valve). |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
PTW8 |  | Shut-off valve on 200mm pipe | nr |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
PTW8 |  | Shut-off valve on 355mm pipe | nr |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
PTW8 |  | Shut-off valve on 560mm pipe | nr |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
PTW8 |  | Shut-off valve on 710mm pipe | nr |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
PTW8 |  | Air valves |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
PTW8 |  | Shut-off valve on 200mm pipe | nr |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
PTW8 |  | Shut-off valve on 225mm pipe | nr |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
PTW8 |  | Shut-off valve on 250mm pipe | nr |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
PTW8 |  | Shut-off valve on 355mm pipe | nr |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
PTW8 |  | Shut-off valve on 560mm pipe | nr |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
PTW8 |  | Shut-off valve on 710mm pipe | nr |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
PTW8 |  | Art (J): Pipe works - fittings and valves (continued) |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
PTW8 |  | Fire nozzles |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
PTW8 |  | Supply and installation of fire nozzles, including covers, foundations, concrete pouring works, reinforcement, supports, restoration of formwork and iron columns, construction work, finishing works, pipe work, valves, installation parts up to the point of connections, valve accessories, protection barriers, and complete necessary installations in accordance with the plans, specifications, and standards of the designated agencies. |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
PTW8 |  | 3-outlet fire nozzle (two 2.5-inch outlets and one 4-inch outlet) in the form of a detachable dry vacuum cylinder | nr | 108.2 | 13847 | 1498245.4 | 8531 | 923054.2 | 108.2 | 108.2 |  | 108.2 | 100% | 13847 | 1498245.4 | 8531 | 923054.2 |  | 923054.2 | [7 empty] | 8531 | 108.2 | 923054.2 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 108.2 | 108.2 |  | 108.2 | [9 empty] | Fire nozzles |  | Ea | 8531 |  | 8531 | 108.2 | 923054.2 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply & Install 3-outlet fire nozzle | SC | LS | 8531 | 1 | 8531 | 108.2 | 923054.2
PTW8 |  | On a pipeline with a diameter of 200 mm, and at a depth of 1.5-2.0 metres | nr |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
PTW8 |  | On a pipeline with a diameter of 250 mm, and at a depth of 1.5-2.0 metres | nr |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
PTW8 |  | On a pipeline with a diameter of 250 mm, and at a depth of 1.5-2.0 metres | nr |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
PTW8 |  | Category (k): Pipe works - Valve rooms: On-site gate valve isolation rooms made of reinforced concrete on the pipeline as specified on the plans, and all that is required of excavation, equipment, and construction supplies, cutting and installing pipe pieces and backfills, and all of this must be accomplished according to the plans and specifications. |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
PTW8 |  | Rooms according to standard specifications |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
PTW8 |  | On a pipeline with a diameter of 355 mm, and at a depth of 2-2.5 metres | nr | 47.6225 | 19197 | 914209.1325 | 12286.1796 | 585098.5869 | 47.6225 | 47.6225 |  | 47.6225 | 100% | 19197 | 914209.1325 | 12286.1796 | 585098.5869 |  | 585098.5869 | [7 empty] | 12286.1796 | 47.6225 | 585098.5869 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 47.6225 | 47.6225 |  | 47.6225 | [9 empty] | Excavate & Disposal (3*3*2.5) |  | Ea | 90.4969 |  | 90.4969 | 47.6225 | 4309.6906 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 4.4444 | 12.6 | 10.7151 | 600.0435
[22 empty] | Fuel | Material | LTR | 1.76 | 0.31746 | 5.544 | 150.0109 | 264.0191
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.90667 | 52.9412 | 52.5248 | 2521.1912
[22 empty] | Fuel | Material | LTR | 1.76 | 0.090667 | 19.4118 | 525.2482 | 924.4368
[9 empty] | 47.6225 | 47.6225 |  | 47.6225 | [9 empty] | Valve Room Installation |  | Ea | 9186.6 |  | 9186.6 | 47.6225 | 437488.8585 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 1.1111 | 225 | 42.8603 | 10715.0625
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.2 | 1750 | 238.1125 | 83339.375
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 2.5 | 1000 | 19.049 | 47622.5
[22 empty] | Workmanship plain concrete | SC | M³ | 150 | 1.1111 | 135 | 42.8603 | 6429.0375
[22 empty] | Workmanship RC concrete | SC | M³ | 450 | 0.2 | 2250 | 238.1125 | 107150.625
[22 empty] | Supply & apply Chamber Cover, frames | Material | Ea | 3500 | 1 | 3500 | 47.6225 | 166678.75
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 4 | 20 | 11.9056 | 952.45
[22 empty] | Fuel | Material | HR | 1.76 | 0.26667 | 6.6 | 178.5844 | 314.3085
[22 empty] | Chamber Pipes Pieces | Material | LS | 150 | 1 | 150 | 47.6225 | 7143.375
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.2 | 85 | 238.1125 | 4047.9125
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.2 | 65 | 238.1125 | 3095.4625
[9 empty] | 47.6225 | 47.6225 |  | 47.6225 | [9 empty] | Internal and external Insulation |  | Ea | 2800 |  | 2800 | 47.6225 | 133343 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply & apply external waterproofing | SC | M² | 40 | 0.025 | 1600 | 1904.9 | 76196
[22 empty] | Supply & apply internal coating | SC | M² | 30 | 0.025 | 1200 | 1904.9 | 57147
[9 empty] | 47.6225 | 47.6225 |  | 47.6225 | [9 empty] | Backfilling |  | Ea | 209.0826 |  | 209.0826 | 47.6225 | 9957.0378 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.083333 | 120 | 571.47 | 5714.7
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 8.3333 | 7.872 | 5.7147 | 374.8843
[22 empty] | Fuel | Material | LTR | 1.76 | 0.92593 | 1.9008 | 51.4323 | 90.5208
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 1.7 | 28.2353 | 28.0132 | 1344.6353
[22 empty] | Fuel | Material | LTR | 1.76 | 0.17 | 10.3529 | 280.1324 | 493.0329
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 4.1667 | 8.64 | 11.4294 | 411.4584
[22 empty] | Fuel | Material | LTR | 1.76 | 0.46296 | 3.8016 | 102.8646 | 181.0417
[22 empty] | Plate Compactor | Machinery | HR | 23 | 1 | 23 | 47.6225 | 1095.3175
[22 empty] | Fuel | Material | LTR | 1.76 | 0.33333 | 5.28 | 142.8675 | 251.4468
PTW8 |  | 0.5 m depth difference on a 355 mm diameter pipe line | nr | 4.945 | 9063 | 44816.535 | 2172.8366 | 10744.677 | 4.945 | 4.945 |  | 4.945 | 100% | 9063 | 44816.535 | 2172.8366 | 10744.677 |  | 10744.677 | [7 empty] | 2172.8366 | 4.945 | 10744.677 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 4.945 | 4.945 |  | 4.945 | [9 empty] | Excavate & Disposal (3*3*0.5) |  | Ea | 18.0994 |  | 18.0994 | 4.945 | 89.5015 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 22.2222 | 2.52 | 0.22253 | 12.4614
[22 empty] | Fuel | Material | LTR | 1.76 | 1.5873 | 1.1088 | 3.1154 | 5.483
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 4.5333 | 10.5882 | 1.0908 | 52.3588
[22 empty] | Fuel | Material | LTR | 1.76 | 0.45333 | 3.8824 | 10.9081 | 19.1982
[9 empty] | 4.945 | 4.945 |  | 4.945 | [9 empty] | Valve Room Installation |  | Ea | 1550 |  | 1550 | 4.945 | 7664.75 | 0 | 0 | 0 | 0 | 0
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 1 | 350 | 4.945 | 1730.75
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 12.5 | 200 | 0.3956 | 989
[22 empty] | Workmanship RC concrete | SC | M³ | 450 | 1 | 450 | 4.945 | 2225.25
[22 empty] | Supply and apply chamber ladder | Material | Ea | 400 | 1 | 400 | 4.945 | 1978
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.2 | 85 | 24.725 | 420.325
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.2 | 65 | 24.725 | 321.425
[9 empty] | 4.945 | 4.945 |  | 4.945 | [9 empty] | Internal and external Insulation |  | Ea | 560 |  | 560 | 4.945 | 2769.2 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply & apply external waterproofing | SC | M² | 40 | 0.125 | 320 | 39.56 | 1582.4
[22 empty] | Supply & apply internal coating | SC | M² | 30 | 0.125 | 240 | 39.56 | 1186.8
[9 empty] | 4.945 | 4.945 |  | 4.945 | [9 empty] | Backfilling |  | Ea | 44.7372 |  | 44.7372 | 4.945 | 221.2255 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.4 | 25 | 12.3625 | 123.625
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 40 | 1.64 | 0.12363 | 8.1098
[22 empty] | Fuel | Material | LTR | 1.76 | 4.4444 | 0.396 | 1.1126 | 1.9582
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 8.16 | 5.8824 | 0.606 | 29.0882
[22 empty] | Fuel | Material | LTR | 1.76 | 0.816 | 2.1569 | 6.06 | 10.6657
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 20 | 1.8 | 0.24725 | 8.901
[22 empty] | Fuel | Material | LTR | 1.76 | 2.2222 | 0.792 | 2.2252 | 3.9164
[22 empty] | Plate Compactor | Machinery | HR | 23 | 4 | 5.75 | 1.2363 | 28.4338
[22 empty] | Fuel | Material | LTR | 1.76 | 1.3333 | 1.32 | 3.7088 | 6.5274
PTW8 |  | 1.0 m depth difference on a 355 mm diameter pipe line | nr | 1.87 | 9819 | 18361.53 | 4195.6732 | 7845.9089 | 1.87 | 1.87 |  | 1.87 | 100% | 9819 | 18361.53 | 4195.6732 | 7845.9089 |  | 7845.9089 | [7 empty] | 4195.6732 | 1.87 | 7845.9089 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 1.87 | 1.87 |  | 1.87 | [9 empty] | Excavate & Disposal (3*3*1.0) |  | Ea | 36.1988 |  | 36.1988 | 1.87 | 67.6917 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 11.1111 | 5.04 | 0.1683 | 9.4248
[22 empty] | Fuel | Material | LTR | 1.76 | 0.79365 | 2.2176 | 2.3562 | 4.1469
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 2.2667 | 21.1765 | 0.825 | 39.6
[22 empty] | Fuel | Material | LTR | 1.76 | 0.22667 | 7.7647 | 8.25 | 14.52
[9 empty] | 1.87 | 1.87 |  | 1.87 | [9 empty] | Valve Room Installation |  | Ea | 2950 |  | 2950 | 1.87 | 5516.5 | 0 | 0 | 0 | 0 | 0
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.5 | 700 | 3.74 | 1309
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 6.25 | 400 | 0.2992 | 748
[22 empty] | Workmanship RC concrete | SC | M³ | 450 | 0.5 | 900 | 3.74 | 1683
[22 empty] | Supply and apply chamber ladder | Material | Ea | 400 | 0.5 | 800 | 3.74 | 1496
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.2 | 85 | 9.35 | 158.95
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.2 | 65 | 9.35 | 121.55
[9 empty] | 1.87 | 1.87 |  | 1.87 | [9 empty] | Internal and external Insulation |  | Ea | 1120 |  | 1120 | 1.87 | 2094.4 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply & apply external waterproofing | SC | M² | 40 | 0.0625 | 640 | 29.92 | 1196.8
[22 empty] | Supply & apply internal coating | SC | M² | 30 | 0.0625 | 480 | 29.92 | 897.6
[9 empty] | 1.87 | 1.87 |  | 1.87 | [9 empty] | Backfilling |  | Ea | 89.4744 |  | 89.4744 | 1.87 | 167.3172 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.2 | 50 | 9.35 | 93.5
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 20 | 3.28 | 0.0935 | 6.1336
[22 empty] | Fuel | Material | LTR | 1.76 | 2.2222 | 0.792 | 0.8415 | 1.481
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 4.08 | 11.7647 | 0.45833 | 22
[22 empty] | Fuel | Material | LTR | 1.76 | 0.408 | 4.3137 | 4.5833 | 8.0667
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 10 | 3.6 | 0.187 | 6.732
[22 empty] | Fuel | Material | LTR | 1.76 | 1.1111 | 1.584 | 1.683 | 2.9621
[22 empty] | Plate Compactor | Machinery | HR | 23 | 2 | 11.5 | 0.935 | 21.505
[22 empty] | Fuel | Material | LTR | 1.76 | 0.66667 | 2.64 | 2.805 | 4.9368
PTW8 |  | 1.5 m depth difference on a 355 mm diameter pipe line | nr | 2.54 | 11493 | 29192.22 | 6216.1543 | 15789.032 | 2.54 | 2.54 |  | 2.54 | 100% | 11493 | 29192.22 | 6216.1543 | 15789.032 |  | 15789.032 | [7 empty] | 6216.1543 | 2.54 | 15789.032 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 2.54 | 2.54 |  | 2.54 | [9 empty] | Excavate & Disposal (3*3*1.5) |  | Ea | 54.2982 |  | 54.2982 | 2.54 | 137.9173 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 7.4074 | 7.56 | 0.3429 | 19.2024
[22 empty] | Fuel | Material | LTR | 1.76 | 0.5291 | 3.3264 | 4.8006 | 8.4491
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 1.5111 | 31.7647 | 1.6809 | 80.6824
[22 empty] | Fuel | Material | LTR | 1.76 | 0.15111 | 11.6471 | 16.8088 | 29.5835
[9 empty] | 2.54 | 2.54 |  | 2.54 | [9 empty] | Valve Room Installation |  | Ea | 4350.0012 |  | 4350.0012 | 2.54 | 11049.003 | 0 | 0 | 0 | 0 | 0
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.33333 | 1050 | 7.62 | 2667
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 4.1667 | 600 | 0.6096 | 1524
[22 empty] | Workmanship RC concrete | SC | M³ | 450 | 0.33333 | 1350 | 7.62 | 3429
[22 empty] | Supply and apply chamber ladder | Material | Ea | 400 | 0.33333 | 1200.0012 | 7.62 | 3048.003
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.2 | 85 | 12.7 | 215.9
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.2 | 65 | 12.7 | 165.1
[9 empty] | 2.54 | 2.54 |  | 2.54 | [9 empty] | Internal and external Insulation |  | Ea | 1680 |  | 1680 | 2.54 | 4267.2 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply & apply external waterproofing | SC | M² | 40 | 0.041667 | 960 | 60.96 | 2438.4
[22 empty] | Supply & apply internal coating | SC | M² | 30 | 0.041667 | 720 | 60.96 | 1828.8
[9 empty] | 2.54 | 2.54 |  | 2.54 | [9 empty] | Backfilling |  | Ea | 131.855 |  | 131.855 | 2.54 | 334.9117 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.13333 | 75 | 19.05 | 190.5
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 13.3333 | 4.92 | 0.1905 | 12.4968
[22 empty] | Fuel | Material | LTR | 1.76 | 1.4815 | 1.188 | 1.7145 | 3.0175
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 2.72 | 17.6471 | 0.93382 | 44.8235
[22 empty] | Fuel | Material | LTR | 1.76 | 0.272 | 6.4706 | 9.3382 | 16.4353
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 6.6667 | 5.4 | 0.381 | 13.716
[22 empty] | Fuel | Material | LTR | 1.76 | 0.74074 | 2.376 | 3.429 | 6.035
[22 empty] | Plate Compactor | Machinery | HR | 23 | 1.5 | 15.3333 | 1.6933 | 38.9467
[22 empty] | Fuel | Material | LTR | 1.76 | 0.5 | 3.52 | 5.08 | 8.9408
PTW8 |  | 2.0 m depth difference on a 355 mm diameter pipe line | nr | 0.77 | 15295 | 11777.15 | 8235.6904 | 6341.4816 | 0.77 | 0.77 |  | 0.77 | 100% | 15295 | 11777.15 | 8235.6904 | 6341.4816 |  | 6341.4816 | [7 empty] | 8235.6904 | 0.77 | 6341.4816 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 0.77 | 0.77 |  | 0.77 | [9 empty] | Excavate & Disposal (3*3*2.0) |  | Ea | 72.3976 |  | 72.3976 | 0.77 | 55.7461 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 5.5556 | 10.08 | 0.1386 | 7.7616
[22 empty] | Fuel | Material | LTR | 1.76 | 0.39683 | 4.4352 | 1.9404 | 3.4151
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 1.1333 | 42.3529 | 0.67941 | 32.6118
[22 empty] | Fuel | Material | LTR | 1.76 | 0.11333 | 15.5294 | 6.7941 | 11.9576
[9 empty] | 0.77 | 0.77 |  | 0.77 | [9 empty] | Valve Room Installation |  | Ea | 5750 |  | 5750 | 0.77 | 4427.5 | 0 | 0 | 0 | 0 | 0
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.25 | 1400 | 3.08 | 1078
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 3.125 | 800 | 0.2464 | 616
[22 empty] | Workmanship RC concrete | SC | M³ | 450 | 0.25 | 1800 | 3.08 | 1386
[22 empty] | Supply and apply chamber ladder | Material | Ea | 400 | 0.25 | 1600 | 3.08 | 1232
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.2 | 85 | 3.85 | 65.45
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.2 | 65 | 3.85 | 50.05
[9 empty] | 0.77 | 0.77 |  | 0.77 | [9 empty] | Internal and external Insulation |  | Ea | 2240 |  | 2240 | 0.77 | 1724.8 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply & apply external waterproofing | SC | M² | 40 | 0.03125 | 1280 | 24.64 | 985.6
[22 empty] | Supply & apply internal coating | SC | M² | 30 | 0.03125 | 960 | 24.64 | 739.2
[9 empty] | 0.77 | 0.77 |  | 0.77 | [9 empty] | Backfilling |  | Ea | 173.2929 |  | 173.2929 | 0.77 | 133.4355 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.1 | 100 | 7.7 | 77
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 10 | 6.56 | 0.077 | 5.0512
[22 empty] | Fuel | Material | LTR | 1.76 | 1.1111 | 1.584 | 0.693 | 1.2197
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 2.04 | 23.5294 | 0.37745 | 18.1176
[22 empty] | Fuel | Material | LTR | 1.76 | 0.204 | 8.6275 | 3.7745 | 6.6431
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 5 | 7.2 | 0.154 | 5.544
[22 empty] | Fuel | Material | LTR | 1.76 | 0.55556 | 3.168 | 1.386 | 2.4394
[22 empty] | Plate Compactor | Machinery | HR | 23 | 1.25 | 18.4 | 0.616 | 14.168
[22 empty] | Fuel | Material | LTR | 1.76 | 0.41667 | 4.224 | 1.848 | 3.2525
PTW8 |  | 2.5 m depth difference on a 355 mm diameter pipe line | nr | 0.93 | 19119 | 17780.67 | 10257.113 | 9539.1151 | 0.93 | 0.93 |  | 0.93 | 100% | 19119 | 17780.67 | 10257.113 | 9539.1151 |  | 9539.1151 | [7 empty] | 10257.113 | 0.93 | 9539.1151 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 0.93 | 0.93 |  | 0.93 | [9 empty] | Excavate & Disposal (3*3*2.5) |  | Ea | 90.4969 |  | 90.4969 | 0.93 | 84.1622 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 4.4444 | 12.6 | 0.20925 | 11.718
[22 empty] | Fuel | Material | LTR | 1.76 | 0.31746 | 5.544 | 2.9295 | 5.1559
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.90667 | 52.9412 | 1.0257 | 49.2353
[22 empty] | Fuel | Material | LTR | 1.76 | 0.090667 | 19.4118 | 10.2574 | 18.0529
[9 empty] | 0.93 | 0.93 |  | 0.93 | [9 empty] | Valve Room Installation |  | Ea | 7150 |  | 7150 | 0.93 | 6649.5 | 0 | 0 | 0 | 0 | 0
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.2 | 1750 | 4.65 | 1627.5
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 2.5 | 1000 | 0.372 | 930
[22 empty] | Workmanship RC concrete | SC | M³ | 450 | 0.2 | 2250 | 4.65 | 2092.5
[22 empty] | Supply and apply chamber ladder | Material | Ea | 400 | 0.2 | 2000 | 4.65 | 1860
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.2 | 85 | 4.65 | 79.05
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.2 | 65 | 4.65 | 60.45
[9 empty] | 0.93 | 0.93 |  | 0.93 | [9 empty] | Internal and external Insulation |  | Ea | 2800 |  | 2800 | 0.93 | 2604 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply & apply external waterproofing | SC | M² | 40 | 0.025 | 1600 | 37.2 | 1488
[22 empty] | Supply & apply internal coating | SC | M² | 30 | 0.025 | 1200 | 37.2 | 1116
[9 empty] | 0.93 | 0.93 |  | 0.93 | [9 empty] | Backfilling |  | Ea | 216.6161 |  | 216.6161 | 0.93 | 201.453 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.08 | 125 | 11.625 | 116.25
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 8 | 8.2 | 0.11625 | 7.626
[22 empty] | Fuel | Material | LTR | 1.76 | 0.88889 | 1.98 | 1.0462 | 1.8414
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 1.632 | 29.4118 | 0.56985 | 27.3529
[22 empty] | Fuel | Material | LTR | 1.76 | 0.1632 | 10.7843 | 5.6985 | 10.0294
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 4 | 9 | 0.2325 | 8.37
[22 empty] | Fuel | Material | LTR | 1.76 | 0.44444 | 3.96 | 2.0925 | 3.6828
[22 empty] | Plate Compactor | Machinery | HR | 23 | 1 | 23 | 0.93 | 21.39
[22 empty] | Fuel | Material | LTR | 1.76 | 0.33333 | 5.28 | 2.79 | 4.9104
PTW8 |  | Depth difference of 3.0 m on a 355 mm diameter pipe line | nr |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
PTW8 |  | On a pipeline with a diameter of 560 mm, and at a depth of 2-2.5 metres | nr | 11.205 | 19826 | 222150.33 | 12286.1796 | 137666.6422 | 11.205 | 11.205 |  | 11.205 | 100% | 19826 | 222150.33 | 12286.1796 | 137666.6422 |  | 137666.6422 | [7 empty] | 12286.1796 | 11.205 | 137666.6422 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 11.205 | 11.205 |  | 11.205 | [9 empty] | Excavate & Disposal (3*3*2.5) |  | Ea | 90.4969 |  | 90.4969 | 11.205 | 1014.0182 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 4.4444 | 12.6 | 2.5211 | 141.183
[22 empty] | Fuel | Material | LTR | 1.76 | 0.31746 | 5.544 | 35.2957 | 62.1205
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.90667 | 52.9412 | 12.3585 | 593.2059
[22 empty] | Fuel | Material | LTR | 1.76 | 0.090667 | 19.4118 | 123.5846 | 217.5088
[9 empty] | 11.205 | 11.205 |  | 11.205 | [9 empty] | Valve Room Installation |  | Ea | 9186.6 |  | 9186.6 | 11.205 | 102935.853 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 1.1111 | 225 | 10.0845 | 2521.125
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.2 | 1750 | 56.025 | 19608.75
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 2.5 | 1000 | 4.482 | 11205
[22 empty] | Workmanship plain concrete | SC | M³ | 150 | 1.1111 | 135 | 10.0845 | 1512.675
[22 empty] | Workmanship RC concrete | SC | M³ | 450 | 0.2 | 2250 | 56.025 | 25211.25
[22 empty] | Supply & apply Chamber Cover, frames | Material | Ea | 3500 | 1 | 3500 | 11.205 | 39217.5
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 4 | 20 | 2.8012 | 224.1
[22 empty] | Fuel | Material | HR | 1.76 | 0.26667 | 6.6 | 42.0187 | 73.953
[22 empty] | Chamber Pipes Pieces | Material | LS | 150 | 1 | 150 | 11.205 | 1680.75
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.2 | 85 | 56.025 | 952.425
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.2 | 65 | 56.025 | 728.325
[9 empty] | 11.205 | 11.205 |  | 11.205 | [9 empty] | Internal and external Insulation |  | Ea | 2800 |  | 2800 | 11.205 | 31374 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply & apply external waterproofing | SC | M² | 40 | 0.025 | 1600 | 448.2 | 17928
[22 empty] | Supply & apply internal coating | SC | M² | 30 | 0.025 | 1200 | 448.2 | 13446
[9 empty] | 11.205 | 11.205 |  | 11.205 | [9 empty] | Backfilling |  | Ea | 209.0826 |  | 209.0826 | 11.205 | 2342.7709 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.083333 | 120 | 134.46 | 1344.6
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 8.3333 | 7.872 | 1.3446 | 88.2058
[22 empty] | Fuel | Material | LTR | 1.76 | 0.92593 | 1.9008 | 12.1014 | 21.2985
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 1.7 | 28.2353 | 6.5912 | 316.3765
[22 empty] | Fuel | Material | LTR | 1.76 | 0.17 | 10.3529 | 65.9118 | 116.0047
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 4.1667 | 8.64 | 2.6892 | 96.8112
[22 empty] | Fuel | Material | LTR | 1.76 | 0.46296 | 3.8016 | 24.2028 | 42.5969
[22 empty] | Plate Compactor | Machinery | HR | 23 | 1 | 23 | 11.205 | 257.715
[22 empty] | Fuel | Material | LTR | 1.76 | 0.33333 | 5.28 | 33.615 | 59.1624
PTW8 |  | Depth difference of 0.5 m on a pipe line with a diameter of 560 mm | nr | 0.695 | 10070 | 6998.65 | 2172.8366 | 1510.1214 | 0.695 | 0.695 |  | 0.695 | 100% | 10070 | 6998.65 | 2172.8366 | 1510.1214 |  | 1510.1214 | [7 empty] | 2172.8366 | 0.695 | 1510.1214 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 0.695 | 0.695 |  | 0.695 | [9 empty] | Excavate & Disposal (3*3*0.5) |  | Ea | 18.0994 |  | 18.0994 | 0.695 | 12.5791 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 22.2222 | 2.52 | 0.031275 | 1.7514
[22 empty] | Fuel | Material | LTR | 1.76 | 1.5873 | 1.1088 | 0.43785 | 0.77062
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 4.5333 | 10.5882 | 0.15331 | 7.3588
[22 empty] | Fuel | Material | LTR | 1.76 | 0.45333 | 3.8824 | 1.5331 | 2.6982
[9 empty] | 0.695 | 0.695 |  | 0.695 | [9 empty] | Valve Room Installation |  | Ea | 1550 |  | 1550 | 0.695 | 1077.25 | 0 | 0 | 0 | 0 | 0
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 1 | 350 | 0.695 | 243.25
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 12.5 | 200 | 0.0556 | 139
[22 empty] | Workmanship RC concrete | SC | M³ | 450 | 1 | 450 | 0.695 | 312.75
[22 empty] | Supply and apply chamber ladder | Material | Ea | 400 | 1 | 400 | 0.695 | 278
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.2 | 85 | 3.475 | 59.075
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.2 | 65 | 3.475 | 45.175
[9 empty] | 0.695 | 0.695 |  | 0.695 | [9 empty] | Internal and external Insulation |  | Ea | 560 |  | 560 | 0.695 | 389.2 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply & apply external waterproofing | SC | M² | 40 | 0.125 | 320 | 5.56 | 222.4
[22 empty] | Supply & apply internal coating | SC | M² | 30 | 0.125 | 240 | 5.56 | 166.8
[9 empty] | 0.695 | 0.695 |  | 0.695 | [9 empty] | Backfilling |  | Ea | 44.7372 |  | 44.7372 | 0.695 | 31.0924 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.4 | 25 | 1.7375 | 17.375
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 40 | 1.64 | 0.017375 | 1.1398
[22 empty] | Fuel | Material | LTR | 1.76 | 4.4444 | 0.396 | 0.15637 | 0.27522
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 8.16 | 5.8824 | 0.085172 | 4.0882
[22 empty] | Fuel | Material | LTR | 1.76 | 0.816 | 2.1569 | 0.85172 | 1.499
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 20 | 1.8 | 0.03475 | 1.251
[22 empty] | Fuel | Material | LTR | 1.76 | 2.2222 | 0.792 | 0.31275 | 0.55044
[22 empty] | Plate Compactor | Machinery | HR | 23 | 4 | 5.75 | 0.17375 | 3.9962
[22 empty] | Fuel | Material | LTR | 1.76 | 1.3333 | 1.32 | 0.52125 | 0.9174
PTW8 |  | 1.0 m depth difference on a 560 mm diameter pipe line | nr | 0.965 | 10951 | 10567.715 | 4195.6732 | 4048.8246 | 0.965 | 0.965 |  | 0.965 | 100% | 10951 | 10567.715 | 4195.6732 | 4048.8246 |  | 4048.8246 | [7 empty] | 4195.6732 | 0.965 | 4048.8246 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 0.965 | 0.965 |  | 0.965 | [9 empty] | Excavate & Disposal (3*3*1.0) |  | Ea | 36.1988 |  | 36.1988 | 0.965 | 34.9318 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 11.1111 | 5.04 | 0.08685 | 4.8636
[22 empty] | Fuel | Material | LTR | 1.76 | 0.79365 | 2.2176 | 1.2159 | 2.14
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 2.2667 | 21.1765 | 0.42574 | 20.4353
[22 empty] | Fuel | Material | LTR | 1.76 | 0.22667 | 7.7647 | 4.2574 | 7.4929
[9 empty] | 0.965 | 0.965 |  | 0.965 | [9 empty] | Valve Room Installation |  | Ea | 2950 |  | 2950 | 0.965 | 2846.75 | 0 | 0 | 0 | 0 | 0
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.5 | 700 | 1.93 | 675.5
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 6.25 | 400 | 0.1544 | 386
[22 empty] | Workmanship RC concrete | SC | M³ | 450 | 0.5 | 900 | 1.93 | 868.5
[22 empty] | Supply and apply chamber ladder | Material | Ea | 400 | 0.5 | 800 | 1.93 | 772
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.2 | 85 | 4.825 | 82.025
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.2 | 65 | 4.825 | 62.725
[9 empty] | 0.965 | 0.965 |  | 0.965 | [9 empty] | Internal and external Insulation |  | Ea | 1120 |  | 1120 | 0.965 | 1080.8 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply & apply external waterproofing | SC | M² | 40 | 0.0625 | 640 | 15.44 | 617.6
[22 empty] | Supply & apply internal coating | SC | M² | 30 | 0.0625 | 480 | 15.44 | 463.2
[9 empty] | 0.965 | 0.965 |  | 0.965 | [9 empty] | Backfilling |  | Ea | 89.4744 |  | 89.4744 | 0.965 | 86.3428 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.2 | 50 | 4.825 | 48.25
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 20 | 3.28 | 0.04825 | 3.1652
[22 empty] | Fuel | Material | LTR | 1.76 | 2.2222 | 0.792 | 0.43425 | 0.76428
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 4.08 | 11.7647 | 0.23652 | 11.3529
[22 empty] | Fuel | Material | LTR | 1.76 | 0.408 | 4.3137 | 2.3652 | 4.1627
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 10 | 3.6 | 0.0965 | 3.474
[22 empty] | Fuel | Material | LTR | 1.76 | 1.1111 | 1.584 | 0.8685 | 1.5286
[22 empty] | Plate Compactor | Machinery | HR | 23 | 2 | 11.5 | 0.4825 | 11.0975
[22 empty] | Fuel | Material | LTR | 1.76 | 0.66667 | 2.64 | 1.4475 | 2.5476
PTW8 |  | Depth difference of 1.5 m on a pipe line with a diameter of 560 mm | nr | 0.43 | 13910 | 5981.3 | 6216.1543 | 2672.9464 | 0.43 | 0.43 |  | 0.43 | 100% | 13910 | 5981.3 | 6216.1543 | 2672.9464 |  | 2672.9464 | [7 empty] | 6216.1543 | 0.43 | 2672.9464 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 0.43 | 0.43 |  | 0.43 | [9 empty] | Excavate & Disposal (3*3*1.5) |  | Ea | 54.2982 |  | 54.2982 | 0.43 | 23.3482 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 7.4074 | 7.56 | 0.05805 | 3.2508
[22 empty] | Fuel | Material | LTR | 1.76 | 0.5291 | 3.3264 | 0.8127 | 1.4304
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 1.5111 | 31.7647 | 0.28456 | 13.6588
[22 empty] | Fuel | Material | LTR | 1.76 | 0.15111 | 11.6471 | 2.8456 | 5.0082
[9 empty] | 0.43 | 0.43 |  | 0.43 | [9 empty] | Valve Room Installation |  | Ea | 4350.0012 |  | 4350.0012 | 0.43 | 1870.5005 | 0 | 0 | 0 | 0 | 0
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.33333 | 1050 | 1.29 | 451.5
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 4.1667 | 600 | 0.1032 | 258
[22 empty] | Workmanship RC concrete | SC | M³ | 450 | 0.33333 | 1350 | 1.29 | 580.5
[22 empty] | Supply and apply chamber ladder | Material | Ea | 400 | 0.33333 | 1200.0012 | 1.29 | 516.0005
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.2 | 85 | 2.15 | 36.55
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.2 | 65 | 2.15 | 27.95
[9 empty] | 0.43 | 0.43 |  | 0.43 | [9 empty] | Internal and external Insulation |  | Ea | 1680 |  | 1680 | 0.43 | 722.4 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply & apply external waterproofing | SC | M² | 40 | 0.041667 | 960 | 10.32 | 412.8
[22 empty] | Supply & apply internal coating | SC | M² | 30 | 0.041667 | 720 | 10.32 | 309.6
[9 empty] | 0.43 | 0.43 |  | 0.43 | [9 empty] | Backfilling |  | Ea | 131.855 |  | 131.855 | 0.43 | 56.6976 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.13333 | 75 | 3.225 | 32.25
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 13.3333 | 4.92 | 0.03225 | 2.1156
[22 empty] | Fuel | Material | LTR | 1.76 | 1.4815 | 1.188 | 0.29025 | 0.51084
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 2.72 | 17.6471 | 0.15809 | 7.5882
[22 empty] | Fuel | Material | LTR | 1.76 | 0.272 | 6.4706 | 1.5809 | 2.7824
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 6.6667 | 5.4 | 0.0645 | 2.322
[22 empty] | Fuel | Material | LTR | 1.76 | 0.74074 | 2.376 | 0.5805 | 1.0217
[22 empty] | Plate Compactor | Machinery | HR | 23 | 1.5 | 15.3333 | 0.28667 | 6.5933
[22 empty] | Fuel | Material | LTR | 1.76 | 0.5 | 3.52 | 0.86 | 1.5136
PTW8 |  | Depth difference of 2.0 m on a pipe line with a diameter of 560 mm | nr | 0.555 | 18693 | 10374.615 | 8235.6904 | 4570.8082 | 0.555 | 0.555 |  | 0.555 | 100% | 18693 | 10374.615 | 8235.6904 | 4570.8082 |  | 4570.8082 | [7 empty] | 8235.6904 | 0.555 | 4570.8082 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 0.555 | 0.555 |  | 0.555 | [9 empty] | Excavate & Disposal (3*3*2.0) |  | Ea | 72.3976 |  | 72.3976 | 0.555 | 40.1806 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 5.5556 | 10.08 | 0.0999 | 5.5944
[22 empty] | Fuel | Material | LTR | 1.76 | 0.39683 | 4.4352 | 1.3986 | 2.4615
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 1.1333 | 42.3529 | 0.48971 | 23.5059
[22 empty] | Fuel | Material | LTR | 1.76 | 0.11333 | 15.5294 | 4.8971 | 8.6188
[9 empty] | 0.555 | 0.555 |  | 0.555 | [9 empty] | Valve Room Installation |  | Ea | 5750 |  | 5750 | 0.555 | 3191.25 | 0 | 0 | 0 | 0 | 0
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.25 | 1400 | 2.22 | 777
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 3.125 | 800 | 0.1776 | 444
[22 empty] | Workmanship RC concrete | SC | M³ | 450 | 0.25 | 1800 | 2.22 | 999
[22 empty] | Supply and apply chamber ladder | Material | Ea | 400 | 0.25 | 1600 | 2.22 | 888
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.2 | 85 | 2.775 | 47.175
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.2 | 65 | 2.775 | 36.075
[9 empty] | 0.555 | 0.555 |  | 0.555 | [9 empty] | Internal and external Insulation |  | Ea | 2240 |  | 2240 | 0.555 | 1243.2 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply & apply external waterproofing | SC | M² | 40 | 0.03125 | 1280 | 17.76 | 710.4
[22 empty] | Supply & apply internal coating | SC | M² | 30 | 0.03125 | 960 | 17.76 | 532.8
[9 empty] | 0.555 | 0.555 |  | 0.555 | [9 empty] | Backfilling |  | Ea | 173.2929 |  | 173.2929 | 0.555 | 96.1775 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.1 | 100 | 5.55 | 55.5
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 10 | 6.56 | 0.0555 | 3.6408
[22 empty] | Fuel | Material | LTR | 1.76 | 1.1111 | 1.584 | 0.4995 | 0.87912
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 2.04 | 23.5294 | 0.27206 | 13.0588
[22 empty] | Fuel | Material | LTR | 1.76 | 0.204 | 8.6275 | 2.7206 | 4.7882
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 5 | 7.2 | 0.111 | 3.996
[22 empty] | Fuel | Material | LTR | 1.76 | 0.55556 | 3.168 | 0.999 | 1.7582
[22 empty] | Plate Compactor | Machinery | HR | 23 | 1.25 | 18.4 | 0.444 | 10.212
[22 empty] | Fuel | Material | LTR | 1.76 | 0.41667 | 4.224 | 1.332 | 2.3443
PTW8 |  | Depth difference of 2.5 m on a pipe line with a diameter of 560 mm | nr | 0.2 | 23351 | 4670.2 | 10257.113 | 2051.4226 | 0.2 | 0.2 |  | 0.2 | 100% | 23351 | 4670.2 | 10257.113 | 2051.4226 |  | 2051.4226 | [7 empty] | 10257.113 | 0.2 | 2051.4226 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 0.2 | 0.2 |  | 0.2 | [9 empty] | Excavate & Disposal (3*3*2.5) |  | Ea | 90.4969 |  | 90.4969 | 0.2 | 18.0994 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 4.4444 | 12.6 | 0.045 | 2.52
[22 empty] | Fuel | Material | LTR | 1.76 | 0.31746 | 5.544 | 0.63 | 1.1088
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.90667 | 52.9412 | 0.22059 | 10.5882
[22 empty] | Fuel | Material | LTR | 1.76 | 0.090667 | 19.4118 | 2.2059 | 3.8824
[9 empty] | 0.2 | 0.2 |  | 0.2 | [9 empty] | Valve Room Installation |  | Ea | 7150 |  | 7150 | 0.2 | 1430 | 0 | 0 | 0 | 0 | 0
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.2 | 1750 | 1 | 350
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 2.5 | 1000 | 0.08 | 200
[22 empty] | Workmanship RC concrete | SC | M³ | 450 | 0.2 | 2250 | 1 | 450
[22 empty] | Supply and apply chamber ladder | Material | Ea | 400 | 0.2 | 2000 | 1 | 400
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.2 | 85 | 1 | 17
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.2 | 65 | 1 | 13
[9 empty] | 0.2 | 0.2 |  | 0.2 | [9 empty] | Internal and external Insulation |  | Ea | 2800 |  | 2800 | 0.2 | 560 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply & apply external waterproofing | SC | M² | 40 | 0.025 | 1600 | 8 | 320
[22 empty] | Supply & apply internal coating | SC | M² | 30 | 0.025 | 1200 | 8 | 240
[9 empty] | 0.2 | 0.2 |  | 0.2 | [9 empty] | Backfilling |  | Ea | 216.6161 |  | 216.6161 | 0.2 | 43.3232 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.08 | 125 | 2.5 | 25
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 8 | 8.2 | 0.025 | 1.64
[22 empty] | Fuel | Material | LTR | 1.76 | 0.88889 | 1.98 | 0.225 | 0.396
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 1.632 | 29.4118 | 0.12255 | 5.8824
[22 empty] | Fuel | Material | LTR | 1.76 | 0.1632 | 10.7843 | 1.2255 | 2.1569
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 4 | 9 | 0.05 | 1.8
[22 empty] | Fuel | Material | LTR | 1.76 | 0.44444 | 3.96 | 0.45 | 0.792
[22 empty] | Plate Compactor | Machinery | HR | 23 | 1 | 23 | 0.2 | 4.6
[22 empty] | Fuel | Material | LTR | 1.76 | 0.33333 | 5.28 | 0.6 | 1.056
PTW8 |  | Depth difference of 3.0 m on a pipe line with a diameter of 560 mm | nr | 0.58 | 27946 | 16208.68 | 11782.3063 | 6833.7376 | 0.58 | 0.58 |  | 0.58 | 100% | 27946 | 16208.68 | 11782.3063 | 6833.7376 |  | 6833.7376 | [7 empty] | 11782.3063 | 0.58 | 6833.7376 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 0.58 | 0.58 |  | 0.58 | [9 empty] | Excavate & Disposal (3*3*3.0) |  | Ea | 108.5963 |  | 108.5963 | 0.58 | 62.9859 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 3.7037 | 15.12 | 0.1566 | 8.7696
[22 empty] | Fuel | Material | LTR | 1.76 | 0.26455 | 6.6528 | 2.1924 | 3.8586
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.75556 | 63.5294 | 0.76765 | 36.8471
[22 empty] | Fuel | Material | LTR | 1.76 | 0.075556 | 23.2941 | 7.6765 | 13.5106
[9 empty] | 0.58 | 0.58 |  | 0.58 | [9 empty] | Valve Room Installation |  | Ea | 8050 |  | 8050 | 0.58 | 4669 | 0 | 0 | 0 | 0 | 0
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.16667 | 2100 | 3.48 | 1218
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 4.1667 | 600 | 0.1392 | 348
[22 empty] | Workmanship RC concrete | SC | M³ | 450 | 0.16667 | 2700 | 3.48 | 1566
[22 empty] | Supply and apply chamber ladder | Material | Ea | 400 | 0.16 | 2500 | 3.625 | 1450
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.2 | 85 | 2.9 | 49.3
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.2 | 65 | 2.9 | 37.7
[9 empty] | 0.58 | 0.58 |  | 0.58 | [9 empty] | Internal and external Insulation |  | Ea | 3360 |  | 3360 | 0.58 | 1948.8 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply & apply external waterproofing | SC | M² | 40 | 0.020833 | 1920 | 27.84 | 1113.6
[22 empty] | Supply & apply internal coating | SC | M² | 30 | 0.020833 | 1440 | 27.84 | 835.2
[9 empty] | 0.58 | 0.58 |  | 0.58 | [9 empty] | Backfilling |  | Ea | 263.71 |  | 263.71 | 0.58 | 152.9518 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.066667 | 150 | 8.7 | 87
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 6.6667 | 9.84 | 0.087 | 5.7072
[22 empty] | Fuel | Material | LTR | 1.76 | 0.74074 | 2.376 | 0.783 | 1.3781
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 1.36 | 35.2941 | 0.42647 | 20.4706
[22 empty] | Fuel | Material | LTR | 1.76 | 0.136 | 12.9412 | 4.2647 | 7.5059
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 3.3333 | 10.8 | 0.174 | 6.264
[22 empty] | Fuel | Material | LTR | 1.76 | 0.37037 | 4.752 | 1.566 | 2.7562
[22 empty] | Plate Compactor | Machinery | HR | 23 | 0.75 | 30.6667 | 0.77333 | 17.7867
[22 empty] | Fuel | Material | LTR | 1.76 | 0.25 | 7.04 | 2.32 | 4.0832
PTW8 |  | On a pipeline with a diameter of 710 mm, and at a depth of 2-2.5 metres | nr | 8.165 | 23036 | 188088.94 | 12286.1796 | 100316.6562 | 8.165 | 8.165 |  | 8.165 | 100% | 23036 | 188088.94 | 12286.1796 | 100316.6562 |  | 100316.6562 | [7 empty] | 12286.1796 | 8.165 | 100316.6562 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 8.165 | 8.165 |  | 8.165 | [9 empty] | Excavate & Disposal (3*3*2.5) |  | Ea | 90.4969 |  | 90.4969 | 8.165 | 738.9075 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 4.4444 | 12.6 | 1.8371 | 102.879
[22 empty] | Fuel | Material | LTR | 1.76 | 0.31746 | 5.544 | 25.7197 | 45.2668
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.90667 | 52.9412 | 9.0055 | 432.2647
[22 empty] | Fuel | Material | LTR | 1.76 | 0.090667 | 19.4118 | 90.0551 | 158.4971
[9 empty] | 8.165 | 8.165 |  | 8.165 | [9 empty] | Valve Room Installation |  | Ea | 9186.6 |  | 9186.6 | 8.165 | 75008.589 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 1.1111 | 225 | 7.3485 | 1837.125
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.2 | 1750 | 40.825 | 14288.75
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 2.5 | 1000 | 3.266 | 8165
[22 empty] | Workmanship plain concrete | SC | M³ | 150 | 1.1111 | 135 | 7.3485 | 1102.275
[22 empty] | Workmanship RC concrete | SC | M³ | 450 | 0.2 | 2250 | 40.825 | 18371.25
[22 empty] | Supply & apply Chamber Cover, frames | Material | Ea | 3500 | 1 | 3500 | 8.165 | 28577.5
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 4 | 20 | 2.0412 | 163.3
[22 empty] | Fuel | Material | HR | 1.76 | 0.26667 | 6.6 | 30.6187 | 53.889
[22 empty] | Chamber Pipes Pieces | Material | LS | 150 | 1 | 150 | 8.165 | 1224.75
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.2 | 85 | 40.825 | 694.025
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.2 | 65 | 40.825 | 530.725
[9 empty] | 8.165 | 8.165 |  | 8.165 | [9 empty] | Internal and external Insulation |  | Ea | 2800 |  | 2800 | 8.165 | 22862 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply & apply external waterproofing | SC | M² | 40 | 0.025 | 1600 | 326.6 | 13064
[22 empty] | Supply & apply internal coating | SC | M² | 30 | 0.025 | 1200 | 326.6 | 9798
[9 empty] | 8.165 | 8.165 |  | 8.165 | [9 empty] | Backfilling |  | Ea | 209.0826 |  | 209.0826 | 8.165 | 1707.1597 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.083333 | 120 | 97.98 | 979.8
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 8.3333 | 7.872 | 0.9798 | 64.2749
[22 empty] | Fuel | Material | LTR | 1.76 | 0.92593 | 1.9008 | 8.8182 | 15.52
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 1.7 | 28.2353 | 4.8029 | 230.5412
[22 empty] | Fuel | Material | LTR | 1.76 | 0.17 | 10.3529 | 48.0294 | 84.5318
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 4.1667 | 8.64 | 1.9596 | 70.5456
[22 empty] | Fuel | Material | LTR | 1.76 | 0.46296 | 3.8016 | 17.6364 | 31.0401
[22 empty] | Plate Compactor | Machinery | HR | 23 | 1 | 23 | 8.165 | 187.795
[22 empty] | Fuel | Material | LTR | 1.76 | 0.33333 | 5.28 | 24.495 | 43.1112
PTW8 |  | Depth difference of 0.5 m on a pipe line with a diameter of 710 mm | nr | 0.375 | 10448 | 3918 | 2172.8366 | 814.8137 | 0.375 | 0.375 |  | 0.375 | 100% | 10448 | 3918 | 2172.8366 | 814.8137 |  | 814.8137 | [7 empty] | 2172.8366 | 0.375 | 814.8137 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 0.375 | 0.375 |  | 0.375 | [9 empty] | Excavate & Disposal (3*3*0.5) |  | Ea | 18.0994 |  | 18.0994 | 0.375 | 6.7873 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 22.2222 | 2.52 | 0.016875 | 0.945
[22 empty] | Fuel | Material | LTR | 1.76 | 1.5873 | 1.1088 | 0.23625 | 0.4158
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 4.5333 | 10.5882 | 0.082721 | 3.9706
[22 empty] | Fuel | Material | LTR | 1.76 | 0.45333 | 3.8824 | 0.82721 | 1.4559
[9 empty] | 0.375 | 0.375 |  | 0.375 | [9 empty] | Valve Room Installation |  | Ea | 1550 |  | 1550 | 0.375 | 581.25 | 0 | 0 | 0 | 0 | 0
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 1 | 350 | 0.375 | 131.25
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 12.5 | 200 | 0.03 | 75
[22 empty] | Workmanship RC concrete | SC | M³ | 450 | 1 | 450 | 0.375 | 168.75
[22 empty] | Supply and apply chamber ladder | Material | Ea | 400 | 1 | 400 | 0.375 | 150
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.2 | 85 | 1.875 | 31.875
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.2 | 65 | 1.875 | 24.375
[9 empty] | 0.375 | 0.375 |  | 0.375 | [9 empty] | Internal and external Insulation |  | Ea | 560 |  | 560 | 0.375 | 210 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply & apply external waterproofing | SC | M² | 40 | 0.125 | 320 | 3 | 120
[22 empty] | Supply & apply internal coating | SC | M² | 30 | 0.125 | 240 | 3 | 90
[9 empty] | 0.375 | 0.375 |  | 0.375 | [9 empty] | Backfilling |  | Ea | 44.7372 |  | 44.7372 | 0.375 | 16.7765 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.4 | 25 | 0.9375 | 9.375
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 40 | 1.64 | 0.009375 | 0.615
[22 empty] | Fuel | Material | LTR | 1.76 | 4.4444 | 0.396 | 0.084375 | 0.1485
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 8.16 | 5.8824 | 0.045956 | 2.2059
[22 empty] | Fuel | Material | LTR | 1.76 | 0.816 | 2.1569 | 0.45956 | 0.80882
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 20 | 1.8 | 0.01875 | 0.675
[22 empty] | Fuel | Material | LTR | 1.76 | 2.2222 | 0.792 | 0.16875 | 0.297
[22 empty] | Plate Compactor | Machinery | HR | 23 | 4 | 5.75 | 0.09375 | 2.1562
[22 empty] | Fuel | Material | LTR | 1.76 | 1.3333 | 1.32 | 0.28125 | 0.495
PTW8 |  | 1.0 m depth difference on a 710 mm diameter pipe line | nr | 2.24 | 11455 | 25659.2 | 4195.6732 | 9398.308 | 2.24 | 2.24 |  | 2.24 | 100% | 11455 | 25659.2 | 4195.6732 | 9398.308 |  | 9398.308 | [7 empty] | 4195.6732 | 2.24 | 9398.308 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 2.24 | 2.24 |  | 2.24 | [9 empty] | Excavate & Disposal (3*3*1.0) |  | Ea | 36.1988 |  | 36.1988 | 2.24 | 81.0853 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 11.1111 | 5.04 | 0.2016 | 11.2896
[22 empty] | Fuel | Material | LTR | 1.76 | 0.79365 | 2.2176 | 2.8224 | 4.9674
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 2.2667 | 21.1765 | 0.98824 | 47.4353
[22 empty] | Fuel | Material | LTR | 1.76 | 0.22667 | 7.7647 | 9.8824 | 17.3929
[9 empty] | 2.24 | 2.24 |  | 2.24 | [9 empty] | Valve Room Installation |  | Ea | 2950 |  | 2950 | 2.24 | 6608 | 0 | 0 | 0 | 0 | 0
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.5 | 700 | 4.48 | 1568
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 6.25 | 400 | 0.3584 | 896
[22 empty] | Workmanship RC concrete | SC | M³ | 450 | 0.5 | 900 | 4.48 | 2016
[22 empty] | Supply and apply chamber ladder | Material | Ea | 400 | 0.5 | 800 | 4.48 | 1792
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.2 | 85 | 11.2 | 190.4
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.2 | 65 | 11.2 | 145.6
[9 empty] | 2.24 | 2.24 |  | 2.24 | [9 empty] | Internal and external Insulation |  | Ea | 1120 |  | 1120 | 2.24 | 2508.8 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply & apply external waterproofing | SC | M² | 40 | 0.0625 | 640 | 35.84 | 1433.6
[22 empty] | Supply & apply internal coating | SC | M² | 30 | 0.0625 | 480 | 35.84 | 1075.2
[9 empty] | 2.24 | 2.24 |  | 2.24 | [9 empty] | Backfilling |  | Ea | 89.4744 |  | 89.4744 | 2.24 | 200.4227 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.2 | 50 | 11.2 | 112
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 20 | 3.28 | 0.112 | 7.3472
[22 empty] | Fuel | Material | LTR | 1.76 | 2.2222 | 0.792 | 1.008 | 1.7741
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 4.08 | 11.7647 | 0.54902 | 26.3529
[22 empty] | Fuel | Material | LTR | 1.76 | 0.408 | 4.3137 | 5.4902 | 9.6627
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 10 | 3.6 | 0.224 | 8.064
[22 empty] | Fuel | Material | LTR | 1.76 | 1.1111 | 1.584 | 2.016 | 3.5482
[22 empty] | Plate Compactor | Machinery | HR | 23 | 2 | 11.5 | 1.12 | 25.76
[22 empty] | Fuel | Material | LTR | 1.76 | 0.66667 | 2.64 | 3.36 | 5.9136
PTW8 |  | Depth difference of 1.5 m on a pipe line with a diameter of 710 mm | nr | 1.815 | 15295 | 27760.425 | 6216.1543 | 11282.3201 | 1.815 | 1.815 |  | 1.815 | 100% | 15295 | 27760.425 | 6216.1543 | 11282.3201 |  | 11282.3201 | [7 empty] | 6216.1543 | 1.815 | 11282.3201 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 1.815 | 1.815 |  | 1.815 | [9 empty] | Excavate & Disposal (3*3*1.5) |  | Ea | 54.2982 |  | 54.2982 | 1.815 | 98.5512 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 7.4074 | 7.56 | 0.24502 | 13.7214
[22 empty] | Fuel | Material | LTR | 1.76 | 0.5291 | 3.3264 | 3.4303 | 6.0374
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 1.5111 | 31.7647 | 1.2011 | 57.6529
[22 empty] | Fuel | Material | LTR | 1.76 | 0.15111 | 11.6471 | 12.011 | 21.1394
[9 empty] | 1.815 | 1.815 |  | 1.815 | [9 empty] | Valve Room Installation |  | Ea | 4350.0012 |  | 4350.0012 | 1.815 | 7895.2522 | 0 | 0 | 0 | 0 | 0
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.33333 | 1050 | 5.445 | 1905.75
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 4.1667 | 600 | 0.4356 | 1089
[22 empty] | Workmanship RC concrete | SC | M³ | 450 | 0.33333 | 1350 | 5.445 | 2450.25
[22 empty] | Supply and apply chamber ladder | Material | Ea | 400 | 0.33333 | 1200.0012 | 5.445 | 2178.0022
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.2 | 85 | 9.075 | 154.275
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.2 | 65 | 9.075 | 117.975
[9 empty] | 1.815 | 1.815 |  | 1.815 | [9 empty] | Internal and external Insulation |  | Ea | 1680 |  | 1680 | 1.815 | 3049.2 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply & apply external waterproofing | SC | M² | 40 | 0.041667 | 960 | 43.56 | 1742.4
[22 empty] | Supply & apply internal coating | SC | M² | 30 | 0.041667 | 720 | 43.56 | 1306.8
[9 empty] | 1.815 | 1.815 |  | 1.815 | [9 empty] | Backfilling |  | Ea | 131.855 |  | 131.855 | 1.815 | 239.3168 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.13333 | 75 | 13.6125 | 136.125
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 13.3333 | 4.92 | 0.13612 | 8.9298
[22 empty] | Fuel | Material | LTR | 1.76 | 1.4815 | 1.188 | 1.2251 | 2.1562
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 2.72 | 17.6471 | 0.66728 | 32.0294
[22 empty] | Fuel | Material | LTR | 1.76 | 0.272 | 6.4706 | 6.6728 | 11.7441
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 6.6667 | 5.4 | 0.27225 | 9.801
[22 empty] | Fuel | Material | LTR | 1.76 | 0.74074 | 2.376 | 2.4502 | 4.3124
[22 empty] | Plate Compactor | Machinery | HR | 23 | 1.5 | 15.3333 | 1.21 | 27.83
[22 empty] | Fuel | Material | LTR | 1.76 | 0.5 | 3.52 | 3.63 | 6.3888
PTW8 |  | 2.0 m depth difference on a 710 mm diameter pipe line | nr | 1.06 | 20393 | 21616.58 | 8235.6904 | 8729.8318 | 1.06 | 1.06 |  | 1.06 | 100% | 20393 | 21616.58 | 8235.6904 | 8729.8318 |  | 8729.8318 | [7 empty] | 8235.6904 | 1.06 | 8729.8318 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 1.06 | 1.06 |  | 1.06 | [9 empty] | Excavate & Disposal (3*3*2.0) |  | Ea | 72.3976 |  | 72.3976 | 1.06 | 76.7414 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 5.5556 | 10.08 | 0.1908 | 10.6848
[22 empty] | Fuel | Material | LTR | 1.76 | 0.39683 | 4.4352 | 2.6712 | 4.7013
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 1.1333 | 42.3529 | 0.93529 | 44.8941
[22 empty] | Fuel | Material | LTR | 1.76 | 0.11333 | 15.5294 | 9.3529 | 16.4612
[9 empty] | 1.06 | 1.06 |  | 1.06 | [9 empty] | Valve Room Installation |  | Ea | 5750 |  | 5750 | 1.06 | 6095 | 0 | 0 | 0 | 0 | 0
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.25 | 1400 | 4.24 | 1484
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 3.125 | 800 | 0.3392 | 848
[22 empty] | Workmanship RC concrete | SC | M³ | 450 | 0.25 | 1800 | 4.24 | 1908
[22 empty] | Supply and apply chamber ladder | Material | Ea | 400 | 0.25 | 1600 | 4.24 | 1696
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.2 | 85 | 5.3 | 90.1
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.2 | 65 | 5.3 | 68.9
[9 empty] | 1.06 | 1.06 |  | 1.06 | [9 empty] | Internal and external Insulation |  | Ea | 2240 |  | 2240 | 1.06 | 2374.4 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply & apply external waterproofing | SC | M² | 40 | 0.03125 | 1280 | 33.92 | 1356.8
[22 empty] | Supply & apply internal coating | SC | M² | 30 | 0.03125 | 960 | 33.92 | 1017.6
[9 empty] | 1.06 | 1.06 |  | 1.06 | [9 empty] | Backfilling |  | Ea | 173.2929 |  | 173.2929 | 1.06 | 183.6904 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.1 | 100 | 10.6 | 106
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 10 | 6.56 | 0.106 | 6.9536
[22 empty] | Fuel | Material | LTR | 1.76 | 1.1111 | 1.584 | 0.954 | 1.679
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 2.04 | 23.5294 | 0.51961 | 24.9412
[22 empty] | Fuel | Material | LTR | 1.76 | 0.204 | 8.6275 | 5.1961 | 9.1451
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 5 | 7.2 | 0.212 | 7.632
[22 empty] | Fuel | Material | LTR | 1.76 | 0.55556 | 3.168 | 1.908 | 3.3581
[22 empty] | Plate Compactor | Machinery | HR | 23 | 1.25 | 18.4 | 0.848 | 19.504
[22 empty] | Fuel | Material | LTR | 1.76 | 0.41667 | 4.224 | 2.544 | 4.4774
PTW8 |  | Depth difference of 3.0 m on a pipe line with a diameter of 710 mm | nr | 0.515 | 29456 | 15169.84 | 11782.3063 | 6067.8877 | 0.515 | 0.515 |  | 0.515 | 100% | 29456 | 15169.84 | 11782.3063 | 6067.8877 |  | 6067.8877 | [7 empty] | 11782.3063 | 0.515 | 6067.8877 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 0.515 | 0.515 |  | 0.515 | [9 empty] | Excavate & Disposal (3*3*3.0) |  | Ea | 108.5963 |  | 108.5963 | 0.515 | 55.9271 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 3.7037 | 15.12 | 0.13905 | 7.7868
[22 empty] | Fuel | Material | LTR | 1.76 | 0.26455 | 6.6528 | 1.9467 | 3.4262
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.75556 | 63.5294 | 0.68162 | 32.7176
[22 empty] | Fuel | Material | LTR | 1.76 | 0.075556 | 23.2941 | 6.8162 | 11.9965
[9 empty] | 0.515 | 0.515 |  | 0.515 | [9 empty] | Valve Room Installation |  | Ea | 8050 |  | 8050 | 0.515 | 4145.75 | 0 | 0 | 0 | 0 | 0
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.16667 | 2100 | 3.09 | 1081.5
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 4.1667 | 600 | 0.1236 | 309
[22 empty] | Workmanship RC concrete | SC | M³ | 450 | 0.16667 | 2700 | 3.09 | 1390.5
[22 empty] | Supply and apply chamber ladder | Material | Ea | 400 | 0.16 | 2500 | 3.2187 | 1287.5
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.2 | 85 | 2.575 | 43.775
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.2 | 65 | 2.575 | 33.475
[9 empty] | 0.515 | 0.515 |  | 0.515 | [9 empty] | Internal and external Insulation |  | Ea | 3360 |  | 3360 | 0.515 | 1730.4 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply & apply external waterproofing | SC | M² | 40 | 0.020833 | 1920 | 24.72 | 988.8
[22 empty] | Supply & apply internal coating | SC | M² | 30 | 0.020833 | 1440 | 24.72 | 741.6
[9 empty] | 0.515 | 0.515 |  | 0.515 | [9 empty] | Backfilling |  | Ea | 263.71 |  | 263.71 | 0.515 | 135.8106 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.066667 | 150 | 7.725 | 77.25
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 6.6667 | 9.84 | 0.07725 | 5.0676
[22 empty] | Fuel | Material | LTR | 1.76 | 0.74074 | 2.376 | 0.69525 | 1.2236
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 1.36 | 35.2941 | 0.37868 | 18.1765
[22 empty] | Fuel | Material | LTR | 1.76 | 0.136 | 12.9412 | 3.7868 | 6.6647
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 3.3333 | 10.8 | 0.1545 | 5.562
[22 empty] | Fuel | Material | LTR | 1.76 | 0.37037 | 4.752 | 1.3905 | 2.4473
[22 empty] | Plate Compactor | Machinery | HR | 23 | 0.75 | 30.6667 | 0.68667 | 15.7933
[22 empty] | Fuel | Material | LTR | 1.76 | 0.25 | 7.04 | 2.06 | 3.6256
PTW8 |  | Depth difference of 3.5 m on a pipe line with a diameter of 710 mm | nr |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
PTW8 |  | Depth difference of 4.5 m on a pipe line with a diameter of 710 mm | nr |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
PTW8 |  | Wash-out chambers (cleaning valve). |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
PTW8 |  | On-site cleaning rooms made of reinforced concrete on the pipeline as specified and shown on the plans, and all that is required, including excavations, equipment, its decision, valves, boxes (containers) with their accessories, piping work, construction supplies and terminations, cutting and installing pipe pieces. |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
PTW8 |  | Cleaning valve on a pipeline with a diameter of 200 mm and a depth of 1.5-2.5 meters | nr |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
PTW8 |  | Cleaning valve on a pipeline with a diameter of 355 mm and a depth of 2.0-2.5 meters | nr | 10.9975 | 27505 | 302486.2375 | 12286.1796 | 135117.2599 | 10.9975 | 10.9975 |  | 10.9975 | 100% | 27505 | 302486.2375 | 12286.1796 | 135117.2599 |  | 135117.2599 | [7 empty] | 12286.1796 | 10.9975 | 135117.2599 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 10.9975 | 10.9975 |  | 10.9975 | [9 empty] | Excavate & Disposal (3*3*2.5) |  | Ea | 90.4969 |  | 90.4969 | 10.9975 | 995.2401 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 4.4444 | 12.6 | 2.4744 | 138.5685
[22 empty] | Fuel | Material | LTR | 1.76 | 0.31746 | 5.544 | 34.6421 | 60.9701
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.90667 | 52.9412 | 12.1296 | 582.2206
[22 empty] | Fuel | Material | LTR | 1.76 | 0.090667 | 19.4118 | 121.296 | 213.4809
[9 empty] | 10.9975 | 10.9975 |  | 10.9975 | [9 empty] | Valve Room Installation |  | Ea | 9186.6 |  | 9186.6 | 10.9975 | 101029.6335 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 1.1111 | 225 | 9.8977 | 2474.4375
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.2 | 1750 | 54.9875 | 19245.625
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 2.5 | 1000 | 4.399 | 10997.5
[22 empty] | Workmanship plain concrete | SC | M³ | 150 | 1.1111 | 135 | 9.8977 | 1484.6625
[22 empty] | Workmanship RC concrete | SC | M³ | 450 | 0.2 | 2250 | 54.9875 | 24744.375
[22 empty] | Supply & apply Chamber Cover, frames | Material | Ea | 3500 | 1 | 3500 | 10.9975 | 38491.25
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 4 | 20 | 2.7494 | 219.95
[22 empty] | Fuel | Material | HR | 1.76 | 0.26667 | 6.6 | 41.2406 | 72.5835
[22 empty] | Chamber Pipes Pieces | Material | LS | 150 | 1 | 150 | 10.9975 | 1649.625
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.2 | 85 | 54.9875 | 934.7875
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.2 | 65 | 54.9875 | 714.8375
[9 empty] | 10.9975 | 10.9975 |  | 10.9975 | [9 empty] | Internal and external Insulation |  | Ea | 2800 |  | 2800 | 10.9975 | 30793 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply & apply external waterproofing | SC | M² | 40 | 0.025 | 1600 | 439.9 | 17596
[22 empty] | Supply & apply internal coating | SC | M² | 30 | 0.025 | 1200 | 439.9 | 13197
[9 empty] | 10.9975 | 10.9975 |  | 10.9975 | [9 empty] | Backfilling |  | Ea | 209.0826 |  | 209.0826 | 10.9975 | 2299.3863 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.083333 | 120 | 131.97 | 1319.7
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 8.3333 | 7.872 | 1.3197 | 86.5723
[22 empty] | Fuel | Material | LTR | 1.76 | 0.92593 | 1.9008 | 11.8773 | 20.904
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 1.7 | 28.2353 | 6.4691 | 310.5176
[22 empty] | Fuel | Material | LTR | 1.76 | 0.17 | 10.3529 | 64.6912 | 113.8565
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 4.1667 | 8.64 | 2.6394 | 95.0184
[22 empty] | Fuel | Material | LTR | 1.76 | 0.46296 | 3.8016 | 23.7546 | 41.8081
[22 empty] | Plate Compactor | Machinery | HR | 23 | 1 | 23 | 10.9975 | 252.9425
[22 empty] | Fuel | Material | LTR | 1.76 | 0.33333 | 5.28 | 32.9925 | 58.0668
PTW8 |  | 0.5 m depth difference on a 355 mm diameter pipe line | nr | 0.625 | 10574 | 6608.75 | 2172.8366 | 1358.0229 | 0.625 | 0.625 |  | 0.625 | 100% | 10574 | 6608.75 | 2172.8366 | 1358.0229 |  | 1358.0229 | [7 empty] | 2172.8366 | 0.625 | 1358.0229 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 0.625 | 0.625 |  | 0.625 | [9 empty] | Excavate & Disposal (3*3*0.5) |  | Ea | 18.0994 |  | 18.0994 | 0.625 | 11.3121 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 22.2222 | 2.52 | 0.028125 | 1.575
[22 empty] | Fuel | Material | LTR | 1.76 | 1.5873 | 1.1088 | 0.39375 | 0.693
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 4.5333 | 10.5882 | 0.13787 | 6.6176
[22 empty] | Fuel | Material | LTR | 1.76 | 0.45333 | 3.8824 | 1.3787 | 2.4265
[9 empty] | 0.625 | 0.625 |  | 0.625 | [9 empty] | Valve Room Installation |  | Ea | 1550 |  | 1550 | 0.625 | 968.75 | 0 | 0 | 0 | 0 | 0
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 1 | 350 | 0.625 | 218.75
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 12.5 | 200 | 0.05 | 125
[22 empty] | Workmanship RC concrete | SC | M³ | 450 | 1 | 450 | 0.625 | 281.25
[22 empty] | Supply and apply chamber ladder | Material | Ea | 400 | 1 | 400 | 0.625 | 250
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.2 | 85 | 3.125 | 53.125
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.2 | 65 | 3.125 | 40.625
[9 empty] | 0.625 | 0.625 |  | 0.625 | [9 empty] | Internal and external Insulation |  | Ea | 560 |  | 560 | 0.625 | 350 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply & apply external waterproofing | SC | M² | 40 | 0.125 | 320 | 5 | 200
[22 empty] | Supply & apply internal coating | SC | M² | 30 | 0.125 | 240 | 5 | 150
[9 empty] | 0.625 | 0.625 |  | 0.625 | [9 empty] | Backfilling |  | Ea | 44.7372 |  | 44.7372 | 0.625 | 27.9608 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.4 | 25 | 1.5625 | 15.625
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 40 | 1.64 | 0.015625 | 1.025
[22 empty] | Fuel | Material | LTR | 1.76 | 4.4444 | 0.396 | 0.14062 | 0.2475
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 8.16 | 5.8824 | 0.076593 | 3.6765
[22 empty] | Fuel | Material | LTR | 1.76 | 0.816 | 2.1569 | 0.76593 | 1.348
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 20 | 1.8 | 0.03125 | 1.125
[22 empty] | Fuel | Material | LTR | 1.76 | 2.2222 | 0.792 | 0.28125 | 0.495
[22 empty] | Plate Compactor | Machinery | HR | 23 | 4 | 5.75 | 0.15625 | 3.5938
[22 empty] | Fuel | Material | LTR | 1.76 | 1.3333 | 1.32 | 0.46875 | 0.825
PTW8 |  | 1.0 m depth difference on a 355 mm diameter pipe line | nr | 0.945 | 11077 | 10467.765 | 4195.6732 | 3964.9112 | 0.945 | 0.945 |  | 0.945 | 100% | 11077 | 10467.765 | 4195.6732 | 3964.9112 |  | 3964.9112 | [7 empty] | 4195.6732 | 0.945 | 3964.9112 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 0.945 | 0.945 |  | 0.945 | [9 empty] | Excavate & Disposal (3*3*1.0) |  | Ea | 36.1988 |  | 36.1988 | 0.945 | 34.2078 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 11.1111 | 5.04 | 0.08505 | 4.7628
[22 empty] | Fuel | Material | LTR | 1.76 | 0.79365 | 2.2176 | 1.1907 | 2.0956
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 2.2667 | 21.1765 | 0.41691 | 20.0118
[22 empty] | Fuel | Material | LTR | 1.76 | 0.22667 | 7.7647 | 4.1691 | 7.3376
[9 empty] | 0.945 | 0.945 |  | 0.945 | [9 empty] | Valve Room Installation |  | Ea | 2950 |  | 2950 | 0.945 | 2787.75 | 0 | 0 | 0 | 0 | 0
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.5 | 700 | 1.89 | 661.5
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 6.25 | 400 | 0.1512 | 378
[22 empty] | Workmanship RC concrete | SC | M³ | 450 | 0.5 | 900 | 1.89 | 850.5
[22 empty] | Supply and apply chamber ladder | Material | Ea | 400 | 0.5 | 800 | 1.89 | 756
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.2 | 85 | 4.725 | 80.325
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.2 | 65 | 4.725 | 61.425
[9 empty] | 0.945 | 0.945 |  | 0.945 | [9 empty] | Internal and external Insulation |  | Ea | 1120 |  | 1120 | 0.945 | 1058.4 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply & apply external waterproofing | SC | M² | 40 | 0.0625 | 640 | 15.12 | 604.8
[22 empty] | Supply & apply internal coating | SC | M² | 30 | 0.0625 | 480 | 15.12 | 453.6
[9 empty] | 0.945 | 0.945 |  | 0.945 | [9 empty] | Backfilling |  | Ea | 89.4744 |  | 89.4744 | 0.945 | 84.5533 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.2 | 50 | 4.725 | 47.25
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 20 | 3.28 | 0.04725 | 3.0996
[22 empty] | Fuel | Material | LTR | 1.76 | 2.2222 | 0.792 | 0.42525 | 0.74844
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 4.08 | 11.7647 | 0.23162 | 11.1176
[22 empty] | Fuel | Material | LTR | 1.76 | 0.408 | 4.3137 | 2.3162 | 4.0765
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 10 | 3.6 | 0.0945 | 3.402
[22 empty] | Fuel | Material | LTR | 1.76 | 1.1111 | 1.584 | 0.8505 | 1.4969
[22 empty] | Plate Compactor | Machinery | HR | 23 | 2 | 11.5 | 0.4725 | 10.8675
[22 empty] | Fuel | Material | LTR | 1.76 | 0.66667 | 2.64 | 1.4175 | 2.4948
PTW8 |  | 1.5 m depth difference on a 355 mm diameter pipe line | nr |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
PTW8 |  | Cleaning valve on a pipeline with a diameter of 560 mm and a depth of 2.0-2.5 meters | nr | 3.795 | 28386 | 107724.87 | 12286.1796 | 46626.0515 | 3.795 | 3.795 |  | 3.795 | 100% | 28386 | 107724.87 | 12286.1796 | 46626.0515 |  | 46626.0515 | [7 empty] | 12286.1796 | 3.795 | 46626.0515 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 3.795 | 3.795 |  | 3.795 | [9 empty] | Excavate & Disposal (3*3*2.5) |  | Ea | 90.4969 |  | 90.4969 | 3.795 | 343.4359 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 4.4444 | 12.6 | 0.85387 | 47.817
[22 empty] | Fuel | Material | LTR | 1.76 | 0.31746 | 5.544 | 11.9542 | 21.0395
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.90667 | 52.9412 | 4.1857 | 200.9118
[22 empty] | Fuel | Material | LTR | 1.76 | 0.090667 | 19.4118 | 41.8566 | 73.6676
[9 empty] | 3.795 | 3.795 |  | 3.795 | [9 empty] | Valve Room Installation |  | Ea | 9186.6 |  | 9186.6 | 3.795 | 34863.147 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 1.1111 | 225 | 3.4155 | 853.875
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.2 | 1750 | 18.975 | 6641.25
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 2.5 | 1000 | 1.518 | 3795
[22 empty] | Workmanship plain concrete | SC | M³ | 150 | 1.1111 | 135 | 3.4155 | 512.325
[22 empty] | Workmanship RC concrete | SC | M³ | 450 | 0.2 | 2250 | 18.975 | 8538.75
[22 empty] | Supply & apply Chamber Cover, frames | Material | Ea | 3500 | 1 | 3500 | 3.795 | 13282.5
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 4 | 20 | 0.94875 | 75.9
[22 empty] | Fuel | Material | HR | 1.76 | 0.26667 | 6.6 | 14.2312 | 25.047
[22 empty] | Chamber Pipes Pieces | Material | LS | 150 | 1 | 150 | 3.795 | 569.25
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.2 | 85 | 18.975 | 322.575
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.2 | 65 | 18.975 | 246.675
[9 empty] | 3.795 | 3.795 |  | 3.795 | [9 empty] | Internal and external Insulation |  | Ea | 2800 |  | 2800 | 3.795 | 10626 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply & apply external waterproofing | SC | M² | 40 | 0.025 | 1600 | 151.8 | 6072
[22 empty] | Supply & apply internal coating | SC | M² | 30 | 0.025 | 1200 | 151.8 | 4554
[9 empty] | 3.795 | 3.795 |  | 3.795 | [9 empty] | Backfilling |  | Ea | 209.0826 |  | 209.0826 | 3.795 | 793.4686 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.083333 | 120 | 45.54 | 455.4
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 8.3333 | 7.872 | 0.4554 | 29.8742
[22 empty] | Fuel | Material | LTR | 1.76 | 0.92593 | 1.9008 | 4.0986 | 7.2135
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 1.7 | 28.2353 | 2.2324 | 107.1529
[22 empty] | Fuel | Material | LTR | 1.76 | 0.17 | 10.3529 | 22.3235 | 39.2894
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 4.1667 | 8.64 | 0.9108 | 32.7888
[22 empty] | Fuel | Material | LTR | 1.76 | 0.46296 | 3.8016 | 8.1972 | 14.4271
[22 empty] | Plate Compactor | Machinery | HR | 23 | 1 | 23 | 3.795 | 87.285
[22 empty] | Fuel | Material | LTR | 1.76 | 0.33333 | 5.28 | 11.385 | 20.0376
PTW8 |  | Depth difference of 0.5 m on a pipe line with a diameter of 560 mm | nr |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
PTW8 |  | 1.0 m depth difference on a 560 mm diameter pipe line | nr |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
PTW8 |  | Depth difference of 1.5 m on a pipe line with a diameter of 560 mm | nr | 0.3 | 17057 | 5117.1 | 6216.1543 | 1864.8463 | 0.3 | 0.3 |  | 0.3 | 100% | 17057 | 5117.1 | 6216.1543 | 1864.8463 |  | 1864.8463 | [7 empty] | 6216.1543 | 0.3 | 1864.8463 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 0.3 | 0.3 |  | 0.3 | [9 empty] | Excavate & Disposal (3*3*1.5) |  | Ea | 54.2982 |  | 54.2982 | 0.3 | 16.2894 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 7.4074 | 7.56 | 0.0405 | 2.268
[22 empty] | Fuel | Material | LTR | 1.76 | 0.5291 | 3.3264 | 0.567 | 0.99792
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 1.5111 | 31.7647 | 0.19853 | 9.5294
[22 empty] | Fuel | Material | LTR | 1.76 | 0.15111 | 11.6471 | 1.9853 | 3.4941
[9 empty] | 0.3 | 0.3 |  | 0.3 | [9 empty] | Valve Room Installation |  | Ea | 4350.0012 |  | 4350.0012 | 0.3 | 1305.0004 | 0 | 0 | 0 | 0 | 0
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.33333 | 1050 | 0.9 | 315
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 4.1667 | 600 | 0.072 | 180
[22 empty] | Workmanship RC concrete | SC | M³ | 450 | 0.33333 | 1350 | 0.9 | 405
[22 empty] | Supply and apply chamber ladder | Material | Ea | 400 | 0.33333 | 1200.0012 | 0.9 | 360.0004
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.2 | 85 | 1.5 | 25.5
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.2 | 65 | 1.5 | 19.5
[9 empty] | 0.3 | 0.3 |  | 0.3 | [9 empty] | Internal and external Insulation |  | Ea | 1680 |  | 1680 | 0.3 | 504 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply & apply external waterproofing | SC | M² | 40 | 0.041667 | 960 | 7.2 | 288
[22 empty] | Supply & apply internal coating | SC | M² | 30 | 0.041667 | 720 | 7.2 | 216
[9 empty] | 0.3 | 0.3 |  | 0.3 | [9 empty] | Backfilling |  | Ea | 131.855 |  | 131.855 | 0.3 | 39.5565 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.13333 | 75 | 2.25 | 22.5
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 13.3333 | 4.92 | 0.0225 | 1.476
[22 empty] | Fuel | Material | LTR | 1.76 | 1.4815 | 1.188 | 0.2025 | 0.3564
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 2.72 | 17.6471 | 0.11029 | 5.2941
[22 empty] | Fuel | Material | LTR | 1.76 | 0.272 | 6.4706 | 1.1029 | 1.9412
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 6.6667 | 5.4 | 0.045 | 1.62
[22 empty] | Fuel | Material | LTR | 1.76 | 0.74074 | 2.376 | 0.405 | 0.7128
[22 empty] | Plate Compactor | Machinery | HR | 23 | 1.5 | 15.3333 | 0.2 | 4.6
[22 empty] | Fuel | Material | LTR | 1.76 | 0.5 | 3.52 | 0.6 | 1.056
PTW8 |  | Depth difference of 2.0 m on a pipe line with a diameter of 560 mm | nr |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
PTW8 |  | Cleaning valve on a pipeline with a diameter of 710 mm and a depth of 3.0-3.5 metres | nr | 2.1921 | 38016 | 83336.5029 | 16017.7128 | 35113.1147 | 2.1921 | 2.1921 |  | 2.1921 | 100% | 38016 | 83336.5029 | 16017.7128 | 35113.1147 |  | 35113.1147 | [7 empty] | 16017.7128 | 2.1921 | 35113.1147 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 2.1921 | 2.1921 |  | 2.1921 | [9 empty] | Excavate & Disposal (3*3*3.5) |  | Ea | 126.6957 |  | 126.6957 | 2.1921 | 277.7351 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 3.1746 | 17.64 | 0.69052 | 38.6694
[22 empty] | Fuel | Material | LTR | 1.76 | 0.22676 | 7.7616 | 9.6673 | 17.0145
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.64762 | 74.1176 | 3.3849 | 162.4765
[22 empty] | Fuel | Material | LTR | 1.76 | 0.064762 | 27.1765 | 33.8493 | 59.5747
[9 empty] | 2.1921 | 2.1921 |  | 2.1921 | [9 empty] | Valve Room Installation |  | Ea | 11686.6 |  | 11686.6 | 2.1921 | 25618.6967 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 1.1111 | 225 | 1.9729 | 493.2321
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.13333 | 2625 | 16.4411 | 5754.375
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 1.6667 | 1500 | 1.3153 | 3288.2143
[22 empty] | Workmanship plain concrete | SC | M³ | 150 | 1.1111 | 135 | 1.9729 | 295.9393
[22 empty] | Workmanship RC concrete | SC | M³ | 450 | 0.13333 | 3375 | 16.4411 | 7398.4821
[22 empty] | Supply & apply Chamber Cover, frames | Material | Ea | 3500 | 1 | 3500 | 2.1921 | 7672.5
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 4 | 20 | 0.54804 | 43.8429
[22 empty] | Fuel | Material | HR | 1.76 | 0.26667 | 6.6 | 8.2205 | 14.4681
[22 empty] | Chamber Pipes Pieces | Material | LS | 150 | 1 | 150 | 2.1921 | 328.8214
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.2 | 85 | 10.9607 | 186.3321
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.2 | 65 | 10.9607 | 142.4893
[9 empty] | 2.1921 | 2.1921 |  | 2.1921 | [9 empty] | Internal and external Insulation |  | Ea | 3920 |  | 3920 | 2.1921 | 8593.2 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply & apply external waterproofing | SC | M² | 40 | 0.017857 | 2240 | 122.76 | 4910.4
[22 empty] | Supply & apply internal coating | SC | M² | 30 | 0.017857 | 1680 | 122.76 | 3682.8
[9 empty] | 2.1921 | 2.1921 |  | 2.1921 | [9 empty] | Backfilling |  | Ea | 284.4171 |  | 284.4171 | 2.1921 | 623.4828 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.058824 | 170 | 37.2664 | 372.6643
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 5.8824 | 11.152 | 0.37266 | 24.4468
[22 empty] | Fuel | Material | LTR | 1.76 | 0.65359 | 2.6928 | 3.354 | 5.903
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 1.2 | 40 | 1.8268 | 87.6857
[22 empty] | Fuel | Material | LTR | 1.76 | 0.12 | 14.6667 | 18.2679 | 32.1514
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 2.9412 | 12.24 | 0.74533 | 26.8318
[22 empty] | Fuel | Material | LTR | 1.76 | 0.3268 | 5.3856 | 6.708 | 11.806
[22 empty] | Plate Compactor | Machinery | HR | 23 | 1 | 23 | 2.1921 | 50.4193
[22 empty] | Fuel | Material | LTR | 1.76 | 0.33333 | 5.28 | 6.5764 | 11.5745
PTW8 |  | Depth difference of 0.5 m on a pipe line with a diameter of 710 mm | nr |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
PTW8 |  | 1.0 m depth difference on a 710 mm diameter pipe line | nr | 0.365 | 12714 | 4640.61 | 4195.6732 | 1531.4207 | 0.365 | 0.365 |  | 0.365 | 100% | 12714 | 4640.61 | 4195.6732 | 1531.4207 |  | 1531.4207 | [7 empty] | 4195.6732 | 0.365 | 1531.4207 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 0.365 | 0.365 |  | 0.365 | [9 empty] | Excavate & Disposal (3*3*1.0) |  | Ea | 36.1988 |  | 36.1988 | 0.365 | 13.2126 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 11.1111 | 5.04 | 0.03285 | 1.8396
[22 empty] | Fuel | Material | LTR | 1.76 | 0.79365 | 2.2176 | 0.4599 | 0.80942
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 2.2667 | 21.1765 | 0.16103 | 7.7294
[22 empty] | Fuel | Material | LTR | 1.76 | 0.22667 | 7.7647 | 1.6103 | 2.8341
[9 empty] | 0.365 | 0.365 |  | 0.365 | [9 empty] | Valve Room Installation |  | Ea | 2950 |  | 2950 | 0.365 | 1076.75 | 0 | 0 | 0 | 0 | 0
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.5 | 700 | 0.73 | 255.5
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 6.25 | 400 | 0.0584 | 146
[22 empty] | Workmanship RC concrete | SC | M³ | 450 | 0.5 | 900 | 0.73 | 328.5
[22 empty] | Supply and apply chamber ladder | Material | Ea | 400 | 0.5 | 800 | 0.73 | 292
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.2 | 85 | 1.825 | 31.025
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.2 | 65 | 1.825 | 23.725
[9 empty] | 0.365 | 0.365 |  | 0.365 | [9 empty] | Internal and external Insulation |  | Ea | 1120 |  | 1120 | 0.365 | 408.8 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply & apply external waterproofing | SC | M² | 40 | 0.0625 | 640 | 5.84 | 233.6
[22 empty] | Supply & apply internal coating | SC | M² | 30 | 0.0625 | 480 | 5.84 | 175.2
[9 empty] | 0.365 | 0.365 |  | 0.365 | [9 empty] | Backfilling |  | Ea | 89.4744 |  | 89.4744 | 0.365 | 32.6582 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.2 | 50 | 1.825 | 18.25
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 20 | 3.28 | 0.01825 | 1.1972
[22 empty] | Fuel | Material | LTR | 1.76 | 2.2222 | 0.792 | 0.16425 | 0.28908
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 4.08 | 11.7647 | 0.089461 | 4.2941
[22 empty] | Fuel | Material | LTR | 1.76 | 0.408 | 4.3137 | 0.89461 | 1.5745
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 10 | 3.6 | 0.0365 | 1.314
[22 empty] | Fuel | Material | LTR | 1.76 | 1.1111 | 1.584 | 0.3285 | 0.57816
[22 empty] | Plate Compactor | Machinery | HR | 23 | 2 | 11.5 | 0.1825 | 4.1975
[22 empty] | Fuel | Material | LTR | 1.76 | 0.66667 | 2.64 | 0.5475 | 0.9636
PTW8 |  | 2.0 m depth difference on a 710 mm diameter pipe line | nr | 0.45 | 23036 | 10366.2 | 8235.6904 | 3706.0607 | 0.45 | 0.45 |  | 0.45 | 100% | 23036 | 10366.2 | 8235.6904 | 3706.0607 |  | 3706.0607 | [7 empty] | 8235.6904 | 0.45 | 3706.0607 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 0.45 | 0.45 |  | 0.45 | [9 empty] | Excavate & Disposal (3*3*2.0) |  | Ea | 72.3976 |  | 72.3976 | 0.45 | 32.5789 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 5.5556 | 10.08 | 0.081 | 4.536
[22 empty] | Fuel | Material | LTR | 1.76 | 0.39683 | 4.4352 | 1.134 | 1.9958
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 1.1333 | 42.3529 | 0.39706 | 19.0588
[22 empty] | Fuel | Material | LTR | 1.76 | 0.11333 | 15.5294 | 3.9706 | 6.9882
[9 empty] | 0.45 | 0.45 |  | 0.45 | [9 empty] | Valve Room Installation |  | Ea | 5750 |  | 5750 | 0.45 | 2587.5 | 0 | 0 | 0 | 0 | 0
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.25 | 1400 | 1.8 | 630
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 3.125 | 800 | 0.144 | 360
[22 empty] | Workmanship RC concrete | SC | M³ | 450 | 0.25 | 1800 | 1.8 | 810
[22 empty] | Supply and apply chamber ladder | Material | Ea | 400 | 0.25 | 1600 | 1.8 | 720
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.2 | 85 | 2.25 | 38.25
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.2 | 65 | 2.25 | 29.25
[9 empty] | 0.45 | 0.45 |  | 0.45 | [9 empty] | Internal and external Insulation |  | Ea | 2240 |  | 2240 | 0.45 | 1008 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply & apply external waterproofing | SC | M² | 40 | 0.03125 | 1280 | 14.4 | 576
[22 empty] | Supply & apply internal coating | SC | M² | 30 | 0.03125 | 960 | 14.4 | 432
[9 empty] | 0.45 | 0.45 |  | 0.45 | [9 empty] | Backfilling |  | Ea | 173.2929 |  | 173.2929 | 0.45 | 77.9818 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.1 | 100 | 4.5 | 45
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 10 | 6.56 | 0.045 | 2.952
[22 empty] | Fuel | Material | LTR | 1.76 | 1.1111 | 1.584 | 0.405 | 0.7128
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 2.04 | 23.5294 | 0.22059 | 10.5882
[22 empty] | Fuel | Material | LTR | 1.76 | 0.204 | 8.6275 | 2.2059 | 3.8824
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 5 | 7.2 | 0.09 | 3.24
[22 empty] | Fuel | Material | LTR | 1.76 | 0.55556 | 3.168 | 0.81 | 1.4256
[22 empty] | Plate Compactor | Machinery | HR | 23 | 1.25 | 18.4 | 0.36 | 8.28
[22 empty] | Fuel | Material | LTR | 1.76 | 0.41667 | 4.224 | 1.08 | 1.9008
PTW8 |  | Depth difference of 2.5 m on a pipe line with a diameter of 710 mm | nr |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
PTW8 |  | Depth difference of 3.5 m on a pipe line with a diameter of 710 mm | nr |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
PTW8 |  | Air valve chambers |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
PTW8 |  | Air valve chamber depth: 200mm diameter pipe line at 1.5-2.0m depth. | nr | 1 | 21399 | 21399 | 10630.413 | 10630.413 | 1 | 1 |  | 1 | 100% | 21399 | 21399 | 10630.413 | 10630.413 |  | 10630.413 | [7 empty] | 10630.413 | 1 | 10630.413 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 1 | 1 |  | 1 | [9 empty] | Excavate & Disposal (3*3*2.0) |  | Ea | 72.3976 |  | 72.3976 | 1 | 72.3976 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 5.5556 | 10.08 | 0.18 | 10.08
[22 empty] | Fuel | Material | LTR | 1.76 | 0.39683 | 4.4352 | 2.52 | 4.4352
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 1.1333 | 42.3529 | 0.88235 | 42.3529
[22 empty] | Fuel | Material | LTR | 1.76 | 0.11333 | 15.5294 | 8.8235 | 15.5294
[9 empty] | 1 | 1 |  | 1 | [9 empty] | Valve Room Installation |  | Ea | 7936.6 |  | 7936.6 | 1 | 7936.6 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 1.1111 | 225 | 0.9 | 225
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.26667 | 1312.5 | 3.75 | 1312.5
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 3.3333 | 750 | 0.3 | 750
[22 empty] | Workmanship plain concrete | SC | M³ | 150 | 1.1111 | 135 | 0.9 | 135
[22 empty] | Workmanship RC concrete | SC | M³ | 450 | 0.26667 | 1687.5 | 3.75 | 1687.5
[22 empty] | Supply & apply Chamber Cover, frames | Material | Ea | 3500 | 1 | 3500 | 1 | 3500
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 4 | 20 | 0.25 | 20
[22 empty] | Fuel | Material | HR | 1.76 | 0.26667 | 6.6 | 3.75 | 6.6
[22 empty] | Chamber Pipes Pieces | Material | LS | 150 | 1 | 150 | 1 | 150
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.2 | 85 | 5 | 85
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.2 | 65 | 5 | 65
[9 empty] | 1 | 1 |  | 1 | [9 empty] | Internal and external Insulation |  | Ea | 2450 |  | 2450 | 1 | 2450 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply & apply external waterproofing | SC | M² | 40 | 0.028571 | 1400 | 35 | 1400
[22 empty] | Supply & apply internal coating | SC | M² | 30 | 0.028571 | 1050 | 35 | 1050
[9 empty] | 1 | 1 |  | 1 | [9 empty] | Backfilling |  | Ea | 171.4154 |  | 171.4154 | 1 | 171.4154 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.10526 | 95 | 9.5 | 95
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 10.5263 | 6.232 | 0.095 | 6.232
[22 empty] | Fuel | Material | LTR | 1.76 | 1.1696 | 1.5048 | 0.855 | 1.5048
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 2.1474 | 22.3529 | 0.46569 | 22.3529
[22 empty] | Fuel | Material | LTR | 1.76 | 0.21474 | 8.1961 | 4.6569 | 8.1961
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 5.2632 | 6.84 | 0.19 | 6.84
[22 empty] | Fuel | Material | LTR | 1.76 | 0.5848 | 3.0096 | 1.71 | 3.0096
[22 empty] | Plate Compactor | Machinery | HR | 23 | 1 | 23 | 1 | 23
[22 empty] | Fuel | Material | LTR | 1.76 | 0.33333 | 5.28 | 3 | 5.28
PTW8 |  | Air valve chamber depth: 225 mm diameter pipe line at a depth of 1.5-2.0 meters | nr |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
PTW8 |  | Air valve chamber depth: pipe line with a diameter of 250 mm and a depth of 2.0-2.5 meters | nr |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
PTW8 |  | Air valve chamber depth: 355mm diameter pipe line with 2 - 2.5m depth | nr | 7.485 | 26765 | 200336.025 | 12286.1796 | 91962.0541 | 7.485 | 7.485 |  | 7.485 | 100% | 26765 | 200336.025 | 12286.1796 | 91962.0541 |  | 91962.0541 | [7 empty] | 12286.1796 | 7.485 | 91962.0541 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 7.485 | 7.485 |  | 7.485 | [9 empty] | Excavate & Disposal (3*3*2.5) |  | Ea | 90.4969 |  | 90.4969 | 7.485 | 677.3696 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 4.4444 | 12.6 | 1.6841 | 94.311
[22 empty] | Fuel | Material | LTR | 1.76 | 0.31746 | 5.544 | 23.5777 | 41.4968
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.90667 | 52.9412 | 8.2555 | 396.2647
[22 empty] | Fuel | Material | LTR | 1.76 | 0.090667 | 19.4118 | 82.5551 | 145.2971
[9 empty] | 7.485 | 7.485 |  | 7.485 | [9 empty] | Valve Room Installation |  | Ea | 9186.6 |  | 9186.6 | 7.485 | 68761.701 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 1.1111 | 225 | 6.7365 | 1684.125
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.2 | 1750 | 37.425 | 13098.75
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 2.5 | 1000 | 2.994 | 7485
[22 empty] | Workmanship plain concrete | SC | M³ | 150 | 1.1111 | 135 | 6.7365 | 1010.475
[22 empty] | Workmanship RC concrete | SC | M³ | 450 | 0.2 | 2250 | 37.425 | 16841.25
[22 empty] | Supply & apply Chamber Cover, frames | Material | Ea | 3500 | 1 | 3500 | 7.485 | 26197.5
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 4 | 20 | 1.8713 | 149.7
[22 empty] | Fuel | Material | HR | 1.76 | 0.26667 | 6.6 | 28.0688 | 49.401
[22 empty] | Chamber Pipes Pieces | Material | LS | 150 | 1 | 150 | 7.485 | 1122.75
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.2 | 85 | 37.425 | 636.225
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.2 | 65 | 37.425 | 486.525
[9 empty] | 7.485 | 7.485 |  | 7.485 | [9 empty] | Internal and external Insulation |  | Ea | 2800 |  | 2800 | 7.485 | 20958 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply & apply external waterproofing | SC | M² | 40 | 0.025 | 1600 | 299.4 | 11976
[22 empty] | Supply & apply internal coating | SC | M² | 30 | 0.025 | 1200 | 299.4 | 8982
[9 empty] | 7.485 | 7.485 |  | 7.485 | [9 empty] | Backfilling |  | Ea | 209.0826 |  | 209.0826 | 7.485 | 1564.9835 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.083333 | 120 | 89.82 | 898.2
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 8.3333 | 7.872 | 0.8982 | 58.9219
[22 empty] | Fuel | Material | LTR | 1.76 | 0.92593 | 1.9008 | 8.0838 | 14.2275
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 1.7 | 28.2353 | 4.4029 | 211.3412
[22 empty] | Fuel | Material | LTR | 1.76 | 0.17 | 10.3529 | 44.0294 | 77.4918
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 4.1667 | 8.64 | 1.7964 | 64.6704
[22 empty] | Fuel | Material | LTR | 1.76 | 0.46296 | 3.8016 | 16.1676 | 28.455
[22 empty] | Plate Compactor | Machinery | HR | 23 | 1 | 23 | 7.485 | 172.155
[22 empty] | Fuel | Material | LTR | 1.76 | 0.33333 | 5.28 | 22.455 | 39.5208
PTW8 |  | 1.0 m depth difference on a 355 mm diameter pipe line | nr | 0.38 | 11329 | 4305.02 | 4195.6732 | 1594.3558 | 0.38 | 0.38 |  | 0.38 | 100% | 11329 | 4305.02 | 4195.6732 | 1594.3558 |  | 1594.3558 | [7 empty] | 4195.6732 | 0.38 | 1594.3558 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 0.38 | 0.38 |  | 0.38 | [9 empty] | Excavate & Disposal (3*3*1.0) |  | Ea | 36.1988 |  | 36.1988 | 0.38 | 13.7555 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 11.1111 | 5.04 | 0.0342 | 1.9152
[22 empty] | Fuel | Material | LTR | 1.76 | 0.79365 | 2.2176 | 0.4788 | 0.84269
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 2.2667 | 21.1765 | 0.16765 | 8.0471
[22 empty] | Fuel | Material | LTR | 1.76 | 0.22667 | 7.7647 | 1.6765 | 2.9506
[9 empty] | 0.38 | 0.38 |  | 0.38 | [9 empty] | Valve Room Installation |  | Ea | 2950 |  | 2950 | 0.38 | 1121 | 0 | 0 | 0 | 0 | 0
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.5 | 700 | 0.76 | 266
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 6.25 | 400 | 0.0608 | 152
[22 empty] | Workmanship RC concrete | SC | M³ | 450 | 0.5 | 900 | 0.76 | 342
[22 empty] | Supply and apply chamber ladder | Material | Ea | 400 | 0.5 | 800 | 0.76 | 304
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.2 | 85 | 1.9 | 32.3
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.2 | 65 | 1.9 | 24.7
[9 empty] | 0.38 | 0.38 |  | 0.38 | [9 empty] | Internal and external Insulation |  | Ea | 1120 |  | 1120 | 0.38 | 425.6 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply & apply external waterproofing | SC | M² | 40 | 0.0625 | 640 | 6.08 | 243.2
[22 empty] | Supply & apply internal coating | SC | M² | 30 | 0.0625 | 480 | 6.08 | 182.4
[9 empty] | 0.38 | 0.38 |  | 0.38 | [9 empty] | Backfilling |  | Ea | 89.4744 |  | 89.4744 | 0.38 | 34.0003 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.2 | 50 | 1.9 | 19
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 20 | 3.28 | 0.019 | 1.2464
[22 empty] | Fuel | Material | LTR | 1.76 | 2.2222 | 0.792 | 0.171 | 0.30096
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 4.08 | 11.7647 | 0.093137 | 4.4706
[22 empty] | Fuel | Material | LTR | 1.76 | 0.408 | 4.3137 | 0.93137 | 1.6392
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 10 | 3.6 | 0.038 | 1.368
[22 empty] | Fuel | Material | LTR | 1.76 | 1.1111 | 1.584 | 0.342 | 0.60192
[22 empty] | Plate Compactor | Machinery | HR | 23 | 2 | 11.5 | 0.19 | 4.37
[22 empty] | Fuel | Material | LTR | 1.76 | 0.66667 | 2.64 | 0.57 | 1.0032
PTW8 |  | Air valve chamber depth: 560mm diameter pipe line with 2 - 2.5m depth | nr | 2.25 | 27505 | 61886.25 | 12286.1796 | 27643.904 | 2.25 | 2.25 |  | 2.25 | 100% | 27505 | 61886.25 | 12286.1796 | 27643.904 |  | 27643.904 | [7 empty] | 12286.1796 | 2.25 | 27643.904 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 2.25 | 2.25 |  | 2.25 | [9 empty] | Excavate & Disposal (3*3*2.5) |  | Ea | 90.4969 |  | 90.4969 | 2.25 | 203.6181 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 4.4444 | 12.6 | 0.50625 | 28.35
[22 empty] | Fuel | Material | LTR | 1.76 | 0.31746 | 5.544 | 7.0875 | 12.474
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.90667 | 52.9412 | 2.4816 | 119.1176
[22 empty] | Fuel | Material | LTR | 1.76 | 0.090667 | 19.4118 | 24.8162 | 43.6765
[9 empty] | 2.25 | 2.25 |  | 2.25 | [9 empty] | Valve Room Installation |  | Ea | 9186.6 |  | 9186.6 | 2.25 | 20669.85 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 1.1111 | 225 | 2.025 | 506.25
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.2 | 1750 | 11.25 | 3937.5
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 2.5 | 1000 | 0.9 | 2250
[22 empty] | Workmanship plain concrete | SC | M³ | 150 | 1.1111 | 135 | 2.025 | 303.75
[22 empty] | Workmanship RC concrete | SC | M³ | 450 | 0.2 | 2250 | 11.25 | 5062.5
[22 empty] | Supply & apply Chamber Cover, frames | Material | Ea | 3500 | 1 | 3500 | 2.25 | 7875
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 4 | 20 | 0.5625 | 45
[22 empty] | Fuel | Material | HR | 1.76 | 0.26667 | 6.6 | 8.4375 | 14.85
[22 empty] | Chamber Pipes Pieces | Material | LS | 150 | 1 | 150 | 2.25 | 337.5
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.2 | 85 | 11.25 | 191.25
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.2 | 65 | 11.25 | 146.25
[9 empty] | 2.25 | 2.25 |  | 2.25 | [9 empty] | Internal and external Insulation |  | Ea | 2800 |  | 2800 | 2.25 | 6300 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply & apply external waterproofing | SC | M² | 40 | 0.025 | 1600 | 90 | 3600
[22 empty] | Supply & apply internal coating | SC | M² | 30 | 0.025 | 1200 | 90 | 2700
[9 empty] | 2.25 | 2.25 |  | 2.25 | [9 empty] | Backfilling |  | Ea | 209.0826 |  | 209.0826 | 2.25 | 470.4359 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.083333 | 120 | 27 | 270
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 8.3333 | 7.872 | 0.27 | 17.712
[22 empty] | Fuel | Material | LTR | 1.76 | 0.92593 | 1.9008 | 2.43 | 4.2768
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 1.7 | 28.2353 | 1.3235 | 63.5294
[22 empty] | Fuel | Material | LTR | 1.76 | 0.17 | 10.3529 | 13.2353 | 23.2941
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 4.1667 | 8.64 | 0.54 | 19.44
[22 empty] | Fuel | Material | LTR | 1.76 | 0.46296 | 3.8016 | 4.86 | 8.5536
[22 empty] | Plate Compactor | Machinery | HR | 23 | 1 | 23 | 2.25 | 51.75
[22 empty] | Fuel | Material | LTR | 1.76 | 0.33333 | 5.28 | 6.75 | 11.88
PTW8 |  | Air valve chamber depth: 710mm diameter pipe line with 2 - 2.5m depth | nr | 2.8375 | 28701 | 81439.0875 | 12286.1796 | 34862.0345 | 2.8375 | 2.8375 |  | 2.8375 | 100% | 28701 | 81439.0875 | 12286.1796 | 34862.0345 |  | 34862.0345 | [7 empty] | 12286.1796 | 2.8375 | 34862.0345 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 2.8375 | 2.8375 |  | 2.8375 | [9 empty] | Excavate & Disposal (3*3*2.5) |  | Ea | 90.4969 |  | 90.4969 | 2.8375 | 256.7851 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 4.4444 | 12.6 | 0.63844 | 35.7525
[22 empty] | Fuel | Material | LTR | 1.76 | 0.31746 | 5.544 | 8.9381 | 15.7311
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.90667 | 52.9412 | 3.1296 | 150.2206
[22 empty] | Fuel | Material | LTR | 1.76 | 0.090667 | 19.4118 | 31.296 | 55.0809
[9 empty] | 2.8375 | 2.8375 |  | 2.8375 | [9 empty] | Valve Room Installation |  | Ea | 9186.6 |  | 9186.6 | 2.8375 | 26066.9775 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 1.1111 | 225 | 2.5538 | 638.4375
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.2 | 1750 | 14.1875 | 4965.625
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 2.5 | 1000 | 1.135 | 2837.5
[22 empty] | Workmanship plain concrete | SC | M³ | 150 | 1.1111 | 135 | 2.5538 | 383.0625
[22 empty] | Workmanship RC concrete | SC | M³ | 450 | 0.2 | 2250 | 14.1875 | 6384.375
[22 empty] | Supply & apply Chamber Cover, frames | Material | Ea | 3500 | 1 | 3500 | 2.8375 | 9931.25
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 4 | 20 | 0.70938 | 56.75
[22 empty] | Fuel | Material | HR | 1.76 | 0.26667 | 6.6 | 10.6406 | 18.7275
[22 empty] | Chamber Pipes Pieces | Material | LS | 150 | 1 | 150 | 2.8375 | 425.625
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.2 | 85 | 14.1875 | 241.1875
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.2 | 65 | 14.1875 | 184.4375
[9 empty] | 2.8375 | 2.8375 |  | 2.8375 | [9 empty] | Internal and external Insulation |  | Ea | 2800 |  | 2800 | 2.8375 | 7945 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply & apply external waterproofing | SC | M² | 40 | 0.025 | 1600 | 113.5 | 4540
[22 empty] | Supply & apply internal coating | SC | M² | 30 | 0.025 | 1200 | 113.5 | 3405
[9 empty] | 2.8375 | 2.8375 |  | 2.8375 | [9 empty] | Backfilling |  | Ea | 209.0826 |  | 209.0826 | 2.8375 | 593.272 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.083333 | 120 | 34.05 | 340.5
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 8.3333 | 7.872 | 0.3405 | 22.3368
[22 empty] | Fuel | Material | LTR | 1.76 | 0.92593 | 1.9008 | 3.0645 | 5.3935
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 1.7 | 28.2353 | 1.6691 | 80.1176
[22 empty] | Fuel | Material | LTR | 1.76 | 0.17 | 10.3529 | 16.6912 | 29.3765
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 4.1667 | 8.64 | 0.681 | 24.516
[22 empty] | Fuel | Material | LTR | 1.76 | 0.46296 | 3.8016 | 6.129 | 10.787
[22 empty] | Plate Compactor | Machinery | HR | 23 | 1 | 23 | 2.8375 | 65.2625
[22 empty] | Fuel | Material | LTR | 1.76 | 0.33333 | 5.28 | 8.5125 | 14.982
PTW8 |  | Art (K): Pipeworks - manholes and pipework accessories (continued) |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
PTW8 |  | TD counter |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
PTW8 |  | Supply, installation and testing of flow meters, including pipes, accessories, installation parts, connections, chambers, supports, the high-resistance cast iron cover and its frame, concrete supports, clean concrete and complete brickwork in accordance with the plans, specifications and requirements of the concerned authority. |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
PTW8 |  | Flow meter on a 200 mm pipe. It includes a flow meter room with a depth of 2 - 2.5 meters. | nr |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
PTW8 |  | Flow meter on a 250 mm pipe. It includes a flow meter room with a depth of 2 - 2.5 meters. | nr |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
PTW8 |  | Flow meter on a 355 mm pipe. It includes a flow meter room with a depth of 2 - 2.5 meters. | nr | 6.34 | 47205 | 299279.7 | 28614.7896 | 181417.7659 | 6.34 | 6.34 |  | 6.34 | 100% | 47205 | 299279.7 | 28614.7896 | 181417.7659 |  | 181417.7659 | [7 empty] | 28614.7896 | 6.34 | 181417.7659 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 6.34 | 6.34 |  | 6.34 | [9 empty] | Excavate & Disposal (3*3*2.5) |  | Ea | 90.4969 |  | 90.4969 | 6.34 | 573.7506 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 4.4444 | 12.6 | 1.4265 | 79.884
[22 empty] | Fuel | Material | LTR | 1.76 | 0.31746 | 5.544 | 19.971 | 35.149
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.90667 | 52.9412 | 6.9926 | 335.6471
[22 empty] | Fuel | Material | LTR | 1.76 | 0.090667 | 19.4118 | 69.9265 | 123.0706
[9 empty] | 6.34 | 6.34 |  | 6.34 | [9 empty] | Flow meter & valve room installation |  | Ea | 25515.21 |  | 25515.21 | 6.34 | 161766.4314 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 1.1111 | 225 | 5.706 | 1426.5
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.2 | 1750 | 31.7 | 11095
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 2.5 | 1000 | 2.536 | 6340
[22 empty] | Workmanship plain concrete | SC | M³ | 150 | 1.1111 | 135 | 5.706 | 855.9
[22 empty] | Workmanship RC concrete | SC | M³ | 450 | 0.2 | 2250 | 31.7 | 14265
[22 empty] | Supply & apply Chamber Cover, frames | Material | Ea | 3500 | 1 | 3500 | 6.34 | 22190
[22 empty] | Supply & apply Flow Meter 355 mm | Material | Ea | 16328.61 | 1 | 16328.61 | 6.34 | 103523.3874
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 4 | 20 | 1.585 | 126.8
[22 empty] | Fuel | Material | HR | 1.76 | 0.26667 | 6.6 | 23.775 | 41.844
[22 empty] | Chamber Pipes Pieces | Material | LS | 150 | 1 | 150 | 6.34 | 951
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.2 | 85 | 31.7 | 538.9
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.2 | 65 | 31.7 | 412.1
[9 empty] | 6.34 | 6.34 |  | 6.34 | [9 empty] | Internal and external Insulation |  | Ea | 2800 |  | 2800 | 6.34 | 17752 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply & apply external waterproofing | SC | M² | 40 | 0.025 | 1600 | 253.6 | 10144
[22 empty] | Supply & apply internal coating | SC | M² | 30 | 0.025 | 1200 | 253.6 | 7608
[9 empty] | 6.34 | 6.34 |  | 6.34 | [9 empty] | Backfilling |  | Ea | 209.0826 |  | 209.0826 | 6.34 | 1325.5839 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.083333 | 120 | 76.08 | 760.8
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 8.3333 | 7.872 | 0.7608 | 49.9085
[22 empty] | Fuel | Material | LTR | 1.76 | 0.92593 | 1.9008 | 6.8472 | 12.0511
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 1.7 | 28.2353 | 3.7294 | 179.0118
[22 empty] | Fuel | Material | LTR | 1.76 | 0.17 | 10.3529 | 37.2941 | 65.6376
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 4.1667 | 8.64 | 1.5216 | 54.7776
[22 empty] | Fuel | Material | LTR | 1.76 | 0.46296 | 3.8016 | 13.6944 | 24.1021
[22 empty] | Plate Compactor | Machinery | HR | 23 | 1 | 23 | 6.34 | 145.82
[22 empty] | Fuel | Material | LTR | 1.76 | 0.33333 | 5.28 | 19.02 | 33.4752
PTW8 |  | Flow meter on a 560 mm pipe, including a flow meter chamber with a depth of 2.5 - 3.0 meters. | nr | 0.81 | 71752 | 58119.12 | 49411.3728 | 40023.212 | 0.81 | 0.81 |  | 0.81 | 100% | 71752 | 58119.12 | 49411.3728 | 40023.212 |  | 40023.212 | [7 empty] | 49411.3728 | 0.81 | 40023.212 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 0.81 | 0.81 |  | 0.81 | [9 empty] | Excavate & Disposal (3*3*3.0) |  | Ea | 108.5963 |  | 108.5963 | 0.81 | 87.963 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 3.7037 | 15.12 | 0.2187 | 12.2472
[22 empty] | Fuel | Material | LTR | 1.76 | 0.26455 | 6.6528 | 3.0618 | 5.3888
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.75556 | 63.5294 | 1.0721 | 51.4588
[22 empty] | Fuel | Material | LTR | 1.76 | 0.075556 | 23.2941 | 10.7206 | 18.8682
[9 empty] | 0.81 | 0.81 |  | 0.81 | [9 empty] | Flow meter & valve room installation |  | Ea | 45686.6 |  | 45686.6 | 0.81 | 37006.146 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 1.1111 | 225 | 0.729 | 182.25
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.16 | 2187.5 | 5.0625 | 1771.875
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 2 | 1250 | 0.405 | 1012.5
[22 empty] | Workmanship plain concrete | SC | M³ | 150 | 1.1111 | 135 | 0.729 | 109.35
[22 empty] | Workmanship RC concrete | SC | M³ | 450 | 0.16 | 2812.5 | 5.0625 | 2278.125
[22 empty] | Supply & apply Chamber Cover, frames | Material | Ea | 3500 | 1 | 3500 | 0.81 | 2835
[22 empty] | Supply & apply Flow Meter 560 mm | Material | Ea | 35250 | 1 | 35250 | 0.81 | 28552.5
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 4 | 20 | 0.2025 | 16.2
[22 empty] | Fuel | Material | HR | 1.76 | 0.26667 | 6.6 | 3.0375 | 5.346
[22 empty] | Chamber Pipes Pieces | Material | LS | 150 | 1 | 150 | 0.81 | 121.5
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.2 | 85 | 4.05 | 68.85
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.2 | 65 | 4.05 | 52.65
[9 empty] | 0.81 | 0.81 |  | 0.81 | [9 empty] | Internal and external Insulation |  | Ea | 3360 |  | 3360 | 0.81 | 2721.6 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply & apply external waterproofing | SC | M² | 40 | 0.020833 | 1920 | 38.88 | 1555.2
[22 empty] | Supply & apply internal coating | SC | M² | 30 | 0.020833 | 1440 | 38.88 | 1166.4
[9 empty] | 0.81 | 0.81 |  | 0.81 | [9 empty] | Backfilling |  | Ea | 256.1765 |  | 256.1765 | 0.81 | 207.503 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.068966 | 145 | 11.745 | 117.45
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 6.8966 | 9.512 | 0.11745 | 7.7047
[22 empty] | Fuel | Material | LTR | 1.76 | 0.76628 | 2.2968 | 1.0571 | 1.8604
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 1.4069 | 34.1176 | 0.57574 | 27.6353
[22 empty] | Fuel | Material | LTR | 1.76 | 0.14069 | 12.5098 | 5.7574 | 10.1329
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 3.4483 | 10.44 | 0.2349 | 8.4564
[22 empty] | Fuel | Material | LTR | 1.76 | 0.38314 | 4.5936 | 2.1141 | 3.7208
[22 empty] | Plate Compactor | Machinery | HR | 23 | 0.75 | 30.6667 | 1.08 | 24.84
[22 empty] | Fuel | Material | LTR | 1.76 | 0.25 | 7.04 | 3.24 | 5.7024
PTW8 |  | Flow meter on a 710 mm pipe, including a flow meter chamber with a depth of 2.5 - 3.0 meters. | m | 1.82 | 80690 | 146855.8 | 62661.3728 | 114043.6986 | 1.82 | 1.82 |  | 1.82 | 100% | 80690 | 146855.8 | 62661.3728 | 114043.6986 |  | 114043.6986 | [7 empty] | 62661.3728 | 1.82 | 114043.6986 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 1.82 | 1.82 |  | 1.82 | [9 empty] | Excavate & Disposal (3*3*3.0) |  | Ea | 108.5963 |  | 108.5963 | 1.82 | 197.6453 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 3.7037 | 15.12 | 0.4914 | 27.5184
[22 empty] | Fuel | Material | LTR | 1.76 | 0.26455 | 6.6528 | 6.8796 | 12.1081
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.75556 | 63.5294 | 2.4088 | 115.6235
[22 empty] | Fuel | Material | LTR | 1.76 | 0.075556 | 23.2941 | 24.0882 | 42.3953
[9 empty] | 1.82 | 1.82 |  | 1.82 | [9 empty] | Flow meter & valve room installation |  | Ea | 58936.6 |  | 58936.6 | 1.82 | 107264.612 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 1.1111 | 225 | 1.638 | 409.5
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.16 | 2187.5 | 11.375 | 3981.25
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 2 | 1250 | 0.91 | 2275
[22 empty] | Workmanship plain concrete | SC | M³ | 150 | 1.1111 | 135 | 1.638 | 245.7
[22 empty] | Workmanship RC concrete | SC | M³ | 450 | 0.16 | 2812.5 | 11.375 | 5118.75
[22 empty] | Supply & apply Chamber Cover, frames | Material | Ea | 3500 | 1 | 3500 | 1.82 | 6370
[22 empty] | Supply & apply Flow Meter 710 mm | Material | Ea | 48500 | 1 | 48500 | 1.82 | 88270
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 4 | 20 | 0.455 | 36.4
[22 empty] | Fuel | Material | HR | 1.76 | 0.26667 | 6.6 | 6.825 | 12.012
[22 empty] | Chamber Pipes Pieces | Material | LS | 150 | 1 | 150 | 1.82 | 273
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.2 | 85 | 9.1 | 154.7
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.2 | 65 | 9.1 | 118.3
[9 empty] | 1.82 | 1.82 |  | 1.82 | [9 empty] | Internal and external Insulation |  | Ea | 3360 |  | 3360 | 1.82 | 6115.2 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply & apply external waterproofing | SC | M² | 40 | 0.020833 | 1920 | 87.36 | 3494.4
[22 empty] | Supply & apply internal coating | SC | M² | 30 | 0.020833 | 1440 | 87.36 | 2620.8
[9 empty] | 1.82 | 1.82 |  | 1.82 | [9 empty] | Backfilling |  | Ea | 256.1765 |  | 256.1765 | 1.82 | 466.2413 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.068966 | 145 | 26.39 | 263.9
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 6.8966 | 9.512 | 0.2639 | 17.3118
[22 empty] | Fuel | Material | LTR | 1.76 | 0.76628 | 2.2968 | 2.3751 | 4.1802
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 1.4069 | 34.1176 | 1.2936 | 62.0941
[22 empty] | Fuel | Material | LTR | 1.76 | 0.14069 | 12.5098 | 12.9363 | 22.7678
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 3.4483 | 10.44 | 0.5278 | 19.0008
[22 empty] | Fuel | Material | LTR | 1.76 | 0.38314 | 4.5936 | 4.7502 | 8.3604
[22 empty] | Plate Compactor | Machinery | HR | 23 | 0.75 | 30.6667 | 2.4267 | 55.8133
[22 empty] | Fuel | Material | LTR | 1.76 | 0.25 | 7.04 | 7.28 | 12.8128
PTW8 |  | Connections to plots of land |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
PTW8 |  | Supply, installation, testing, and connections for plots of land, including all parts such as pipes, fittings, valves, pipe end caps, all accessories, pipe fittings, and complete construction and installation work, as shown in the plans and specifications in accordance with the requirements of the designated area (the pipes included above are type 1) |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
PTW8 |  | Connections to plots of land with a depth scale of less than 1.5 m | nr |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
PTW8 |  | Backfill materials under and around pipes - Type (A) |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
PTW8 |  | Of granular or gravel material, it is well compacted under the pipe and on its sides in accordance with the specifications, plans and what the Authority requires. |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
PTW8 |  | Pipes with a diameter not exceeding 200 mm | m |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
PTW8 |  | Pipes with a diameter not exceeding 225 mm | m |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
PTW8 |  | Pipes with a diameter not exceeding 250 mm | m |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
PTW8 |  | Pipes with a diameter not exceeding 355 mm | m |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
PTW8 |  | Pipes with a diameter not exceeding 560 mm | m |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
PTW8 |  | Pipes with a diameter not exceeding 710 mm | m |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
PTW8 |  | Made of materials selected from the drilling output and stacked at 95% of the maximum dry density of the pipes at different levels in accordance with the specifications, plans and what the Authority requires. |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
PTW8 |  | Pipes with a diameter not exceeding 200 mm | m | 2342.564 | 31 | 72619.484 | 13.0872 | 30657.5913 | 2342.564 | 2342.564 |  | 2342.564 | 100% | 31 | 72619.484 | 13.0872 | 30657.5913 |  | 30657.5913 | [7 empty] | 13.0872 | 2342.564 | 30657.5913 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 2342.564 | 2342.564 |  | 2342.564 | [9 empty] | Backfilling (W=1.0, D=2.0) |  | M | 13.0872 |  | 13.0872 | 2342.564 | 30657.5913 | 0 | 0 | 0 | 0 | 0
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 50 | 1.312 | 46.8513 | 3073.444
[22 empty] | Fuel | Material | LTR | 1.76 | 5.5556 | 0.3168 | 421.6615 | 742.1243
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 10.2 | 4.7059 | 229.6631 | 11023.8306
[22 empty] | Fuel | Material | LTR | 1.76 | 1.02 | 1.7255 | 2296.6314 | 4042.0712
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 25 | 1.44 | 93.7026 | 3373.2922
[22 empty] | Fuel | Material | LTR | 1.76 | 2.7778 | 0.6336 | 843.323 | 1484.2486
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 36 | 1.3333 | 65.0712 | 3123.4187
[22 empty] | Fuel | Material | LTR | 1.76 | 3.6 | 0.48889 | 650.7122 | 1145.2535
[22 empty] | Plate Compactor | Machinery | HR | 23 | 25 | 0.92 | 93.7026 | 2155.1589
[22 empty] | Fuel | Material | LTR | 1.76 | 8.3333 | 0.2112 | 281.1077 | 494.7495
PTW8 |  | Pipes with a diameter not exceeding 225 mm | m | 2369.53 | 35 | 82933.55 | 13.0872 | 31010.5006 | 2369.53 | 2369.53 |  | 2369.53 | 100% | 35 | 82933.55 | 13.0872 | 31010.5006 |  | 31010.5006 | [7 empty] | 13.0872 | 2369.53 | 31010.5006 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 2369.53 | 2369.53 |  | 2369.53 | [9 empty] | Backfilling (W=1.0, D=2.0) |  | M | 13.0872 |  | 13.0872 | 2369.53 | 31010.5006 | 0 | 0 | 0 | 0 | 0
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 50 | 1.312 | 47.3906 | 3108.8234
[22 empty] | Fuel | Material | LTR | 1.76 | 5.5556 | 0.3168 | 426.5154 | 750.6671
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 10.2 | 4.7059 | 232.3069 | 11150.7294
[22 empty] | Fuel | Material | LTR | 1.76 | 1.02 | 1.7255 | 2323.0686 | 4088.6008
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 25 | 1.44 | 94.7812 | 3412.1232
[22 empty] | Fuel | Material | LTR | 1.76 | 2.7778 | 0.6336 | 853.0308 | 1501.3342
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 36 | 1.3333 | 65.8203 | 3159.3733
[22 empty] | Fuel | Material | LTR | 1.76 | 3.6 | 0.48889 | 658.2028 | 1158.4369
[22 empty] | Plate Compactor | Machinery | HR | 23 | 25 | 0.92 | 94.7812 | 2179.9676
[22 empty] | Fuel | Material | LTR | 1.76 | 8.3333 | 0.2112 | 284.3436 | 500.4447
PTW8 |  | Pipes with a diameter not exceeding 250 mm | m | 1283.887 | 43 | 55207.141 | 13.0872 | 16802.4792 | 1283.887 | 1283.887 |  | 1283.887 | 100% | 43 | 55207.141 | 13.0872 | 16802.4792 |  | 16802.4792 | [7 empty] | 13.0872 | 1283.887 | 16802.4792 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 1283.887 | 1283.887 |  | 1283.887 | [9 empty] | Backfilling (W=1.0, D=2.0) |  | M | 13.0872 |  | 13.0872 | 1283.887 | 16802.4792 | 0 | 0 | 0 | 0 | 0
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 50 | 1.312 | 25.6777 | 1684.4597
[22 empty] | Fuel | Material | LTR | 1.76 | 5.5556 | 0.3168 | 231.0997 | 406.7354
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 10.2 | 4.7059 | 125.8713 | 6041.8212
[22 empty] | Fuel | Material | LTR | 1.76 | 1.02 | 1.7255 | 1258.7127 | 2215.3344
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 25 | 1.44 | 51.3555 | 1848.7973
[22 empty] | Fuel | Material | LTR | 1.76 | 2.7778 | 0.6336 | 462.1993 | 813.4708
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 36 | 1.3333 | 35.6635 | 1711.8493
[22 empty] | Fuel | Material | LTR | 1.76 | 3.6 | 0.48889 | 356.6353 | 627.6781
[22 empty] | Plate Compactor | Machinery | HR | 23 | 25 | 0.92 | 51.3555 | 1181.176
[22 empty] | Fuel | Material | LTR | 1.76 | 8.3333 | 0.2112 | 154.0664 | 271.1569
PTW8 |  | Pipes with a diameter not exceeding 355 mm | m |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
PTW8 |  | Pipes with a diameter not exceeding 560 mm | m |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
PTW8 |  | Pipes with a diameter not exceeding 710 mm | m |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
PTW8 |  | Concrete anchor blocks to prevent pipe movement (Thrust Block) Concrete stabilization blocks to prevent movement at elbows or other installation parts of various diameters, including formwork, reinforcement, concrete, etc., in accordance with the requirements of the concerned authorities and specifications. |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
PTW8 |  | Block volume from 0-1 cubic meter | nr | 87.125 | 755 | 65779.375 | 675 | 58809.375 | 87.125 | 87.125 |  | 87.125 | 100% | 755 | 65779.375 | 675 | 58809.375 |  | 58809.375 | [7 empty] | 675 | 87.125 | 58809.375 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 87.125 | 87.125 |  | 87.125 | [9 empty] | Thrust Block (0.75 m³) |  | Ea | 675 |  | 675 | 87.125 | 58809.375 | 0 | 0 | 0 | 0 | 0
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 1.3333 | 262.5 | 65.3437 | 22870.3125
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 16.6667 | 150 | 5.2275 | 13068.75
[22 empty] | Workmanship Thrust Block | SC | M³ | 350 | 1.3333 | 262.5 | 65.3437 | 22870.3125
PTW8 |  | The block volume is 1-2 cubes | nr | 59.575 | 1133 | 67498.475 | 1350 | 80426.25 | 59.575 | 59.575 |  | 59.575 | 100% | 1133 | 67498.475 | 1350 | 80426.25 |  | 80426.25 | [7 empty] | 1350 | 59.575 | 80426.25 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 59.575 | 59.575 |  | 59.575 | [9 empty] | Thrust Block (1.5 m³) |  | Ea | 1350 |  | 1350 | 59.575 | 80426.25 | 0 | 0 | 0 | 0 | 0
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.66667 | 525 | 89.3625 | 31276.875
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 8.3333 | 300 | 7.149 | 17872.5
[22 empty] | Workmanship Thrust Block | SC | M³ | 350 | 0.66667 | 525 | 89.3625 | 31276.875
PTW8 |  | The block size is 2-4 cubes | nr | 28.6 | 4249 | 121521.4 | 2700 | 77220 | 28.6 | 28.6 |  | 28.6 | 100% | 4249 | 121521.4 | 2700 | 77220 |  | 77220 | [7 empty] | 2700 | 28.6 | 77220 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 28.6 | 28.6 |  | 28.6 | [9 empty] | Thrust Block (3.0 m³) |  | Ea | 2700 |  | 2700 | 28.6 | 77220 | 0 | 0 | 0 | 0 | 0
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.33333 | 1050 | 85.8 | 30030
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 4.1667 | 600 | 6.864 | 17160
[22 empty] | Workmanship Thrust Block | SC | M³ | 350 | 0.33333 | 1050 | 85.8 | 30030
PTW8 |  | The block volume is 4-6 cubes | nr | 6.25 | 4532 | 28325 | 4500 | 28125 | 6.25 | 6.25 |  | 6.25 | 100% | 4532 | 28325 | 4500 | 28125 |  | 28125 | [7 empty] | 4500 | 6.25 | 28125 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 6.25 | 6.25 |  | 6.25 | [9 empty] | Thrust Block (5.0 m³) |  | Ea | 4500 |  | 4500 | 6.25 | 28125 | 0 | 0 | 0 | 0 | 0
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.2 | 1750 | 31.25 | 10937.5
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 2.5 | 1000 | 2.5 | 6250
[22 empty] | Workmanship Thrust Block | SC | M³ | 350 | 0.2 | 1750 | 31.25 | 10937.5
PTW8 |  | Block volume of 6 cube | nr | 27.65 | 10763 | 297596.95 | 5400 | 149310 | 27.65 | 27.65 |  | 27.65 | 100% | 10763 | 297596.95 | 5400 | 149310 |  | 149310 | [7 empty] | 5400 | 27.65 | 149310 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 27.65 | 27.65 |  | 27.65 | [9 empty] | Thrust Block (6.0 m³) |  | Ea | 5400 |  | 5400 | 27.65 | 149310 | 0 | 0 | 0 | 0 | 0
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.16667 | 2100 | 165.9 | 58065
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 2.0833 | 1200 | 13.272 | 33180
[22 empty] | Workmanship Thrust Block | SC | M³ | 350 | 0.16667 | 2100 | 165.9 | 58065
PTW8 |  | Extra work |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
PTW8 |  | Additional excavation and backfilling works, drilling into rock to various depths, including disposal of waste to approved locations, warning tapes, and dewatering. | m³ | 1 | 50 | 50 | 30.658 | 30.658 | 1 | 1 |  | 1 | 100% | 50 | 50 | 30.658 | 30.658 |  | 30.658 | [7 empty] | 30.658 | 1 | 30.658 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 1 | 1 |  | 1 | [9 empty] | Rock Excavation & Disposal |  | M³ | 22.3553 |  | 22.3553 | 1 | 22.3553 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Hydraulic Hammer 50T | Machinery | HR | 150.4 | 15 | 10.0267 | 0.066667 | 10.0267
[22 empty] | Fuel | Material | LTR | 1.76 | 0.46875 | 3.7547 | 2.1333 | 3.7547
[22 empty] | Excavator with Bucket 50T | Machinery | HR | 131.2 | 50 | 2.624 | 0.02 | 2.624
[22 empty] | Fuel | Material | LTR | 1.76 | 1.5625 | 1.1264 | 0.64 | 1.1264
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 13.6 | 3.5294 | 0.073529 | 3.5294
[22 empty] | Fuel | Material | LTR | 1.76 | 1.36 | 1.2941 | 0.73529 | 1.2941
[9 empty] | 1 | 1 |  | 1 | [9 empty] | Backfilling & Compaction |  | M³ | 8.3027 |  | 8.3027 | 1 | 8.3027 | 0 | 0 | 0 | 0 | 0
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 100 | 0.656 | 0.01 | 0.656
[22 empty] | Fuel | Material | LTR | 1.76 | 11.1111 | 0.1584 | 0.09 | 0.1584
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 13.6 | 3.5294 | 0.073529 | 3.5294
[22 empty] | Fuel | Material | LTR | 1.76 | 1.36 | 1.2941 | 0.73529 | 1.2941
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 50 | 0.72 | 0.02 | 0.72
[22 empty] | Fuel | Material | LTR | 1.76 | 5.5556 | 0.3168 | 0.18 | 0.3168
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 80 | 0.6 | 0.0125 | 0.6
[22 empty] | Fuel | Material | LTR | 1.76 | 8 | 0.22 | 0.125 | 0.22
[22 empty] | Roller Compactor 10 Ton | Machinery | HR | 40 | 80 | 0.5 | 0.0125 | 0.5
[22 empty] | Fuel | Material | LTR | 1.76 | 5.7143 | 0.308 | 0.175 | 0.308
PTW8 |  | Pumping station made of reinforced concrete/reinforced fiberglass plastic, M & E design model, including excavation and lining works, with a single and tight type cover, and surface pipes, and completion of all pipe extension works and accessories inside the room, pumps, and valves room (cocks), with MCC & DB water flow control pipes, electrical connection with Breakers, installed according to specifications and drawings. |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
PTW8 |  | KW250 electric water pump with capacity (295 litres/second and 60m pressure with the possibility of installing variable speed pumps with MCC) | nr | 1.4065 | 1022781 | 1438541.4765 | 630093.75 | 886226.8594 | 1.4065 | 1.4065 |  | 1.4065 | 100% | 1022781 | 1438541.4765 | 630093.75 | 886226.8594 |  | 886226.8594 | [7 empty] | 630093.75 | 1.4065 | 886226.8594 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 1.4065 | 1.4065 |  | 1.4065 | [9 empty] | Water Pump |  | Ea | 630093.75 |  | 630093.75 | 1.4065 | 886226.8594 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply & apply KW250 elec water pump 295 l/s | SC | Ea | 630093.75 | 1 | 630093.75 | 1.4065 | 886226.8594
PTW8 |  | Electric fire water pump with capacity (64 litres/second and pressure 60 m) (with the possibility of installing variable speed pumps) | nr | 1 | 314702 | 314702 | 193875 | 193875 | 1 | 1 |  | 1 | 100% | 314702 | 314702 | 193875 | 193875 |  | 193875 | [7 empty] | 193875 | 1 | 193875 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 1 | 1 |  | 1 | [9 empty] | Electric Fire Pump |  | Ea | 193875 |  | 193875 | 1 | 193875 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply & apply elec fire water pump 64 l/s | SC | Ea | 193875 | 1 | 193875 | 1 | 193875
PTW8 |  | Diesel fire water pump with capacity (64 litres/second and pressure 60 m) with the possibility of installing variable speed pumps | nr | 1 | 283232 | 283232 | 174487.5 | 174487.5 | 1 | 1 |  | 1 | 100% | 283232 | 283232 | 174487.5 | 174487.5 |  | 174487.5 | [7 empty] | 174487.5 | 1 | 174487.5 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 1 | 1 |  | 1 | [9 empty] | Diesel Fire Pump |  | Ea | 174487.5 |  | 174487.5 | 1 | 174487.5 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply & apply Diesel fire water pump 64 l/s | SC | Ea | 174487.5 | 1 | 174487.5 | 1 | 174487.5
PTW8 |  | Jockey electric fire water pump with capacity (64 litres/second and pressure 60 m) with the possibility of installing variable speed pumps | nr | 1 | 157351 | 157351 | 69937.5 | 69937.5 | 1 | 1 |  | 1 | 100% | 157351 | 157351 | 69937.5 | 69937.5 |  | 69937.5 | [7 empty] | 69937.5 | 1 | 69937.5 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 1 | 1 |  | 1 | [9 empty] | Jockey Electric Fire Pump |  | Ea | 69937.5 |  | 69937.5 | 1 | 69937.5 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply & apply Jockey elec fire pump 64 l/s | SC | Ea | 69937.5 | 1 | 69937.5 | 1 | 69937.5
PTW8 |  | Submersible electric fire water pump with a capacity of 10 liters/second and a pressure of 10 m (with the possibility of installing variable-speed pumps | nr | 2 | 59793 | 119586 | 49115 | 98230 | 2 | 2 |  | 2 | 100% | 59793 | 119586 | 49115 | 98230 |  | 98230 | [7 empty] | 49115 | 2 | 98230 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 2 | 2 |  | 2 | [9 empty] | Submersible Electric Fire Pump |  | Ea | 49115 |  | 49115 | 2 | 98230 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply & apply Submersible fire pump 10 l/s | SC | Ea | 49115 | 1 | 49115 | 2 | 98230
PTW8 |  | Surge vessel and pipe work as per surge analysis | nr | 1 | 46262 | 46262 | 28500 | 28500 | 1 | 1 |  | 1 | 100% | 46262 | 46262 | 28500 | 28500 |  | 28500 | [7 empty] | 28500 | 1 | 28500 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 1 | 1 |  | 1 | [9 empty] | Surge vessel |  | Ea | 28500 |  | 28500 | 1 | 28500 | 0 | 0 | 0 | 0 | 0
[22 empty] | Surge vessel and pipe work | SC | Ea | 28500 | 1 | 28500 | 1 | 28500
PTW8 |  | Flow meter on an 800 mm pipe. It includes a flow meter room with a depth of 2 - 2.5 meters. | nr | 0.5944 | 456530 | 271361.432 | 192406.9462 | 114366.6888 | 0.5944 | 0.5944 |  | 0.5944 | 100% | 456530 | 271361.432 | 192406.9462 | 114366.6888 |  | 114366.6888 | [7 empty] | 192406.9462 | 0.5944 | 114366.6888 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 0.5944 | 0.5944 |  | 0.5944 | [9 empty] | Excavate & Disposal (3.5*3.5*2.5) |  | Ea | 123.1764 |  | 123.1764 | 0.5944 | 73.216 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 3.2653 | 17.15 | 0.18204 | 10.194
[22 empty] | Fuel | Material | LTR | 1.76 | 0.23324 | 7.546 | 2.5485 | 4.4853
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.66612 | 72.0588 | 0.89233 | 42.8318
[22 empty] | Fuel | Material | LTR | 1.76 | 0.066612 | 26.4216 | 8.9233 | 15.705
[9 empty] | 0.5944 | 0.5944 |  | 0.5944 | [9 empty] | Flow meter & valve room installation |  | Ea | 187829.1 |  | 187829.1 | 0.5944 | 111645.617 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 0.81633 | 306.25 | 0.72814 | 182.035
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.128 | 2734.375 | 4.6437 | 1625.3125
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 1.6 | 1562.5 | 0.3715 | 928.75
[22 empty] | Workmanship plain concrete | SC | M³ | 150 | 0.81633 | 183.75 | 0.72814 | 109.221
[22 empty] | Workmanship RC concrete | SC | M³ | 450 | 0.128 | 3515.625 | 4.6437 | 2089.6875
[22 empty] | Supply & apply Chamber Cover, frames | Material | Ea | 3500 | 1 | 3500 | 0.5944 | 2080.4
[22 empty] | Supply & apply Flow Meter 800 mm | Material | Ea | 175250 | 1 | 175250 | 0.5944 | 104168.6
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 4 | 20 | 0.1486 | 11.888
[22 empty] | Fuel | Material | HR | 1.76 | 0.26667 | 6.6 | 2.229 | 3.923
[22 empty] | Chamber Pipes Pieces | Material | LS | 150 | 0.25 | 600 | 2.3776 | 356.64
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.2 | 85 | 2.972 | 50.524
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.2 | 65 | 2.972 | 38.636
[9 empty] | 0.5944 | 0.5944 |  | 0.5944 | [9 empty] | Internal and external Insulation |  | Ea | 4200 |  | 4200 | 0.5944 | 2496.48 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply & apply external waterproofing | SC | M² | 40 | 0.016667 | 2400 | 35.664 | 1426.56
[22 empty] | Supply & apply internal coating | SC | M² | 30 | 0.016667 | 1800 | 35.664 | 1069.92
[9 empty] | 0.5944 | 0.5944 |  | 0.5944 | [9 empty] | Backfilling |  | Ea | 254.6698 |  | 254.6698 | 0.5944 | 151.3757 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.069444 | 144 | 8.5594 | 85.5936
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 6.9444 | 9.4464 | 0.085594 | 5.6149
[22 empty] | Fuel | Material | LTR | 1.76 | 0.7716 | 2.281 | 0.77034 | 1.3558
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 1.4167 | 33.8824 | 0.41958 | 20.1397
[22 empty] | Fuel | Material | LTR | 1.76 | 0.14167 | 12.4235 | 4.1958 | 7.3845
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 3.4722 | 10.368 | 0.17119 | 6.1627
[22 empty] | Fuel | Material | LTR | 1.76 | 0.3858 | 4.5619 | 1.5407 | 2.7116
[22 empty] | Plate Compactor | Machinery | HR | 23 | 0.75 | 30.6667 | 0.79253 | 18.2283
[22 empty] | Fuel | Material | LTR | 1.76 | 0.25 | 7.04 | 2.3776 | 4.1846
PTW8 |  | A pumping station building with a complete 5t crane in accordance with what is stated in the specifications, plans and the Authority’s approval. | nr | 0.09 | 472053 | 42484.77 | 1061111.1111 | 95500 | 0.09 | 0.09 |  | 0.09 | 100% | 472053 | 42484.77 | 1061111.1111 | 95500 |  | 95500 | [7 empty] | 1061111.1111 | 0.09 | 95500 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 0.09 | 0.09 |  | 0.09 | [9 empty] | Pumping Station Building (Remining Work) |  | Ea | 1061111.1111 |  | 1061111.1111 | 0.09 | 95500 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply& apply painting for toilets & Chloride | SC | LS | 20000 | 0.09 | 222222.2222 | 1 | 20000
[22 empty] | Supply & apply Steel ladders | SC | LS | 40000 | 0.09 | 444444.4444 | 1 | 40000
[22 empty] | Supply & Install doors and windows | SC | LS | 35500 | 0.09 | 394444.4444 | 1 | 35500
PTW8 |  | A tank built of reinforced concrete, including excavation work, waterproofing, lining with a leak-proof membrane, installing a heavy-duty steel cover, the inlet and overflow pipes, complete pipe extension works and their supplies, making a protection layer of reinforced concrete, walls and other works and insulation layer, connecting to pumping rooms, valves, water level indicators, super-flow rooms, inspection paths, installing a protective fence around the tank and other necessary works, completed in all respects according to what is stated in the specifications, plans and approval. Body. |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
PTW8 |  | Water storage basin made of reinforced concrete (at each pumping station, capacity 21.678 cubic metres). | nr |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
PTW8 |  | Price difference between a reinforced concrete tank with a capacity of 25,000 m3 and between two reinforced concrete tanks with a capacity of 43,000 m3 | nr | 0.56637 | 14930039 | 8455961.9583 | 9272697.6785 | 5251800 | 0.56637 | 0.56637 |  | 0.56637 | 100% | 14930039 | 8455961.9583 | 9272697.6785 | 5251800 |  | 5251800 | [7 empty] | 9272697.6785 | 0.56637 | 5251800 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 0.56637 | 0.56637 |  | 0.56637 | [9 empty] | Reinforced Concrete Tank (Remining Works) |  | Ea | 9272697.6785 |  | 9272697.6785 | 0.56637 | 5251800 | 0 | 0 | 0 | 0 | 0
[22 empty] | Reinforced Concrete Tank (Remining Works) | SC | Ea | 5251800 | 0.56637 | 9272697.6785 | 1 | 5251800
PTW8 |  | 500 kVA generator Standby generator with umbrella tank in accordance with what is stated in the specifications, drawings and the authority’s approval. | ls | 1.53 | 3054459 | 4673322.27 | 1181727.9412 | 1808043.75 | 1.53 | 1.53 |  | 1.53 | 100% | 3054459 | 4673322.27 | 1181727.9412 | 1808043.75 |  | 1808043.75 | [7 empty] | 1181727.9412 | 1.53 | 1808043.75 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 1.53 | 1.53 |  | 1.53 | [9 empty] | 500 KVA Generator |  | Ea | 1181727.9412 |  | 1181727.9412 | 1.53 | 1808043.75 | 0 | 0 | 0 | 0 | 0
[22 empty] | 500 KVA generator with umbrella tank | SC | Ea | 1181727.9412 | 1 | 1181727.9412 | 1.53 | 1808043.75
PTW8 |  | Chlorination device according to specifications and drawings. | ls | 1 | 849695 | 849695 | 323462.5 | 323462.5 | 1 | 1 |  | 1 | 100% | 849695 | 849695 | 323462.5 | 323462.5 |  | 323462.5 | [7 empty] | 323462.5 | 1 | 323462.5 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 1 | 1 |  | 1 | [9 empty] | Chlorination device |  | Ea | 323462.5 |  | 323462.5 | 1 | 323462.5 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply and apply Chlorination device | SC | Ea | 323462.5 | 1 | 323462.5 | 1 | 323462.5
PTW8 |  | Street lighting according to specifications and plans | ls | 1 | 786755 | 786755 | 353479.2776 | 353479.2776 | 1 | 1 |  | 1 | 100% | 786755 | 786755 | 353479.2776 | 353479.2776 |  | 353479.2776 | [7 empty] | 353479.2776 | 1 | 353479.2776 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 1 | 1 |  | 1 | [9 empty] | Excavation & Disposal for 30 Poles |  | LS | 397.6299 |  | 397.6299 | 1 | 397.6299 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 1.9753 | 28.35 | 0.50625 | 28.35
[22 empty] | Fuel | Material | LTR | 1.76 | 0.14109 | 12.474 | 7.0875 | 12.474
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.45333 | 105.8824 | 2.2059 | 105.8824
[22 empty] | Fuel | Material | LTR | 1.76 | 0.045333 | 38.8235 | 22.0588 | 38.8235
[22 empty] | Plate Compactor | Machinery | HR | 23 | 0.13333 | 172.5 | 7.5 | 172.5
[22 empty] | Fuel | Material | LTR | 1.76 | 0.044444 | 39.6 | 22.5 | 39.6
[9 empty] | 1 | 1 |  | 1 | [9 empty] | 30 Lighting Poles |  | Ea | 352500 |  | 352500 | 1 | 352500 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply & apply lighting Poles with laminars | SC | LS | 9500 | 0.033333 | 285000 | 30 | 285000
[22 empty] | Supply & apply Poles Foundations | SC | LS | 750 | 0.033333 | 22500 | 30 | 22500
[22 empty] | Electric source (Junction Boxes, cables, .. Etc) | SC | LS | 1500 | 0.033333 | 45000 | 30 | 45000
[9 empty] | 1 | 1 |  | 1 | [9 empty] | Backfilling & Compaction for 30 Poles |  | M³ | 581.6478 |  | 581.6478 | 1 | 581.6478 | 0 | 0 | 0 | 0 | 0
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 3.3333 | 19.68 | 0.3 | 19.68
[22 empty] | Fuel | Material | LTR | 1.76 | 0.37037 | 4.752 | 2.7 | 4.752
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.22667 | 211.7647 | 4.4118 | 211.7647
[22 empty] | Fuel | Material | LTR | 1.76 | 0.022667 | 77.6471 | 44.1176 | 77.6471
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 1.6667 | 21.6 | 0.6 | 21.6
[22 empty] | Fuel | Material | LTR | 1.76 | 0.18519 | 9.504 | 5.4 | 9.504
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 2.6667 | 18 | 0.375 | 18
[22 empty] | Fuel | Material | LTR | 1.76 | 0.26667 | 6.6 | 3.75 | 6.6
[22 empty] | Plate Compactor | Machinery | HR | 23 | 0.13333 | 172.5 | 7.5 | 172.5
[22 empty] | Fuel | Material | LTR | 1.76 | 0.044444 | 39.6 | 22.5 | 39.6
PTW8 |  | Extra work |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
PTW8 |  | Additional excavation and backfilling works, drilling into rock to various depths, including disposal of waste to approved locations, warning tapes, and dewatering. | m³ |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
Category (I): Piping works - pipes
IRR 9 |  | HDPE pipe, HDPE, PE 100, SDR 11, for (PN 16) rod |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
IRR 9 |  | Pipes with an outer diameter of 125 mm at a depth of less than 1.5 m | m | 6486.8264 | 139 | 901668.8731 | 106.1661 | 688680.8213 | 6486.8264 | 6486.8264 |  | 6486.8264 | 100% | 139 | 901668.8731 | 106.1661 | 688680.8213 |  | 688680.8213 | [7 empty] | 106.1661 | 6486.8264 | 688680.8213 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 6486.8264 | 6486.8264 |  | 6486.8264 | [9 empty] | Excavation ( W= 1.0 & d= 1.5 ) |  | M | 7.5827 |  | 7.5827 | 6486.8264 | 49187.8495 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 66.6667 | 0.84 | 97.3024 | 5448.9342
[22 empty] | Fuel | Material | LTR | 1.76 | 4.7619 | 0.3696 | 1362.2335 | 2397.531
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 13.6 | 3.5294 | 476.9725 | 22894.6815
[22 empty] | Fuel | Material | LTR | 1.76 | 1.36 | 1.2941 | 4769.7253 | 8394.7166
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 129.7365 | 2983.9402
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 389.2096 | 685.0089
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 66.6667 | 0.72 | 97.3024 | 4670.515
[22 empty] | Fuel | Material | LTR | 1.76 | 6.6667 | 0.264 | 973.024 | 1712.5222
[9 empty] | 6486.8264 | 6486.8264 |  | 6486.8264 | [9 empty] | Pipe Laying & Protection |  | M | 93.5833 |  | 93.5833 | 6486.8264 | 607058.8396 | 0 | 0 | 0 | 0 | 0
[22 empty] | 125 mm solid HDPE Pipe DR 11 | Material | M | 35 | 1 | 35 | 6486.8264 | 227038.9249
[22 empty] | 125 mm HDPE Pipe Installation | SC | M | 18 | 1 | 18 | 6486.8264 | 116762.8757
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 10 | 25 | 648.6826 | 162170.6606
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 10 | 15 | 648.6826 | 97302.3964
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 21.6228 | 3783.9821
[9 empty] | 6486.8264 | 6486.8264 |  | 6486.8264 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 6486.8264 | 32434.1321 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 6486.8264 | 32434.1321
IRR 9 |  | Pipes with an outer diameter of 125 mm at a depth of less than 1.5-2.0 m | m | 201.374 | 143 | 28796.4784 | 108.5051 | 21850.1045 | 201.374 | 201.374 |  | 201.374 | 100% | 143 | 28796.4784 | 108.5051 | 21850.1045 |  | 21850.1045 | [7 empty] | 108.5051 | 201.374 | 21850.1045 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 201.374 | 201.374 |  | 201.374 | [9 empty] | Excavation ( W= 1.0 & d= 2.0 ) |  | M | 9.9218 |  | 9.9218 | 201.374 | 1997.9868 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 50 | 1.12 | 4.0275 | 225.5389
[22 empty] | Fuel | Material | LTR | 1.76 | 3.5714 | 0.4928 | 56.3847 | 99.2371
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 10.2 | 4.7059 | 19.7425 | 947.6422
[22 empty] | Fuel | Material | LTR | 1.76 | 1.02 | 1.7255 | 197.4255 | 347.4688
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 4.0275 | 92.632
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 12.0824 | 21.2651
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 50 | 0.96 | 4.0275 | 193.319
[22 empty] | Fuel | Material | LTR | 1.76 | 5 | 0.352 | 40.2748 | 70.8836
[9 empty] | 201.374 | 201.374 |  | 201.374 | [9 empty] | Pipe Laying & Protection |  | M | 93.5833 |  | 93.5833 | 201.374 | 18845.2478 | 0 | 0 | 0 | 0 | 0
[22 empty] | 125 mm solid HDPE Pipe DR 11 | Material | M | 35 | 1 | 35 | 201.374 | 7048.0891
[22 empty] | 125 mm HDPE Pipe Installation | SC | M | 18 | 1 | 18 | 201.374 | 3624.7315
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 10 | 25 | 20.1374 | 5034.3494
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 10 | 15 | 20.1374 | 3020.6096
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.67125 | 117.4682
[9 empty] | 201.374 | 201.374 |  | 201.374 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 201.374 | 1006.8699 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 201.374 | 1006.8699
IRR 9 |  | Pipes with an outer diameter of 125 mm at a depth of less than 2.0-2.5 m | m | 28.7675 | 158 | 4545.2689 | 145.8441 | 4195.5752 | 28.7675 | 28.7675 |  | 28.7675 | 100% | 158 | 4545.2689 | 145.8441 | 4195.5752 |  | 4195.5752 | [7 empty] | 145.8441 | 28.7675 | 4195.5752 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 28.7675 | 28.7675 |  | 28.7675 | [9 empty] | Excavation ( W= 1.0 & d= 2.5 ) |  | M | 47.2608 |  | 47.2608 | 28.7675 | 1359.5767 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 40 | 1.4 | 0.71919 | 40.2745
[22 empty] | Fuel | Material | LTR | 1.76 | 2.8571 | 0.616 | 10.0686 | 17.7208
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 8.16 | 5.8824 | 3.5254 | 169.2207
[22 empty] | Fuel | Material | LTR | 1.76 | 0.816 | 2.1569 | 35.2543 | 62.0476
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 0.57535 | 13.2331
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 1.7261 | 3.0379
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 40 | 1.2 | 0.71919 | 34.521
[22 empty] | Fuel | Material | LTR | 1.76 | 4 | 0.44 | 7.1919 | 12.6577
[22 empty] | Steel Shoring D=2.5 M | Material | M | 35 | 1 | 35 | 28.7675 | 1006.8634
[9 empty] | 28.7675 | 28.7675 |  | 28.7675 | [9 empty] | Pipe Laying & Protection |  | M | 93.5833 |  | 93.5833 | 28.7675 | 2692.1609 | 0 | 0 | 0 | 0 | 0
[22 empty] | 125 mm solid HDPE Pipe DR 11 | Material | M | 35 | 1 | 35 | 28.7675 | 1006.8634
[22 empty] | 125 mm HDPE Pipe Installation | SC | M | 18 | 1 | 18 | 28.7675 | 517.8154
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 10 | 25 | 2.8768 | 719.1881
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 10 | 15 | 2.8768 | 431.5129
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.095892 | 16.7811
[9 empty] | 28.7675 | 28.7675 |  | 28.7675 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 28.7675 | 143.8376 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 28.7675 | 143.8376
IRR 9 |  | Pipes with an outer diameter of 160 mm at a depth of less than 1.5 m | m | 1672.1968 | 148 | 247485.1227 | 112.1661 | 187563.7284 | 1672.1968 | 1672.1968 |  | 1672.1968 | 100% | 148 | 247485.1227 | 112.1661 | 187563.7284 |  | 187563.7284 | [7 empty] | 112.1661 | 1672.1968 | 187563.7284 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 1672.1968 | 1672.1968 |  | 1672.1968 | [9 empty] | Excavation ( W= 1.0 & d= 1.5 ) |  | M | 7.5827 |  | 7.5827 | 1672.1968 | 12679.8157 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 66.6667 | 0.84 | 25.083 | 1404.6453
[22 empty] | Fuel | Material | LTR | 1.76 | 4.7619 | 0.3696 | 351.1613 | 618.0439
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 13.6 | 3.5294 | 122.9556 | 5901.871
[22 empty] | Fuel | Material | LTR | 1.76 | 1.36 | 1.2941 | 1229.5565 | 2164.0194
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 33.4439 | 769.2105
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 100.3318 | 176.584
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 66.6667 | 0.72 | 25.083 | 1203.9817
[22 empty] | Fuel | Material | LTR | 1.76 | 6.6667 | 0.264 | 250.8295 | 441.4599
[9 empty] | 1672.1968 | 1672.1968 |  | 1672.1968 | [9 empty] | Pipe Laying & Protection |  | M | 99.5833 |  | 99.5833 | 1672.1968 | 166522.9288 | 0 | 0 | 0 | 0 | 0
[22 empty] | 160 mm solid HDPE Pipe DR 11 | Material | M | 39 | 1 | 39 | 1672.1968 | 65215.6742
[22 empty] | 160 mm HDPE Pipe Installation | SC | M | 20 | 1 | 20 | 1672.1968 | 33443.9355
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 10 | 25 | 167.2197 | 41804.9194
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 10 | 15 | 167.2197 | 25082.9516
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 5.574 | 975.4481
[9 empty] | 1672.1968 | 1672.1968 |  | 1672.1968 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 1672.1968 | 8360.9839 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 1672.1968 | 8360.9839
IRR 9 |  | Pipes with an outer diameter of 160 mm at a depth of less than 1.5 m | m | 10.42 | 156 | 1625.52 | 112.1661 | 1168.7704 | 10.42 | 10.42 |  | 10.42 | 100% | 156 | 1625.52 | 112.1661 | 1168.7704 |  | 1168.7704 | [7 empty] | 112.1661 | 10.42 | 1168.7704 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 10.42 | 10.42 |  | 10.42 | [9 empty] | Excavation ( W= 1.0 & d= 1.5 ) |  | M | 7.5827 |  | 7.5827 | 10.42 | 79.012 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 66.6667 | 0.84 | 0.1563 | 8.7528
[22 empty] | Fuel | Material | LTR | 1.76 | 4.7619 | 0.3696 | 2.1882 | 3.8512
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 13.6 | 3.5294 | 0.76618 | 36.7765
[22 empty] | Fuel | Material | LTR | 1.76 | 1.36 | 1.2941 | 7.6618 | 13.4847
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 0.2084 | 4.7932
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 0.6252 | 1.1004
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 66.6667 | 0.72 | 0.1563 | 7.5024
[22 empty] | Fuel | Material | LTR | 1.76 | 6.6667 | 0.264 | 1.563 | 2.7509
[9 empty] | 10.42 | 10.42 |  | 10.42 | [9 empty] | Pipe Laying & Protection |  | M | 99.5833 |  | 99.5833 | 10.42 | 1037.6583 | 0 | 0 | 0 | 0 | 0
[22 empty] | 160 mm solid HDPE Pipe DR 11 | Material | M | 39 | 1 | 39 | 10.42 | 406.38
[22 empty] | 160 mm HDPE Pipe Installation | SC | M | 20 | 1 | 20 | 10.42 | 208.4
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 10 | 25 | 1.042 | 260.5
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 10 | 15 | 1.042 | 156.3
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.034733 | 6.0783
[9 empty] | 10.42 | 10.42 |  | 10.42 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 10.42 | 52.1 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 10.42 | 52.1
IRR 9 |  | Pipes with an outer diameter of 160 mm at a depth of less than 1.5 m | m |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
IRR 9 |  | Pipes with an outer diameter of 280 mm at a depth of less than 1.5 m | m | 1136.7469 | 336 | 381946.9668 | 196.1661 | 222991.1686 | 1136.7469 | 1136.7469 |  | 1136.7469 | 100% | 336 | 381946.9668 | 196.1661 | 222991.1686 |  | 222991.1686 | [7 empty] | 196.1661 | 1136.7469 | 222991.1686 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 1136.7469 | 1136.7469 |  | 1136.7469 | [9 empty] | Excavation ( W= 1.0 & d= 1.5 ) |  | M | 7.5827 |  | 7.5827 | 1136.7469 | 8619.6443 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 66.6667 | 0.84 | 17.0512 | 954.8674
[22 empty] | Fuel | Material | LTR | 1.76 | 4.7619 | 0.3696 | 238.7169 | 420.1417
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 13.6 | 3.5294 | 83.5843 | 4012.048
[22 empty] | Fuel | Material | LTR | 1.76 | 1.36 | 1.2941 | 835.8433 | 1471.0843
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 22.7349 | 522.9036
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 68.2048 | 120.0405
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 66.6667 | 0.72 | 17.0512 | 818.4578
[22 empty] | Fuel | Material | LTR | 1.76 | 6.6667 | 0.264 | 170.512 | 300.1012
[9 empty] | 1136.7469 | 1136.7469 |  | 1136.7469 | [9 empty] | Pipe Laying & Protection |  | M | 183.5833 |  | 183.5833 | 1136.7469 | 208687.7896 | 0 | 0 | 0 | 0 | 0
[22 empty] | 280 mm solid HDPE Pipe DR 11 | Material | M | 110 | 1 | 110 | 1136.7469 | 125042.1617
[22 empty] | 280 mm HDPE Pipe Installation | SC | M | 33 | 1 | 33 | 1136.7469 | 37512.6485
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 10 | 25 | 113.6747 | 28418.6731
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 10 | 15 | 113.6747 | 17051.2039
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 3.7892 | 663.1024
[9 empty] | 1136.7469 | 1136.7469 |  | 1136.7469 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 1136.7469 | 5683.7346 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 1136.7469 | 5683.7346
IRR 9 |  | Pipes with an outer diameter of 280 mm at a depth of 1.5 - 2.00 m | m | 440.8757 | 388 | 171059.7716 | 198.5051 | 87516.0775 | 440.8757 | 440.8757 |  | 440.8757 | 100% | 388 | 171059.7716 | 198.5051 | 87516.0775 |  | 87516.0775 | [7 empty] | 198.5051 | 440.8757 | 87516.0775 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 440.8757 | 440.8757 |  | 440.8757 | [9 empty] | Excavation ( W= 1.0 & d= 2.0 ) |  | M | 9.9218 |  | 9.9218 | 440.8757 | 4374.2684 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 50 | 1.12 | 8.8175 | 493.7808
[22 empty] | Fuel | Material | LTR | 1.76 | 3.5714 | 0.4928 | 123.4452 | 217.2635
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 10.2 | 4.7059 | 43.2231 | 2074.7092
[22 empty] | Fuel | Material | LTR | 1.76 | 1.02 | 1.7255 | 432.2311 | 760.7267
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 8.8175 | 202.8028
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 26.4525 | 46.5565
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 50 | 0.96 | 8.8175 | 423.2407
[22 empty] | Fuel | Material | LTR | 1.76 | 5 | 0.352 | 88.1751 | 155.1882
[9 empty] | 440.8757 | 440.8757 |  | 440.8757 | [9 empty] | Pipe Laying & Protection |  | M | 183.5833 |  | 183.5833 | 440.8757 | 80937.4306 | 0 | 0 | 0 | 0 | 0
[22 empty] | 280 mm solid HDPE Pipe DR 11 | Material | M | 110 | 1 | 110 | 440.8757 | 48496.327
[22 empty] | 280 mm HDPE Pipe Installation | SC | M | 33 | 1 | 33 | 440.8757 | 14548.8981
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 10 | 25 | 44.0876 | 11021.8925
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 10 | 15 | 44.0876 | 6613.1355
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 1.4696 | 257.1775
[9 empty] | 440.8757 | 440.8757 |  | 440.8757 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 440.8757 | 2204.3785 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 440.8757 | 2204.3785
IRR 9 |  | Pipes with an outer diameter of 280 mm at a depth of 2.0 - 2.5 m | m | 24.2189 | 410 | 9929.749 | 235.8441 | 5711.8859 | 24.2189 | 24.2189 |  | 24.2189 | 100% | 410 | 9929.749 | 235.8441 | 5711.8859 |  | 5711.8859 | [7 empty] | 235.8441 | 24.2189 | 5711.8859 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 24.2189 | 24.2189 |  | 24.2189 | [9 empty] | Excavation ( W= 1.0 & d= 2.5 ) |  | M | 47.2608 |  | 47.2608 | 24.2189 | 1144.605 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 40 | 1.4 | 0.60547 | 33.9065
[22 empty] | Fuel | Material | LTR | 1.76 | 2.8571 | 0.616 | 8.4766 | 14.9188
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 8.16 | 5.8824 | 2.968 | 142.4641
[22 empty] | Fuel | Material | LTR | 1.76 | 0.816 | 2.1569 | 29.68 | 52.2368
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 0.48438 | 11.1407
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 1.4531 | 2.5575
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 40 | 1.2 | 0.60547 | 29.0627
[22 empty] | Fuel | Material | LTR | 1.76 | 4 | 0.44 | 6.0547 | 10.6563
[22 empty] | Steel Shoring D=2.5 M | Material | M | 35 | 1 | 35 | 24.2189 | 847.6615
[9 empty] | 24.2189 | 24.2189 |  | 24.2189 | [9 empty] | Pipe Laying & Protection |  | M | 183.5833 |  | 183.5833 | 24.2189 | 4446.1864 | 0 | 0 | 0 | 0 | 0
[22 empty] | 280 mm solid HDPE Pipe DR 11 | Material | M | 110 | 1 | 110 | 24.2189 | 2664.079
[22 empty] | 280 mm HDPE Pipe Installation | SC | M | 33 | 1 | 33 | 24.2189 | 799.2237
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 10 | 25 | 2.4219 | 605.4725
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 10 | 15 | 2.4219 | 363.2835
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.08073 | 14.1277
[9 empty] | 24.2189 | 24.2189 |  | 24.2189 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 24.2189 | 121.0945 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 24.2189 | 121.0945
IRR 9 |  | Pipes with an outer diameter of 500 mm at a depth of 1.5 - 2.0 m | m | 793.0368 | 1180 | 935783.483 | 480.1832 | 380802.9661 | 793.0368 | 793.0368 |  | 793.0368 | 100% | 1180 | 935783.483 | 480.1832 | 380802.9661 |  | 380802.9661 | [7 empty] | 480.1832 | 793.0368 | 380802.9661 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 793.0368 | 793.0368 |  | 793.0368 | [9 empty] | Excavation ( W= 1.5 & d= 2.0 ) |  | M | 14.5999 |  | 14.5999 | 793.0368 | 11578.2261 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 33.3333 | 1.68 | 23.7911 | 1332.3019
[22 empty] | Fuel | Material | LTR | 1.76 | 2.381 | 0.7392 | 333.0755 | 586.2128
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 6.8 | 7.0588 | 116.6231 | 5597.9072
[22 empty] | Fuel | Material | LTR | 1.76 | 0.68 | 2.5882 | 1166.2307 | 2052.566
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 15.8607 | 364.797
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 47.5822 | 83.7447
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 33.3333 | 1.44 | 23.7911 | 1141.9731
[22 empty] | Fuel | Material | LTR | 1.76 | 3.3333 | 0.528 | 237.9111 | 418.7235
[9 empty] | 793.0368 | 793.0368 |  | 793.0368 | [9 empty] | Pipe Laying & Protection |  | M | 460.5833 |  | 460.5833 | 793.0368 | 365259.5558 | 0 | 0 | 0 | 0 | 0
[22 empty] | 500 mm solid HDPE Pipe DR 11 | Material | M | 345 | 1 | 345 | 793.0368 | 273597.7132
[22 empty] | 500 mm HDPE Pipe Installation | SC | M | 55 | 1 | 55 | 793.0368 | 43617.0267
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 6.6667 | 37.5 | 118.9555 | 29738.8819
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 6.6667 | 22.5 | 118.9555 | 17843.3291
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 2.6435 | 462.6048
[9 empty] | 793.0368 | 793.0368 |  | 793.0368 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 793.0368 | 3965.1842 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 793.0368 | 3965.1842
IRR 9 |  | Pipes with an outer diameter of 500 mm at a depth of 2.0 - 2.5 m | m | 13.1178 | 1211 | 15885.6558 | 518.6918 | 6804.0947 | 13.1178 | 13.1178 |  | 13.1178 | 100% | 1211 | 15885.6558 | 518.6918 | 6804.0947 |  | 6804.0947 | [7 empty] | 518.6918 | 13.1178 | 6804.0947 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 13.1178 | 13.1178 |  | 13.1178 | [9 empty] | Excavation ( W= 1.5 & d= 2.5 ) |  | M | 53.1084 |  | 53.1084 | 13.1178 | 696.6657 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 26.6667 | 2.1 | 0.49192 | 27.5474
[22 empty] | Fuel | Material | LTR | 1.76 | 1.9048 | 0.924 | 6.8868 | 12.1208
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 5.44 | 8.8235 | 2.4114 | 115.7453
[22 empty] | Fuel | Material | LTR | 1.76 | 0.544 | 3.2353 | 24.1136 | 42.4399
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 0.26236 | 6.0342
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 0.78707 | 1.3852
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 26.6667 | 1.8 | 0.49192 | 23.612
[22 empty] | Fuel | Material | LTR | 1.76 | 2.6667 | 0.66 | 4.9192 | 8.6577
[22 empty] | Steel Shoring D=2.5 M | Material | M | 35 | 1 | 35 | 13.1178 | 459.123
[9 empty] | 13.1178 | 13.1178 |  | 13.1178 | [9 empty] | Pipe Laying & Protection |  | M | 460.5833 |  | 460.5833 | 13.1178 | 6041.84 | 0 | 0 | 0 | 0 | 0
[22 empty] | 500 mm solid HDPE Pipe DR 11 | Material | M | 345 | 1 | 345 | 13.1178 | 4525.641
[22 empty] | 500 mm HDPE Pipe Installation | SC | M | 55 | 1 | 55 | 13.1178 | 721.479
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 6.6667 | 37.5 | 1.9677 | 491.9175
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 6.6667 | 22.5 | 1.9677 | 295.1505
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.043726 | 7.652
[9 empty] | 13.1178 | 13.1178 |  | 13.1178 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 13.1178 | 65.589 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 13.1178 | 65.589
IRR 9 |  | Pipes with an outer diameter of 500 mm at a depth of 2.5 - 3.0 m | m | 45.5887 | 1284 | 58535.8908 | 543.6918 | 24786.2004 | 45.5887 | 45.5887 |  | 45.5887 | 100% | 1284 | 58535.8908 | 543.6918 | 24786.2004 |  | 24786.2004 | [7 empty] | 543.6918 | 45.5887 | 24786.2004 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 45.5887 | 45.5887 |  | 45.5887 | [9 empty] | Excavation ( W= 1.5 & d= 3.0 ) |  | M | 78.1084 |  | 78.1084 | 45.5887 | 3560.8615 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 26.6667 | 2.1 | 1.7096 | 95.7363
[22 empty] | Fuel | Material | LTR | 1.76 | 1.9048 | 0.924 | 23.9341 | 42.124
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 5.44 | 8.8235 | 8.3803 | 402.2532
[22 empty] | Fuel | Material | LTR | 1.76 | 0.544 | 3.2353 | 83.8028 | 147.4929
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 0.91177 | 20.9708
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 2.7353 | 4.8142
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 26.6667 | 1.8 | 1.7096 | 82.0597
[22 empty] | Fuel | Material | LTR | 1.76 | 2.6667 | 0.66 | 17.0958 | 30.0885
[22 empty] | Steel Shoring D>3.0 M | Material | M | 60 | 1 | 60 | 45.5887 | 2735.322
[9 empty] | 45.5887 | 45.5887 |  | 45.5887 | [9 empty] | Pipe Laying & Protection |  | M | 460.5833 |  | 460.5833 | 45.5887 | 20997.3954 | 0 | 0 | 0 | 0 | 0
[22 empty] | 500 mm solid HDPE Pipe DR 11 | Material | M | 345 | 1 | 345 | 45.5887 | 15728.1015
[22 empty] | 500 mm HDPE Pipe Installation | SC | M | 55 | 1 | 55 | 45.5887 | 2507.3785
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 6.6667 | 37.5 | 6.8383 | 1709.5763
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 6.6667 | 22.5 | 6.8383 | 1025.7458
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.15196 | 26.5934
[9 empty] | 45.5887 | 45.5887 |  | 45.5887 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 45.5887 | 227.9435 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 45.5887 | 227.9435
IRR 9 |  | Pipes with an outer diameter of 500 mm at a depth of 3.5 - 4.0 m | m | 8.3817 | 1465 | 12279.1905 | 554.2175 | 4645.2844 | 8.3817 | 8.3817 |  | 8.3817 | 100% | 1465 | 12279.1905 | 554.2175 | 4645.2844 |  | 4645.2844 | [7 empty] | 554.2175 | 8.3817 | 4645.2844 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 8.3817 | 8.3817 |  | 8.3817 | [9 empty] | Excavation ( W= 1.5 & d= 4.0 ) |  | M | 88.6341 |  | 88.6341 | 8.3817 | 742.9046 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 16.6667 | 3.36 | 0.5029 | 28.1625
[22 empty] | Fuel | Material | LTR | 1.76 | 1.1905 | 1.4784 | 7.0406 | 12.3915
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 3.4 | 14.1176 | 2.4652 | 118.3299
[22 empty] | Fuel | Material | LTR | 1.76 | 0.34 | 5.1765 | 24.6521 | 43.3876
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 0.16763 | 3.8556
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 0.5029 | 0.88511
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 16.6667 | 2.88 | 0.5029 | 24.1393
[22 empty] | Fuel | Material | LTR | 1.76 | 1.6667 | 1.056 | 5.029 | 8.8511
[22 empty] | Steel Shoring D>3.0 M | Material | M | 60 | 1 | 60 | 8.3817 | 502.902
[9 empty] | 8.3817 | 8.3817 |  | 8.3817 | [9 empty] | Pipe Laying & Protection |  | M | 460.5833 |  | 460.5833 | 8.3817 | 3860.4713 | 0 | 0 | 0 | 0 | 0
[22 empty] | 500 mm solid HDPE Pipe DR 11 | Material | M | 345 | 1 | 345 | 8.3817 | 2891.6865
[22 empty] | 500 mm HDPE Pipe Installation | SC | M | 55 | 1 | 55 | 8.3817 | 460.9935
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 6.6667 | 37.5 | 1.2573 | 314.3138
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 6.6667 | 22.5 | 1.2573 | 188.5883
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.027939 | 4.8893
[9 empty] | 8.3817 | 8.3817 |  | 8.3817 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 8.3817 | 41.9085 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 8.3817 | 41.9085
IRR 9 |  | Increased depth difference of 0.5 m for 500 mm diameter pipes | m |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
IRR 9 |  | Increased depth difference of 1.0 m for 500 mm diameter pipes | m |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
IRR 9 |  | Increased depth difference of 1.5 m for 500 mm diameter pipes | m |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
IRR 9 |  | Increased depth difference of 2.0 m for 500 mm diameter pipes | m |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
IRR 9 |  | Increased depth difference of 3.0 m for 500 mm diameter pipes | m |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
IRR 9 |  | Increased depth difference of 3.5 m for 500 mm diameter pipes | m |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
IRR 9 |  | Pipes with an outer diameter of 630 mm at a depth of 2.0 - 2.50 m | m | 122.7401 | 1908 | 234188.1585 | 525.4121 | 64489.1511 | 122.7401 | 122.7401 |  | 122.7401 | 100% | 1908 | 234188.1585 | 525.4121 | 64489.1511 |  | 64489.1511 | [7 empty] | 525.4121 | 122.7401 | 64489.1511 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 122.7401 | 122.7401 |  | 122.7401 | [9 empty] | Excavation ( W= 1.63 & d= 2.5 ) |  | M | 54.6288 |  | 54.6288 | 122.7401 | 6705.1459 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 24.5399 | 2.282 | 5.0017 | 280.093
[22 empty] | Fuel | Material | LTR | 1.76 | 1.7528 | 1.0041 | 70.0232 | 123.2409
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 5.0061 | 9.5882 | 24.5179 | 1176.8612
[22 empty] | Fuel | Material | LTR | 1.76 | 0.50061 | 3.5157 | 245.1794 | 431.5158
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 2.4548 | 56.4605
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 7.3644 | 12.9614
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 24.5399 | 1.956 | 5.0017 | 240.0797
[22 empty] | Fuel | Material | LTR | 1.76 | 2.454 | 0.7172 | 50.0166 | 88.0292
[22 empty] | Steel Shoring D=2.5 M | Material | M | 35 | 1 | 35 | 122.7401 | 4295.9044
[9 empty] | 122.7401 | 122.7401 |  | 122.7401 | [9 empty] | Pipe Laying & Protection |  | M | 465.7833 |  | 465.7833 | 122.7401 | 57170.3046 | 0 | 0 | 0 | 0 | 0
[22 empty] | 500 mm solid HDPE Pipe DR 11 | Material | M | 345 | 1 | 345 | 122.7401 | 42345.3431
[22 empty] | 500 mm HDPE Pipe Installation | SC | M | 55 | 1 | 55 | 122.7401 | 6750.7069
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 6.135 | 40.75 | 20.0066 | 5001.6601
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 6.135 | 24.45 | 20.0066 | 3000.9961
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.40913 | 71.5984
[9 empty] | 122.7401 | 122.7401 |  | 122.7401 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 122.7401 | 613.7006 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 122.7401 | 613.7006
IRR 9 |  | Pipes with an outer diameter of 630 mm at a depth of 2.5 - 3.0 m | m |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
IRR 9 |  | Pipes with an outer diameter of 630 mm at a depth of 3.5 - 4.0 m | m |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
IRR 9 |  | Pipes with an outer diameter of 630 mm at a depth of more than 4.0 m | m |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
IRR 9 |  | Supply and installation of installation parts and accessories for HDPE polyethylene pipes in accordance with the procedures of the competent authorities, specifications and plans. |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
IRR 9 |  | Elbow 11.5°, diameter 125mm | nr | 24.9 | 1064 | 26493.6 | 265 | 6598.5 | 24.9 | 24.9 |  | 24.9 | 100% | 1064 | 26493.6 | 265 | 6598.5 |  | 6598.5 | [7 empty] | 265 | 24.9 | 6598.5 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 24.9 | 24.9 |  | 24.9 | [9 empty] | Supply & Install fittings |  | Ea | 265 |  | 265 | 24.9 | 6598.5 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Elbow 11.5°, diameter 125mm | Material | Ea | 205 | 1 | 205 | 24.9 | 5104.5
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.5 | 34 | 49.8 | 846.6
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.5 | 26 | 49.8 | 647.4
IRR 9 |  | Elbow 11.5°, diameter 160mm | nr | 9.3 | 1096 | 10192.8 | 284.5 | 2645.85 | 9.3 | 9.3 |  | 9.3 | 100% | 1096 | 10192.8 | 284.5 | 2645.85 |  | 2645.85 | [7 empty] | 284.5 | 9.3 | 2645.85 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 9.3 | 9.3 |  | 9.3 | [9 empty] | Supply & Install fittings |  | Ea | 284.5 |  | 284.5 | 9.3 | 2645.85 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Elbow 11.5°, diameter 160mm | Material | Ea | 224.5 | 1 | 224.5 | 9.3 | 2087.85
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.5 | 34 | 18.6 | 316.2
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.5 | 26 | 18.6 | 241.8
IRR 9 |  | Elbow 11.5°, diameter 280mm | nr | 27.1 | 1490 | 40379 | 851 | 23062.1 | 27.1 | 27.1 |  | 27.1 | 100% | 1490 | 40379 | 851 | 23062.1 |  | 23062.1 | [7 empty] | 851 | 27.1 | 23062.1 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 27.1 | 27.1 |  | 27.1 | [9 empty] | Supply & Install fittings |  | Ea | 851 |  | 851 | 27.1 | 23062.1 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Elbow 11.5°, diameter 280mm | Material | Ea | 791 | 1 | 791 | 27.1 | 21436.1
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.5 | 34 | 54.2 | 921.4
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.5 | 26 | 54.2 | 704.6
IRR 9 |  | Elbow 11.5°, diameter 500mm | nr | 2.5 | 2618 | 6545 | 1944 | 4860 | 2.5 | 2.5 |  | 2.5 | 100% | 2618 | 6545 | 1944 | 4860 |  | 4860 | [7 empty] | 1944 | 2.5 | 4860 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 2.5 | 2.5 |  | 2.5 | [9 empty] | Supply & Install fittings |  | Ea | 1944 |  | 1944 | 2.5 | 4860 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Elbow 11.5°, diameter 500mm | Material | Ea | 1844 | 1 | 1844 | 2.5 | 4610
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.3 | 56.6667 | 8.3333 | 141.6667
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.3 | 43.3333 | 8.3333 | 108.3333
IRR 9 |  | Elbow 45°, diameter 125mm | nr | 47.7 | 1071 | 51086.7 | 275 | 13117.5 | 47.7 | 47.7 |  | 47.7 | 100% | 1071 | 51086.7 | 275 | 13117.5 |  | 13117.5 | [7 empty] | 275 | 47.7 | 13117.5 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 47.7 | 47.7 |  | 47.7 | [9 empty] | Supply & Install fittings |  | Ea | 275 |  | 275 | 47.7 | 13117.5 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Elbow 45°, diameter 125mm | Material | Ea | 215 | 1 | 215 | 47.7 | 10255.5
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.5 | 34 | 95.4 | 1621.8
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.5 | 26 | 95.4 | 1240.2
IRR 9 |  | Elbow 45°, diameter 160mm | nr | 25.6 | 1130 | 28928 | 289 | 7398.4 | 25.6 | 25.6 |  | 25.6 | 100% | 1130 | 28928 | 289 | 7398.4 |  | 7398.4 | [7 empty] | 289 | 25.6 | 7398.4 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 25.6 | 25.6 |  | 25.6 | [9 empty] | Supply & Install fittings |  | Ea | 289 |  | 289 | 25.6 | 7398.4 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Elbow 45°, diameter 160mm | Material | Ea | 229 | 1 | 229 | 25.6 | 5862.4
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.5 | 34 | 51.2 | 870.4
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.5 | 26 | 51.2 | 665.6
IRR 9 |  | Elbow 45°, diameter 280mm | nr | 22.2 | 1538 | 34143.6 | 880 | 19536 | 22.2 | 22.2 |  | 22.2 | 100% | 1538 | 34143.6 | 880 | 19536 |  | 19536 | [7 empty] | 880 | 22.2 | 19536 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 22.2 | 22.2 |  | 22.2 | [9 empty] | Supply & Install fittings |  | Ea | 880 |  | 880 | 22.2 | 19536 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Elbow 45°, diameter 280mm | Material | Ea | 820 | 1 | 820 | 22.2 | 18204
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.5 | 34 | 44.4 | 754.8
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.5 | 26 | 44.4 | 577.2
IRR 9 |  | Elbow 45°, diameter 500mm | nr | 17.4 | 2706 | 47084.4 | 1957 | 34051.8 | 17.4 | 17.4 |  | 17.4 | 100% | 2706 | 47084.4 | 1957 | 34051.8 |  | 34051.8 | [7 empty] | 1957 | 17.4 | 34051.8 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 17.4 | 17.4 |  | 17.4 | [9 empty] | Supply & Install fittings |  | Ea | 1957 |  | 1957 | 17.4 | 34051.8 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Elbow 45°, diameter 500mm | Material | Ea | 1857 | 1 | 1857 | 17.4 | 32311.8
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.3 | 56.6667 | 58 | 986
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.3 | 43.3333 | 58 | 754
IRR 9 |  | Elbow 90°, diameter 125mm | nr | 0.4 | 1071 | 428.4 | 287.5 | 115 | 0.4 | 0.4 |  | 0.4 | 100% | 1071 | 428.4 | 287.5 | 115 |  | 115 | [7 empty] | 287.5 | 0.4 | 115 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 0.4 | 0.4 |  | 0.4 | [9 empty] | Supply & Install fittings |  | Ea | 287.5 |  | 287.5 | 0.4 | 115 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Elbow 90°, diameter 125mm | Material | Ea | 227.5 | 1 | 227.5 | 0.4 | 91
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.5 | 34 | 0.8 | 13.6
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.5 | 26 | 0.8 | 10.4
IRR 9 |  | Elbow 90°, diameter 160mm | nr |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
IRR 9 |  | 90° elbow, diameter 630mm | nr | 0.2 | 3587 | 717.4 | 2520 | 504 | 0.2 | 0.2 |  | 0.2 | 100% | 3587 | 717.4 | 2520 | 504 |  | 504 | [7 empty] | 2520 | 0.2 | 504 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 0.2 | 0.2 |  | 0.2 | [9 empty] | Supply & Install fittings |  | Ea | 2520 |  | 2520 | 0.2 | 504 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Elbow 90°, diameter 630mm | Material | Ea | 2370 | 1 | 2370 | 0.2 | 474
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.2 | 85 | 1 | 17
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.2 | 65 | 1 | 13
IRR 9 |  | Measurement difference between 90° elbow, diameter 280 mm and 11.5° elbow, diameter 280 mm | nr | 1.7 | 1554 | 2641.8 | 921 | 1565.7 | 1.7 | 1.7 |  | 1.7 | 100% | 1554 | 2641.8 | 921 | 1565.7 |  | 1565.7 | [7 empty] | 921 | 1.7 | 1565.7 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 1.7 | 1.7 |  | 1.7 | [9 empty] | Supply & Install fittings |  | Ea | 921 |  | 921 | 1.7 | 1565.7 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Elbow 90°, diameter 280mm | Material | Ea | 861 | 1 | 861 | 1.7 | 1463.7
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.5 | 34 | 3.4 | 57.8
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.5 | 26 | 3.4 | 44.2
IRR 9 |  | Pipe Fittings (continued) |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
IRR 9 |  | TEE connection mm 125x125x125 | nr | 132.3 | 1276 | 168814.8 | 388 | 51332.4 | 132.3 | 132.3 |  | 132.3 | 100% | 1276 | 168814.8 | 388 | 51332.4 |  | 51332.4 | [7 empty] | 388 | 132.3 | 51332.4 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 132.3 | 132.3 |  | 132.3 | [9 empty] | Supply & Install fittings |  | Ea | 388 |  | 388 | 132.3 | 51332.4 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Tee size mm 125x125x125 | Material | Ea | 288 | 1 | 288 | 132.3 | 38102.4
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.3 | 56.6667 | 441 | 7497
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.3 | 43.3333 | 441 | 5733
IRR 9 |  | TEE connection mm 160x160x125 | nr | 22.8 | 1310 | 29868 | 407 | 9279.6 | 22.8 | 22.8 |  | 22.8 | 100% | 1310 | 29868 | 407 | 9279.6 |  | 9279.6 | [7 empty] | 407 | 22.8 | 9279.6 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 22.8 | 22.8 |  | 22.8 | [9 empty] | Supply & Install fittings |  | Ea | 407 |  | 407 | 22.8 | 9279.6 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Tee size mm 160x160x125 | Material | Ea | 307 | 1 | 307 | 22.8 | 6999.6
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.3 | 56.6667 | 76 | 1292
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.3 | 43.3333 | 76 | 988
IRR 9 |  | TEE connection mm 160x160x160 | nr | 16.9 | 1391 | 23507.9 | 445 | 7520.5 | 16.9 | 16.9 |  | 16.9 | 100% | 1391 | 23507.9 | 445 | 7520.5 |  | 7520.5 | [7 empty] | 445 | 16.9 | 7520.5 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 16.9 | 16.9 |  | 16.9 | [9 empty] | Supply & Install fittings |  | Ea | 445 |  | 445 | 16.9 | 7520.5 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Tee size mm 160x160x160 | Material | Ea | 345 | 1 | 345 | 16.9 | 5830.5
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.3 | 56.6667 | 56.3333 | 957.6667
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.3 | 43.3333 | 56.3333 | 732.3333
IRR 9 |  | TEE connection mm 280x280x125 | nr | 28.5 | 1882 | 53637 | 1035 | 29497.5 | 28.5 | 28.5 |  | 28.5 | 100% | 1882 | 53637 | 1035 | 29497.5 |  | 29497.5 | [7 empty] | 1035 | 28.5 | 29497.5 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 28.5 | 28.5 |  | 28.5 | [9 empty] | Supply & Install fittings |  | Ea | 1035 |  | 1035 | 28.5 | 29497.5 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Tee size mm 280x280x125 | Material | Ea | 935 | 1 | 935 | 28.5 | 26647.5
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.3 | 56.6667 | 95 | 1615
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.3 | 43.3333 | 95 | 1235
IRR 9 |  | TEE connection mm 280x280x160 | nr | 1.3 | 1964 | 2553.2 | 1058 | 1375.4 | 1.3 | 1.3 |  | 1.3 | 100% | 1964 | 2553.2 | 1058 | 1375.4 |  | 1375.4 | [7 empty] | 1058 | 1.3 | 1375.4 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 1.3 | 1.3 |  | 1.3 | [9 empty] | Supply & Install fittings |  | Ea | 1058 |  | 1058 | 1.3 | 1375.4 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Tee size mm 280x280x160 | Material | Ea | 958 | 1 | 958 | 1.3 | 1245.4
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.3 | 56.6667 | 4.3333 | 73.6667
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.3 | 43.3333 | 4.3333 | 56.3333
IRR 9 |  | TEE connection mm 280x280x280 | nr | 22.8 | 2094 | 47743.2 | 1290 | 29412 | 22.8 | 22.8 |  | 22.8 | 100% | 2094 | 47743.2 | 1290 | 29412 |  | 29412 | [7 empty] | 1290 | 22.8 | 29412 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 22.8 | 22.8 |  | 22.8 | [9 empty] | Supply & Install fittings |  | Ea | 1290 |  | 1290 | 22.8 | 29412 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Tee size mm 280x280x280 | Material | Ea | 1190 | 1 | 1190 | 22.8 | 27132
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.3 | 56.6667 | 76 | 1292
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.3 | 43.3333 | 76 | 988
IRR 9 |  | TEE connection mm 500x500x125 | nr | 14.4 | 3600 | 51840 | 2270 | 32688 | 14.4 | 14.4 |  | 14.4 | 100% | 3600 | 51840 | 2270 | 32688 |  | 32688 | [7 empty] | 2270 | 14.4 | 32688 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 14.4 | 14.4 |  | 14.4 | [9 empty] | Supply & Install fittings |  | Ea | 2270 |  | 2270 | 14.4 | 32688 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Tee size mm 500x500x125 | Material | Ea | 2150 | 1 | 2150 | 14.4 | 30960
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.25 | 68 | 57.6 | 979.2
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.25 | 52 | 57.6 | 748.8
IRR 9 |  | TEE connection mm 500x500x280 | nr | 5.9 | 3764 | 22207.6 | 2579 | 15216.1 | 5.9 | 5.9 |  | 5.9 | 100% | 3764 | 22207.6 | 2579 | 15216.1 |  | 15216.1 | [7 empty] | 2579 | 5.9 | 15216.1 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 5.9 | 5.9 |  | 5.9 | [9 empty] | Supply & Install fittings |  | Ea | 2579 |  | 2579 | 5.9 | 15216.1 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Tee size mm 500x500x280 | Material | Ea | 2459 | 1 | 2459 | 5.9 | 14508.1
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.25 | 68 | 23.6 | 401.2
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.25 | 52 | 23.6 | 306.8
IRR 9 |  | TEE connection mm 500x500x500 | nr | 11.3 | 4091 | 46228.3 | 2698 | 30487.4 | 11.3 | 11.3 |  | 11.3 | 100% | 4091 | 46228.3 | 2698 | 30487.4 |  | 30487.4 | [7 empty] | 2698 | 11.3 | 30487.4 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 11.3 | 11.3 |  | 11.3 | [9 empty] | Supply & Install fittings |  | Ea | 2698 |  | 2698 | 11.3 | 30487.4 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Tee size mm 500x500x500 | Material | Ea | 2578 | 1 | 2578 | 11.3 | 29131.4
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.25 | 68 | 45.2 | 768.4
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.25 | 52 | 45.2 | 587.6
IRR 9 |  | TEE connection mm 630x630x630 | nr | 0.1 | 5073 | 507.3 | 3405 | 340.5 | 0.1 | 0.1 |  | 0.1 | 100% | 5073 | 507.3 | 3405 | 340.5 |  | 340.5 | [7 empty] | 3405 | 0.1 | 340.5 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 0.1 | 0.1 |  | 0.1 | [9 empty] | Supply & Install fittings |  | Ea | 3405 |  | 3405 | 0.1 | 340.5 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Tee size mm 630x630x630 | Material | Ea | 3255 | 1 | 3255 | 0.1 | 325.5
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.2 | 85 | 0.5 | 8.5
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.2 | 65 | 0.5 | 6.5
IRR 9 |  | 125 mm closed tube | nr | 296.5 | 372 | 110298 | 105 | 31132.5 | 296.5 | 296.5 |  | 296.5 | 100% | 372 | 110298 | 105 | 31132.5 |  | 31132.5 | [7 empty] | 105 | 296.5 | 31132.5 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 296.5 | 296.5 |  | 296.5 | [9 empty] | Supply & Install fittings |  | Ea | 105 |  | 105 | 296.5 | 31132.5 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply 125 mm closed tube | Material | Ea | 45 | 1 | 45 | 296.5 | 13342.5
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.5 | 34 | 593 | 10081
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.5 | 26 | 593 | 7709
IRR 9 |  | 160mm closed tube | nr | 3.2 | 437 | 1398.4 | 115 | 368 | 3.2 | 3.2 |  | 3.2 | 100% | 437 | 1398.4 | 115 | 368 |  | 368 | [7 empty] | 115 | 3.2 | 368 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 3.2 | 3.2 |  | 3.2 | [9 empty] | Supply & Install fittings |  | Ea | 115 |  | 115 | 3.2 | 368 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply 160 mm closed tube | Material | Ea | 55 | 1 | 55 | 3.2 | 176
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.5 | 34 | 6.4 | 108.8
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.5 | 26 | 6.4 | 83.2
IRR 9 |  | Closed tube measuring 280 mm | nr | 3.2 | 552 | 1766.4 | 164 | 524.8 | 3.2 | 3.2 |  | 3.2 | 100% | 552 | 1766.4 | 164 | 524.8 |  | 524.8 | [7 empty] | 164 | 3.2 | 524.8 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 3.2 | 3.2 |  | 3.2 | [9 empty] | Supply & Install fittings |  | Ea | 164 |  | 164 | 3.2 | 524.8 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply 280 mm closed tube | Material | Ea | 89 | 1 | 89 | 3.2 | 284.8
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.4 | 42.5 | 8 | 136
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.4 | 32.5 | 8 | 104
IRR 9 |  | 500mm closed tube | nr | 1.2 | 894 | 1072.8 | 740 | 888 | 1.2 | 1.2 |  | 1.2 | 100% | 894 | 1072.8 | 740 | 888 |  | 888 | [7 empty] | 740 | 1.2 | 888 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 1.2 | 1.2 |  | 1.2 | [9 empty] | Supply & Install fittings |  | Ea | 740 |  | 740 | 1.2 | 888 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply 500 mm closed tube | Material | Ea | 640 | 1 | 640 | 1.2 | 768
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.3 | 56.6667 | 4 | 68
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.3 | 43.3333 | 4 | 52
IRR 9 |  | Closed tube measuring 630 mm | nr | 1 | 1125 | 1125 | 960 | 960 | 1 | 1 |  | 1 | 100% | 1125 | 1125 | 960 | 960 |  | 960 | [7 empty] | 960 | 1 | 960 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 1 | 1 |  | 1 | [9 empty] | Supply & Install fittings |  | Ea | 960 |  | 960 | 1 | 960 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply 630 mm closed tube | Material | Ea | 810 | 1 | 810 | 1 | 810
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.2 | 85 | 5 | 85
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.2 | 65 | 5 | 65
IRR 9 |  | Reducers / Tapers |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
IRR 9 |  | Connector size 125x160 mm | nr | 12.2 | 1048 | 12785.6 | 345 | 4209 | 12.2 | 12.2 |  | 12.2 | 100% | 1048 | 12785.6 | 345 | 4209 |  | 4209 | [7 empty] | 345 | 12.2 | 4209 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 12.2 | 12.2 |  | 12.2 | [9 empty] | Supply & Install fittings |  | Ea | 345 |  | 345 | 12.2 | 4209 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Reducer size 125x160 mm | Material | Ea | 285 | 1 | 285 | 12.2 | 3477
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.5 | 34 | 24.4 | 414.8
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.5 | 26 | 24.4 | 317.2
IRR 9 |  | Connector size 280*125 mm | nr | 18.2 | 1506 | 27409.2 | 380 | 6916 | 18.2 | 18.2 |  | 18.2 | 100% | 1506 | 27409.2 | 380 | 6916 |  | 6916 | [7 empty] | 380 | 18.2 | 6916 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 18.2 | 18.2 |  | 18.2 | [9 empty] | Supply & Install fittings |  | Ea | 380 |  | 380 | 18.2 | 6916 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Reducer size 280*125 mm | Material | Ea | 320 | 1 | 320 | 18.2 | 5824
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.5 | 34 | 36.4 | 618.8
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.5 | 26 | 36.4 | 473.2
IRR 9 |  | Connector size 125x500 mm | nr | 14.3 | 1800 | 25740 | 1750 | 25025 | 14.3 | 14.3 |  | 14.3 | 100% | 1800 | 25740 | 1750 | 25025 |  | 25025 | [7 empty] | 1750 | 14.3 | 25025 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 14.3 | 14.3 |  | 14.3 | [9 empty] | Supply & Install fittings |  | Ea | 1750 |  | 1750 | 14.3 | 25025 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Reducer size 125x500 mm | Material | Ea | 1600 | 1 | 1600 | 14.3 | 22880
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.2 | 85 | 71.5 | 1215.5
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.2 | 65 | 71.5 | 929.5
IRR 9 |  | Connector size 280x500 mm | nr | 0.1 | 2454 | 245.4 | 2350 | 235 | 0.1 | 0.1 |  | 0.1 | 100% | 2454 | 245.4 | 2350 | 235 |  | 235 | [7 empty] | 2350 | 0.1 | 235 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 0.1 | 0.1 |  | 0.1 | [9 empty] | Supply & Install fittings |  | Ea | 2350 |  | 2350 | 0.1 | 235 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Reducer size 280x500 mm | Material | Ea | 2200 | 1 | 2200 | 0.1 | 220
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.2 | 85 | 0.5 | 8.5
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.2 | 65 | 0.5 | 6.5
IRR 9 |  | Connector size 500x630 mm | nr | 0.1 | 3110 | 311 | 2900 | 290 | 0.1 | 0.1 |  | 0.1 | 100% | 3110 | 311 | 2900 | 290 |  | 290 | [7 empty] | 2900 | 0.1 | 290 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 0.1 | 0.1 |  | 0.1 | [9 empty] | Supply & Install fittings |  | Ea | 2900 |  | 2900 | 0.1 | 290 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Reducer size 500x630 mm | Material | Ea | 2750 | 1 | 2750 | 0.1 | 275
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.2 | 85 | 0.5 | 8.5
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.2 | 65 | 0.5 | 6.5
IRR 9 |  | Valves: Supply, installation, and testing of valves, including collars, flange connections, flange rates, and spacers, in addition to bolts, nuts, and all the work required for pipes inside the room, along with all accessories (columns) and ribbed bolts, according to the specifications and the required standards. |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
IRR 9 |  | Gate Valves Gate water control valve |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
IRR 9 |  | Shut-off valve on 125mm pipe | nr | 196.85 | 1190 | 234251.5 | 925 | 182086.25 | 196.85 | 196.85 |  | 196.85 | 100% | 1190 | 234251.5 | 925 | 182086.25 |  | 182086.25 | [7 empty] | 925 | 196.85 | 182086.25 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 196.85 | 196.85 |  | 196.85 | [9 empty] | Supply & Install Valves |  | Ea | 925 |  | 925 | 196.85 | 182086.25 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Gate Valve 125 mm | Material | Ea | 750 | 1 | 750 | 196.85 | 147637.5
[22 empty] | Fitting and Accessories 125 | Material | Ea | 75 | 1 | 75 | 196.85 | 14763.75
[22 empty] | Installation Valve 125mm | SC | Ea | 100 | 1 | 100 | 196.85 | 19685
IRR 9 |  | Shut-off valve on 160mm pipe | nr | 16.9 | 1260 | 21294 | 1106.5 | 18699.85 | 16.9 | 16.9 |  | 16.9 | 100% | 1260 | 21294 | 1106.5 | 18699.85 |  | 18699.85 | [7 empty] | 1106.5 | 16.9 | 18699.85 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 16.9 | 16.9 |  | 16.9 | [9 empty] | Supply & Install Valves |  | Ea | 1106.5 |  | 1106.5 | 16.9 | 18699.85 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Gate Valve 160 mm | Material | Ea | 915 | 1 | 915 | 16.9 | 15463.5
[22 empty] | Fitting and Accessories 160 | Material | Ea | 91.5 | 1 | 91.5 | 16.9 | 1546.35
[22 empty] | Installation Valve 160mm | SC | Ea | 100 | 1 | 100 | 16.9 | 1690
IRR 9 |  | Shut-off valve on 280mm pipe | nr | 37.5 | 2757 | 103387.5 | 2240 | 84000 | 37.5 | 37.5 |  | 37.5 | 100% | 2757 | 103387.5 | 2240 | 84000 |  | 84000 | [7 empty] | 2240 | 37.5 | 84000 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 37.5 | 37.5 |  | 37.5 | [9 empty] | Supply & Install Valves |  | Ea | 2240 |  | 2240 | 37.5 | 84000 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Gate Valve 280 MM | Material | Ea | 1870 | 1 | 1870 | 37.5 | 70125
[22 empty] | Fitting and Accessories 280 | Material | Ea | 170 | 1 | 170 | 37.5 | 6375
[22 empty] | Installation Valve 280mm | SC | Ea | 200 | 1 | 200 | 37.5 | 7500
IRR 9 |  | Butterfly Valves Butterfly water control valve |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
IRR 9 |  | Shut-off valve on 500mm pipe | nr | 11.45 | 12273 | 140525.85 | 9431 | 107984.95 | 11.45 | 11.45 |  | 11.45 | 100% | 12273 | 140525.85 | 9431 | 107984.95 |  | 107984.95 | [7 empty] | 9431 | 11.45 | 107984.95 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 11.45 | 11.45 |  | 11.45 | [9 empty] | Supply & Install Valves |  | Ea | 9431 |  | 9431 | 11.45 | 107984.95 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Butterfly Valve 500 MM | Material | Ea | 7210 | 1 | 7210 | 11.45 | 82554.5
[22 empty] | Fitting and Accessories 500 | Material | Ea | 721 | 1 | 721 | 11.45 | 8255.45
[22 empty] | Installation Valve 500mm | SC | Ea | 1500 | 1 | 1500 | 11.45 | 17175
IRR 9 |  | Shut-off valve on 630mm pipe | nr | 1.3 | 16691 | 21698.3 | 12225 | 15892.5 | 1.3 | 1.3 |  | 1.3 | 100% | 16691 | 21698.3 | 12225 | 15892.5 |  | 15892.5 | [7 empty] | 12225 | 1.3 | 15892.5 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 1.3 | 1.3 |  | 1.3 | [9 empty] | Supply & Install Valves |  | Ea | 12225 |  | 12225 | 1.3 | 15892.5 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Butterfly Valve 630 MM | Material | Ea | 9750 | 1 | 9750 | 1.3 | 12675
[22 empty] | Fitting and Accessories 630 | Material | Ea | 975 | 1 | 975 | 1.3 | 1267.5
[22 empty] | Installation Valve 630mm | SC | Ea | 1500 | 1 | 1500 | 1.3 | 1950
IRR 9 |  | Shut-off valve on 125mm pipe | nr |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
IRR 9 |  | Shut-off valve on 160mm pipe | nr |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
IRR 9 |  | Shut-off valve on 280mm pipe | nr |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
IRR 9 |  | Shut-off valve on 500mm pipe | nr |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
IRR 9 |  | Shut-off valve on 630mm pipe | nr |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
IRR 9 |  | Shut-off valve on 125mm pipe | nr |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
IRR 9 |  | Shut-off valve on 160mm pipe | nr |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
IRR 9 |  | Shut-off valve on 280mm pipe | nr |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
IRR 9 |  | Shut-off valve on 500mm pipe | nr |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
IRR 9 |  | Shut-off valve on 630mm pipe | nr |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
IRR 9 |  | Direct burial |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
IRR 9 |  | On a pipe line with a diameter of 125 mm, at a depth of 1.5-2.0 meters | nr |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
IRR 9 |  | On a pipe line with a diameter of 160 mm, at a depth of 1.5-2.0 meters | nr |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
IRR 9 |  | On a pipe line with a diameter of 280 mm, at a depth of 1.5-2.0 m | nr |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
IRR 9 |  | Category (K): Piping works - valve rooms |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
IRR 9 |  | On a pipe line with a diameter of 500 mm, and at a depth of 2-2.5 metres | nr | 11.1075 | 36631 | 406878.8325 | 12286.1796 | 136468.7396 | 11.1075 | 11.1075 |  | 11.1075 | 100% | 36631 | 406878.8325 | 12286.1796 | 136468.7396 |  | 136468.7396 | [7 empty] | 12286.1796 | 11.1075 | 136468.7396 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 11.1075 | 11.1075 |  | 11.1075 | [9 empty] | Excavate & Disposal (3*3*2.5) |  | Ea | 90.4969 |  | 90.4969 | 11.1075 | 1005.1948 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 4.4444 | 12.6 | 2.4992 | 139.9545
[22 empty] | Fuel | Material | LTR | 1.76 | 0.31746 | 5.544 | 34.9886 | 61.58
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.90667 | 52.9412 | 12.2509 | 588.0441
[22 empty] | Fuel | Material | LTR | 1.76 | 0.090667 | 19.4118 | 122.5092 | 215.6162
[9 empty] | 11.1075 | 11.1075 |  | 11.1075 | [9 empty] | Valve Room Installation |  | Ea | 9186.6 |  | 9186.6 | 11.1075 | 102040.1595 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 1.1111 | 225 | 9.9968 | 2499.1875
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.2 | 1750 | 55.5375 | 19438.125
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 2.5 | 1000 | 4.443 | 11107.5
[22 empty] | Workmanship plain concrete | SC | M³ | 150 | 1.1111 | 135 | 9.9968 | 1499.5125
[22 empty] | Workmanship RC concrete | SC | M³ | 450 | 0.2 | 2250 | 55.5375 | 24991.875
[22 empty] | Supply & apply Chamber Cover, frames | Material | Ea | 3500 | 1 | 3500 | 11.1075 | 38876.25
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 4 | 20 | 2.7769 | 222.15
[22 empty] | Fuel | Material | HR | 1.76 | 0.26667 | 6.6 | 41.6531 | 73.3095
[22 empty] | Chamber Pipes Pieces | Material | LS | 150 | 1 | 150 | 11.1075 | 1666.125
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.2 | 85 | 55.5375 | 944.1375
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.2 | 65 | 55.5375 | 721.9875
[9 empty] | 11.1075 | 11.1075 |  | 11.1075 | [9 empty] | Internal and external Insulation |  | Ea | 2800 |  | 2800 | 11.1075 | 31101 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply & apply external waterproofing | SC | M² | 40 | 0.025 | 1600 | 444.3 | 17772
[22 empty] | Supply & apply internal coating | SC | M² | 30 | 0.025 | 1200 | 444.3 | 13329
[9 empty] | 11.1075 | 11.1075 |  | 11.1075 | [9 empty] | Backfilling |  | Ea | 209.0826 |  | 209.0826 | 11.1075 | 2322.3854 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.083333 | 120 | 133.29 | 1332.9
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 8.3333 | 7.872 | 1.3329 | 87.4382
[22 empty] | Fuel | Material | LTR | 1.76 | 0.92593 | 1.9008 | 11.9961 | 21.1131
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 1.7 | 28.2353 | 6.5338 | 313.6235
[22 empty] | Fuel | Material | LTR | 1.76 | 0.17 | 10.3529 | 65.3382 | 114.9953
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 4.1667 | 8.64 | 2.6658 | 95.9688
[22 empty] | Fuel | Material | LTR | 1.76 | 0.46296 | 3.8016 | 23.9922 | 42.2263
[22 empty] | Plate Compactor | Machinery | HR | 23 | 1 | 23 | 11.1075 | 255.4725
[22 empty] | Fuel | Material | LTR | 1.76 | 0.33333 | 5.28 | 33.3225 | 58.6476
IRR 9 |  | On a pipe line with a diameter of 630 mm, at a depth of 2.0-2.5 metres | nr | 2.06 | 41748 | 86000.88 | 12286.1796 | 25309.5299 | 2.06 | 2.06 |  | 2.06 | 100% | 41748 | 86000.88 | 12286.1796 | 25309.5299 |  | 25309.5299 | [7 empty] | 12286.1796 | 2.06 | 25309.5299 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 2.06 | 2.06 |  | 2.06 | [9 empty] | Excavate & Disposal (3*3*2.5) |  | Ea | 90.4969 |  | 90.4969 | 2.06 | 186.4237 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 4.4444 | 12.6 | 0.4635 | 25.956
[22 empty] | Fuel | Material | LTR | 1.76 | 0.31746 | 5.544 | 6.489 | 11.4206
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.90667 | 52.9412 | 2.2721 | 109.0588
[22 empty] | Fuel | Material | LTR | 1.76 | 0.090667 | 19.4118 | 22.7206 | 39.9882
[9 empty] | 2.06 | 2.06 |  | 2.06 | [9 empty] | Valve Room Installation |  | Ea | 9186.6 |  | 9186.6 | 2.06 | 18924.396 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 1.1111 | 225 | 1.854 | 463.5
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.2 | 1750 | 10.3 | 3605
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 2.5 | 1000 | 0.824 | 2060
[22 empty] | Workmanship plain concrete | SC | M³ | 150 | 1.1111 | 135 | 1.854 | 278.1
[22 empty] | Workmanship RC concrete | SC | M³ | 450 | 0.2 | 2250 | 10.3 | 4635
[22 empty] | Supply & apply Chamber Cover, frames | Material | Ea | 3500 | 1 | 3500 | 2.06 | 7210
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 4 | 20 | 0.515 | 41.2
[22 empty] | Fuel | Material | HR | 1.76 | 0.26667 | 6.6 | 7.725 | 13.596
[22 empty] | Chamber Pipes Pieces | Material | LS | 150 | 1 | 150 | 2.06 | 309
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.2 | 85 | 10.3 | 175.1
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.2 | 65 | 10.3 | 133.9
[9 empty] | 2.06 | 2.06 |  | 2.06 | [9 empty] | Internal and external Insulation |  | Ea | 2800 |  | 2800 | 2.06 | 5768 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply & apply external waterproofing | SC | M² | 40 | 0.025 | 1600 | 82.4 | 3296
[22 empty] | Supply & apply internal coating | SC | M² | 30 | 0.025 | 1200 | 82.4 | 2472
[9 empty] | 2.06 | 2.06 |  | 2.06 | [9 empty] | Backfilling |  | Ea | 209.0826 |  | 209.0826 | 2.06 | 430.7102 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.083333 | 120 | 24.72 | 247.2
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 8.3333 | 7.872 | 0.2472 | 16.2163
[22 empty] | Fuel | Material | LTR | 1.76 | 0.92593 | 1.9008 | 2.2248 | 3.9156
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 1.7 | 28.2353 | 1.2118 | 58.1647
[22 empty] | Fuel | Material | LTR | 1.76 | 0.17 | 10.3529 | 12.1176 | 21.3271
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 4.1667 | 8.64 | 0.4944 | 17.7984
[22 empty] | Fuel | Material | LTR | 1.76 | 0.46296 | 3.8016 | 4.4496 | 7.8313
[22 empty] | Plate Compactor | Machinery | HR | 23 | 1 | 23 | 2.06 | 47.38
[22 empty] | Fuel | Material | LTR | 1.76 | 0.33333 | 5.28 | 6.18 | 10.8768
IRR 9 |  | On-site cleaning rooms made of reinforced concrete on the pipeline as specified and shown on the plans, and all that is required, including excavations, equipment, its decision, valves, boxes (containers) with their accessories, piping work, construction supplies and terminations, cutting and installing pipe pieces. |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
IRR 9 |  | The cleaning room is on a pipe line with a diameter of 125 mm, and at a depth of 1.5-2.5 meters |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
IRR 9 |  | The cleaning room is on a 160 mm diameter pipe line, at a depth of 2.5-2.0 metres |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
IRR 9 |  | The cleaning room is on a pipe line with a diameter of 280 mm, and at a depth of 2.0-2.5 metres | nr | 14.975 | 27442 | 410943.95 | 12286.1796 | 183985.5392 | 14.975 | 14.975 |  | 14.975 | 100% | 27442 | 410943.95 | 12286.1796 | 183985.5392 |  | 183985.5392 | [7 empty] | 12286.1796 | 14.975 | 183985.5392 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 14.975 | 14.975 |  | 14.975 | [9 empty] | Excavate & Disposal (3*3*2.5) |  | Ea | 90.4969 |  | 90.4969 | 14.975 | 1355.1917 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 4.4444 | 12.6 | 3.3694 | 188.685
[22 empty] | Fuel | Material | LTR | 1.76 | 0.31746 | 5.544 | 47.1713 | 83.0214
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.90667 | 52.9412 | 16.5165 | 792.7941
[22 empty] | Fuel | Material | LTR | 1.76 | 0.090667 | 19.4118 | 165.1654 | 290.6912
[9 empty] | 14.975 | 14.975 |  | 14.975 | [9 empty] | Cleaning Room Installation |  | Ea | 9186.6 |  | 9186.6 | 14.975 | 137569.335 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 1.1111 | 225 | 13.4775 | 3369.375
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.2 | 1750 | 74.875 | 26206.25
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 2.5 | 1000 | 5.99 | 14975
[22 empty] | Workmanship plain concrete | SC | M³ | 150 | 1.1111 | 135 | 13.4775 | 2021.625
[22 empty] | Workmanship RC concrete | SC | M³ | 450 | 0.2 | 2250 | 74.875 | 33693.75
[22 empty] | Supply & apply Chamber Cover, frames | Material | Ea | 3500 | 1 | 3500 | 14.975 | 52412.5
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 4 | 20 | 3.7438 | 299.5
[22 empty] | Fuel | Material | HR | 1.76 | 0.26667 | 6.6 | 56.1563 | 98.835
[22 empty] | Chamber Pipes Pieces | Material | LS | 150 | 1 | 150 | 14.975 | 2246.25
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.2 | 85 | 74.875 | 1272.875
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.2 | 65 | 74.875 | 973.375
[9 empty] | 14.975 | 14.975 |  | 14.975 | [9 empty] | Internal and external Insulation |  | Ea | 2800 |  | 2800 | 14.975 | 41930 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply & apply external waterproofing | SC | M² | 40 | 0.025 | 1600 | 599 | 23960
[22 empty] | Supply & apply internal coating | SC | M² | 30 | 0.025 | 1200 | 599 | 17970
[9 empty] | 14.975 | 14.975 |  | 14.975 | [9 empty] | Backfilling |  | Ea | 209.0826 |  | 209.0826 | 14.975 | 3131.0125 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.083333 | 120 | 179.7 | 1797
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 8.3333 | 7.872 | 1.797 | 117.8832
[22 empty] | Fuel | Material | LTR | 1.76 | 0.92593 | 1.9008 | 16.173 | 28.4645
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 1.7 | 28.2353 | 8.8088 | 422.8235
[22 empty] | Fuel | Material | LTR | 1.76 | 0.17 | 10.3529 | 88.0882 | 155.0353
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 4.1667 | 8.64 | 3.594 | 129.384
[22 empty] | Fuel | Material | LTR | 1.76 | 0.46296 | 3.8016 | 32.346 | 56.929
[22 empty] | Plate Compactor | Machinery | HR | 23 | 1 | 23 | 14.975 | 344.425
[22 empty] | Fuel | Material | LTR | 1.76 | 0.33333 | 5.28 | 44.925 | 79.068
IRR 9 |  | Cleaning room is on a 500mm diameter pipe line, at a depth of 3.0-3.5 metres | nr | 5.12 | 30966 | 158545.92 | 16017.7128 | 82010.6895 | 5.12 | 5.12 |  | 5.12 | 100% | 30966 | 158545.92 | 16017.7128 | 82010.6895 |  | 82010.6895 | [7 empty] | 16017.7128 | 5.12 | 82010.6895 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 5.12 | 5.12 |  | 5.12 | [9 empty] | Excavate & Disposal (3*3*3.5) |  | Ea | 126.6957 |  | 126.6957 | 5.12 | 648.6821 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 3.1746 | 17.64 | 1.6128 | 90.3168
[22 empty] | Fuel | Material | LTR | 1.76 | 0.22676 | 7.7616 | 22.5792 | 39.7394
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.64762 | 74.1176 | 7.9059 | 379.4824
[22 empty] | Fuel | Material | LTR | 1.76 | 0.064762 | 27.1765 | 79.0588 | 139.1435
[9 empty] | 5.12 | 5.12 |  | 5.12 | [9 empty] | Cleaning Room Installation |  | Ea | 11686.6 |  | 11686.6 | 5.12 | 59835.392 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 1.1111 | 225 | 4.608 | 1152
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.13333 | 2625 | 38.4 | 13440
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 1.6667 | 1500 | 3.072 | 7680
[22 empty] | Workmanship plain concrete | SC | M³ | 150 | 1.1111 | 135 | 4.608 | 691.2
[22 empty] | Workmanship RC concrete | SC | M³ | 450 | 0.13333 | 3375 | 38.4 | 17280
[22 empty] | Supply & apply Chamber Cover, frames | Material | Ea | 3500 | 1 | 3500 | 5.12 | 17920
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 4 | 20 | 1.28 | 102.4
[22 empty] | Fuel | Material | HR | 1.76 | 0.26667 | 6.6 | 19.2 | 33.792
[22 empty] | Chamber Pipes Pieces | Material | LS | 150 | 1 | 150 | 5.12 | 768
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.2 | 85 | 25.6 | 435.2
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.2 | 65 | 25.6 | 332.8
[9 empty] | 5.12 | 5.12 |  | 5.12 | [9 empty] | Internal and external Insulation |  | Ea | 3920 |  | 3920 | 5.12 | 20070.4 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply & apply external waterproofing | SC | M² | 40 | 0.017857 | 2240 | 286.72 | 11468.8
[22 empty] | Supply & apply internal coating | SC | M² | 30 | 0.017857 | 1680 | 286.72 | 8601.6
[9 empty] | 5.12 | 5.12 |  | 5.12 | [9 empty] | Backfilling |  | Ea | 284.4171 |  | 284.4171 | 5.12 | 1456.2154 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.058824 | 170 | 87.04 | 870.4
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 5.8824 | 11.152 | 0.8704 | 57.0982
[22 empty] | Fuel | Material | LTR | 1.76 | 0.65359 | 2.6928 | 7.8336 | 13.7871
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 1.2 | 40 | 4.2667 | 204.8
[22 empty] | Fuel | Material | LTR | 1.76 | 0.12 | 14.6667 | 42.6667 | 75.0933
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 2.9412 | 12.24 | 1.7408 | 62.6688
[22 empty] | Fuel | Material | LTR | 1.76 | 0.3268 | 5.3856 | 15.6672 | 27.5743
[22 empty] | Plate Compactor | Machinery | HR | 23 | 1 | 23 | 5.12 | 117.76
[22 empty] | Fuel | Material | LTR | 1.76 | 0.33333 | 5.28 | 15.36 | 27.0336
IRR 9 |  | Cleaning room on a pipe line with a diameter of 630 mm and a depth of 2.5 - 3.0 metres | nr | 0.21 | 31596 | 6635.16 | 14151.9462 | 2971.9087 | 0.21 | 0.21 |  | 0.21 | 100% | 31596 | 6635.16 | 14151.9462 | 2971.9087 |  | 2971.9087 | [7 empty] | 14151.9462 | 0.21 | 2971.9087 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 0.21 | 0.21 |  | 0.21 | [9 empty] | Excavate & Disposal (3*3*3.0) |  | Ea | 108.5963 |  | 108.5963 | 0.21 | 22.8052 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 3.7037 | 15.12 | 0.0567 | 3.1752
[22 empty] | Fuel | Material | LTR | 1.76 | 0.26455 | 6.6528 | 0.7938 | 1.3971
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.75556 | 63.5294 | 0.27794 | 13.3412
[22 empty] | Fuel | Material | LTR | 1.76 | 0.075556 | 23.2941 | 2.7794 | 4.8918
[9 empty] | 0.21 | 0.21 |  | 0.21 | [9 empty] | Cleaning Room Installation |  | Ea | 10436.6 |  | 10436.6 | 0.21 | 2191.686 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 1.1111 | 225 | 0.189 | 47.25
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.16 | 2187.5 | 1.3125 | 459.375
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 2 | 1250 | 0.105 | 262.5
[22 empty] | Workmanship plain concrete | SC | M³ | 150 | 1.1111 | 135 | 0.189 | 28.35
[22 empty] | Workmanship RC concrete | SC | M³ | 450 | 0.16 | 2812.5 | 1.3125 | 590.625
[22 empty] | Supply & apply Chamber Cover, frames | Material | Ea | 3500 | 1 | 3500 | 0.21 | 735
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 4 | 20 | 0.0525 | 4.2
[22 empty] | Fuel | Material | HR | 1.76 | 0.26667 | 6.6 | 0.7875 | 1.386
[22 empty] | Chamber Pipes Pieces | Material | LS | 150 | 1 | 150 | 0.21 | 31.5
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.2 | 85 | 1.05 | 17.85
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.2 | 65 | 1.05 | 13.65
[9 empty] | 0.21 | 0.21 |  | 0.21 | [9 empty] | Internal and external Insulation |  | Ea | 3360 |  | 3360 | 0.21 | 705.6 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply & apply external waterproofing | SC | M² | 40 | 0.020833 | 1920 | 10.08 | 403.2
[22 empty] | Supply & apply internal coating | SC | M² | 30 | 0.020833 | 1440 | 10.08 | 302.4
[9 empty] | 0.21 | 0.21 |  | 0.21 | [9 empty] | Backfilling |  | Ea | 246.7499 |  | 246.7499 | 0.21 | 51.8175 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.068966 | 145 | 3.045 | 30.45
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 6.8966 | 9.512 | 0.03045 | 1.9975
[22 empty] | Fuel | Material | LTR | 1.76 | 0.76628 | 2.2968 | 0.27405 | 0.48233
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 1.4069 | 34.1176 | 0.14926 | 7.1647
[22 empty] | Fuel | Material | LTR | 1.76 | 0.14069 | 12.5098 | 1.4926 | 2.6271
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 3.4483 | 10.44 | 0.0609 | 2.1924
[22 empty] | Fuel | Material | LTR | 1.76 | 0.38314 | 4.5936 | 0.5481 | 0.96466
[22 empty] | Plate Compactor | Machinery | HR | 23 | 1 | 23 | 0.21 | 4.83
[22 empty] | Fuel | Material | LTR | 1.76 | 0.33333 | 5.28 | 0.63 | 1.1088
IRR 9 |  | On-site reinforced concrete air valve chambers on the pipeline as specified and shown on the plans, and all that is required in terms of excavations, equipment, its decision, valves and boxes (containers) with their accessories, piping work, construction supplies and terminations, cutting and installing pipe pieces. |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
IRR 9 |  | Air valve chamber depth: 125mm diameter pipe line with 2 - 1.5m depth | nr |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
IRR 9 |  | Air valve chamber depth: 160mm diameter pipe line with 2 - 1.5m depth | nr |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
IRR 9 |  | Air valve chamber depth: 280mm diameter pipe line with 2 - 2.5m depth | nr | 13 | 22406 | 291278 | 12286.1796 | 159720.3345 | 13 | 13 |  | 13 | 100% | 22406 | 291278 | 12286.1796 | 159720.3345 |  | 159720.3345 | [7 empty] | 12286.1796 | 13 | 159720.3345 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 13 | 13 |  | 13 | [9 empty] | Excavate & Disposal (3*3*2.5) |  | Ea | 90.4969 |  | 90.4969 | 13 | 1176.4602 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 4.4444 | 12.6 | 2.925 | 163.8
[22 empty] | Fuel | Material | LTR | 1.76 | 0.31746 | 5.544 | 40.95 | 72.072
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.90667 | 52.9412 | 14.3382 | 688.2353
[22 empty] | Fuel | Material | LTR | 1.76 | 0.090667 | 19.4118 | 143.3824 | 252.3529
[9 empty] | 13 | 13 |  | 13 | [9 empty] | Valve Room Installation |  | Ea | 9186.6 |  | 9186.6 | 13 | 119425.8 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 1.1111 | 225 | 11.7 | 2925
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.2 | 1750 | 65 | 22750
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 2.5 | 1000 | 5.2 | 13000
[22 empty] | Workmanship plain concrete | SC | M³ | 150 | 1.1111 | 135 | 11.7 | 1755
[22 empty] | Workmanship RC concrete | SC | M³ | 450 | 0.2 | 2250 | 65 | 29250
[22 empty] | Supply & apply Chamber Cover, frames | Material | Ea | 3500 | 1 | 3500 | 13 | 45500
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 4 | 20 | 3.25 | 260
[22 empty] | Fuel | Material | HR | 1.76 | 0.26667 | 6.6 | 48.75 | 85.8
[22 empty] | Chamber Pipes Pieces | Material | LS | 150 | 1 | 150 | 13 | 1950
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.2 | 85 | 65 | 1105
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.2 | 65 | 65 | 845
[9 empty] | 13 | 13 |  | 13 | [9 empty] | Internal and external Insulation |  | Ea | 2800 |  | 2800 | 13 | 36400 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply & apply external waterproofing | SC | M² | 40 | 0.025 | 1600 | 520 | 20800
[22 empty] | Supply & apply internal coating | SC | M² | 30 | 0.025 | 1200 | 520 | 15600
[9 empty] | 13 | 13 |  | 13 | [9 empty] | Backfilling |  | Ea | 209.0826 |  | 209.0826 | 13 | 2718.0743 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.083333 | 120 | 156 | 1560
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 8.3333 | 7.872 | 1.56 | 102.336
[22 empty] | Fuel | Material | LTR | 1.76 | 0.92593 | 1.9008 | 14.04 | 24.7104
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 1.7 | 28.2353 | 7.6471 | 367.0588
[22 empty] | Fuel | Material | LTR | 1.76 | 0.17 | 10.3529 | 76.4706 | 134.5882
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 4.1667 | 8.64 | 3.12 | 112.32
[22 empty] | Fuel | Material | LTR | 1.76 | 0.46296 | 3.8016 | 28.08 | 49.4208
[22 empty] | Plate Compactor | Machinery | HR | 23 | 1 | 23 | 13 | 299
[22 empty] | Fuel | Material | LTR | 1.76 | 0.33333 | 5.28 | 39 | 68.64
IRR 9 |  | Air valve chamber depth: 500mm diameter pipe line with 2 - 2.5m depth | nr | 3.32 | 23414 | 77734.48 | 12286.1796 | 40790.1162 | 3.32 | 3.32 |  | 3.32 | 100% | 23414 | 77734.48 | 12286.1796 | 40790.1162 |  | 40790.1162 | [7 empty] | 12286.1796 | 3.32 | 40790.1162 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 3.32 | 3.32 |  | 3.32 | [9 empty] | Excavate & Disposal (3*3*2.5) |  | Ea | 90.4969 |  | 90.4969 | 3.32 | 300.4498 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 4.4444 | 12.6 | 0.747 | 41.832
[22 empty] | Fuel | Material | LTR | 1.76 | 0.31746 | 5.544 | 10.458 | 18.4061
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.90667 | 52.9412 | 3.6618 | 175.7647
[22 empty] | Fuel | Material | LTR | 1.76 | 0.090667 | 19.4118 | 36.6176 | 64.4471
[9 empty] | 3.32 | 3.32 |  | 3.32 | [9 empty] | Valve Room Installation |  | Ea | 9186.6 |  | 9186.6 | 3.32 | 30499.512 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 1.1111 | 225 | 2.988 | 747
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.2 | 1750 | 16.6 | 5810
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 2.5 | 1000 | 1.328 | 3320
[22 empty] | Workmanship plain concrete | SC | M³ | 150 | 1.1111 | 135 | 2.988 | 448.2
[22 empty] | Workmanship RC concrete | SC | M³ | 450 | 0.2 | 2250 | 16.6 | 7470
[22 empty] | Supply & apply Chamber Cover, frames | Material | Ea | 3500 | 1 | 3500 | 3.32 | 11620
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 4 | 20 | 0.83 | 66.4
[22 empty] | Fuel | Material | HR | 1.76 | 0.26667 | 6.6 | 12.45 | 21.912
[22 empty] | Chamber Pipes Pieces | Material | LS | 150 | 1 | 150 | 3.32 | 498
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.2 | 85 | 16.6 | 282.2
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.2 | 65 | 16.6 | 215.8
[9 empty] | 3.32 | 3.32 |  | 3.32 | [9 empty] | Internal and external Insulation |  | Ea | 2800 |  | 2800 | 3.32 | 9296 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply & apply external waterproofing | SC | M² | 40 | 0.025 | 1600 | 132.8 | 5312
[22 empty] | Supply & apply internal coating | SC | M² | 30 | 0.025 | 1200 | 132.8 | 3984
[9 empty] | 3.32 | 3.32 |  | 3.32 | [9 empty] | Backfilling |  | Ea | 209.0826 |  | 209.0826 | 3.32 | 694.1543 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.083333 | 120 | 39.84 | 398.4
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 8.3333 | 7.872 | 0.3984 | 26.135
[22 empty] | Fuel | Material | LTR | 1.76 | 0.92593 | 1.9008 | 3.5856 | 6.3107
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 1.7 | 28.2353 | 1.9529 | 93.7412
[22 empty] | Fuel | Material | LTR | 1.76 | 0.17 | 10.3529 | 19.5294 | 34.3718
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 4.1667 | 8.64 | 0.7968 | 28.6848
[22 empty] | Fuel | Material | LTR | 1.76 | 0.46296 | 3.8016 | 7.1712 | 12.6213
[22 empty] | Plate Compactor | Machinery | HR | 23 | 1 | 23 | 3.32 | 76.36
[22 empty] | Fuel | Material | LTR | 1.76 | 0.33333 | 5.28 | 9.96 | 17.5296
IRR 9 |  | Air valve chamber depth: 630mm diameter pipe line with 2 - 2.5m depth | nr | 0.815 | 24295 | 19800.425 | 12286.1796 | 10013.2364 | 0.815 | 0.815 |  | 0.815 | 100% | 24295 | 19800.425 | 12286.1796 | 10013.2364 |  | 10013.2364 | [7 empty] | 12286.1796 | 0.815 | 10013.2364 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 0.815 | 0.815 |  | 0.815 | [9 empty] | Excavate & Disposal (3*3*2.5) |  | Ea | 90.4969 |  | 90.4969 | 0.815 | 73.755 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 4.4444 | 12.6 | 0.18338 | 10.269
[22 empty] | Fuel | Material | LTR | 1.76 | 0.31746 | 5.544 | 2.5673 | 4.5184
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.90667 | 52.9412 | 0.8989 | 43.1471
[22 empty] | Fuel | Material | LTR | 1.76 | 0.090667 | 19.4118 | 8.989 | 15.8206
[9 empty] | 0.815 | 0.815 |  | 0.815 | [9 empty] | Valve Room Installation |  | Ea | 9186.6 |  | 9186.6 | 0.815 | 7487.079 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 1.1111 | 225 | 0.7335 | 183.375
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.2 | 1750 | 4.075 | 1426.25
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 2.5 | 1000 | 0.326 | 815
[22 empty] | Workmanship plain concrete | SC | M³ | 150 | 1.1111 | 135 | 0.7335 | 110.025
[22 empty] | Workmanship RC concrete | SC | M³ | 450 | 0.2 | 2250 | 4.075 | 1833.75
[22 empty] | Supply & apply Chamber Cover, frames | Material | Ea | 3500 | 1 | 3500 | 0.815 | 2852.5
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 4 | 20 | 0.20375 | 16.3
[22 empty] | Fuel | Material | HR | 1.76 | 0.26667 | 6.6 | 3.0563 | 5.379
[22 empty] | Chamber Pipes Pieces | Material | LS | 150 | 1 | 150 | 0.815 | 122.25
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.2 | 85 | 4.075 | 69.275
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.2 | 65 | 4.075 | 52.975
[9 empty] | 0.815 | 0.815 |  | 0.815 | [9 empty] | Internal and external Insulation |  | Ea | 2800 |  | 2800 | 0.815 | 2282 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply & apply external waterproofing | SC | M² | 40 | 0.025 | 1600 | 32.6 | 1304
[22 empty] | Supply & apply internal coating | SC | M² | 30 | 0.025 | 1200 | 32.6 | 978
[9 empty] | 0.815 | 0.815 |  | 0.815 | [9 empty] | Backfilling |  | Ea | 209.0826 |  | 209.0826 | 0.815 | 170.4023 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.083333 | 120 | 9.78 | 97.8
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 8.3333 | 7.872 | 0.0978 | 6.4157
[22 empty] | Fuel | Material | LTR | 1.76 | 0.92593 | 1.9008 | 0.8802 | 1.5492
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 1.7 | 28.2353 | 0.47941 | 23.0118
[22 empty] | Fuel | Material | LTR | 1.76 | 0.17 | 10.3529 | 4.7941 | 8.4376
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 4.1667 | 8.64 | 0.1956 | 7.0416
[22 empty] | Fuel | Material | LTR | 1.76 | 0.46296 | 3.8016 | 1.7604 | 3.0983
[22 empty] | Plate Compactor | Machinery | HR | 23 | 1 | 23 | 0.815 | 18.745
[22 empty] | Fuel | Material | LTR | 1.76 | 0.33333 | 5.28 | 2.445 | 4.3032
IRR 9 |  | Art (K): Pipeworks - manholes and pipework accessories (continued) |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
IRR 9 |  | Flow meter on a 125 mm pipe. It includes a flow meter room with a depth of 2 - 2.5 meters. | nr | 2 | 38534 | 77068 | 24043.5396 | 48087.0792 | 2 | 2 |  | 2 | 100% | 38534 | 77068 | 24043.5396 | 48087.0792 |  | 48087.0792 | [7 empty] | 24043.5396 | 2 | 48087.0792 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 2 | 2 |  | 2 | [9 empty] | Excavate & Disposal (3*3*2.5) |  | Ea | 90.4969 |  | 90.4969 | 2 | 180.9939 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 4.4444 | 12.6 | 0.45 | 25.2
[22 empty] | Fuel | Material | LTR | 1.76 | 0.31746 | 5.544 | 6.3 | 11.088
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.90667 | 52.9412 | 2.2059 | 105.8824
[22 empty] | Fuel | Material | LTR | 1.76 | 0.090667 | 19.4118 | 22.0588 | 38.8235
[9 empty] | 2 | 2 |  | 2 | [9 empty] | Flow meter & valve room installation |  | Ea | 20943.96 |  | 20943.96 | 2 | 41887.92 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 1.1111 | 225 | 1.8 | 450
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.2 | 1750 | 10 | 3500
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 2.5 | 1000 | 0.8 | 2000
[22 empty] | Workmanship plain concrete | SC | M³ | 150 | 1.1111 | 135 | 1.8 | 270
[22 empty] | Workmanship RC concrete | SC | M³ | 450 | 0.2 | 2250 | 10 | 4500
[22 empty] | Supply & apply Chamber Cover, frames | Material | Ea | 3500 | 1 | 3500 | 2 | 7000
[22 empty] | Supply & apply Flow Meter 125 mm | Material | Ea | 11757.36 | 1 | 11757.36 | 2 | 23514.72
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 4 | 20 | 0.5 | 40
[22 empty] | Fuel | Material | HR | 1.76 | 0.26667 | 6.6 | 7.5 | 13.2
[22 empty] | Chamber Pipes Pieces | Material | LS | 150 | 1 | 150 | 2 | 300
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.2 | 85 | 10 | 170
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.2 | 65 | 10 | 130
[9 empty] | 2 | 2 |  | 2 | [9 empty] | Internal and external Insulation |  | Ea | 2800 |  | 2800 | 2 | 5600 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply & apply external waterproofing | SC | M² | 40 | 0.025 | 1600 | 80 | 3200
[22 empty] | Supply & apply internal coating | SC | M² | 30 | 0.025 | 1200 | 80 | 2400
[9 empty] | 2 | 2 |  | 2 | [9 empty] | Backfilling |  | Ea | 209.0826 |  | 209.0826 | 2 | 418.1653 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.083333 | 120 | 24 | 240
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 8.3333 | 7.872 | 0.24 | 15.744
[22 empty] | Fuel | Material | LTR | 1.76 | 0.92593 | 1.9008 | 2.16 | 3.8016
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 1.7 | 28.2353 | 1.1765 | 56.4706
[22 empty] | Fuel | Material | LTR | 1.76 | 0.17 | 10.3529 | 11.7647 | 20.7059
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 4.1667 | 8.64 | 0.48 | 17.28
[22 empty] | Fuel | Material | LTR | 1.76 | 0.46296 | 3.8016 | 4.32 | 7.6032
[22 empty] | Plate Compactor | Machinery | HR | 23 | 1 | 23 | 2 | 46
[22 empty] | Fuel | Material | LTR | 1.76 | 0.33333 | 5.28 | 6 | 10.56
IRR 9 |  | Flow meter on a 280 mm pipe. It includes a flow meter room with a depth of 2 - 2.5 meters. | nr | 6.505 | 40785 | 265306.425 | 25903.1696 | 168500.1181 | 6.505 | 6.505 |  | 6.505 | 100% | 40785 | 265306.425 | 25903.1696 | 168500.1181 |  | 168500.1181 | [7 empty] | 25903.1696 | 6.505 | 168500.1181 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 6.505 | 6.505 |  | 6.505 | [9 empty] | Excavate & Disposal (3*3*2.5) |  | Ea | 90.4969 |  | 90.4969 | 6.505 | 588.6826 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 4.4444 | 12.6 | 1.4636 | 81.963
[22 empty] | Fuel | Material | LTR | 1.76 | 0.31746 | 5.544 | 20.4907 | 36.0637
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.90667 | 52.9412 | 7.1746 | 344.3824
[22 empty] | Fuel | Material | LTR | 1.76 | 0.090667 | 19.4118 | 71.7463 | 126.2735
[9 empty] | 6.505 | 6.505 |  | 6.505 | [9 empty] | Flow meter & valve room installation |  | Ea | 22803.59 |  | 22803.59 | 6.505 | 148337.353 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 1.1111 | 225 | 5.8545 | 1463.625
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.2 | 1750 | 32.525 | 11383.75
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 2.5 | 1000 | 2.602 | 6505
[22 empty] | Workmanship plain concrete | SC | M³ | 150 | 1.1111 | 135 | 5.8545 | 878.175
[22 empty] | Workmanship RC concrete | SC | M³ | 450 | 0.2 | 2250 | 32.525 | 14636.25
[22 empty] | Supply & apply Chamber Cover, frames | Material | Ea | 3500 | 1 | 3500 | 6.505 | 22767.5
[22 empty] | Supply & apply Flow Meter 280 mm | Material | Ea | 13616.99 | 1 | 13616.99 | 6.505 | 88578.52
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 4 | 20 | 1.6262 | 130.1
[22 empty] | Fuel | Material | HR | 1.76 | 0.26667 | 6.6 | 24.3938 | 42.933
[22 empty] | Chamber Pipes Pieces | Material | LS | 150 | 1 | 150 | 6.505 | 975.75
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.2 | 85 | 32.525 | 552.925
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.2 | 65 | 32.525 | 422.825
[9 empty] | 6.505 | 6.505 |  | 6.505 | [9 empty] | Internal and external Insulation |  | Ea | 2800 |  | 2800 | 6.505 | 18214 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply & apply external waterproofing | SC | M² | 40 | 0.025 | 1600 | 260.2 | 10408
[22 empty] | Supply & apply internal coating | SC | M² | 30 | 0.025 | 1200 | 260.2 | 7806
[9 empty] | 6.505 | 6.505 |  | 6.505 | [9 empty] | Backfilling |  | Ea | 209.0826 |  | 209.0826 | 6.505 | 1360.0825 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.083333 | 120 | 78.06 | 780.6
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 8.3333 | 7.872 | 0.7806 | 51.2074
[22 empty] | Fuel | Material | LTR | 1.76 | 0.92593 | 1.9008 | 7.0254 | 12.3647
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 1.7 | 28.2353 | 3.8265 | 183.6706
[22 empty] | Fuel | Material | LTR | 1.76 | 0.17 | 10.3529 | 38.2647 | 67.3459
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 4.1667 | 8.64 | 1.5612 | 56.2032
[22 empty] | Fuel | Material | LTR | 1.76 | 0.46296 | 3.8016 | 14.0508 | 24.7294
[22 empty] | Plate Compactor | Machinery | HR | 23 | 1 | 23 | 6.505 | 149.615
[22 empty] | Fuel | Material | LTR | 1.76 | 0.33333 | 5.28 | 19.515 | 34.3464
IRR 9 |  | Flow meter on a 500 mm pipe, including a flow meter chamber with a depth of 2 - 2.5 meters. | nr | 0.49 | 51107 | 25042.43 | 38614.7896 | 18921.2469 | 0.49 | 0.49 |  | 0.49 | 100% | 51107 | 25042.43 | 38614.7896 | 18921.2469 |  | 18921.2469 | [7 empty] | 38614.7896 | 0.49 | 18921.2469 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 0.49 | 0.49 |  | 0.49 | [9 empty] | Excavate & Disposal (3*3*2.5) |  | Ea | 90.4969 |  | 90.4969 | 0.49 | 44.3435 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 4.4444 | 12.6 | 0.11025 | 6.174
[22 empty] | Fuel | Material | LTR | 1.76 | 0.31746 | 5.544 | 1.5435 | 2.7166
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.90667 | 52.9412 | 0.54044 | 25.9412
[22 empty] | Fuel | Material | LTR | 1.76 | 0.090667 | 19.4118 | 5.4044 | 9.5118
[9 empty] | 0.49 | 0.49 |  | 0.49 | [9 empty] | Flow meter & valve room installation |  | Ea | 35515.21 |  | 35515.21 | 0.49 | 17402.4529 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 1.1111 | 225 | 0.441 | 110.25
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.2 | 1750 | 2.45 | 857.5
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 2.5 | 1000 | 0.196 | 490
[22 empty] | Workmanship plain concrete | SC | M³ | 150 | 1.1111 | 135 | 0.441 | 66.15
[22 empty] | Workmanship RC concrete | SC | M³ | 450 | 0.2 | 2250 | 2.45 | 1102.5
[22 empty] | Supply & apply Chamber Cover, frames | Material | Ea | 3500 | 1 | 3500 | 0.49 | 1715
[22 empty] | Supply & apply Flow Meter 500 mm | Material | Ea | 26328.61 | 1 | 26328.61 | 0.49 | 12901.0189
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 4 | 20 | 0.1225 | 9.8
[22 empty] | Fuel | Material | HR | 1.76 | 0.26667 | 6.6 | 1.8375 | 3.234
[22 empty] | Chamber Pipes Pieces | Material | LS | 150 | 1 | 150 | 0.49 | 73.5
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.2 | 85 | 2.45 | 41.65
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.2 | 65 | 2.45 | 31.85
[9 empty] | 0.49 | 0.49 |  | 0.49 | [9 empty] | Internal and external Insulation |  | Ea | 2800 |  | 2800 | 0.49 | 1372 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply & apply external waterproofing | SC | M² | 40 | 0.025 | 1600 | 19.6 | 784
[22 empty] | Supply & apply internal coating | SC | M² | 30 | 0.025 | 1200 | 19.6 | 588
[9 empty] | 0.49 | 0.49 |  | 0.49 | [9 empty] | Backfilling |  | Ea | 209.0826 |  | 209.0826 | 0.49 | 102.4505 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.083333 | 120 | 5.88 | 58.8
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 8.3333 | 7.872 | 0.0588 | 3.8573
[22 empty] | Fuel | Material | LTR | 1.76 | 0.92593 | 1.9008 | 0.5292 | 0.93139
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 1.7 | 28.2353 | 0.28824 | 13.8353
[22 empty] | Fuel | Material | LTR | 1.76 | 0.17 | 10.3529 | 2.8824 | 5.0729
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 4.1667 | 8.64 | 0.1176 | 4.2336
[22 empty] | Fuel | Material | LTR | 1.76 | 0.46296 | 3.8016 | 1.0584 | 1.8628
[22 empty] | Plate Compactor | Machinery | HR | 23 | 1 | 23 | 0.49 | 11.27
[22 empty] | Fuel | Material | LTR | 1.76 | 0.33333 | 5.28 | 1.47 | 2.5872
IRR 9 |  | Category (L): Pipe works - supports, protection and accessories related to extension and excavation works. |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
IRR 9 |  | Backfill materials under and around pipes - Type (A) |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
IRR 9 |  | Pipes with a diameter not exceeding 125 mm | m |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
IRR 9 |  | Pipes with a diameter not exceeding 160 mm | m |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
IRR 9 |  | Pipes with a diameter not exceeding 280 mm | m |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
IRR 9 |  | Pipes with a diameter not exceeding 500 mm | m |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
IRR 9 |  | Pipes with a diameter not exceeding 630 mm | m |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
IRR 9 |  | Backfill materials under and around pipes - Type (B) |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
IRR 9 |  | Made of materials selected from the drilling output and stacked at 95% of the maximum dry density of the pipes at different levels in accordance with the specifications, plans and what the Authority requires. |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
IRR 9 |  | Pipes with a diameter not exceeding 125 mm | m | 3402.192 | 20 | 68043.84 | 13.0872 | 44525.1494 | 3402.192 | 3402.192 |  | 3402.192 | 100% | 20 | 68043.84 | 13.0872 | 44525.1494 |  | 44525.1494 | [7 empty] | 13.0872 | 3402.192 | 44525.1494 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 3402.192 | 3402.192 |  | 3402.192 | [9 empty] | Backfilling (W=1.0, D=2.0) |  | M | 13.0872 |  | 13.0872 | 3402.192 | 44525.1494 | 0 | 0 | 0 | 0 | 0
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 50 | 1.312 | 68.0438 | 4463.6759
[22 empty] | Fuel | Material | LTR | 1.76 | 5.5556 | 0.3168 | 612.3946 | 1077.8144
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 10.2 | 4.7059 | 333.5482 | 16010.3153
[22 empty] | Fuel | Material | LTR | 1.76 | 1.02 | 1.7255 | 3335.4824 | 5870.4489
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 25 | 1.44 | 136.0877 | 4899.1565
[22 empty] | Fuel | Material | LTR | 1.76 | 2.7778 | 0.6336 | 1224.7891 | 2155.6289
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 36 | 1.3333 | 94.5053 | 4536.256
[22 empty] | Fuel | Material | LTR | 1.76 | 3.6 | 0.48889 | 945.0533 | 1663.2939
[22 empty] | Plate Compactor | Machinery | HR | 23 | 25 | 0.92 | 136.0877 | 3130.0166
[22 empty] | Fuel | Material | LTR | 1.76 | 8.3333 | 0.2112 | 408.263 | 718.543
IRR 9 |  | Pipes with a diameter not exceeding 160 mm | m | 1214.63 | 24 | 29151.12 | 13.0872 | 15896.0994 | 1214.63 | 1214.63 |  | 1214.63 | 100% | 24 | 29151.12 | 13.0872 | 15896.0994 |  | 15896.0994 | [7 empty] | 13.0872 | 1214.63 | 15896.0994 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 1214.63 | 1214.63 |  | 1214.63 | [9 empty] | Backfilling (W=1.0, D=2.0) |  | M | 13.0872 |  | 13.0872 | 1214.63 | 15896.0994 | 0 | 0 | 0 | 0 | 0
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 50 | 1.312 | 24.2926 | 1593.5946
[22 empty] | Fuel | Material | LTR | 1.76 | 5.5556 | 0.3168 | 218.6334 | 384.7948
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 10.2 | 4.7059 | 119.0814 | 5715.9059
[22 empty] | Fuel | Material | LTR | 1.76 | 1.02 | 1.7255 | 1190.8137 | 2095.8322
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 25 | 1.44 | 48.5852 | 1749.0672
[22 empty] | Fuel | Material | LTR | 1.76 | 2.7778 | 0.6336 | 437.2668 | 769.5896
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 36 | 1.3333 | 33.7397 | 1619.5067
[22 empty] | Fuel | Material | LTR | 1.76 | 3.6 | 0.48889 | 337.3972 | 593.8191
[22 empty] | Plate Compactor | Machinery | HR | 23 | 25 | 0.92 | 48.5852 | 1117.4596
[22 empty] | Fuel | Material | LTR | 1.76 | 8.3333 | 0.2112 | 145.7556 | 256.5299
IRR 9 |  | Pipes with a diameter not exceeding 280 mm | m | 330.677 | 32 | 10581.664 | 13.0872 | 4327.6343 | 330.677 | 330.677 |  | 330.677 | 100% | 32 | 10581.664 | 13.0872 | 4327.6343 |  | 4327.6343 | [7 empty] | 13.0872 | 330.677 | 4327.6343 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 330.677 | 330.677 |  | 330.677 | [9 empty] | Backfilling (W=1.0, D=2.0) |  | M | 13.0872 |  | 13.0872 | 330.677 | 4327.6343 | 0 | 0 | 0 | 0 | 0
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 50 | 1.312 | 6.6135 | 433.8482
[22 empty] | Fuel | Material | LTR | 1.76 | 5.5556 | 0.3168 | 59.5219 | 104.7585
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 10.2 | 4.7059 | 32.4193 | 1556.1271
[22 empty] | Fuel | Material | LTR | 1.76 | 1.02 | 1.7255 | 324.1931 | 570.5799
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 25 | 1.44 | 13.2271 | 476.1749
[22 empty] | Fuel | Material | LTR | 1.76 | 2.7778 | 0.6336 | 119.0437 | 209.5169
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 36 | 1.3333 | 9.1855 | 440.9027
[22 empty] | Fuel | Material | LTR | 1.76 | 3.6 | 0.48889 | 91.8547 | 161.6643
[22 empty] | Plate Compactor | Machinery | HR | 23 | 25 | 0.92 | 13.2271 | 304.2228
[22 empty] | Fuel | Material | LTR | 1.76 | 8.3333 | 0.2112 | 39.6812 | 69.839
IRR 9 |  | Pipes with a diameter not exceeding 500 mm | m | 25.537 | 53 | 1353.461 | 18.1541 | 463.6008 | 25.537 | 25.537 |  | 25.537 | 100% | 53 | 1353.461 | 18.1541 | 463.6008 |  | 463.6008 | [7 empty] | 18.1541 | 25.537 | 463.6008 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 25.537 | 25.537 |  | 25.537 | [9 empty] | Backfilling (W=1.5, D=2.0) |  | M | 18.1541 |  | 18.1541 | 25.537 | 463.6008 | 0 | 0 | 0 | 0 | 0
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 33.3333 | 1.968 | 0.76611 | 50.2568
[22 empty] | Fuel | Material | LTR | 1.76 | 3.7037 | 0.4752 | 6.895 | 12.1352
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 6.8 | 7.0588 | 3.7554 | 180.2612
[22 empty] | Fuel | Material | LTR | 1.76 | 0.68 | 2.5882 | 37.5544 | 66.0958
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 16.6667 | 2.16 | 1.5322 | 55.1599
[22 empty] | Fuel | Material | LTR | 1.76 | 1.8519 | 0.9504 | 13.79 | 24.2704
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 36 | 1.3333 | 0.70936 | 34.0493
[22 empty] | Fuel | Material | LTR | 1.76 | 3.6 | 0.48889 | 7.0936 | 12.4848
[22 empty] | Plate Compactor | Machinery | HR | 23 | 25 | 0.92 | 1.0215 | 23.494
[22 empty] | Fuel | Material | LTR | 1.76 | 8.3333 | 0.2112 | 3.0644 | 5.3934
IRR 9 |  | Pipes with a diameter not exceeding 630 mm | m | 91.395 | 68 | 6214.86 | 19.4715 | 1779.5951 | 91.395 | 91.395 |  | 91.395 | 100% | 68 | 6214.86 | 19.4715 | 1779.5951 |  | 1779.5951 | [7 empty] | 19.4715 | 91.395 | 1779.5951 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 91.395 | 91.395 |  | 91.395 | [9 empty] | Backfilling (W=1.63, D=2.0) |  | M | 19.4715 |  | 19.4715 | 91.395 | 1779.5951 | 0 | 0 | 0 | 0 | 0
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 30.6748 | 2.1386 | 2.9795 | 195.4537
[22 empty] | Fuel | Material | LTR | 1.76 | 3.4083 | 0.51638 | 26.8153 | 47.1949
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 6.2577 | 7.6706 | 14.6053 | 701.0534
[22 empty] | Fuel | Material | LTR | 1.76 | 0.62577 | 2.8125 | 146.0528 | 257.0529
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 15.3374 | 2.3472 | 5.959 | 214.5223
[22 empty] | Fuel | Material | LTR | 1.76 | 1.7042 | 1.0328 | 53.6306 | 94.3898
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 36 | 1.3333 | 2.5387 | 121.86
[22 empty] | Fuel | Material | LTR | 1.76 | 3.6 | 0.48889 | 25.3875 | 44.682
[22 empty] | Plate Compactor | Machinery | HR | 23 | 25 | 0.92 | 3.6558 | 84.0834
[22 empty] | Fuel | Material | LTR | 1.76 | 8.3333 | 0.2112 | 10.9674 | 19.3026
IRR 9 |  | Block volume from 0-1 cubic meter | nr | 318 | 755 | 240090 | 675 | 214650 | 318 | 318 |  | 318 | 100% | 755 | 240090 | 675 | 214650 |  | 214650 | [7 empty] | 675 | 318 | 214650 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 318 | 318 |  | 318 | [9 empty] | Thrust Block (0.75 m³) |  | Ea | 675 |  | 675 | 318 | 214650 | 0 | 0 | 0 | 0 | 0
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 1.3333 | 262.5 | 238.5 | 83475
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 16.6667 | 150 | 19.08 | 47700
[22 empty] | Workmanship Thrust Block | SC | M³ | 350 | 1.3333 | 262.5 | 238.5 | 83475
IRR 9 |  | The block volume is 1-2 cubic metres | nr | 43.25 | 1133 | 49002.25 | 1350 | 58387.5 | 43.25 | 43.25 |  | 43.25 | 100% | 1133 | 49002.25 | 1350 | 58387.5 |  | 58387.5 | [7 empty] | 1350 | 43.25 | 58387.5 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 43.25 | 43.25 |  | 43.25 | [9 empty] | Thrust Block (1.5 m³) |  | Ea | 1350 |  | 1350 | 43.25 | 58387.5 | 0 | 0 | 0 | 0 | 0
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.66667 | 525 | 64.875 | 22706.25
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 8.3333 | 300 | 5.19 | 12975
[22 empty] | Workmanship Thrust Block | SC | M³ | 350 | 0.66667 | 525 | 64.875 | 22706.25
IRR 9 |  | The block volume is 4-6 cubic metres | nr | 13.2 | 4249 | 56086.8 | 4500 | 59400 | 13.2 | 13.2 |  | 13.2 | 100% | 4249 | 56086.8 | 4500 | 59400 |  | 59400 | [7 empty] | 4500 | 13.2 | 59400 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 13.2 | 13.2 |  | 13.2 | [9 empty] | Thrust Block (5.0 m³) |  | Ea | 4500 |  | 4500 | 13.2 | 59400 | 0 | 0 | 0 | 0 | 0
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.2 | 1750 | 66 | 23100
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 2.5 | 1000 | 5.28 | 13200
[22 empty] | Workmanship Thrust Block | SC | M³ | 350 | 0.2 | 1750 | 66 | 23100
IRR 9 |  | Block volume of 6 cubic metres | nr | 29.5 | 4532 | 133694 | 5400 | 159300 | 29.5 | 29.5 |  | 29.5 | 100% | 4532 | 133694 | 5400 | 159300 |  | 159300 | [7 empty] | 5400 | 29.5 | 159300 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 29.5 | 29.5 |  | 29.5 | [9 empty] | Thrust Block (6.0 m³) |  | Ea | 5400 |  | 5400 | 29.5 | 159300 | 0 | 0 | 0 | 0 | 0
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.16667 | 2100 | 177 | 61950
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 2.0833 | 1200 | 14.16 | 35400
[22 empty] | Workmanship Thrust Block | SC | M³ | 350 | 0.16667 | 2100 | 177 | 61950
IRR 9 |  | Additional excavation and backfilling works, drilling into rock to various depths, including disposal of waste to approved locations, warning tapes, and dewatering. | m³ | 17 | 50 | 850 | 30.658 | 521.1859 | 17 | 17 |  | 17 | 100% | 50 | 850 | 30.658 | 521.1859 |  | 521.1859 | [7 empty] | 30.658 | 17 | 521.1859 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 17 | 17 |  | 17 | [9 empty] | Rock Excavation & Disposal |  | M³ | 22.3553 |  | 22.3553 | 17 | 380.0395 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Hydraulic Hammer 50T | Machinery | HR | 150.4 | 15 | 10.0267 | 1.1333 | 170.4533
[22 empty] | Fuel | Material | LTR | 1.76 | 0.46875 | 3.7547 | 36.2667 | 63.8293
[22 empty] | Excavator with Bucket 50T | Machinery | HR | 131.2 | 50 | 2.624 | 0.34 | 44.608
[22 empty] | Fuel | Material | LTR | 1.76 | 1.5625 | 1.1264 | 10.88 | 19.1488
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 13.6 | 3.5294 | 1.25 | 60
[22 empty] | Fuel | Material | LTR | 1.76 | 1.36 | 1.2941 | 12.5 | 22
[9 empty] | 17 | 17 |  | 17 | [9 empty] | Backfilling & Compaction |  | M³ | 8.3027 |  | 8.3027 | 17 | 141.1464 | 0 | 0 | 0 | 0 | 0
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 100 | 0.656 | 0.17 | 11.152
[22 empty] | Fuel | Material | LTR | 1.76 | 11.1111 | 0.1584 | 1.53 | 2.6928
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 13.6 | 3.5294 | 1.25 | 60
[22 empty] | Fuel | Material | LTR | 1.76 | 1.36 | 1.2941 | 12.5 | 22
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 50 | 0.72 | 0.34 | 12.24
[22 empty] | Fuel | Material | LTR | 1.76 | 5.5556 | 0.3168 | 3.06 | 5.3856
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 80 | 0.6 | 0.2125 | 10.2
[22 empty] | Fuel | Material | LTR | 1.76 | 8 | 0.22 | 2.125 | 3.74
[22 empty] | Roller Compactor 10 Ton | Machinery | HR | 40 | 80 | 0.5 | 0.2125 | 8.5
[22 empty] | Fuel | Material | LTR | 1.76 | 5.7143 | 0.308 | 2.975 | 5.236
Category 1: Pipework – Pipes Supply and installation of UPVC plastic pipes in the designated trenches, including drilling, backfilling, compaction, waste removal, protection of services and facilities, supports, warning tape, testing and operation upon completion according to the drawings, specifications and requirements of the relevant authority (backfilling works under the pipe, draining water, reinforcing and protecting the excavated surfaces to reach the required depths and disposing of groundwater resulting from the drainage around them are measured individually)
SEW 10 |  | Pipes, 150 mm inner diameter, at a maximum depth of 1.5 m | m | 99.9093 | 122 | 12188.9407 | 91.1661 | 9108.3421 | 99.9093 | 99.9093 |  | 99.9093 | 100% | 122 | 12188.9407 | 91.1661 | 9108.3421 |  | 9108.3421 | [7 empty] | 91.1661 | 99.9093 | 9108.3421 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 99.9093 | 99.9093 |  | 99.9093 | [9 empty] | Excavation ( W= 1.0 & d= 1.5 ) |  | M | 7.5827 |  | 7.5827 | 99.9093 | 757.5856 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 66.6667 | 0.84 | 1.4986 | 83.9239
[22 empty] | Fuel | Material | LTR | 1.76 | 4.7619 | 0.3696 | 20.981 | 36.9265
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 13.6 | 3.5294 | 7.3463 | 352.6212
[22 empty] | Fuel | Material | LTR | 1.76 | 1.36 | 1.2941 | 73.4628 | 129.2945
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 1.9982 | 45.9583
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 5.9946 | 10.5504
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 66.6667 | 0.72 | 1.4986 | 71.9347
[22 empty] | Fuel | Material | LTR | 1.76 | 6.6667 | 0.264 | 14.9864 | 26.3761
[9 empty] | 99.9093 | 99.9093 |  | 99.9093 | [9 empty] | Pipe Laying & Protection |  | M | 78.5833 |  | 78.5833 | 99.9093 | 7851.2098 | 0 | 0 | 0 | 0 | 0
[22 empty] | UPVC Pipe 150 mm | Material | M | 33.5 | 1 | 33.5 | 99.9093 | 3346.9632
[22 empty] | UPVC Fitting 150 mm | Material | M | 2 | 1 | 2 | 99.9093 | 199.8187
[22 empty] | Skilled Labor | Manpower | HR | 17 | 12 | 1.4167 | 8.3258 | 141.5382
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 12 | 1.0833 | 8.3258 | 108.2351
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 10 | 25 | 9.9909 | 2497.7337
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 10 | 15 | 9.9909 | 1498.6402
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.33303 | 58.2805
[9 empty] | 99.9093 | 99.9093 |  | 99.9093 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 99.9093 | 499.5467 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 99.9093 | 499.5467
SEW 10 |  | Pipes, 150 mm inner diameter, at a maximum depth of 1.5-2.0 m | m | 210.3187 | 132 | 27762.0618 | 93.5051 | 19665.8676 | 210.3187 | 210.3187 |  | 210.3187 | 100% | 132 | 27762.0618 | 93.5051 | 19665.8676 |  | 19665.8676 | [7 empty] | 93.5051 | 210.3187 | 19665.8676 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 210.3187 | 210.3187 |  | 210.3187 | [9 empty] | Excavation ( W= 1.0 & d= 2.0 ) |  | M | 9.9218 |  | 9.9218 | 210.3187 | 2086.7338 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 50 | 1.12 | 4.2064 | 235.5569
[22 empty] | Fuel | Material | LTR | 1.76 | 3.5714 | 0.4928 | 58.8892 | 103.645
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 10.2 | 4.7059 | 20.6195 | 989.7348
[22 empty] | Fuel | Material | LTR | 1.76 | 1.02 | 1.7255 | 206.1948 | 362.9028
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 4.2064 | 96.7466
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 12.6191 | 22.2096
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 50 | 0.96 | 4.2064 | 201.9059
[22 empty] | Fuel | Material | LTR | 1.76 | 5 | 0.352 | 42.0637 | 74.0322
[9 empty] | 210.3187 | 210.3187 |  | 210.3187 | [9 empty] | Pipe Laying & Protection |  | M | 78.5833 |  | 78.5833 | 210.3187 | 16527.5406 | 0 | 0 | 0 | 0 | 0
[22 empty] | UPVC Pipe 150 mm | Material | M | 33.5 | 1 | 33.5 | 210.3187 | 7045.6748
[22 empty] | UPVC Fitting 150 mm | Material | M | 2 | 1 | 2 | 210.3187 | 420.6373
[22 empty] | Skilled Labor | Manpower | HR | 17 | 12 | 1.4167 | 17.5266 | 297.9514
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 12 | 1.0833 | 17.5266 | 227.8452
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 10 | 25 | 21.0319 | 5257.9663
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 10 | 15 | 21.0319 | 3154.7798
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.70106 | 122.6859
[9 empty] | 210.3187 | 210.3187 |  | 210.3187 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 210.3187 | 1051.5933 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 210.3187 | 1051.5933
SEW 10 |  | Pipes, 150 mm inner diameter, at a maximum depth of 2.0-2.5 m | m | 57.9276 | 148 | 8573.2922 | 130.8441 | 7579.4941 | 57.9276 | 57.9276 |  | 57.9276 | 100% | 148 | 8573.2922 | 130.8441 | 7579.4941 |  | 7579.4941 | [7 empty] | 130.8441 | 57.9276 | 7579.4941 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 57.9276 | 57.9276 |  | 57.9276 | [9 empty] | Excavation ( W= 1.0 & d= 2.5 ) |  | M | 47.2608 |  | 47.2608 | 57.9276 | 2737.708 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 40 | 1.4 | 1.4482 | 81.0987
[22 empty] | Fuel | Material | LTR | 1.76 | 2.8571 | 0.616 | 20.2747 | 35.6834
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 8.16 | 5.8824 | 7.099 | 340.7509
[22 empty] | Fuel | Material | LTR | 1.76 | 0.816 | 2.1569 | 70.9898 | 124.942
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 1.1586 | 26.6467
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 3.4757 | 6.1172
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 40 | 1.2 | 1.4482 | 69.5132
[22 empty] | Fuel | Material | LTR | 1.76 | 4 | 0.44 | 14.4819 | 25.4882
[22 empty] | Steel Shoring D=2.5 M | Material | M | 35 | 1 | 35 | 57.9276 | 2027.4677
[9 empty] | 57.9276 | 57.9276 |  | 57.9276 | [9 empty] | Pipe Laying & Protection |  | M | 78.5833 |  | 78.5833 | 57.9276 | 4552.1478 | 0 | 0 | 0 | 0 | 0
[22 empty] | UPVC Pipe 150 mm | Material | M | 33.5 | 1 | 33.5 | 57.9276 | 1940.5763
[22 empty] | UPVC Fitting 150 mm | Material | M | 2 | 1 | 2 | 57.9276 | 115.8553
[22 empty] | Skilled Labor | Manpower | HR | 17 | 12 | 1.4167 | 4.8273 | 82.0642
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 12 | 1.0833 | 4.8273 | 62.755
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 10 | 25 | 5.7928 | 1448.1912
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 10 | 15 | 5.7928 | 868.9147
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.19309 | 33.7911
[9 empty] | 57.9276 | 57.9276 |  | 57.9276 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 57.9276 | 289.6382 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 57.9276 | 289.6382
SEW 10 |  | Pipes, 150 mm inner diameter, at a maximum depth of 2.5-3.0 m | m |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | Pipes, 200 mm inner diameter, at a maximum depth of 1.5 m | m | 65.2924 | 174 | 11360.8863 | 100.9161 | 6589.057 | 65.2924 | 65.2924 |  | 65.2924 | 100% | 174 | 11360.8863 | 100.9161 | 6589.057 |  | 6589.057 | [7 empty] | 100.9161 | 65.2924 | 6589.057 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 65.2924 | 65.2924 |  | 65.2924 | [9 empty] | Excavation ( W= 1.0 & d= 1.5 ) |  | M | 7.5827 |  | 7.5827 | 65.2924 | 495.095 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 66.6667 | 0.84 | 0.97939 | 54.8457
[22 empty] | Fuel | Material | LTR | 1.76 | 4.7619 | 0.3696 | 13.7114 | 24.1321
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 13.6 | 3.5294 | 4.8009 | 230.4439
[22 empty] | Fuel | Material | LTR | 1.76 | 1.36 | 1.2941 | 48.0092 | 84.4961
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 1.3058 | 30.0345
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 3.9175 | 6.8949
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 66.6667 | 0.72 | 0.97939 | 47.0106
[22 empty] | Fuel | Material | LTR | 1.76 | 6.6667 | 0.264 | 9.7939 | 17.2372
[9 empty] | 65.2924 | 65.2924 |  | 65.2924 | [9 empty] | Pipe Laying & Protection |  | M | 88.3333 |  | 88.3333 | 65.2924 | 5767.4997 | 0 | 0 | 0 | 0 | 0
[22 empty] | UPVC Pipe 200 mm | Material | M | 40 | 1 | 40 | 65.2924 | 2611.698
[22 empty] | UPVC Fitting 200 mm | Material | M | 4 | 1 | 4 | 65.2924 | 261.1698
[22 empty] | Skilled Labor | Manpower | HR | 17 | 8 | 2.125 | 8.1616 | 138.7465
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 8 | 1.625 | 8.1616 | 106.1002
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 10 | 25 | 6.5292 | 1632.3112
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 10 | 15 | 6.5292 | 979.3867
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.21764 | 38.0873
[9 empty] | 65.2924 | 65.2924 |  | 65.2924 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 65.2924 | 326.4622 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 65.2924 | 326.4622
SEW 10 |  | Pipes, 200 mm inner diameter, at a maximum depth of 1.5-2.0 m | m | 30.1015 | 184 | 5538.676 | 103.2551 | 3108.1336 | 30.1015 | 30.1015 |  | 30.1015 | 100% | 184 | 5538.676 | 103.2551 | 3108.1336 |  | 3108.1336 | [7 empty] | 103.2551 | 30.1015 | 3108.1336 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 30.1015 | 30.1015 |  | 30.1015 | [9 empty] | Excavation ( W= 1.0 & d= 2.0 ) |  | M | 9.9218 |  | 9.9218 | 30.1015 | 298.6602 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 50 | 1.12 | 0.60203 | 33.7137
[22 empty] | Fuel | Material | LTR | 1.76 | 3.5714 | 0.4928 | 8.4284 | 14.834
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 10.2 | 4.7059 | 2.9511 | 141.6541
[22 empty] | Fuel | Material | LTR | 1.76 | 1.02 | 1.7255 | 29.5113 | 51.9398
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 0.60203 | 13.8467
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 1.8061 | 3.1787
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 50 | 0.96 | 0.60203 | 28.8974
[22 empty] | Fuel | Material | LTR | 1.76 | 5 | 0.352 | 6.0203 | 10.5957
[9 empty] | 30.1015 | 30.1015 |  | 30.1015 | [9 empty] | Pipe Laying & Protection |  | M | 88.3333 |  | 88.3333 | 30.1015 | 2658.9658 | 0 | 0 | 0 | 0 | 0
[22 empty] | UPVC Pipe 200 mm | Material | M | 40 | 1 | 40 | 30.1015 | 1204.06
[22 empty] | UPVC Fitting 200 mm | Material | M | 4 | 1 | 4 | 30.1015 | 120.406
[22 empty] | Skilled Labor | Manpower | HR | 17 | 8 | 2.125 | 3.7627 | 63.9657
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 8 | 1.625 | 3.7627 | 48.9149
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 10 | 25 | 3.0101 | 752.5375
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 10 | 15 | 3.0101 | 451.5225
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.10034 | 17.5592
[9 empty] | 30.1015 | 30.1015 |  | 30.1015 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 30.1015 | 150.5075 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 30.1015 | 150.5075
SEW 10 |  | Pipes, 200 mm inner diameter, at a maximum depth of 2.0-2.5 m | m | 259.433 | 195 | 50589.4253 | 140.5941 | 36474.7548 | 259.433 | 259.433 |  | 259.433 | 100% | 195 | 50589.4253 | 140.5941 | 36474.7548 |  | 36474.7548 | [7 empty] | 140.5941 | 259.433 | 36474.7548 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 259.433 | 259.433 |  | 259.433 | [9 empty] | Excavation ( W= 1.0 & d= 2.5 ) |  | M | 47.2608 |  | 47.2608 | 259.433 | 12261.0128 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 40 | 1.4 | 6.4858 | 363.2061
[22 empty] | Fuel | Material | LTR | 1.76 | 2.8571 | 0.616 | 90.8015 | 159.8107
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 8.16 | 5.8824 | 31.7933 | 1526.0762
[22 empty] | Fuel | Material | LTR | 1.76 | 0.816 | 2.1569 | 317.9325 | 559.5613
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 5.1887 | 119.3392
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 15.566 | 27.3961
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 40 | 1.2 | 6.4858 | 311.3195
[22 empty] | Fuel | Material | LTR | 1.76 | 4 | 0.44 | 64.8582 | 114.1505
[22 empty] | Steel Shoring D=2.5 M | Material | M | 35 | 1 | 35 | 259.433 | 9080.1533
[9 empty] | 259.433 | 259.433 |  | 259.433 | [9 empty] | Pipe Laying & Protection |  | M | 88.3333 |  | 88.3333 | 259.433 | 22916.5773 | 0 | 0 | 0 | 0 | 0
[22 empty] | UPVC Pipe 200 mm | Material | M | 40 | 1 | 40 | 259.433 | 10377.318
[22 empty] | UPVC Fitting 200 mm | Material | M | 4 | 1 | 4 | 259.433 | 1037.7318
[22 empty] | Skilled Labor | Manpower | HR | 17 | 8 | 2.125 | 32.4291 | 551.295
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 8 | 1.625 | 32.4291 | 421.5785
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 10 | 25 | 25.9433 | 6485.8238
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 10 | 15 | 25.9433 | 3891.4943
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.86478 | 151.3359
[9 empty] | 259.433 | 259.433 |  | 259.433 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 259.433 | 1297.1648 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 259.433 | 1297.1648
SEW 10 |  | Pipes, 200 mm inner diameter, at a maximum depth of 2.5-3.0 m | m | 288.8409 | 325 | 93873.2925 | 167.9332 | 48505.9744 | 288.8409 | 288.8409 |  | 288.8409 | 100% | 325 | 93873.2925 | 167.9332 | 48505.9744 |  | 48505.9744 | [7 empty] | 167.9332 | 288.8409 | 48505.9744 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 288.8409 | 288.8409 |  | 288.8409 | [9 empty] | Excavation ( W= 1.0 & d= 3.0 ) |  | M | 74.5999 |  | 74.5999 | 288.8409 | 21547.4904 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 33.3333 | 1.68 | 8.6652 | 485.2527
[22 empty] | Fuel | Material | LTR | 1.76 | 2.381 | 0.7392 | 121.3132 | 213.5112
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 6.8 | 7.0588 | 42.4766 | 2038.8769
[22 empty] | Fuel | Material | LTR | 1.76 | 0.68 | 2.5882 | 424.766 | 747.5882
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 5.7768 | 132.8668
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 17.3305 | 30.5016
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 33.3333 | 1.44 | 8.6652 | 415.9309
[22 empty] | Fuel | Material | LTR | 1.76 | 3.3333 | 0.528 | 86.6523 | 152.508
[22 empty] | Steel Shoring D>3.0 M | Material | M | 60 | 1 | 60 | 288.8409 | 17330.454
[9 empty] | 288.8409 | 288.8409 |  | 288.8409 | [9 empty] | Pipe Laying & Protection |  | M | 88.3333 |  | 88.3333 | 288.8409 | 25514.2795 | 0 | 0 | 0 | 0 | 0
[22 empty] | UPVC Pipe 200 mm | Material | M | 40 | 1 | 40 | 288.8409 | 11553.636
[22 empty] | UPVC Fitting 200 mm | Material | M | 4 | 1 | 4 | 288.8409 | 1155.3636
[22 empty] | Skilled Labor | Manpower | HR | 17 | 8 | 2.125 | 36.1051 | 613.7869
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 8 | 1.625 | 36.1051 | 469.3665
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 10 | 25 | 28.8841 | 7221.0225
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 10 | 15 | 28.8841 | 4332.6135
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.9628 | 168.4905
[9 empty] | 288.8409 | 288.8409 |  | 288.8409 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 288.8409 | 1444.2045 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 288.8409 | 1444.2045
SEW 10 |  | Pipes, 200 mm inner diameter, at a maximum depth of 3.0-3.5 m | m | 333.0092 | 410 | 136533.7515 | 170.2722 | 56702.2123 | 333.0092 | 333.0092 |  | 333.0092 | 100% | 410 | 136533.7515 | 170.2722 | 56702.2123 |  | 56702.2123 | [7 empty] | 170.2722 | 333.0092 | 56702.2123 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 333.0092 | 333.0092 |  | 333.0092 | [9 empty] | Excavation ( W= 1.0 & d= 3.5 ) |  | M | 76.9389 |  | 76.9389 | 333.0092 | 25621.3583 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 28.5714 | 1.96 | 11.6553 | 652.6979
[22 empty] | Fuel | Material | LTR | 1.76 | 2.0408 | 0.8624 | 163.1745 | 287.1871
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 5.8286 | 8.2353 | 57.1339 | 2742.4283
[22 empty] | Fuel | Material | LTR | 1.76 | 0.58286 | 3.0196 | 571.3392 | 1005.557
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 6.6602 | 153.1842
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 19.9805 | 35.1658
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 28.5714 | 1.68 | 11.6553 | 559.4554
[22 empty] | Fuel | Material | LTR | 1.76 | 2.8571 | 0.616 | 116.5532 | 205.1336
[22 empty] | Steel Shoring D>3.0 M | Material | M | 60 | 1 | 60 | 333.0092 | 19980.549
[9 empty] | 333.0092 | 333.0092 |  | 333.0092 | [9 empty] | Pipe Laying & Protection |  | M | 88.3333 |  | 88.3333 | 333.0092 | 29415.8083 | 0 | 0 | 0 | 0 | 0
[22 empty] | UPVC Pipe 200 mm | Material | M | 40 | 1 | 40 | 333.0092 | 13320.366
[22 empty] | UPVC Fitting 200 mm | Material | M | 4 | 1 | 4 | 333.0092 | 1332.0366
[22 empty] | Skilled Labor | Manpower | HR | 17 | 8 | 2.125 | 41.6261 | 707.6444
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 8 | 1.625 | 41.6261 | 541.1399
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 10 | 25 | 33.3009 | 8325.2288
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 10 | 15 | 33.3009 | 4995.1373
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 1.11 | 194.2553
[9 empty] | 333.0092 | 333.0092 |  | 333.0092 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 333.0092 | 1665.0458 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 333.0092 | 1665.0458
SEW 10 |  | Pipes, 200 mm inner diameter, at a maximum depth of 3.5-4.0 m | m | 239.3941 | 432 | 103418.2296 | 172.6113 | 41322.113 | 239.3941 | 239.3941 |  | 239.3941 | 100% | 432 | 103418.2296 | 172.6113 | 41322.113 |  | 41322.113 | [7 empty] | 172.6113 | 239.3941 | 41322.113 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 239.3941 | 239.3941 |  | 239.3941 | [9 empty] | Excavation ( W= 1.0 & d= 4.0 ) |  | M | 79.2779 |  | 79.2779 | 239.3941 | 18978.6684 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 25 | 2.24 | 9.5758 | 536.2427
[22 empty] | Fuel | Material | LTR | 1.76 | 1.7857 | 0.9856 | 134.0607 | 235.9468
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 5.1 | 9.4118 | 46.94 | 2253.1205
[22 empty] | Fuel | Material | LTR | 1.76 | 0.51 | 3.451 | 469.4001 | 826.1442
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 4.7879 | 110.1213
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 14.3636 | 25.28
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 25 | 1.92 | 9.5758 | 459.6366
[22 empty] | Fuel | Material | LTR | 1.76 | 2.5 | 0.704 | 95.7576 | 168.5334
[22 empty] | Steel Shoring D>3.0 M | Material | M | 60 | 1 | 60 | 239.3941 | 14363.643
[9 empty] | 239.3941 | 239.3941 |  | 239.3941 | [9 empty] | Pipe Laying & Protection |  | M | 88.3333 |  | 88.3333 | 239.3941 | 21146.4744 | 0 | 0 | 0 | 0 | 0
[22 empty] | UPVC Pipe 200 mm | Material | M | 40 | 1 | 40 | 239.3941 | 9575.762
[22 empty] | UPVC Fitting 200 mm | Material | M | 4 | 1 | 4 | 239.3941 | 957.5762
[22 empty] | Skilled Labor | Manpower | HR | 17 | 8 | 2.125 | 29.9243 | 508.7124
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 8 | 1.625 | 29.9243 | 389.0153
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 10 | 25 | 23.9394 | 5984.8513
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 10 | 15 | 23.9394 | 3590.9108
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.79798 | 139.6465
[9 empty] | 239.3941 | 239.3941 |  | 239.3941 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 239.3941 | 1196.9703 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 239.3941 | 1196.9703
SEW 10 |  | Pipes, 200 mm inner diameter, at a maximum depth of 4.0-4.5 m | m | 327.9432 | 518 | 169874.5776 | 174.9503 | 57373.7683 | 327.9432 | 327.9432 |  | 327.9432 | 100% | 518 | 169874.5776 | 174.9503 | 57373.7683 |  | 57373.7683 | [7 empty] | 174.9503 | 327.9432 | 57373.7683 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 327.9432 | 327.9432 |  | 327.9432 | [9 empty] | Excavation ( W= 1.0 & d= 4.5 ) |  | M | 81.617 |  | 81.617 | 327.9432 | 26765.7363 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 22.2222 | 2.52 | 14.7574 | 826.4169
[22 empty] | Fuel | Material | LTR | 1.76 | 1.5873 | 1.1088 | 206.6042 | 363.6234
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 4.5333 | 10.5882 | 72.3404 | 3472.3398
[22 empty] | Fuel | Material | LTR | 1.76 | 0.45333 | 3.8824 | 723.4041 | 1273.1912
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 6.5589 | 150.8539
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 19.6766 | 34.6308
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 22.2222 | 2.16 | 14.7574 | 708.3573
[22 empty] | Fuel | Material | LTR | 1.76 | 2.2222 | 0.792 | 147.5744 | 259.731
[22 empty] | Steel Shoring D>3.0 M | Material | M | 60 | 1 | 60 | 327.9432 | 19676.592
[9 empty] | 327.9432 | 327.9432 |  | 327.9432 | [9 empty] | Pipe Laying & Protection |  | M | 88.3333 |  | 88.3333 | 327.9432 | 28968.316 | 0 | 0 | 0 | 0 | 0
[22 empty] | UPVC Pipe 200 mm | Material | M | 40 | 1 | 40 | 327.9432 | 13117.728
[22 empty] | UPVC Fitting 200 mm | Material | M | 4 | 1 | 4 | 327.9432 | 1311.7728
[22 empty] | Skilled Labor | Manpower | HR | 17 | 8 | 2.125 | 40.9929 | 696.8793
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 8 | 1.625 | 40.9929 | 532.9077
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 10 | 25 | 32.7943 | 8198.58
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 10 | 15 | 32.7943 | 4919.148
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 1.0931 | 191.3002
[9 empty] | 327.9432 | 327.9432 |  | 327.9432 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 327.9432 | 1639.716 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 327.9432 | 1639.716
SEW 10 |  | Pipes, 200 mm inner diameter, at a maximum depth of 4.5-5.0 m | m | 120.8171 | 602 | 72731.8942 | 185.7974 | 22447.4988 | 120.8171 | 120.8171 |  | 120.8171 | 100% | 602 | 72731.8942 | 185.7974 | 22447.4988 |  | 22447.4988 | [7 empty] | 185.7974 | 120.8171 | 22447.4988 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 120.8171 | 120.8171 |  | 120.8171 | [9 empty] | Excavation ( W= 1.0 & d= 5.0 ) |  | M | 92.464 |  | 92.464 | 120.8171 | 11171.2361 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 50T | Machinery | HR | 131.2 | 16 | 8.2 | 7.5511 | 990.7002
[22 empty] | Fuel | Material | LTR | 1.76 | 0.5 | 3.52 | 241.6342 | 425.2762
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 4.08 | 11.7647 | 29.612 | 1421.3776
[22 empty] | Fuel | Material | LTR | 1.76 | 0.408 | 4.3137 | 296.1203 | 521.1718
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 2.4163 | 55.5759
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 7.249 | 12.7583
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 16 | 3 | 7.5511 | 362.4513
[22 empty] | Fuel | Material | LTR | 1.76 | 1.6 | 1.1 | 75.5107 | 132.8988
[22 empty] | Steel Shoring D>3.0 M | Material | M | 60 | 1 | 60 | 120.8171 | 7249.026
[9 empty] | 120.8171 | 120.8171 |  | 120.8171 | [9 empty] | Pipe Laying & Protection |  | M | 88.3333 |  | 88.3333 | 120.8171 | 10672.1772 | 0 | 0 | 0 | 0 | 0
[22 empty] | UPVC Pipe 200 mm | Material | M | 40 | 1 | 40 | 120.8171 | 4832.684
[22 empty] | UPVC Fitting 200 mm | Material | M | 4 | 1 | 4 | 120.8171 | 483.2684
[22 empty] | Skilled Labor | Manpower | HR | 17 | 8 | 2.125 | 15.1021 | 256.7363
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 8 | 1.625 | 15.1021 | 196.3278
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 10 | 25 | 12.0817 | 3020.4275
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 10 | 15 | 12.0817 | 1812.2565
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.40272 | 70.4766
[9 empty] | 120.8171 | 120.8171 |  | 120.8171 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 120.8171 | 604.0855 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 120.8171 | 604.0855
SEW 10 |  | Pipes, 200 mm inner diameter, at a maximum depth of 5.0-5.5 m | m | 156.4077 | 631 | 98693.2587 | 188.9872 | 29559.0545 | 156.4077 | 156.4077 |  | 156.4077 | 100% | 631 | 98693.2587 | 188.9872 | 29559.0545 |  | 29559.0545 | [7 empty] | 188.9872 | 156.4077 | 29559.0545 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 156.4077 | 156.4077 |  | 156.4077 | [9 empty] | Excavation ( W= 1.0 & d= 5.5 ) |  | M | 95.6539 |  | 95.6539 | 156.4077 | 14961.0025 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 50T | Machinery | HR | 131.2 | 14.5455 | 9.02 | 10.753 | 1410.7975
[22 empty] | Fuel | Material | LTR | 1.76 | 0.45455 | 3.872 | 344.0969 | 605.6106
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 3.7091 | 12.9412 | 42.1687 | 2024.0996
[22 empty] | Fuel | Material | LTR | 1.76 | 0.37091 | 4.7451 | 421.6874 | 742.1699
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 3.1282 | 71.9475
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 9.3845 | 16.5167
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 14.5455 | 3.3 | 10.753 | 516.1454
[22 empty] | Fuel | Material | LTR | 1.76 | 1.4545 | 1.21 | 107.5303 | 189.2533
[22 empty] | Steel Shoring D>3.0 M | Material | M | 60 | 1 | 60 | 156.4077 | 9384.462
[9 empty] | 156.4077 | 156.4077 |  | 156.4077 | [9 empty] | Pipe Laying & Protection |  | M | 88.3333 |  | 88.3333 | 156.4077 | 13816.0135 | 0 | 0 | 0 | 0 | 0
[22 empty] | UPVC Pipe 200 mm | Material | M | 40 | 1 | 40 | 156.4077 | 6256.308
[22 empty] | UPVC Fitting 200 mm | Material | M | 4 | 1 | 4 | 156.4077 | 625.6308
[22 empty] | Skilled Labor | Manpower | HR | 17 | 8 | 2.125 | 19.551 | 332.3664
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 8 | 1.625 | 19.551 | 254.1625
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 10 | 25 | 15.6408 | 3910.1925
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 10 | 15 | 15.6408 | 2346.1155
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.52136 | 91.2378
[9 empty] | 156.4077 | 156.4077 |  | 156.4077 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 156.4077 | 782.0385 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 156.4077 | 782.0385
SEW 10 |  | Pipes, 200 mm inner diameter, at a maximum depth of 5.5-6.0 m | m | 25.5378 | 659 | 16829.4431 | 192.1771 | 4907.7887 | 25.5378 | 25.5378 |  | 25.5378 | 100% | 659 | 16829.4431 | 192.1771 | 4907.7887 |  | 4907.7887 | [7 empty] | 192.1771 | 25.5378 | 4907.7887 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 25.5378 | 25.5378 |  | 25.5378 | [9 empty] | Excavation ( W= 1.0 & d= 6.0 ) |  | M | 98.8437 |  | 98.8437 | 25.5378 | 2524.256 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 50T | Machinery | HR | 131.2 | 13.3333 | 9.84 | 1.9153 | 251.2924
[22 empty] | Fuel | Material | LTR | 1.76 | 0.41667 | 4.224 | 61.2908 | 107.8719
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 3.4 | 14.1176 | 7.5111 | 360.5344
[22 empty] | Fuel | Material | LTR | 1.76 | 0.34 | 5.1765 | 75.1113 | 132.1959
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 0.51076 | 11.7474
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 1.5323 | 2.6968
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 13.3333 | 3.6 | 1.9153 | 91.9363
[22 empty] | Fuel | Material | LTR | 1.76 | 1.3333 | 1.32 | 19.1534 | 33.71
[22 empty] | Steel Shoring D>3.0 M | Material | M | 60 | 1 | 60 | 25.5378 | 1532.271
[9 empty] | 25.5378 | 25.5378 |  | 25.5378 | [9 empty] | Pipe Laying & Protection |  | M | 88.3333 |  | 88.3333 | 25.5378 | 2255.8434 | 0 | 0 | 0 | 0 | 0
[22 empty] | UPVC Pipe 200 mm | Material | M | 40 | 1 | 40 | 25.5378 | 1021.514
[22 empty] | UPVC Fitting 200 mm | Material | M | 4 | 1 | 4 | 25.5378 | 102.1514
[22 empty] | Skilled Labor | Manpower | HR | 17 | 8 | 2.125 | 3.1922 | 54.2679
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 8 | 1.625 | 3.1922 | 41.499
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 10 | 25 | 2.5538 | 638.4462
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 10 | 15 | 2.5538 | 383.0677
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.085126 | 14.8971
[9 empty] | 25.5378 | 25.5378 |  | 25.5378 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 25.5378 | 127.6892 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 25.5378 | 127.6892
SEW 10 |  | Depth variation increase of 0.5 m for 200 mm internal diameter pipes | m | 1.4825 | 195 | 289.0875 | 3.7554 | 5.5674 | 1.4825 | 1.4825 |  | 1.4825 | 100% | 195 | 289.0875 | 3.7554 | 5.5674 |  | 5.5674 | [7 empty] | 3.7554 | 1.4825 | 5.5674 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 1.4825 | 1.4825 |  | 1.4825 | [9 empty] | Excavation ( W= 1.0 & d= 0.5 ) |  | M | 3.7554 |  | 3.7554 | 1.4825 | 5.5674 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 50T | Machinery | HR | 131.2 | 160 | 0.82 | 0.0092656 | 1.2156
[22 empty] | Fuel | Material | LTR | 1.76 | 5 | 0.352 | 0.2965 | 0.52184
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 40.8 | 1.1765 | 0.036336 | 1.7441
[22 empty] | Fuel | Material | LTR | 1.76 | 4.08 | 0.43137 | 0.36336 | 0.63951
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 0.02965 | 0.68195
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 0.08895 | 0.15655
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 160 | 0.3 | 0.0092656 | 0.44475
[22 empty] | Fuel | Material | LTR | 1.76 | 16 | 0.11 | 0.092656 | 0.16307
SEW 10 |  | Depth variation increase of 1.0 m for 200 mm internal diameter pipes | m |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | Depth variation increase of 1.5 m for 200 mm internal diameter pipes | m |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | Depth variation increase of 2.0 m for 200 mm internal diameter pipes | m |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | Depth variation increase of 2.5 m for 200 mm internal diameter pipes | m |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | Depth variation increase of 3.0 m for 200 mm internal diameter pipes | m |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | Depth variation increase of 3.5 m for 200 mm internal diameter pipes | m |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | Depth variation increase of 4.0 m for 200 mm internal diameter pipes | m |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | Depth variation increase of 4.5 m for 200 mm internal diameter pipes | m |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | Depth variation increase of 5.0 m for 200 mm internal diameter pipes | m |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | Pipes, 250 mm inner diameter, at a maximum depth of 2.0-2.5 m | m | 11.82 | 280 | 3309.6 | 154.8441 | 1830.2578 | 11.82 | 11.82 |  | 11.82 | 100% | 280 | 3309.6 | 154.8441 | 1830.2578 |  | 1830.2578 | [7 empty] | 154.8441 | 11.82 | 1830.2578 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 11.82 | 11.82 |  | 11.82 | [9 empty] | Excavation ( W= 1.0 & d= 2.5 ) |  | M | 47.2608 |  | 47.2608 | 11.82 | 558.6228 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 40 | 1.4 | 0.2955 | 16.548
[22 empty] | Fuel | Material | LTR | 1.76 | 2.8571 | 0.616 | 4.137 | 7.2811
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 8.16 | 5.8824 | 1.4485 | 69.5294
[22 empty] | Fuel | Material | LTR | 1.76 | 0.816 | 2.1569 | 14.4853 | 25.4941
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 0.2364 | 5.4372
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 0.7092 | 1.2482
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 40 | 1.2 | 0.2955 | 14.184
[22 empty] | Fuel | Material | LTR | 1.76 | 4 | 0.44 | 2.955 | 5.2008
[22 empty] | Steel Shoring D=2.5 M | Material | M | 35 | 1 | 35 | 11.82 | 413.7
[9 empty] | 11.82 | 11.82 |  | 11.82 | [9 empty] | Pipe Laying & Protection |  | M | 102.5833 |  | 102.5833 | 11.82 | 1212.535 | 0 | 0 | 0 | 0 | 0
[22 empty] | UPVC Pipe 250 mm | Material | M | 52 | 1 | 52 | 11.82 | 614.64
[22 empty] | UPVC Fitting 250 mm | Material | M | 5 | 1 | 5 | 11.82 | 59.1
[22 empty] | Skilled Labor | Manpower | HR | 17 | 6 | 2.8333 | 1.97 | 33.49
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 6 | 2.1667 | 1.97 | 25.61
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 10 | 25 | 1.182 | 295.5
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 10 | 15 | 1.182 | 177.3
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.0394 | 6.895
[9 empty] | 11.82 | 11.82 |  | 11.82 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 11.82 | 59.1 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 11.82 | 59.1
SEW 10 |  | Pipes, 250 mm inner diameter, at a maximum depth of 2.5-3.0 m | m | 2.94 | 345 | 1014.3 | 182.1832 | 535.6186 | 2.94 | 2.94 |  | 2.94 | 100% | 345 | 1014.3 | 182.1832 | 535.6186 |  | 535.6186 | [7 empty] | 182.1832 | 2.94 | 535.6186 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 2.94 | 2.94 |  | 2.94 | [9 empty] | Excavation ( W= 1.0 & d= 3.0 ) |  | M | 74.5999 |  | 74.5999 | 2.94 | 219.3236 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 33.3333 | 1.68 | 0.0882 | 4.9392
[22 empty] | Fuel | Material | LTR | 1.76 | 2.381 | 0.7392 | 1.2348 | 2.1732
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 6.8 | 7.0588 | 0.43235 | 20.7529
[22 empty] | Fuel | Material | LTR | 1.76 | 0.68 | 2.5882 | 4.3235 | 7.6094
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 0.0588 | 1.3524
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 0.1764 | 0.31046
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 33.3333 | 1.44 | 0.0882 | 4.2336
[22 empty] | Fuel | Material | LTR | 1.76 | 3.3333 | 0.528 | 0.882 | 1.5523
[22 empty] | Steel Shoring D>3.0 M | Material | M | 60 | 1 | 60 | 2.94 | 176.4
[9 empty] | 2.94 | 2.94 |  | 2.94 | [9 empty] | Pipe Laying & Protection |  | M | 102.5833 |  | 102.5833 | 2.94 | 301.595 | 0 | 0 | 0 | 0 | 0
[22 empty] | UPVC Pipe 250 mm | Material | M | 52 | 1 | 52 | 2.94 | 152.88
[22 empty] | UPVC Fitting 250 mm | Material | M | 5 | 1 | 5 | 2.94 | 14.7
[22 empty] | Skilled Labor | Manpower | HR | 17 | 6 | 2.8333 | 0.49 | 8.33
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 6 | 2.1667 | 0.49 | 6.37
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 10 | 25 | 0.294 | 73.5
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 10 | 15 | 0.294 | 44.1
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.0098 | 1.715
[9 empty] | 2.94 | 2.94 |  | 2.94 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 2.94 | 14.7 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 2.94 | 14.7
SEW 10 |  | Pipes, 250 mm inner diameter, at a maximum depth of 3.0-3.5 m | m | 65.2018 | 392 | 25559.1056 | 184.5222 | 12031.1819 | 65.2018 | 65.2018 |  | 65.2018 | 100% | 392 | 25559.1056 | 184.5222 | 12031.1819 |  | 12031.1819 | [7 empty] | 184.5222 | 65.2018 | 12031.1819 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 65.2018 | 65.2018 |  | 65.2018 | [9 empty] | Excavation ( W= 1.0 & d= 3.5 ) |  | M | 76.9389 |  | 76.9389 | 65.2018 | 5016.5549 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 28.5714 | 1.96 | 2.2821 | 127.7955
[22 empty] | Fuel | Material | LTR | 1.76 | 2.0408 | 0.8624 | 31.9489 | 56.23
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 5.8286 | 8.2353 | 11.1866 | 536.956
[22 empty] | Fuel | Material | LTR | 1.76 | 0.58286 | 3.0196 | 111.8658 | 196.8839
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 1.304 | 29.9928
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 3.9121 | 6.8853
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 28.5714 | 1.68 | 2.2821 | 109.539
[22 empty] | Fuel | Material | LTR | 1.76 | 2.8571 | 0.616 | 22.8206 | 40.1643
[22 empty] | Steel Shoring D>3.0 M | Material | M | 60 | 1 | 60 | 65.2018 | 3912.108
[9 empty] | 65.2018 | 65.2018 |  | 65.2018 | [9 empty] | Pipe Laying & Protection |  | M | 102.5833 |  | 102.5833 | 65.2018 | 6688.618 | 0 | 0 | 0 | 0 | 0
[22 empty] | UPVC Pipe 250 mm | Material | M | 52 | 1 | 52 | 65.2018 | 3390.4936
[22 empty] | UPVC Fitting 250 mm | Material | M | 5 | 1 | 5 | 65.2018 | 326.009
[22 empty] | Skilled Labor | Manpower | HR | 17 | 6 | 2.8333 | 10.867 | 184.7384
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 6 | 2.1667 | 10.867 | 141.2706
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 10 | 25 | 6.5202 | 1630.045
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 10 | 15 | 6.5202 | 978.027
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.21734 | 38.0344
[9 empty] | 65.2018 | 65.2018 |  | 65.2018 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 65.2018 | 326.009 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 65.2018 | 326.009
SEW 10 |  | Pipes, 250 mm inner diameter, at a maximum depth of 3.5-4.0 m | m | 65.8101 | 541 | 35603.2641 | 186.8613 | 12297.3594 | 65.8101 | 65.8101 |  | 65.8101 | 100% | 541 | 35603.2641 | 186.8613 | 12297.3594 |  | 12297.3594 | [7 empty] | 186.8613 | 65.8101 | 12297.3594 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 65.8101 | 65.8101 |  | 65.8101 | [9 empty] | Excavation ( W= 1.0 & d= 4.0 ) |  | M | 79.2779 |  | 79.2779 | 65.8101 | 5217.2895 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 25 | 2.24 | 2.6324 | 147.4146
[22 empty] | Fuel | Material | LTR | 1.76 | 1.7857 | 0.9856 | 36.8537 | 64.8624
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 5.1 | 9.4118 | 12.9039 | 619.3892
[22 empty] | Fuel | Material | LTR | 1.76 | 0.51 | 3.451 | 129.0394 | 227.1094
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 1.3162 | 30.2726
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 3.9486 | 6.9495
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 25 | 1.92 | 2.6324 | 126.3554
[22 empty] | Fuel | Material | LTR | 1.76 | 2.5 | 0.704 | 26.324 | 46.3303
[22 empty] | Steel Shoring D>3.0 M | Material | M | 60 | 1 | 60 | 65.8101 | 3948.606
[9 empty] | 65.8101 | 65.8101 |  | 65.8101 | [9 empty] | Pipe Laying & Protection |  | M | 102.5833 |  | 102.5833 | 65.8101 | 6751.0194 | 0 | 0 | 0 | 0 | 0
[22 empty] | UPVC Pipe 250 mm | Material | M | 52 | 1 | 52 | 65.8101 | 3422.1252
[22 empty] | UPVC Fitting 250 mm | Material | M | 5 | 1 | 5 | 65.8101 | 329.0505
[22 empty] | Skilled Labor | Manpower | HR | 17 | 6 | 2.8333 | 10.9683 | 186.4619
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 6 | 2.1667 | 10.9683 | 142.5885
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 10 | 25 | 6.581 | 1645.2525
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 10 | 15 | 6.581 | 987.1515
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.21937 | 38.3892
[9 empty] | 65.8101 | 65.8101 |  | 65.8101 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 65.8101 | 329.0505 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 65.8101 | 329.0505
SEW 10 |  | Pipes, 250 mm inner diameter, at a maximum depth of 4.0-4.5 m | m | 78.5005 | 563 | 44195.8096 | 189.2003 | 14852.3293 | 78.5005 | 78.5005 |  | 78.5005 | 100% | 563 | 44195.8096 | 189.2003 | 14852.3293 |  | 14852.3293 | [7 empty] | 189.2003 | 78.5005 | 14852.3293 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 78.5005 | 78.5005 |  | 78.5005 | [9 empty] | Excavation ( W= 1.0 & d= 4.5 ) |  | M | 81.617 |  | 81.617 | 78.5005 | 6406.9785 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 22.2222 | 2.52 | 3.5325 | 197.8214
[22 empty] | Fuel | Material | LTR | 1.76 | 1.5873 | 1.1088 | 49.4553 | 87.0414
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 4.5333 | 10.5882 | 17.3163 | 831.1823
[22 empty] | Fuel | Material | LTR | 1.76 | 0.45333 | 3.8824 | 173.163 | 304.7668
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 1.57 | 36.1103
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 4.71 | 8.2897
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 22.2222 | 2.16 | 3.5325 | 169.5612
[22 empty] | Fuel | Material | LTR | 1.76 | 2.2222 | 0.792 | 35.3252 | 62.1724
[22 empty] | Steel Shoring D>3.0 M | Material | M | 60 | 1 | 60 | 78.5005 | 4710.033
[9 empty] | 78.5005 | 78.5005 |  | 78.5005 | [9 empty] | Pipe Laying & Protection |  | M | 102.5833 |  | 102.5833 | 78.5005 | 8052.8481 | 0 | 0 | 0 | 0 | 0
[22 empty] | UPVC Pipe 250 mm | Material | M | 52 | 1 | 52 | 78.5005 | 4082.0286
[22 empty] | UPVC Fitting 250 mm | Material | M | 5 | 1 | 5 | 78.5005 | 392.5027
[22 empty] | Skilled Labor | Manpower | HR | 17 | 6 | 2.8333 | 13.0834 | 222.4182
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 6 | 2.1667 | 13.0834 | 170.0845
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 10 | 25 | 7.8501 | 1962.5137
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 10 | 15 | 7.8501 | 1177.5082
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.26167 | 45.792
[9 empty] | 78.5005 | 78.5005 |  | 78.5005 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 78.5005 | 392.5027 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 78.5005 | 392.5027
SEW 10 |  | Pipes, 250 mm inner diameter, at a maximum depth of 4.5-5.0 m | m | 181.1337 | 588 | 106506.645 | 200.0474 | 36235.3293 | 181.1337 | 181.1337 |  | 181.1337 | 100% | 588 | 106506.645 | 200.0474 | 36235.3293 |  | 36235.3293 | [7 empty] | 200.0474 | 181.1337 | 36235.3293 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 181.1337 | 181.1337 |  | 181.1337 | [9 empty] | Excavation ( W= 1.0 & d= 5.0 ) |  | M | 92.464 |  | 92.464 | 181.1337 | 16748.3567 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 50T | Machinery | HR | 131.2 | 16 | 8.2 | 11.3209 | 1485.2967
[22 empty] | Fuel | Material | LTR | 1.76 | 0.5 | 3.52 | 362.2675 | 637.5908
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 4.08 | 11.7647 | 44.3955 | 2130.9853
[22 empty] | Fuel | Material | LTR | 1.76 | 0.408 | 4.3137 | 443.9553 | 781.3613
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 3.6227 | 83.3215
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 10.868 | 19.1277
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 16 | 3 | 11.3209 | 543.4012
[22 empty] | Fuel | Material | LTR | 1.76 | 1.6 | 1.1 | 113.2086 | 199.2471
[22 empty] | Steel Shoring D>3.0 M | Material | M | 60 | 1 | 60 | 181.1337 | 10868.025
[9 empty] | 181.1337 | 181.1337 |  | 181.1337 | [9 empty] | Pipe Laying & Protection |  | M | 102.5833 |  | 102.5833 | 181.1337 | 18581.3039 | 0 | 0 | 0 | 0 | 0
[22 empty] | UPVC Pipe 250 mm | Material | M | 52 | 1 | 52 | 181.1337 | 9418.955
[22 empty] | UPVC Fitting 250 mm | Material | M | 5 | 1 | 5 | 181.1337 | 905.6687
[22 empty] | Skilled Labor | Manpower | HR | 17 | 6 | 2.8333 | 30.189 | 513.2123
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 6 | 2.1667 | 30.189 | 392.4565
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 10 | 25 | 18.1134 | 4528.3437
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 10 | 15 | 18.1134 | 2717.0062
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.60378 | 105.6614
[9 empty] | 181.1337 | 181.1337 |  | 181.1337 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 181.1337 | 905.6687 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 181.1337 | 905.6687
SEW 10 |  | Pipes, 250 mm inner diameter, at a maximum depth of 5.0-5.5 m | m | 19.5774 | 622 | 12177.1739 | 203.2372 | 3978.8663 | 19.5774 | 19.5774 |  | 19.5774 | 100% | 622 | 12177.1739 | 203.2372 | 3978.8663 |  | 3978.8663 | [7 empty] | 203.2372 | 19.5774 | 3978.8663 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 19.5774 | 19.5774 |  | 19.5774 | [9 empty] | Excavation ( W= 1.0 & d= 5.5 ) |  | M | 95.6539 |  | 95.6539 | 19.5774 | 1872.6589 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 50T | Machinery | HR | 131.2 | 14.5455 | 9.02 | 1.3459 | 176.5886
[22 empty] | Fuel | Material | LTR | 1.76 | 0.45455 | 3.872 | 43.0704 | 75.8039
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 3.7091 | 12.9412 | 5.2782 | 253.3552
[22 empty] | Fuel | Material | LTR | 1.76 | 0.37091 | 4.7451 | 52.7823 | 92.8969
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 0.39155 | 9.0056
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 1.1746 | 2.0674
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 14.5455 | 3.3 | 1.3459 | 64.6056
[22 empty] | Fuel | Material | LTR | 1.76 | 1.4545 | 1.21 | 13.4595 | 23.6887
[22 empty] | Steel Shoring D>3.0 M | Material | M | 60 | 1 | 60 | 19.5774 | 1174.647
[9 empty] | 19.5774 | 19.5774 |  | 19.5774 | [9 empty] | Pipe Laying & Protection |  | M | 102.5833 |  | 102.5833 | 19.5774 | 2008.3201 | 0 | 0 | 0 | 0 | 0
[22 empty] | UPVC Pipe 250 mm | Material | M | 52 | 1 | 52 | 19.5774 | 1018.0274
[22 empty] | UPVC Fitting 250 mm | Material | M | 5 | 1 | 5 | 19.5774 | 97.8872
[22 empty] | Skilled Labor | Manpower | HR | 17 | 6 | 2.8333 | 3.2629 | 55.4694
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 6 | 2.1667 | 3.2629 | 42.4178
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 10 | 25 | 1.9577 | 489.4362
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 10 | 15 | 1.9577 | 293.6617
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.065258 | 11.4202
[9 empty] | 19.5774 | 19.5774 |  | 19.5774 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 19.5774 | 97.8872 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 19.5774 | 97.8872
SEW 10 |  | Pipes, 250 mm inner diameter, at a maximum depth of 5.5-6.0 m | m | 43.34 | 657 | 28474.38 | 206.4271 | 8946.5484 | 43.34 | 43.34 |  | 43.34 | 100% | 657 | 28474.38 | 206.4271 | 8946.5484 |  | 8946.5484 | [7 empty] | 206.4271 | 43.34 | 8946.5484 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 43.34 | 43.34 |  | 43.34 | [9 empty] | Excavation ( W= 1.0 & d= 6.0 ) |  | M | 98.8437 |  | 98.8437 | 43.34 | 4283.8867 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 50T | Machinery | HR | 131.2 | 13.3333 | 9.84 | 3.2505 | 426.4656
[22 empty] | Fuel | Material | LTR | 1.76 | 0.41667 | 4.224 | 104.016 | 183.0682
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 3.4 | 14.1176 | 12.7471 | 611.8588
[22 empty] | Fuel | Material | LTR | 1.76 | 0.34 | 5.1765 | 127.4706 | 224.3482
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 0.8668 | 19.9364
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 2.6004 | 4.5767
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 13.3333 | 3.6 | 3.2505 | 156.024
[22 empty] | Fuel | Material | LTR | 1.76 | 1.3333 | 1.32 | 32.505 | 57.2088
[22 empty] | Steel Shoring D>3.0 M | Material | M | 60 | 1 | 60 | 43.34 | 2600.4
[9 empty] | 43.34 | 43.34 |  | 43.34 | [9 empty] | Pipe Laying & Protection |  | M | 102.5833 |  | 102.5833 | 43.34 | 4445.9617 | 0 | 0 | 0 | 0 | 0
[22 empty] | UPVC Pipe 250 mm | Material | M | 52 | 1 | 52 | 43.34 | 2253.68
[22 empty] | UPVC Fitting 250 mm | Material | M | 5 | 1 | 5 | 43.34 | 216.7
[22 empty] | Skilled Labor | Manpower | HR | 17 | 6 | 2.8333 | 7.2233 | 122.7967
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 6 | 2.1667 | 7.2233 | 93.9033
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 10 | 25 | 4.334 | 1083.5
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 10 | 15 | 4.334 | 650.1
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.14447 | 25.2817
[9 empty] | 43.34 | 43.34 |  | 43.34 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 43.34 | 216.7 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 43.34 | 216.7
SEW 10 |  | Pipes, 250 mm inner diameter, at a maximum depth of 6.0-6.5 m | m | 59.7548 | 701 | 41888.0798 | 209.6169 | 12525.6051 | 59.7548 | 59.7548 |  | 59.7548 | 100% | 701 | 41888.0798 | 209.6169 | 12525.6051 |  | 12525.6051 | [7 empty] | 209.6169 | 59.7548 | 12525.6051 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 59.7548 | 59.7548 |  | 59.7548 | [9 empty] | Excavation ( W= 1.0 & d= 6.5 ) |  | M | 102.0336 |  | 102.0336 | 59.7548 | 6096.9899 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 50T | Machinery | HR | 131.2 | 12.3077 | 10.66 | 4.8551 | 636.9856
[22 empty] | Fuel | Material | LTR | 1.76 | 0.38462 | 4.576 | 155.3624 | 273.4377
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 3.1385 | 15.2941 | 19.0395 | 913.8962
[22 empty] | Fuel | Material | LTR | 1.76 | 0.31385 | 5.6078 | 190.395 | 335.0953
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 1.1951 | 27.4872
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 3.5853 | 6.3101
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 12.3077 | 3.9 | 4.8551 | 233.0435
[22 empty] | Fuel | Material | LTR | 1.76 | 1.2308 | 1.43 | 48.5507 | 85.4493
[22 empty] | Steel Shoring D>3.0 M | Material | M | 60 | 1 | 60 | 59.7548 | 3585.285
[9 empty] | 59.7548 | 59.7548 |  | 59.7548 | [9 empty] | Pipe Laying & Protection |  | M | 102.5833 |  | 102.5833 | 59.7548 | 6129.8414 | 0 | 0 | 0 | 0 | 0
[22 empty] | UPVC Pipe 250 mm | Material | M | 52 | 1 | 52 | 59.7548 | 3107.247
[22 empty] | UPVC Fitting 250 mm | Material | M | 5 | 1 | 5 | 59.7548 | 298.7738
[22 empty] | Skilled Labor | Manpower | HR | 17 | 6 | 2.8333 | 9.9591 | 169.3051
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 6 | 2.1667 | 9.9591 | 129.4686
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 10 | 25 | 5.9755 | 1493.8688
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 10 | 15 | 5.9755 | 896.3213
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.19918 | 34.8569
[9 empty] | 59.7548 | 59.7548 |  | 59.7548 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 59.7548 | 298.7738 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 59.7548 | 298.7738
SEW 10 |  | Pipes, 250 mm inner diameter, at a maximum depth of 6.5-7.0 m | m | 2.4876 | 821 | 2042.3196 | 212.8067 | 529.378 | 2.4876 | 2.4876 |  | 2.4876 | 100% | 821 | 2042.3196 | 212.8067 | 529.378 |  | 529.378 | [7 empty] | 212.8067 | 2.4876 | 529.378 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 2.4876 | 2.4876 |  | 2.4876 | [9 empty] | Excavation ( W= 1.0 & d= 7.0 ) |  | M | 105.2234 |  | 105.2234 | 2.4876 | 261.7537 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 50T | Machinery | HR | 131.2 | 11.4286 | 11.48 | 0.21766 | 28.5576
[22 empty] | Fuel | Material | LTR | 1.76 | 0.35714 | 4.928 | 6.9653 | 12.2589
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 2.9143 | 16.4706 | 0.85359 | 40.9722
[22 empty] | Fuel | Material | LTR | 1.76 | 0.29143 | 6.0392 | 8.5359 | 15.0232
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 0.049752 | 1.1443
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 0.14926 | 0.26269
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 11.4286 | 4.2 | 0.21766 | 10.4479
[22 empty] | Fuel | Material | LTR | 1.76 | 1.1429 | 1.54 | 2.1766 | 3.8309
[22 empty] | Steel Shoring D>3.0 M | Material | M | 60 | 1 | 60 | 2.4876 | 149.256
[9 empty] | 2.4876 | 2.4876 |  | 2.4876 | [9 empty] | Pipe Laying & Protection |  | M | 102.5833 |  | 102.5833 | 2.4876 | 255.1863 | 0 | 0 | 0 | 0 | 0
[22 empty] | UPVC Pipe 250 mm | Material | M | 52 | 1 | 52 | 2.4876 | 129.3552
[22 empty] | UPVC Fitting 250 mm | Material | M | 5 | 1 | 5 | 2.4876 | 12.438
[22 empty] | Skilled Labor | Manpower | HR | 17 | 6 | 2.8333 | 0.4146 | 7.0482
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 6 | 2.1667 | 0.4146 | 5.3898
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 10 | 25 | 0.24876 | 62.19
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 10 | 15 | 0.24876 | 37.314
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.008292 | 1.4511
[9 empty] | 2.4876 | 2.4876 |  | 2.4876 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 2.4876 | 12.438 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 2.4876 | 12.438
SEW 10 |  | Pipes, 315 mm inner diameter, at a maximum depth of 2.0-2.5 m | m | 3.925 | 320 | 1256 | 202.8441 | 796.1633 | 3.925 | 3.925 |  | 3.925 | 100% | 320 | 1256 | 202.8441 | 796.1633 |  | 796.1633 | [7 empty] | 202.8441 | 3.925 | 796.1633 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 3.925 | 3.925 |  | 3.925 | [9 empty] | Excavation ( W= 1.0 & d= 2.5 ) |  | M | 47.2608 |  | 47.2608 | 3.925 | 185.4987 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 40 | 1.4 | 0.098125 | 5.495
[22 empty] | Fuel | Material | LTR | 1.76 | 2.8571 | 0.616 | 1.3737 | 2.4178
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 8.16 | 5.8824 | 0.481 | 23.0882
[22 empty] | Fuel | Material | LTR | 1.76 | 0.816 | 2.1569 | 4.81 | 8.4657
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 0.0785 | 1.8055
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 0.2355 | 0.41448
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 40 | 1.2 | 0.098125 | 4.71
[22 empty] | Fuel | Material | LTR | 1.76 | 4 | 0.44 | 0.98125 | 1.727
[22 empty] | Steel Shoring D=2.5 M | Material | M | 35 | 1 | 35 | 3.925 | 137.375
[9 empty] | 3.925 | 3.925 |  | 3.925 | [9 empty] | Pipe Laying & Protection |  | M | 150.5833 |  | 150.5833 | 3.925 | 591.0396 | 0 | 0 | 0 | 0 | 0
[22 empty] | UPVC Pipe 315 mm | Material | M | 95 | 1 | 95 | 3.925 | 372.875
[22 empty] | UPVC Fitting 315 mm | Material | M | 10 | 1 | 10 | 3.925 | 39.25
[22 empty] | Skilled Labor | Manpower | HR | 17 | 6 | 2.8333 | 0.65417 | 11.1208
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 6 | 2.1667 | 0.65417 | 8.5042
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 10 | 25 | 0.3925 | 98.125
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 10 | 15 | 0.3925 | 58.875
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.013083 | 2.2896
[9 empty] | 3.925 | 3.925 |  | 3.925 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 3.925 | 19.625 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 3.925 | 19.625
SEW 10 |  | Pipes, 315 mm inner diameter, at a maximum depth of 2.5-3.0 m | m | 3.5971 | 466 | 1676.2719 | 230.1832 | 828.0035 | 3.5971 | 3.5971 |  | 3.5971 | 100% | 466 | 1676.2719 | 230.1832 | 828.0035 |  | 828.0035 | [7 empty] | 230.1832 | 3.5971 | 828.0035 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 3.5971 | 3.5971 |  | 3.5971 | [9 empty] | Excavation ( W= 1.0 & d= 3.0 ) |  | M | 74.5999 |  | 74.5999 | 3.5971 | 268.3469 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 33.3333 | 1.68 | 0.10791 | 6.0432
[22 empty] | Fuel | Material | LTR | 1.76 | 2.381 | 0.7392 | 1.5108 | 2.659
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 6.8 | 7.0588 | 0.52899 | 25.3916
[22 empty] | Fuel | Material | LTR | 1.76 | 0.68 | 2.5882 | 5.2899 | 9.3103
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 0.071943 | 1.6547
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 0.21583 | 0.37986
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 33.3333 | 1.44 | 0.10791 | 5.1799
[22 empty] | Fuel | Material | LTR | 1.76 | 3.3333 | 0.528 | 1.0791 | 1.8993
[22 empty] | Steel Shoring D>3.0 M | Material | M | 60 | 1 | 60 | 3.5971 | 215.829
[9 empty] | 3.5971 | 3.5971 |  | 3.5971 | [9 empty] | Pipe Laying & Protection |  | M | 150.5833 |  | 150.5833 | 3.5971 | 541.6708 | 0 | 0 | 0 | 0 | 0
[22 empty] | UPVC Pipe 315 mm | Material | M | 95 | 1 | 95 | 3.5971 | 341.7292
[22 empty] | UPVC Fitting 315 mm | Material | M | 10 | 1 | 10 | 3.5971 | 35.9715
[22 empty] | Skilled Labor | Manpower | HR | 17 | 6 | 2.8333 | 0.59952 | 10.1919
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 6 | 2.1667 | 0.59952 | 7.7938
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 10 | 25 | 0.35971 | 89.9287
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 10 | 15 | 0.35971 | 53.9572
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.01199 | 2.0983
[9 empty] | 3.5971 | 3.5971 |  | 3.5971 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 3.5971 | 17.9857 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 3.5971 | 17.9857
SEW 10 |  | Pipes, 315 mm inner diameter, at a maximum depth of 3.0-3.5 m | m | 49.2812 | 487 | 23999.9444 | 232.5222 | 11458.9748 | 49.2812 | 49.2812 |  | 49.2812 | 100% | 487 | 23999.9444 | 232.5222 | 11458.9748 |  | 11458.9748 | [7 empty] | 232.5222 | 49.2812 | 11458.9748 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 49.2812 | 49.2812 |  | 49.2812 | [9 empty] | Excavation ( W= 1.0 & d= 3.5 ) |  | M | 76.9389 |  | 76.9389 | 49.2812 | 3791.6414 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 28.5714 | 1.96 | 1.7248 | 96.5912
[22 empty] | Fuel | Material | LTR | 1.76 | 2.0408 | 0.8624 | 24.1478 | 42.5001
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 5.8286 | 8.2353 | 8.4551 | 405.8452
[22 empty] | Fuel | Material | LTR | 1.76 | 0.58286 | 3.0196 | 84.5511 | 148.8099
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 0.98562 | 22.6694
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 2.9569 | 5.2041
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 28.5714 | 1.68 | 1.7248 | 82.7924
[22 empty] | Fuel | Material | LTR | 1.76 | 2.8571 | 0.616 | 17.2484 | 30.3572
[22 empty] | Steel Shoring D>3.0 M | Material | M | 60 | 1 | 60 | 49.2812 | 2956.872
[9 empty] | 49.2812 | 49.2812 |  | 49.2812 | [9 empty] | Pipe Laying & Protection |  | M | 150.5833 |  | 150.5833 | 49.2812 | 7420.9274 | 0 | 0 | 0 | 0 | 0
[22 empty] | UPVC Pipe 315 mm | Material | M | 95 | 1 | 95 | 49.2812 | 4681.714
[22 empty] | UPVC Fitting 315 mm | Material | M | 10 | 1 | 10 | 49.2812 | 492.812
[22 empty] | Skilled Labor | Manpower | HR | 17 | 6 | 2.8333 | 8.2135 | 139.6301
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 6 | 2.1667 | 8.2135 | 106.7759
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 10 | 25 | 4.9281 | 1232.03
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 10 | 15 | 4.9281 | 739.218
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.16427 | 28.7474
[9 empty] | 49.2812 | 49.2812 |  | 49.2812 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 49.2812 | 246.406 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 49.2812 | 246.406
SEW 10 |  | Pipes, 315 mm inner diameter, at a maximum depth of 3.5-4.0 m | m | 22.5498 | 635 | 14319.1547 | 234.8613 | 5296.0866 | 22.5498 | 22.5498 |  | 22.5498 | 100% | 635 | 14319.1547 | 234.8613 | 5296.0866 |  | 5296.0866 | [7 empty] | 234.8613 | 22.5498 | 5296.0866 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 22.5498 | 22.5498 |  | 22.5498 | [9 empty] | Excavation ( W= 1.0 & d= 4.0 ) |  | M | 79.2779 |  | 79.2779 | 22.5498 | 1787.7058 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 25 | 2.24 | 0.90199 | 50.5117
[22 empty] | Fuel | Material | LTR | 1.76 | 1.7857 | 0.9856 | 12.6279 | 22.2251
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 5.1 | 9.4118 | 4.4215 | 212.2339
[22 empty] | Fuel | Material | LTR | 1.76 | 0.51 | 3.451 | 44.2154 | 77.8191
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 0.451 | 10.3729
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 1.353 | 2.3813
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 25 | 1.92 | 0.90199 | 43.2957
[22 empty] | Fuel | Material | LTR | 1.76 | 2.5 | 0.704 | 9.0199 | 15.8751
[22 empty] | Steel Shoring D>3.0 M | Material | M | 60 | 1 | 60 | 22.5498 | 1352.991
[9 empty] | 22.5498 | 22.5498 |  | 22.5498 | [9 empty] | Pipe Laying & Protection |  | M | 150.5833 |  | 150.5833 | 22.5498 | 3395.6316 | 0 | 0 | 0 | 0 | 0
[22 empty] | UPVC Pipe 315 mm | Material | M | 95 | 1 | 95 | 22.5498 | 2142.2357
[22 empty] | UPVC Fitting 315 mm | Material | M | 10 | 1 | 10 | 22.5498 | 225.4985
[22 empty] | Skilled Labor | Manpower | HR | 17 | 6 | 2.8333 | 3.7583 | 63.8912
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 6 | 2.1667 | 3.7583 | 48.858
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 10 | 25 | 2.255 | 563.7462
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 10 | 15 | 2.255 | 338.2477
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.075166 | 13.1541
[9 empty] | 22.5498 | 22.5498 |  | 22.5498 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 22.5498 | 112.7492 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 22.5498 | 112.7492
SEW 10 |  | Pipes, 315 mm inner diameter, at a maximum depth of 4.0-4.5 m | m |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | Pipes, 315 mm inner diameter, at a maximum depth of 4.5-5.0 m | m | 55.7026 | 698 | 38880.4148 | 248.0474 | 13816.8831 | 55.7026 | 55.7026 |  | 55.7026 | 100% | 698 | 38880.4148 | 248.0474 | 13816.8831 |  | 13816.8831 | [7 empty] | 248.0474 | 55.7026 | 13816.8831 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 55.7026 | 55.7026 |  | 55.7026 | [9 empty] | Excavation ( W= 1.0 & d= 5.0 ) |  | M | 92.464 |  | 92.464 | 55.7026 | 5150.487 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 50T | Machinery | HR | 131.2 | 16 | 8.2 | 3.4814 | 456.7613
[22 empty] | Fuel | Material | LTR | 1.76 | 0.5 | 3.52 | 111.4052 | 196.0732
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 4.08 | 11.7647 | 13.6526 | 655.3247
[22 empty] | Fuel | Material | LTR | 1.76 | 0.408 | 4.3137 | 136.526 | 240.2857
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 1.1141 | 25.6232
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 3.3422 | 5.8822
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 16 | 3 | 3.4814 | 167.1078
[22 empty] | Fuel | Material | LTR | 1.76 | 1.6 | 1.1 | 34.8141 | 61.2729
[22 empty] | Steel Shoring D>3.0 M | Material | M | 60 | 1 | 60 | 55.7026 | 3342.156
[9 empty] | 55.7026 | 55.7026 |  | 55.7026 | [9 empty] | Pipe Laying & Protection |  | M | 150.5833 |  | 150.5833 | 55.7026 | 8387.8832 | 0 | 0 | 0 | 0 | 0
[22 empty] | UPVC Pipe 315 mm | Material | M | 95 | 1 | 95 | 55.7026 | 5291.747
[22 empty] | UPVC Fitting 315 mm | Material | M | 10 | 1 | 10 | 55.7026 | 557.026
[22 empty] | Skilled Labor | Manpower | HR | 17 | 6 | 2.8333 | 9.2838 | 157.824
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 6 | 2.1667 | 9.2838 | 120.689
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 10 | 25 | 5.5703 | 1392.565
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 10 | 15 | 5.5703 | 835.539
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.18568 | 32.4932
[9 empty] | 55.7026 | 55.7026 |  | 55.7026 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 55.7026 | 278.513 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 55.7026 | 278.513
SEW 10 |  | Pipes, 315 mm inner diameter, at a maximum depth of 5.0-5.5 m | m | 90.384 | 720 | 65076.48 | 251.2372 | 22707.8238 | 90.384 | 90.384 |  | 90.384 | 100% | 720 | 65076.48 | 251.2372 | 22707.8238 |  | 22707.8238 | [7 empty] | 251.2372 | 90.384 | 22707.8238 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 90.384 | 90.384 |  | 90.384 | [9 empty] | Excavation ( W= 1.0 & d= 5.5 ) |  | M | 95.6539 |  | 95.6539 | 90.384 | 8645.5798 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 50T | Machinery | HR | 131.2 | 14.5455 | 9.02 | 6.2139 | 815.2637
[22 empty] | Fuel | Material | LTR | 1.76 | 0.45455 | 3.872 | 198.8448 | 349.9668
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 3.7091 | 12.9412 | 24.3682 | 1169.6753
[22 empty] | Fuel | Material | LTR | 1.76 | 0.37091 | 4.7451 | 243.6824 | 428.8809
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 1.8077 | 41.5766
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 5.423 | 9.5446
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 14.5455 | 3.3 | 6.2139 | 298.2672
[22 empty] | Fuel | Material | LTR | 1.76 | 1.4545 | 1.21 | 62.139 | 109.3646
[22 empty] | Steel Shoring D>3.0 M | Material | M | 60 | 1 | 60 | 90.384 | 5423.04
[9 empty] | 90.384 | 90.384 |  | 90.384 | [9 empty] | Pipe Laying & Protection |  | M | 150.5833 |  | 150.5833 | 90.384 | 13610.324 | 0 | 0 | 0 | 0 | 0
[22 empty] | UPVC Pipe 315 mm | Material | M | 95 | 1 | 95 | 90.384 | 8586.48
[22 empty] | UPVC Fitting 315 mm | Material | M | 10 | 1 | 10 | 90.384 | 903.84
[22 empty] | Skilled Labor | Manpower | HR | 17 | 6 | 2.8333 | 15.064 | 256.088
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 6 | 2.1667 | 15.064 | 195.832
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 10 | 25 | 9.0384 | 2259.6
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 10 | 15 | 9.0384 | 1355.76
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.30128 | 52.724
[9 empty] | 90.384 | 90.384 |  | 90.384 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 90.384 | 451.92 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 90.384 | 451.92
SEW 10 |  | Pipes, 315 mm inner diameter, at a maximum depth of 5.5-6.0 m | m | 6.2373 | 768 | 4790.208 | 254.4271 | 1586.9251 | 6.2373 | 6.2373 |  | 6.2373 | 100% | 768 | 4790.208 | 254.4271 | 1586.9251 |  | 1586.9251 | [7 empty] | 254.4271 | 6.2373 | 1586.9251 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 6.2373 | 6.2373 |  | 6.2373 | [9 empty] | Excavation ( W= 1.0 & d= 6.0 ) |  | M | 98.8437 |  | 98.8437 | 6.2373 | 616.513 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 50T | Machinery | HR | 131.2 | 13.3333 | 9.84 | 0.46779 | 61.3745
[22 empty] | Fuel | Material | LTR | 1.76 | 0.41667 | 4.224 | 14.9694 | 26.3461
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 3.4 | 14.1176 | 1.8345 | 88.0553
[22 empty] | Fuel | Material | LTR | 1.76 | 0.34 | 5.1765 | 18.3449 | 32.2869
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 0.12475 | 2.8691
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 0.37424 | 0.65865
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 13.3333 | 3.6 | 0.46779 | 22.4541
[22 empty] | Fuel | Material | LTR | 1.76 | 1.3333 | 1.32 | 4.6779 | 8.2332
[22 empty] | Steel Shoring D>3.0 M | Material | M | 60 | 1 | 60 | 6.2373 | 374.235
[9 empty] | 6.2373 | 6.2373 |  | 6.2373 | [9 empty] | Pipe Laying & Protection |  | M | 150.5833 |  | 150.5833 | 6.2373 | 939.2259 | 0 | 0 | 0 | 0 | 0
[22 empty] | UPVC Pipe 315 mm | Material | M | 95 | 1 | 95 | 6.2373 | 592.5388
[22 empty] | UPVC Fitting 315 mm | Material | M | 10 | 1 | 10 | 6.2373 | 62.3725
[22 empty] | Skilled Labor | Manpower | HR | 17 | 6 | 2.8333 | 1.0395 | 17.6722
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 6 | 2.1667 | 1.0395 | 13.514
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 10 | 25 | 0.62373 | 155.9313
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 10 | 15 | 0.62373 | 93.5588
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.020791 | 3.6384
[9 empty] | 6.2373 | 6.2373 |  | 6.2373 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 6.2373 | 31.1863 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 6.2373 | 31.1863
SEW 10 |  | Category (I): Pipework - Pipes Supply and installation of GRP pipes with a hardness of not less than 10,000 N/m2 in the designated trenches, including drilling, backfilling, compaction, waste removal, protection of services and facilities, supports, warning tape, testing and operation upon completion in accordance with the drawings, specifications and requirements of the relevant authority (backfilling under the pipe, draining water, reinforcing and protecting the excavated surfaces to reach the required depths and disposing of groundwater resulting from the drainage around them are measured individually)
SEW 10 |  | 400 mm inner diameter pipes |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | At a depth of 1.5 - 2.0 m | m | 8.351 | 334 | 2789.234 | 274.3763 | 2291.3168 | 8.351 | 8.351 |  | 8.351 | 100% | 334 | 2789.234 | 274.3763 | 2291.3168 |  | 2291.3168 | [7 empty] | 274.3763 | 8.351 | 2291.3168 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 8.351 | 8.351 |  | 8.351 | [9 empty] | Excavation ( W= 1.20 & d= 2.0 ) |  | M | 11.793 |  | 11.793 | 8.351 | 98.4834 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 41.6667 | 1.344 | 0.20042 | 11.2237
[22 empty] | Fuel | Material | LTR | 1.76 | 2.9762 | 0.59136 | 2.8059 | 4.9384
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 8.5 | 5.6471 | 0.98247 | 47.1586
[22 empty] | Fuel | Material | LTR | 1.76 | 0.85 | 2.0706 | 9.8247 | 17.2915
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 0.16702 | 3.8415
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 0.50106 | 0.88187
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 41.6667 | 1.152 | 0.20042 | 9.6204
[22 empty] | Fuel | Material | LTR | 1.76 | 4.1667 | 0.4224 | 2.0042 | 3.5275
[9 empty] | 8.351 | 8.351 |  | 8.351 | [9 empty] | Pipe Laying & Protection |  | M | 257.5833 |  | 257.5833 | 8.351 | 2151.0784 | 0 | 0 | 0 | 0 | 0
[22 empty] | GRP Pipe 400 mm | Material | M | 144 | 1 | 144 | 8.351 | 1202.544
[22 empty] | GRP Fitting 400 mm | Material | M | 15 | 1 | 15 | 8.351 | 125.265
[22 empty] | Workmanship GRP pipe 400 mm | SC | M | 50 | 1 | 50 | 8.351 | 417.55
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 8.3333 | 30 | 1.0021 | 250.53
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 8.3333 | 18 | 1.0021 | 150.318
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.027837 | 4.8714
[9 empty] | 8.351 | 8.351 |  | 8.351 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 8.351 | 41.755 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 8.351 | 41.755
SEW 10 |  | At a depth of 3.0 - 3.5 m | m | 33.6574 | 502 | 16896.0148 | 342.7969 | 11537.6522 | 33.6574 | 33.6574 |  | 33.6574 | 100% | 502 | 16896.0148 | 342.7969 | 11537.6522 |  | 11537.6522 | [7 empty] | 342.7969 | 33.6574 | 11537.6522 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 33.6574 | 33.6574 |  | 33.6574 | [9 empty] | Excavation ( W= 1.20 & d= 3.5 ) |  | M | 80.2136 |  | 80.2136 | 33.6574 | 2699.78 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 23.8095 | 2.352 | 1.4136 | 79.1622
[22 empty] | Fuel | Material | LTR | 1.76 | 1.7007 | 1.0349 | 19.7906 | 34.8314
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 4.8571 | 9.8824 | 6.9295 | 332.6143
[22 empty] | Fuel | Material | LTR | 1.76 | 0.48571 | 3.6235 | 69.2946 | 121.9586
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 0.67315 | 15.4824
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 2.0194 | 3.5542
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 23.8095 | 2.016 | 1.4136 | 67.8533
[22 empty] | Fuel | Material | LTR | 1.76 | 2.381 | 0.7392 | 14.1361 | 24.8796
[22 empty] | Steel Shoring D>3.0 M | Material | M | 60 | 1 | 60 | 33.6574 | 2019.444
[9 empty] | 33.6574 | 33.6574 |  | 33.6574 | [9 empty] | Pipe Laying & Protection |  | M | 257.5833 |  | 257.5833 | 33.6574 | 8669.5853 | 0 | 0 | 0 | 0 | 0
[22 empty] | GRP Pipe 400 mm | Material | M | 144 | 1 | 144 | 33.6574 | 4846.6656
[22 empty] | GRP Fitting 400 mm | Material | M | 15 | 1 | 15 | 33.6574 | 504.861
[22 empty] | Workmanship GRP pipe 400 mm | SC | M | 50 | 1 | 50 | 33.6574 | 1682.87
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 8.3333 | 30 | 4.0389 | 1009.722
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 8.3333 | 18 | 4.0389 | 605.8332
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.11219 | 19.6335
[9 empty] | 33.6574 | 33.6574 |  | 33.6574 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 33.6574 | 168.287 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 33.6574 | 168.287
SEW 10 |  | At a depth of 3.5 - 4.0 m | m | 34.8841 | 590 | 20581.619 | 345.6037 | 12056.0757 | 34.8841 | 34.8841 |  | 34.8841 | 100% | 590 | 20581.619 | 345.6037 | 12056.0757 |  | 12056.0757 | [7 empty] | 345.6037 | 34.8841 | 12056.0757 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 34.8841 | 34.8841 |  | 34.8841 | [9 empty] | Excavation ( W= 1.20 & d= 4.0 ) |  | M | 83.0204 |  | 83.0204 | 34.8841 | 2896.0924 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 20.8333 | 2.688 | 1.6744 | 93.7685
[22 empty] | Fuel | Material | LTR | 1.76 | 1.4881 | 1.1827 | 23.4421 | 41.2581
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 4.25 | 11.2941 | 8.208 | 393.9851
[22 empty] | Fuel | Material | LTR | 1.76 | 0.425 | 4.1412 | 82.0802 | 144.4612
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 0.69768 | 16.0467
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 2.093 | 3.6838
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 20.8333 | 2.304 | 1.6744 | 80.373
[22 empty] | Fuel | Material | LTR | 1.76 | 2.0833 | 0.8448 | 16.7444 | 29.4701
[22 empty] | Steel Shoring D>3.0 M | Material | M | 60 | 1 | 60 | 34.8841 | 2093.046
[9 empty] | 34.8841 | 34.8841 |  | 34.8841 | [9 empty] | Pipe Laying & Protection |  | M | 257.5833 |  | 257.5833 | 34.8841 | 8985.5628 | 0 | 0 | 0 | 0 | 0
[22 empty] | GRP Pipe 400 mm | Material | M | 144 | 1 | 144 | 34.8841 | 5023.3104
[22 empty] | GRP Fitting 400 mm | Material | M | 15 | 1 | 15 | 34.8841 | 523.2615
[22 empty] | Workmanship GRP pipe 400 mm | SC | M | 50 | 1 | 50 | 34.8841 | 1744.205
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 8.3333 | 30 | 4.1861 | 1046.523
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 8.3333 | 18 | 4.1861 | 627.9138
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.11628 | 20.3491
[9 empty] | 34.8841 | 34.8841 |  | 34.8841 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 34.8841 | 174.4205 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 34.8841 | 174.4205
SEW 10 |  | At a depth of 4.0 - 4.5 m | m | 96.932 | 618 | 59903.976 | 348.4106 | 33772.1362 | 96.932 | 96.932 |  | 96.932 | 100% | 618 | 59903.976 | 348.4106 | 33772.1362 |  | 33772.1362 | [7 empty] | 348.4106 | 96.932 | 33772.1362 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 96.932 | 96.932 |  | 96.932 | [9 empty] | Excavation ( W= 1.20 & d= 4.5 ) |  | M | 85.8273 |  | 85.8273 | 96.932 | 8319.4085 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 18.5185 | 3.024 | 5.2343 | 293.1224
[22 empty] | Fuel | Material | LTR | 1.76 | 1.3228 | 1.3306 | 73.2806 | 128.9738
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 3.7778 | 12.7059 | 25.6585 | 1231.6066
[22 empty] | Fuel | Material | LTR | 1.76 | 0.37778 | 4.6588 | 256.5847 | 451.5891
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 1.9386 | 44.5887
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 5.8159 | 10.236
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 18.5185 | 2.592 | 5.2343 | 251.2477
[22 empty] | Fuel | Material | LTR | 1.76 | 1.8519 | 0.9504 | 52.3433 | 92.1242
[22 empty] | Steel Shoring D>3.0 M | Material | M | 60 | 1 | 60 | 96.932 | 5815.92
[9 empty] | 96.932 | 96.932 |  | 96.932 | [9 empty] | Pipe Laying & Protection |  | M | 257.5833 |  | 257.5833 | 96.932 | 24968.0677 | 0 | 0 | 0 | 0 | 0
[22 empty] | GRP Pipe 400 mm | Material | M | 144 | 1 | 144 | 96.932 | 13958.208
[22 empty] | GRP Fitting 400 mm | Material | M | 15 | 1 | 15 | 96.932 | 1453.98
[22 empty] | Workmanship GRP pipe 400 mm | SC | M | 50 | 1 | 50 | 96.932 | 4846.6
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 8.3333 | 30 | 11.6318 | 2907.96
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 8.3333 | 18 | 11.6318 | 1744.776
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.32311 | 56.5437
[9 empty] | 96.932 | 96.932 |  | 96.932 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 96.932 | 484.66 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 96.932 | 484.66
SEW 10 |  | At a depth of 4.5 - 5.0 m | m | 42.6404 | 705 | 30061.4468 | 361.4271 | 15411.376 | 42.6404 | 42.6404 |  | 42.6404 | 100% | 705 | 30061.4468 | 361.4271 | 15411.376 |  | 15411.376 | [7 empty] | 361.4271 | 42.6404 | 15411.376 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 42.6404 | 42.6404 |  | 42.6404 | [9 empty] | Excavation ( W= 1.20 & d= 5.0 ) |  | M | 98.8437 |  | 98.8437 | 42.6404 | 4214.7307 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 50T | Machinery | HR | 131.2 | 13.3333 | 9.84 | 3.198 | 419.581
[22 empty] | Fuel | Material | LTR | 1.76 | 0.41667 | 4.224 | 102.3368 | 180.1128
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 3.4 | 14.1176 | 12.5413 | 601.9814
[22 empty] | Fuel | Material | LTR | 1.76 | 0.34 | 5.1765 | 125.4128 | 220.7265
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 0.85281 | 19.6146
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 2.5584 | 4.5028
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 13.3333 | 3.6 | 3.198 | 153.5053
[22 empty] | Fuel | Material | LTR | 1.76 | 1.3333 | 1.32 | 31.9803 | 56.2853
[22 empty] | Steel Shoring D>3.0 M | Material | M | 60 | 1 | 60 | 42.6404 | 2558.421
[9 empty] | 42.6404 | 42.6404 |  | 42.6404 | [9 empty] | Pipe Laying & Protection |  | M | 257.5833 |  | 257.5833 | 42.6404 | 10983.4435 | 0 | 0 | 0 | 0 | 0
[22 empty] | GRP Pipe 400 mm | Material | M | 144 | 1 | 144 | 42.6404 | 6140.2104
[22 empty] | GRP Fitting 400 mm | Material | M | 15 | 1 | 15 | 42.6404 | 639.6053
[22 empty] | Workmanship GRP pipe 400 mm | SC | M | 50 | 1 | 50 | 42.6404 | 2132.0175
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 8.3333 | 30 | 5.1168 | 1279.2105
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 8.3333 | 18 | 5.1168 | 767.5263
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.14213 | 24.8735
[9 empty] | 42.6404 | 42.6404 |  | 42.6404 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 42.6404 | 213.2018 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 42.6404 | 213.2018
SEW 10 |  | At a depth of 5.0 - 5.5 m | m | 8.1026 | 734 | 5947.3084 | 365.2549 | 2959.5141 | 8.1026 | 8.1026 |  | 8.1026 | 100% | 734 | 5947.3084 | 365.2549 | 2959.5141 |  | 2959.5141 | [7 empty] | 365.2549 | 8.1026 | 2959.5141 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 8.1026 | 8.1026 |  | 8.1026 | [9 empty] | Excavation ( W= 1.20 & d= 5.5 ) |  | M | 102.6715 |  | 102.6715 | 8.1026 | 831.9063 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 50T | Machinery | HR | 131.2 | 12.1212 | 10.824 | 0.66846 | 87.7025
[22 empty] | Fuel | Material | LTR | 1.76 | 0.37879 | 4.6464 | 21.3909 | 37.6479
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 3.0909 | 15.5294 | 2.6214 | 125.8286
[22 empty] | Fuel | Material | LTR | 1.76 | 0.30909 | 5.6941 | 26.2143 | 46.1372
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 0.16205 | 3.7272
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 0.48616 | 0.85563
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 12.1212 | 3.96 | 0.66846 | 32.0863
[22 empty] | Fuel | Material | LTR | 1.76 | 1.2121 | 1.452 | 6.6846 | 11.765
[22 empty] | Steel Shoring D>3.0 M | Material | M | 60 | 1 | 60 | 8.1026 | 486.156
[9 empty] | 8.1026 | 8.1026 |  | 8.1026 | [9 empty] | Pipe Laying & Protection |  | M | 257.5833 |  | 257.5833 | 8.1026 | 2087.0947 | 0 | 0 | 0 | 0 | 0
[22 empty] | GRP Pipe 400 mm | Material | M | 144 | 1 | 144 | 8.1026 | 1166.7744
[22 empty] | GRP Fitting 400 mm | Material | M | 15 | 1 | 15 | 8.1026 | 121.539
[22 empty] | Workmanship GRP pipe 400 mm | SC | M | 50 | 1 | 50 | 8.1026 | 405.13
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 8.3333 | 30 | 0.97231 | 243.078
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 8.3333 | 18 | 0.97231 | 145.8468
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.027009 | 4.7265
[9 empty] | 8.1026 | 8.1026 |  | 8.1026 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 8.1026 | 40.513 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 8.1026 | 40.513
SEW 10 |  | At a depth of 5.5 - 6.0 m | m |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | At a depth of 6.0 - 6.5 m | m |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | At a depth of 6.5 - 7.0 m | m | 24.2838 | 809 | 19645.5942 | 376.7383 | 9148.6375 | 24.2838 | 24.2838 |  | 24.2838 | 100% | 809 | 19645.5942 | 376.7383 | 9148.6375 |  | 9148.6375 | [7 empty] | 376.7383 | 24.2838 | 9148.6375 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 24.2838 | 24.2838 |  | 24.2838 | [9 empty] | Excavation ( W= 1.20 & d= 7.0 ) |  | M | 114.155 |  | 114.155 | 24.2838 | 2772.1163 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 50T | Machinery | HR | 131.2 | 9.5238 | 13.776 | 2.5498 | 334.5336
[22 empty] | Fuel | Material | LTR | 1.76 | 0.29762 | 5.9136 | 81.5936 | 143.6047
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 2.4286 | 19.7647 | 9.9992 | 479.9622
[22 empty] | Fuel | Material | LTR | 1.76 | 0.24286 | 7.2471 | 99.9921 | 175.9861
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 0.48568 | 11.1705
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 1.457 | 2.5644
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 9.5238 | 5.04 | 2.5498 | 122.3904
[22 empty] | Fuel | Material | LTR | 1.76 | 0.95238 | 1.848 | 25.498 | 44.8765
[22 empty] | Steel Shoring D>3.0 M | Material | M | 60 | 1 | 60 | 24.2838 | 1457.028
[9 empty] | 24.2838 | 24.2838 |  | 24.2838 | [9 empty] | Pipe Laying & Protection |  | M | 257.5833 |  | 257.5833 | 24.2838 | 6255.1021 | 0 | 0 | 0 | 0 | 0
[22 empty] | GRP Pipe 400 mm | Material | M | 144 | 1 | 144 | 24.2838 | 3496.8672
[22 empty] | GRP Fitting 400 mm | Material | M | 15 | 1 | 15 | 24.2838 | 364.257
[22 empty] | Workmanship GRP pipe 400 mm | SC | M | 50 | 1 | 50 | 24.2838 | 1214.19
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 8.3333 | 30 | 2.9141 | 728.514
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 8.3333 | 18 | 2.9141 | 437.1084
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.080946 | 14.1656
[9 empty] | 24.2838 | 24.2838 |  | 24.2838 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 24.2838 | 121.419 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 24.2838 | 121.419
SEW 10 |  | At a depth of 7.0 - 7.5 m | m |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | 500 mm inner diameter pipes |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | At a depth of 1.5 - 2.0 m | m | 7.2222 | 395 | 2852.769 | 410.1832 | 2962.4251 | 7.2222 | 7.2222 |  | 7.2222 | 100% | 395 | 2852.769 | 410.1832 | 2962.4251 |  | 2962.4251 | [7 empty] | 410.1832 | 7.2222 | 2962.4251 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 7.2222 | 7.2222 |  | 7.2222 | [9 empty] | Excavation ( W= 1.50 & d= 2.0 ) |  | M | 14.5999 |  | 14.5999 | 7.2222 | 105.4431 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 33.3333 | 1.68 | 0.21667 | 12.1333
[22 empty] | Fuel | Material | LTR | 1.76 | 2.381 | 0.7392 | 3.0333 | 5.3387
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 6.8 | 7.0588 | 1.0621 | 50.9802
[22 empty] | Fuel | Material | LTR | 1.76 | 0.68 | 2.5882 | 10.6209 | 18.6928
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 0.14444 | 3.3222
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 0.43333 | 0.76266
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 33.3333 | 1.44 | 0.21667 | 10.4
[22 empty] | Fuel | Material | LTR | 1.76 | 3.3333 | 0.528 | 2.1667 | 3.8133
[9 empty] | 7.2222 | 7.2222 |  | 7.2222 | [9 empty] | Pipe Laying & Protection |  | M | 390.5833 |  | 390.5833 | 7.2222 | 2820.8709 | 0 | 0 | 0 | 0 | 0
[22 empty] | GRP Pipe 500 mm | Material | M | 250 | 1 | 250 | 7.2222 | 1805.55
[22 empty] | GRP Fitting 500 mm | Material | M | 25 | 1 | 25 | 7.2222 | 180.555
[22 empty] | Workmanship GRP pipe 500 mm | SC | M | 55 | 1 | 55 | 7.2222 | 397.221
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 6.6667 | 37.5 | 1.0833 | 270.8325
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 6.6667 | 22.5 | 1.0833 | 162.4995
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.024074 | 4.2129
[9 empty] | 7.2222 | 7.2222 |  | 7.2222 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 7.2222 | 36.111 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 7.2222 | 36.111
SEW 10 |  | At a depth of 2.0 - 2.5 m | m |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | At a depth of 2.5 - 3.0 m | m |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | At a depth of 3.0 - 3.5 m | m |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | At a depth of 3.5 - 4.00 m | m |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | At a depth of 4.0 - 4.5 m | m |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | At a depth of 4.5 - 5.0 m | m | 90.097 | 759 | 68383.623 | 503.9966 | 45408.5799 | 90.097 | 90.097 |  | 90.097 | 100% | 759 | 68383.623 | 503.9966 | 45408.5799 |  | 45408.5799 | [7 empty] | 503.9966 | 90.097 | 45408.5799 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 90.097 | 90.097 |  | 90.097 | [9 empty] | Excavation ( W= 1.5 & d= 5.0 ) |  | M | 108.4132 |  | 108.4132 | 90.097 | 9767.7083 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 50T | Machinery | HR | 131.2 | 10.6667 | 12.3 | 8.4466 | 1108.1931
[22 empty] | Fuel | Material | LTR | 1.76 | 0.33333 | 5.28 | 270.291 | 475.7122
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 2.72 | 17.6471 | 33.1239 | 1589.9471
[22 empty] | Fuel | Material | LTR | 1.76 | 0.272 | 6.4706 | 331.239 | 582.9806
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 1.8019 | 41.4446
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 5.4058 | 9.5142
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 10.6667 | 4.5 | 8.4466 | 405.4365
[22 empty] | Fuel | Material | LTR | 1.76 | 1.0667 | 1.65 | 84.4659 | 148.66
[22 empty] | Steel Shoring D>3.0 M | Material | M | 60 | 1 | 60 | 90.097 | 5405.82
[9 empty] | 90.097 | 90.097 |  | 90.097 | [9 empty] | Pipe Laying & Protection |  | M | 390.5833 |  | 390.5833 | 90.097 | 35190.3866 | 0 | 0 | 0 | 0 | 0
[22 empty] | GRP Pipe 500 mm | Material | M | 250 | 1 | 250 | 90.097 | 22524.25
[22 empty] | GRP Fitting 500 mm | Material | M | 25 | 1 | 25 | 90.097 | 2252.425
[22 empty] | Workmanship GRP pipe 500 mm | SC | M | 55 | 1 | 55 | 90.097 | 4955.335
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 6.6667 | 37.5 | 13.5145 | 3378.6375
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 6.6667 | 22.5 | 13.5145 | 2027.1825
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.30032 | 52.5566
[9 empty] | 90.097 | 90.097 |  | 90.097 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 90.097 | 450.485 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 90.097 | 450.485
SEW 10 |  | At a depth of 5.0 - 5.5 m | m | 30.0643 | 787 | 23660.6434 | 508.7813 | 15296.1804 | 30.0643 | 30.0643 |  | 30.0643 | 100% | 787 | 23660.6434 | 508.7813 | 15296.1804 |  | 15296.1804 | [7 empty] | 508.7813 | 30.0643 | 15296.1804 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 30.0643 | 30.0643 |  | 30.0643 | [9 empty] | Excavation ( W= 1.5 & d= 5.5 ) |  | M | 113.198 |  | 113.198 | 30.0643 | 3403.2246 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 50T | Machinery | HR | 131.2 | 9.697 | 13.53 | 3.1004 | 406.7707
[22 empty] | Fuel | Material | LTR | 1.76 | 0.30303 | 5.808 | 99.2124 | 174.6137
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 2.4727 | 19.4118 | 12.1584 | 583.6021
[22 empty] | Fuel | Material | LTR | 1.76 | 0.24727 | 7.1176 | 121.5838 | 213.9874
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 0.60129 | 13.8296
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 1.8039 | 3.1748
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 9.697 | 4.95 | 3.1004 | 148.8185
[22 empty] | Fuel | Material | LTR | 1.76 | 0.9697 | 1.815 | 31.0039 | 54.5668
[22 empty] | Steel Shoring D>3.0 M | Material | M | 60 | 1 | 60 | 30.0643 | 1803.861
[9 empty] | 30.0643 | 30.0643 |  | 30.0643 | [9 empty] | Pipe Laying & Protection |  | M | 390.5833 |  | 390.5833 | 30.0643 | 11742.634 | 0 | 0 | 0 | 0 | 0
[22 empty] | GRP Pipe 500 mm | Material | M | 250 | 1 | 250 | 30.0643 | 7516.0875
[22 empty] | GRP Fitting 500 mm | Material | M | 25 | 1 | 25 | 30.0643 | 751.6087
[22 empty] | Workmanship GRP pipe 500 mm | SC | M | 55 | 1 | 55 | 30.0643 | 1653.5392
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 6.6667 | 37.5 | 4.5097 | 1127.4131
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 6.6667 | 22.5 | 4.5097 | 676.4479
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.10021 | 17.5375
[9 empty] | 30.0643 | 30.0643 |  | 30.0643 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 30.0643 | 150.3217 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 30.0643 | 150.3217
SEW 10 |  | At a depth of 5.5 - 6.0 m | m |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | At a depth of 6.0 - 6.5 m | m |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | At a depth of 6.5 - 7.0 m | m |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | At a depth of 7.0 - 7.5 m | m |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | 600 mm inner diameter pipes |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | At a depth of 1.5 - 2.0 m | m | 1.3035 | 474 | 617.8827 | 464.1188 | 605.0021 | 1.3035 | 1.3035 |  | 1.3035 | 100% | 474 | 617.8827 | 464.1188 | 605.0021 |  | 605.0021 | [7 empty] | 464.1188 | 1.3035 | 605.0021 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 1.3035 | 1.3035 |  | 1.3035 | [9 empty] | Excavation ( W= 1.6 & d= 2.0 ) |  | M | 15.5355 |  | 15.5355 | 1.3035 | 20.2513 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 31.25 | 1.792 | 0.041714 | 2.336
[22 empty] | Fuel | Material | LTR | 1.76 | 2.2321 | 0.78848 | 0.58399 | 1.0278
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 6.375 | 7.5294 | 0.20448 | 9.815
[22 empty] | Fuel | Material | LTR | 1.76 | 0.6375 | 2.7608 | 2.0448 | 3.5988
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 0.026071 | 0.59963
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 0.078213 | 0.13765
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 31.25 | 1.536 | 0.041714 | 2.0023
[22 empty] | Fuel | Material | LTR | 1.76 | 3.125 | 0.5632 | 0.41714 | 0.73416
[9 empty] | 1.3035 | 1.3035 |  | 1.3035 | [9 empty] | Pipe Laying & Protection |  | M | 443.5833 |  | 443.5833 | 1.3035 | 578.2331 | 0 | 0 | 0 | 0 | 0
[22 empty] | GRP Pipe 600 mm | Material | M | 290 | 1 | 290 | 1.3035 | 378.0295
[22 empty] | GRP Fitting 600 mm | Material | M | 29 | 1 | 29 | 1.3035 | 37.8029
[22 empty] | Workmanship GRP pipe 600 mm | SC | M | 60 | 1 | 60 | 1.3035 | 78.213
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 6.25 | 40 | 0.20857 | 52.142
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 6.25 | 24 | 0.20857 | 31.2852
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.0043452 | 0.7604
[9 empty] | 1.3035 | 1.3035 |  | 1.3035 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 1.3035 | 6.5177 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 1.3035 | 6.5177
SEW 10 |  | At a depth of 2.0 - 2.5 m | m | 42.6343 | 503 | 21445.078 | 502.8613 | 21439.1637 | 42.6343 | 42.6343 |  | 42.6343 | 100% | 503 | 21445.078 | 502.8613 | 21439.1637 |  | 21439.1637 | [7 empty] | 502.8613 | 42.6343 | 21439.1637 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 42.6343 | 42.6343 |  | 42.6343 | [9 empty] | Excavation ( W= 1.6 & d= 2.5 ) |  | M | 54.2779 |  | 54.2779 | 42.6343 | 2314.1049 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 25 | 2.24 | 1.7054 | 95.5009
[22 empty] | Fuel | Material | LTR | 1.76 | 1.7857 | 0.9856 | 23.8752 | 42.0204
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 5.1 | 9.4118 | 8.3597 | 401.2645
[22 empty] | Fuel | Material | LTR | 1.76 | 0.51 | 3.451 | 83.5968 | 147.1303
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 0.85269 | 19.6118
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 2.5581 | 4.5022
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 25 | 1.92 | 1.7054 | 81.858
[22 empty] | Fuel | Material | LTR | 1.76 | 2.5 | 0.704 | 17.0537 | 30.0146
[22 empty] | Steel Shoring D=2.5 M | Material | M | 35 | 1 | 35 | 42.6343 | 1492.2022
[9 empty] | 42.6343 | 42.6343 |  | 42.6343 | [9 empty] | Pipe Laying & Protection |  | M | 443.5833 |  | 443.5833 | 42.6343 | 18911.8871 | 0 | 0 | 0 | 0 | 0
[22 empty] | GRP Pipe 600 mm | Material | M | 290 | 1 | 290 | 42.6343 | 12363.9615
[22 empty] | GRP Fitting 600 mm | Material | M | 29 | 1 | 29 | 42.6343 | 1236.3961
[22 empty] | Workmanship GRP pipe 600 mm | SC | M | 60 | 1 | 60 | 42.6343 | 2558.061
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 6.25 | 40 | 6.8215 | 1705.374
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 6.25 | 24 | 6.8215 | 1023.2244
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.14211 | 24.87
[9 empty] | 42.6343 | 42.6343 |  | 42.6343 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 42.6343 | 213.1717 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 42.6343 | 213.1717
SEW 10 |  | At a depth of 2.5 - 3.0 m | m |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | At a depth of 3.0 - 3.5 m | m |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | At a depth of 3.5 - 4.00 m | m | 6.2336 | 770 | 4799.9105 | 539.0887 | 3360.4902 | 6.2336 | 6.2336 |  | 6.2336 | 100% | 770 | 4799.9105 | 539.0887 | 3360.4902 |  | 3360.4902 | [7 empty] | 539.0887 | 6.2336 | 3360.4902 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 6.2336 | 6.2336 |  | 6.2336 | [9 empty] | Excavation ( W= 1.6 & d= 4.0 ) |  | M | 90.5054 |  | 90.5054 | 6.2336 | 564.1787 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 15.625 | 3.584 | 0.39895 | 22.3414
[22 empty] | Fuel | Material | LTR | 1.76 | 1.1161 | 1.577 | 5.5854 | 9.8302
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 3.1875 | 15.0588 | 1.9557 | 93.8714
[22 empty] | Fuel | Material | LTR | 1.76 | 0.31875 | 5.5216 | 19.5565 | 34.4195
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 0.12467 | 2.8675
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 0.37402 | 0.65827
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 15.625 | 3.072 | 0.39895 | 19.1498
[22 empty] | Fuel | Material | LTR | 1.76 | 1.5625 | 1.1264 | 3.9895 | 7.0216
[22 empty] | Steel Shoring D>3.0 M | Material | M | 60 | 1 | 60 | 6.2336 | 374.019
[9 empty] | 6.2336 | 6.2336 |  | 6.2336 | [9 empty] | Pipe Laying & Protection |  | M | 443.5833 |  | 443.5833 | 6.2336 | 2765.1432 | 0 | 0 | 0 | 0 | 0
[22 empty] | GRP Pipe 600 mm | Material | M | 290 | 1 | 290 | 6.2336 | 1807.7585
[22 empty] | GRP Fitting 600 mm | Material | M | 29 | 1 | 29 | 6.2336 | 180.7758
[22 empty] | Workmanship GRP pipe 600 mm | SC | M | 60 | 1 | 60 | 6.2336 | 374.019
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 6.25 | 40 | 0.99738 | 249.346
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 6.25 | 24 | 0.99738 | 149.6076
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.020779 | 3.6363
[9 empty] | 6.2336 | 6.2336 |  | 6.2336 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 6.2336 | 31.1682 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 6.2336 | 31.1682
SEW 10 |  | At a depth of 4.0 - 4.5 m | m | 3.925 | 803 | 3151.775 | 542.8312 | 2130.6123 | 3.925 | 3.925 |  | 3.925 | 100% | 803 | 3151.775 | 542.8312 | 2130.6123 |  | 2130.6123 | [7 empty] | 542.8312 | 3.925 | 2130.6123 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 3.925 | 3.925 |  | 3.925 | [9 empty] | Excavation ( W= 1.6 & d= 4.5 ) |  | M | 94.2478 |  | 94.2478 | 3.925 | 369.9227 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 13.8889 | 4.032 | 0.2826 | 15.8256
[22 empty] | Fuel | Material | LTR | 1.76 | 0.99206 | 1.7741 | 3.9564 | 6.9633
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 2.8333 | 16.9412 | 1.3853 | 66.4941
[22 empty] | Fuel | Material | LTR | 1.76 | 0.28333 | 6.2118 | 13.8529 | 24.3812
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 0.0785 | 1.8055
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 0.2355 | 0.41448
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 13.8889 | 3.456 | 0.2826 | 13.5648
[22 empty] | Fuel | Material | LTR | 1.76 | 1.3889 | 1.2672 | 2.826 | 4.9738
[22 empty] | Steel Shoring D>3.0 M | Material | M | 60 | 1 | 60 | 3.925 | 235.5
[9 empty] | 3.925 | 3.925 |  | 3.925 | [9 empty] | Pipe Laying & Protection |  | M | 443.5833 |  | 443.5833 | 3.925 | 1741.0646 | 0 | 0 | 0 | 0 | 0
[22 empty] | GRP Pipe 600 mm | Material | M | 290 | 1 | 290 | 3.925 | 1138.25
[22 empty] | GRP Fitting 600 mm | Material | M | 29 | 1 | 29 | 3.925 | 113.825
[22 empty] | Workmanship GRP pipe 600 mm | SC | M | 60 | 1 | 60 | 3.925 | 235.5
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 6.25 | 40 | 0.628 | 157
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 6.25 | 24 | 0.628 | 94.2
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.013083 | 2.2896
[9 empty] | 3.925 | 3.925 |  | 3.925 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 3.925 | 19.625 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 3.925 | 19.625
SEW 10 |  | At a depth of 4.5 - 5.0 m | m | 49.285 | 834 | 41103.7317 | 560.1864 | 27608.8159 | 49.285 | 49.285 |  | 49.285 | 100% | 834 | 41103.7317 | 560.1864 | 27608.8159 |  | 27608.8159 | [7 empty] | 560.1864 | 49.285 | 27608.8159 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 49.285 | 49.285 |  | 49.285 | [9 empty] | Excavation ( W= 1.6 & d= 5.0 ) |  | M | 111.6031 |  | 111.6031 | 49.285 | 5500.3639 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 50T | Machinery | HR | 131.2 | 10 | 13.12 | 4.9285 | 646.6199
[22 empty] | Fuel | Material | LTR | 1.76 | 0.3125 | 5.632 | 157.7122 | 277.5734
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 2.55 | 18.8235 | 19.3275 | 927.7186
[22 empty] | Fuel | Material | LTR | 1.76 | 0.255 | 6.902 | 193.2747 | 340.1635
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 0.9857 | 22.6711
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 2.9571 | 5.2045
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 10 | 4.8 | 4.9285 | 236.5682
[22 empty] | Fuel | Material | LTR | 1.76 | 1 | 1.76 | 49.285 | 86.7417
[22 empty] | Steel Shoring D>3.0 M | Material | M | 60 | 1 | 60 | 49.285 | 2957.103
[9 empty] | 49.285 | 49.285 |  | 49.285 | [9 empty] | Pipe Laying & Protection |  | M | 443.5833 |  | 443.5833 | 49.285 | 21862.0268 | 0 | 0 | 0 | 0 | 0
[22 empty] | GRP Pipe 600 mm | Material | M | 290 | 1 | 290 | 49.285 | 14292.6645
[22 empty] | GRP Fitting 600 mm | Material | M | 29 | 1 | 29 | 49.285 | 1429.2664
[22 empty] | Workmanship GRP pipe 600 mm | SC | M | 60 | 1 | 60 | 49.285 | 2957.103
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 6.25 | 40 | 7.8856 | 1971.402
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 6.25 | 24 | 7.8856 | 1182.8412
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.16428 | 28.7496
[9 empty] | 49.285 | 49.285 |  | 49.285 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 49.285 | 246.4252 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 49.285 | 246.4252
SEW 10 |  | At a depth of 5.0 - 5.5 m | m | 40.4508 | 860 | 34787.688 | 565.2902 | 22866.4397 | 40.4508 | 40.4508 |  | 40.4508 | 100% | 860 | 34787.688 | 565.2902 | 22866.4397 |  | 22866.4397 | [7 empty] | 565.2902 | 40.4508 | 22866.4397 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 40.4508 | 40.4508 |  | 40.4508 | [9 empty] | Excavation ( W= 1.6 & d= 5.5 ) |  | M | 116.7068 |  | 116.7068 | 40.4508 | 4720.885 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 50T | Machinery | HR | 131.2 | 9.0909 | 14.432 | 4.4496 | 583.7859
[22 empty] | Fuel | Material | LTR | 1.76 | 0.28409 | 6.1952 | 142.3868 | 250.6008
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 2.3182 | 20.7059 | 17.4494 | 837.5695
[22 empty] | Fuel | Material | LTR | 1.76 | 0.23182 | 7.5922 | 174.4936 | 307.1088
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 0.80902 | 18.6074
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 2.427 | 4.2716
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 9.0909 | 5.28 | 4.4496 | 213.5802
[22 empty] | Fuel | Material | LTR | 1.76 | 0.90909 | 1.936 | 44.4959 | 78.3127
[22 empty] | Steel Shoring D>3.0 M | Material | M | 60 | 1 | 60 | 40.4508 | 2427.048
[9 empty] | 40.4508 | 40.4508 |  | 40.4508 | [9 empty] | Pipe Laying & Protection |  | M | 443.5833 |  | 443.5833 | 40.4508 | 17943.3007 | 0 | 0 | 0 | 0 | 0
[22 empty] | GRP Pipe 600 mm | Material | M | 290 | 1 | 290 | 40.4508 | 11730.732
[22 empty] | GRP Fitting 600 mm | Material | M | 29 | 1 | 29 | 40.4508 | 1173.0732
[22 empty] | Workmanship GRP pipe 600 mm | SC | M | 60 | 1 | 60 | 40.4508 | 2427.048
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 6.25 | 40 | 6.4721 | 1618.032
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 6.25 | 24 | 6.4721 | 970.8192
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.13484 | 23.5963
[9 empty] | 40.4508 | 40.4508 |  | 40.4508 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 40.4508 | 202.254 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 40.4508 | 202.254
SEW 10 |  | At a depth of 5.5 - 6.0 m | m | 31.1475 | 885 | 27565.5375 | 570.3939 | 17766.3447 | 31.1475 | 31.1475 |  | 31.1475 | 100% | 885 | 27565.5375 | 570.3939 | 17766.3447 |  | 17766.3447 | [7 empty] | 570.3939 | 31.1475 | 17766.3447 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 31.1475 | 31.1475 |  | 31.1475 | [9 empty] | Excavation ( W= 1.6 & d= 6.0 ) |  | M | 121.8106 |  | 121.8106 | 31.1475 | 3794.0953 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 50T | Machinery | HR | 131.2 | 8.3333 | 15.744 | 3.7377 | 490.3862
[22 empty] | Fuel | Material | LTR | 1.76 | 0.26042 | 6.7584 | 119.6064 | 210.5073
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 2.125 | 22.5882 | 14.6576 | 703.5671
[22 empty] | Fuel | Material | LTR | 1.76 | 0.2125 | 8.2824 | 146.5765 | 257.9746
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 0.62295 | 14.3279
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 1.8689 | 3.2892
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 8.3333 | 5.76 | 3.7377 | 179.4096
[22 empty] | Fuel | Material | LTR | 1.76 | 0.83333 | 2.112 | 37.377 | 65.7835
[22 empty] | Steel Shoring D>3.0 M | Material | M | 60 | 1 | 60 | 31.1475 | 1868.85
[9 empty] | 31.1475 | 31.1475 |  | 31.1475 | [9 empty] | Pipe Laying & Protection |  | M | 443.5833 |  | 443.5833 | 31.1475 | 13816.5119 | 0 | 0 | 0 | 0 | 0
[22 empty] | GRP Pipe 600 mm | Material | M | 290 | 1 | 290 | 31.1475 | 9032.775
[22 empty] | GRP Fitting 600 mm | Material | M | 29 | 1 | 29 | 31.1475 | 903.2775
[22 empty] | Workmanship GRP pipe 600 mm | SC | M | 60 | 1 | 60 | 31.1475 | 1868.85
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 6.25 | 40 | 4.9836 | 1245.9
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 6.25 | 24 | 4.9836 | 747.54
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.10383 | 18.1694
[9 empty] | 31.1475 | 31.1475 |  | 31.1475 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 31.1475 | 155.7375 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 31.1475 | 155.7375
SEW 10 |  | At a depth of 6.0 - 6.5 m | m |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | At a depth of 6.5 - 7.0 m | m |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | At a depth of 7.0 - 7.5 m | m | 0.61335 | 941 | 577.1623 | 585.7052 | 359.2423 | 0.61335 | 0.61335 |  | 0.61335 | 100% | 941 | 577.1623 | 585.7052 | 359.2423 |  | 359.2423 | [7 empty] | 585.7052 | 0.61335 | 359.2423 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 0.61335 | 0.61335 |  | 0.61335 | [9 empty] | Excavation ( W= 1.6 & d= 7.5 ) |  | M | 137.1218 |  | 137.1218 | 0.61335 | 84.1037 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 50T | Machinery | HR | 131.2 | 6.6667 | 19.68 | 0.092002 | 12.0707
[22 empty] | Fuel | Material | LTR | 1.76 | 0.20833 | 8.448 | 2.9441 | 5.1816
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 1.7 | 28.2353 | 0.36079 | 17.3181
[22 empty] | Fuel | Material | LTR | 1.76 | 0.17 | 10.3529 | 3.6079 | 6.35
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 0.012267 | 0.28214
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 0.036801 | 0.06477
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 6.6667 | 7.2 | 0.092002 | 4.4161
[22 empty] | Fuel | Material | LTR | 1.76 | 0.66667 | 2.64 | 0.92002 | 1.6192
[22 empty] | Steel Shoring D>3.0 M | Material | M | 60 | 1 | 60 | 0.61335 | 36.801
[9 empty] | 0.61335 | 0.61335 |  | 0.61335 | [9 empty] | Pipe Laying & Protection |  | M | 443.5833 |  | 443.5833 | 0.61335 | 272.0718 | 0 | 0 | 0 | 0 | 0
[22 empty] | GRP Pipe 600 mm | Material | M | 290 | 1 | 290 | 0.61335 | 177.8715
[22 empty] | GRP Fitting 600 mm | Material | M | 29 | 1 | 29 | 0.61335 | 17.7871
[22 empty] | Workmanship GRP pipe 600 mm | SC | M | 60 | 1 | 60 | 0.61335 | 36.801
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 6.25 | 40 | 0.098136 | 24.534
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 6.25 | 24 | 0.098136 | 14.7204
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.0020445 | 0.35779
[9 empty] | 0.61335 | 0.61335 |  | 0.61335 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 0.61335 | 3.0667 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 0.61335 | 3.0667
SEW 10 |  | 700 mm inner diameter pipes | m |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | At a depth of 1.5 - 2.0 m | m | 1.1914 | 676 | 805.4202 | 540.0544 | 643.4478 | 1.1914 | 1.1914 |  | 1.1914 | 100% | 676 | 805.4202 | 540.0544 | 643.4478 |  | 643.4478 | [7 empty] | 540.0544 | 1.1914 | 643.4478 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 1.1914 | 1.1914 |  | 1.1914 | [9 empty] | Excavation ( W= 1.7 & d= 2.0 ) |  | M | 16.4711 |  | 16.4711 | 1.1914 | 19.6245 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 29.4118 | 1.904 | 0.040509 | 2.2685
[22 empty] | Fuel | Material | LTR | 1.76 | 2.1008 | 0.83776 | 0.56713 | 0.99815
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 6 | 8 | 0.19857 | 9.5316
[22 empty] | Fuel | Material | LTR | 1.76 | 0.6 | 2.9333 | 1.9857 | 3.4949
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 0.023829 | 0.54807
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 0.071487 | 0.12582
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 29.4118 | 1.632 | 0.040509 | 1.9444
[22 empty] | Fuel | Material | LTR | 1.76 | 2.9412 | 0.5984 | 0.40509 | 0.71296
[9 empty] | 1.1914 | 1.1914 |  | 1.1914 | [9 empty] | Pipe Laying & Protection |  | M | 518.5833 |  | 518.5833 | 1.1914 | 617.8661 | 0 | 0 | 0 | 0 | 0
[22 empty] | GRP Pipe 700 mm | Material | M | 350 | 1 | 350 | 1.1914 | 417.0075
[22 empty] | GRP Fitting 700 mm | Material | M | 35 | 1 | 35 | 1.1914 | 41.7007
[22 empty] | Workmanship GRP pipe 700 mm | SC | M | 65 | 1 | 65 | 1.1914 | 77.4442
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 5.8824 | 42.5 | 0.20255 | 50.6366
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 5.8824 | 25.5 | 0.20255 | 30.382
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.0039715 | 0.69501
[9 empty] | 1.1914 | 1.1914 |  | 1.1914 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 1.1914 | 5.9572 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 1.1914 | 5.9572
SEW 10 |  | At a depth of 2.0 - 2.5 m | m | 37.8984 | 705 | 26718.3368 | 579.0308 | 21944.3119 | 37.8984 | 37.8984 |  | 37.8984 | 100% | 705 | 26718.3368 | 579.0308 | 21944.3119 |  | 21944.3119 | [7 empty] | 579.0308 | 37.8984 | 21944.3119 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 37.8984 | 37.8984 |  | 37.8984 | [9 empty] | Excavation ( W= 1.7 & d= 2.5 ) |  | M | 55.4475 |  | 55.4475 | 37.8984 | 2101.3675 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 23.5294 | 2.38 | 1.6107 | 90.1981
[22 empty] | Fuel | Material | LTR | 1.76 | 1.6807 | 1.0472 | 22.5495 | 39.6872
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 4.8 | 10 | 7.8955 | 378.9835
[22 empty] | Fuel | Material | LTR | 1.76 | 0.48 | 3.6667 | 78.9549 | 138.9606
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 0.75797 | 17.4332
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 2.2739 | 4.0021
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 23.5294 | 2.04 | 1.6107 | 77.3126
[22 empty] | Fuel | Material | LTR | 1.76 | 2.3529 | 0.748 | 16.1068 | 28.348
[22 empty] | Steel Shoring D=2.5 M | Material | M | 35 | 1 | 35 | 37.8984 | 1326.4423
[9 empty] | 37.8984 | 37.8984 |  | 37.8984 | [9 empty] | Pipe Laying & Protection |  | M | 518.5833 |  | 518.5833 | 37.8984 | 19653.4527 | 0 | 0 | 0 | 0 | 0
[22 empty] | GRP Pipe 700 mm | Material | M | 350 | 1 | 350 | 37.8984 | 13264.4225
[22 empty] | GRP Fitting 700 mm | Material | M | 35 | 1 | 35 | 37.8984 | 1326.4423
[22 empty] | Workmanship GRP pipe 700 mm | SC | M | 65 | 1 | 65 | 37.8984 | 2463.3928
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 5.8824 | 42.5 | 6.4427 | 1610.6799
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 5.8824 | 25.5 | 6.4427 | 966.4079
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.12633 | 22.1074
[9 empty] | 37.8984 | 37.8984 |  | 37.8984 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 37.8984 | 189.4918 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 37.8984 | 189.4918
SEW 10 |  | At a depth of 2.5 - 3.0 m | m | 3.91 | 793 | 3100.63 | 608.0072 | 2377.308 | 3.91 | 3.91 |  | 3.91 | 100% | 793 | 3100.63 | 608.0072 | 2377.308 |  | 2377.308 | [7 empty] | 608.0072 | 3.91 | 2377.308 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 3.91 | 3.91 |  | 3.91 | [9 empty] | Excavation ( W= 1.7 & d= 3.0 ) |  | M | 84.4238 |  | 84.4238 | 3.91 | 330.0972 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 19.6078 | 2.856 | 0.19941 | 11.167
[22 empty] | Fuel | Material | LTR | 1.76 | 1.4006 | 1.2566 | 2.7917 | 4.9135
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 4 | 12 | 0.9775 | 46.92
[22 empty] | Fuel | Material | LTR | 1.76 | 0.4 | 4.4 | 9.775 | 17.204
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 0.0782 | 1.7986
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 0.2346 | 0.4129
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 19.6078 | 2.448 | 0.19941 | 9.5717
[22 empty] | Fuel | Material | LTR | 1.76 | 1.9608 | 0.8976 | 1.9941 | 3.5096
[22 empty] | Steel Shoring D>3.0 M | Material | M | 60 | 1 | 60 | 3.91 | 234.6
[9 empty] | 3.91 | 3.91 |  | 3.91 | [9 empty] | Pipe Laying & Protection |  | M | 518.5833 |  | 518.5833 | 3.91 | 2027.6608 | 0 | 0 | 0 | 0 | 0
[22 empty] | GRP Pipe 700 mm | Material | M | 350 | 1 | 350 | 3.91 | 1368.5
[22 empty] | GRP Fitting 700 mm | Material | M | 35 | 1 | 35 | 3.91 | 136.85
[22 empty] | Workmanship GRP pipe 700 mm | SC | M | 65 | 1 | 65 | 3.91 | 254.15
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 5.8824 | 42.5 | 0.6647 | 166.175
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 5.8824 | 25.5 | 0.6647 | 99.705
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.013033 | 2.2808
[9 empty] | 3.91 | 3.91 |  | 3.91 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 3.91 | 19.55 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 3.91 | 19.55
SEW 10 |  | At a depth of 3.0 - 3.5 m | m |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | At a depth of 3.5 - 4.00 m | m | 12.8161 | 979 | 12546.9619 | 615.9599 | 7894.2039 | 12.8161 | 12.8161 |  | 12.8161 | 100% | 979 | 12546.9619 | 615.9599 | 7894.2039 |  | 7894.2039 | [7 empty] | 615.9599 | 12.8161 | 7894.2039 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 12.8161 | 12.8161 |  | 12.8161 | [9 empty] | Excavation ( W= 1.7 & d= 4.0 ) |  | M | 92.3766 |  | 92.3766 | 12.8161 | 1183.9076 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 14.7059 | 3.808 | 0.87149 | 48.8037
[22 empty] | Fuel | Material | LTR | 1.76 | 1.0504 | 1.6755 | 12.2009 | 21.4736
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 3 | 16 | 4.272 | 205.0576
[22 empty] | Fuel | Material | LTR | 1.76 | 0.3 | 5.8667 | 42.7203 | 75.1878
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 0.25632 | 5.8954
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 0.76897 | 1.3534
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 14.7059 | 3.264 | 0.87149 | 41.8318
[22 empty] | Fuel | Material | LTR | 1.76 | 1.4706 | 1.1968 | 8.7149 | 15.3383
[22 empty] | Steel Shoring D>3.0 M | Material | M | 60 | 1 | 60 | 12.8161 | 768.966
[9 empty] | 12.8161 | 12.8161 |  | 12.8161 | [9 empty] | Pipe Laying & Protection |  | M | 518.5833 |  | 518.5833 | 12.8161 | 6646.2159 | 0 | 0 | 0 | 0 | 0
[22 empty] | GRP Pipe 700 mm | Material | M | 350 | 1 | 350 | 12.8161 | 4485.635
[22 empty] | GRP Fitting 700 mm | Material | M | 35 | 1 | 35 | 12.8161 | 448.5635
[22 empty] | Workmanship GRP pipe 700 mm | SC | M | 65 | 1 | 65 | 12.8161 | 833.0465
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 5.8824 | 42.5 | 2.1787 | 544.6843
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 5.8824 | 25.5 | 2.1787 | 326.8106
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.04272 | 7.4761
[9 empty] | 12.8161 | 12.8161 |  | 12.8161 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 12.8161 | 64.0805 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 12.8161 | 64.0805
SEW 10 |  | At a depth of 4.0 - 4.5 m | m | 3.91 | 1017 | 3976.47 | 619.9363 | 2423.9509 | 3.91 | 3.91 |  | 3.91 | 100% | 1017 | 3976.47 | 619.9363 | 2423.9509 |  | 2423.9509 | [7 empty] | 619.9363 | 3.91 | 2423.9509 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 3.91 | 3.91 |  | 3.91 | [9 empty] | Excavation ( W= 1.7 & d= 4.5 ) |  | M | 96.353 |  | 96.353 | 3.91 | 376.7401 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 13.0719 | 4.284 | 0.29911 | 16.7504
[22 empty] | Fuel | Material | LTR | 1.76 | 0.93371 | 1.885 | 4.1876 | 7.3702
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 2.6667 | 18 | 1.4662 | 70.38
[22 empty] | Fuel | Material | LTR | 1.76 | 0.26667 | 6.6 | 14.6625 | 25.806
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 0.0782 | 1.7986
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 0.2346 | 0.4129
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 13.0719 | 3.672 | 0.29911 | 14.3575
[22 empty] | Fuel | Material | LTR | 1.76 | 1.3072 | 1.3464 | 2.9911 | 5.2644
[22 empty] | Steel Shoring D>3.0 M | Material | M | 60 | 1 | 60 | 3.91 | 234.6
[9 empty] | 3.91 | 3.91 |  | 3.91 | [9 empty] | Pipe Laying & Protection |  | M | 518.5833 |  | 518.5833 | 3.91 | 2027.6608 | 0 | 0 | 0 | 0 | 0
[22 empty] | GRP Pipe 700 mm | Material | M | 350 | 1 | 350 | 3.91 | 1368.5
[22 empty] | GRP Fitting 700 mm | Material | M | 35 | 1 | 35 | 3.91 | 136.85
[22 empty] | Workmanship GRP pipe 700 mm | SC | M | 65 | 1 | 65 | 3.91 | 254.15
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 5.8824 | 42.5 | 0.6647 | 166.175
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 5.8824 | 25.5 | 0.6647 | 99.705
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.013033 | 2.2808
[9 empty] | 3.91 | 3.91 |  | 3.91 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 3.91 | 19.55 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 3.91 | 19.55
SEW 10 |  | At a depth of 4.5 - 5.0 m | m | 3.91 | 1039 | 4062.49 | 638.3763 | 2496.0512 | 3.91 | 3.91 |  | 3.91 | 100% | 1039 | 4062.49 | 638.3763 | 2496.0512 |  | 2496.0512 | [7 empty] | 638.3763 | 3.91 | 2496.0512 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 3.91 | 3.91 |  | 3.91 | [9 empty] | Excavation ( W= 1.7 & d= 5.0 ) |  | M | 114.7929 |  | 114.7929 | 3.91 | 448.8404 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 50T | Machinery | HR | 131.2 | 9.4118 | 13.94 | 0.41544 | 54.5054
[22 empty] | Fuel | Material | LTR | 1.76 | 0.29412 | 5.984 | 13.294 | 23.3974
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 2.4 | 20 | 1.6292 | 78.2
[22 empty] | Fuel | Material | LTR | 1.76 | 0.24 | 7.3333 | 16.2917 | 28.6733
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 0.0782 | 1.7986
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 0.2346 | 0.4129
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 9.4118 | 5.1 | 0.41544 | 19.941
[22 empty] | Fuel | Material | LTR | 1.76 | 0.94118 | 1.87 | 4.1544 | 7.3117
[22 empty] | Steel Shoring D>3.0 M | Material | M | 60 | 1 | 60 | 3.91 | 234.6
[9 empty] | 3.91 | 3.91 |  | 3.91 | [9 empty] | Pipe Laying & Protection |  | M | 518.5833 |  | 518.5833 | 3.91 | 2027.6608 | 0 | 0 | 0 | 0 | 0
[22 empty] | GRP Pipe 700 mm | Material | M | 350 | 1 | 350 | 3.91 | 1368.5
[22 empty] | GRP Fitting 700 mm | Material | M | 35 | 1 | 35 | 3.91 | 136.85
[22 empty] | Workmanship GRP pipe 700 mm | SC | M | 65 | 1 | 65 | 3.91 | 254.15
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 5.8824 | 42.5 | 0.6647 | 166.175
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 5.8824 | 25.5 | 0.6647 | 99.705
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.013033 | 2.2808
[9 empty] | 3.91 | 3.91 |  | 3.91 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 3.91 | 19.55 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 3.91 | 19.55
SEW 10 |  | At a depth of 5.0 – 5.5 m | m | 56.4856 | 1080 | 61004.502 | 643.799 | 36365.405 | 56.4856 | 56.4856 |  | 56.4856 | 100% | 1080 | 61004.502 | 643.799 | 36365.405 |  | 36365.405 | [7 empty] | 643.799 | 56.4856 | 36365.405 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 56.4856 | 56.4856 |  | 56.4856 | [9 empty] | Excavation ( W= 1.7 & d= 5.5 ) |  | M | 120.2157 |  | 120.2157 | 56.4856 | 6790.4601 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 50T | Machinery | HR | 131.2 | 8.5561 | 15.334 | 6.6018 | 866.151
[22 empty] | Fuel | Material | LTR | 1.76 | 0.26738 | 6.5824 | 211.2563 | 371.8111
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 2.1818 | 22 | 25.8893 | 1242.6843
[22 empty] | Fuel | Material | LTR | 1.76 | 0.21818 | 8.0667 | 258.8926 | 455.6509
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 1.1297 | 25.9834
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 3.3891 | 5.9649
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 8.5561 | 5.61 | 6.6018 | 316.8845
[22 empty] | Fuel | Material | LTR | 1.76 | 0.85561 | 2.057 | 66.0176 | 116.191
[22 empty] | Steel Shoring D>3.0 M | Material | M | 60 | 1 | 60 | 56.4856 | 3389.139
[9 empty] | 56.4856 | 56.4856 |  | 56.4856 | [9 empty] | Pipe Laying & Protection |  | M | 518.5833 |  | 518.5833 | 56.4856 | 29292.5167 | 0 | 0 | 0 | 0 | 0
[22 empty] | GRP Pipe 700 mm | Material | M | 350 | 1 | 350 | 56.4856 | 19769.9775
[22 empty] | GRP Fitting 700 mm | Material | M | 35 | 1 | 35 | 56.4856 | 1976.9977
[22 empty] | Workmanship GRP pipe 700 mm | SC | M | 65 | 1 | 65 | 56.4856 | 3671.5672
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 5.8824 | 42.5 | 9.6026 | 2400.6401
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 5.8824 | 25.5 | 9.6026 | 1440.3841
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.18829 | 32.95
[9 empty] | 56.4856 | 56.4856 |  | 56.4856 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 56.4856 | 282.4282 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 56.4856 | 282.4282
SEW 10 |  | At a depth of 5.5 – 6.0 m | m | 48.951 | 1105 | 54090.855 | 649.2217 | 31780.0531 | 48.951 | 48.951 |  | 48.951 | 100% | 1105 | 54090.855 | 649.2217 | 31780.0531 |  | 31780.0531 | [7 empty] | 649.2217 | 48.951 | 31780.0531 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 48.951 | 48.951 |  | 48.951 | [9 empty] | Excavation ( W= 1.7 & d= 6.0 ) |  | M | 125.6384 |  | 125.6384 | 48.951 | 6150.1253 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 50T | Machinery | HR | 131.2 | 7.8431 | 16.728 | 6.2413 | 818.8523
[22 empty] | Fuel | Material | LTR | 1.76 | 0.2451 | 7.1808 | 199.7201 | 351.5073
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 2 | 24 | 24.4755 | 1174.824
[22 empty] | Fuel | Material | LTR | 1.76 | 0.2 | 8.8 | 244.755 | 430.7688
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 0.97902 | 22.5175
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 2.9371 | 5.1692
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 7.8431 | 6.12 | 6.2413 | 299.5801
[22 empty] | Fuel | Material | LTR | 1.76 | 0.78431 | 2.244 | 62.4125 | 109.846
[22 empty] | Steel Shoring D>3.0 M | Material | M | 60 | 1 | 60 | 48.951 | 2937.06
[9 empty] | 48.951 | 48.951 |  | 48.951 | [9 empty] | Pipe Laying & Protection |  | M | 518.5833 |  | 518.5833 | 48.951 | 25385.1727 | 0 | 0 | 0 | 0 | 0
[22 empty] | GRP Pipe 700 mm | Material | M | 350 | 1 | 350 | 48.951 | 17132.85
[22 empty] | GRP Fitting 700 mm | Material | M | 35 | 1 | 35 | 48.951 | 1713.285
[22 empty] | Workmanship GRP pipe 700 mm | SC | M | 65 | 1 | 65 | 48.951 | 3181.815
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 5.8824 | 42.5 | 8.3217 | 2080.4175
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 5.8824 | 25.5 | 8.3217 | 1248.2505
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.16317 | 28.5547
[9 empty] | 48.951 | 48.951 |  | 48.951 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 48.951 | 244.755 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 48.951 | 244.755
SEW 10 |  | At a depth of 6.0 – 6.5 m | m | 9.7688 | 1140 | 11136.432 | 654.6445 | 6395.0909 | 9.7688 | 9.7688 |  | 9.7688 | 100% | 1140 | 11136.432 | 654.6445 | 6395.0909 |  | 6395.0909 | [7 empty] | 654.6445 | 9.7688 | 6395.0909 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 9.7688 | 9.7688 |  | 9.7688 | [9 empty] | Excavation ( W= 1.7 & d= 6.5 ) |  | M | 131.0611 |  | 131.0611 | 9.7688 | 1280.31 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 50T | Machinery | HR | 131.2 | 7.2398 | 18.122 | 1.3493 | 177.0302
[22 empty] | Fuel | Material | LTR | 1.76 | 0.22624 | 7.7792 | 43.1781 | 75.9934
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 1.8462 | 26 | 5.2914 | 253.9888
[22 empty] | Fuel | Material | LTR | 1.76 | 0.18462 | 9.5333 | 52.9143 | 93.1292
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 0.19538 | 4.4936
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 0.58613 | 1.0316
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 7.2398 | 6.63 | 1.3493 | 64.7671
[22 empty] | Fuel | Material | LTR | 1.76 | 0.72398 | 2.431 | 13.4932 | 23.748
[22 empty] | Steel Shoring D>3.0 M | Material | M | 60 | 1 | 60 | 9.7688 | 586.128
[9 empty] | 9.7688 | 9.7688 |  | 9.7688 | [9 empty] | Pipe Laying & Protection |  | M | 518.5833 |  | 518.5833 | 9.7688 | 5065.9369 | 0 | 0 | 0 | 0 | 0
[22 empty] | GRP Pipe 700 mm | Material | M | 350 | 1 | 350 | 9.7688 | 3419.08
[22 empty] | GRP Fitting 700 mm | Material | M | 35 | 1 | 35 | 9.7688 | 341.908
[22 empty] | Workmanship GRP pipe 700 mm | SC | M | 65 | 1 | 65 | 9.7688 | 634.972
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 5.8824 | 42.5 | 1.6607 | 415.174
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 5.8824 | 25.5 | 1.6607 | 249.1044
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.032563 | 5.6985
[9 empty] | 9.7688 | 9.7688 |  | 9.7688 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 9.7688 | 48.844 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 9.7688 | 48.844
SEW 10 |  | At a depth of 6.5 – 7.0 m | m | 5.1006 | 1168 | 5957.5008 | 660.0672 | 3366.7388 | 5.1006 | 5.1006 |  | 5.1006 | 100% | 1168 | 5957.5008 | 660.0672 | 3366.7388 |  | 3366.7388 | [7 empty] | 660.0672 | 5.1006 | 3366.7388 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 5.1006 | 5.1006 |  | 5.1006 | [9 empty] | Excavation ( W= 1.7 & d= 7.0 ) |  | M | 136.4839 |  | 136.4839 | 5.1006 | 696.1496 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 50T | Machinery | HR | 131.2 | 6.7227 | 19.516 | 0.75871 | 99.5433
[22 empty] | Fuel | Material | LTR | 1.76 | 0.21008 | 8.3776 | 24.2789 | 42.7308
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 1.7143 | 28 | 2.9753 | 142.8168
[22 empty] | Fuel | Material | LTR | 1.76 | 0.17143 | 10.2667 | 29.7535 | 52.3662
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 0.10201 | 2.3463
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 0.30604 | 0.53862
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 6.7227 | 7.14 | 0.75871 | 36.4183
[22 empty] | Fuel | Material | LTR | 1.76 | 0.67227 | 2.618 | 7.5871 | 13.3534
[22 empty] | Steel Shoring D>3.0 M | Material | M | 60 | 1 | 60 | 5.1006 | 306.036
[9 empty] | 5.1006 | 5.1006 |  | 5.1006 | [9 empty] | Pipe Laying & Protection |  | M | 518.5833 |  | 518.5833 | 5.1006 | 2645.0861 | 0 | 0 | 0 | 0 | 0
[22 empty] | GRP Pipe 700 mm | Material | M | 350 | 1 | 350 | 5.1006 | 1785.21
[22 empty] | GRP Fitting 700 mm | Material | M | 35 | 1 | 35 | 5.1006 | 178.521
[22 empty] | Workmanship GRP pipe 700 mm | SC | M | 65 | 1 | 65 | 5.1006 | 331.539
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 5.8824 | 42.5 | 0.8671 | 216.7755
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 5.8824 | 25.5 | 0.8671 | 130.0653
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.017002 | 2.9753
[9 empty] | 5.1006 | 5.1006 |  | 5.1006 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 5.1006 | 25.503 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 5.1006 | 25.503
SEW 10 |  | Category (1): Pipe Works – Pipes (continued) (Force Mains) Supply, installation, connection, testing, and commissioning of HDPE force mains in the designated trenches, including: Excavation, backfilling, compaction, disposal of waste, dewatering, flushing, installation of concrete thrust blocks, all in accordance with the procedures of the competent authority, specifications, and drawings (the backfilling works beneath and around the force main shall be subject to separate measurement)
SEW 10 |  | HDPE force main, 315 mm diameter, at a depth of 1.5 – 2.0 m | m | 160.8167 | 481 | 77352.8567 | 238.5051 | 38355.616 | 160.8167 | 160.8167 |  | 160.8167 | 100% | 481 | 77352.8567 | 238.5051 | 38355.616 |  | 38355.616 | [7 empty] | 238.5051 | 160.8167 | 38355.616 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 160.8167 | 160.8167 |  | 160.8167 | [9 empty] | Excavation ( W= 1.0 & d= 2.0 ) |  | M | 9.9218 |  | 9.9218 | 160.8167 | 1595.5872 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 50 | 1.12 | 3.2163 | 180.1148
[22 empty] | Fuel | Material | LTR | 1.76 | 3.5714 | 0.4928 | 45.0287 | 79.2505
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 10.2 | 4.7059 | 15.7663 | 756.7847
[22 empty] | Fuel | Material | LTR | 1.76 | 1.02 | 1.7255 | 157.6635 | 277.4877
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 3.2163 | 73.9757
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 9.649 | 16.9822
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 50 | 0.96 | 3.2163 | 154.3841
[22 empty] | Fuel | Material | LTR | 1.76 | 5 | 0.352 | 32.1633 | 56.6075
[9 empty] | 160.8167 | 160.8167 |  | 160.8167 | [9 empty] | Pipe Laying & Protection |  | M | 223.5833 |  | 223.5833 | 160.8167 | 35955.945 | 0 | 0 | 0 | 0 | 0
[22 empty] | 315 mm solid HDPE Pipe DR 11 | Material | M | 145 | 1 | 145 | 160.8167 | 23318.4287
[22 empty] | 315 mm HDPE Pipe Installation | SC | M | 38 | 1 | 38 | 160.8167 | 6111.0365
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 10 | 25 | 16.0817 | 4020.4187
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 10 | 15 | 16.0817 | 2412.2512
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.53606 | 93.8098
[9 empty] | 160.8167 | 160.8167 |  | 160.8167 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 160.8167 | 804.0837 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 160.8167 | 804.0837
SEW 10 |  | HDPE force main, 315 mm diameter, at a depth of 2.0 – 2.5 m | m |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | HDPE force main, 315 mm diameter, at a depth of 2.5 – 3.0 m | m |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | HDPE force main, 630 mm diameter, at a depth of 2.0 – 2.5 m | m | 56.5305 | 1701 | 96158.3465 | 795.4121 | 44965.0298 | 56.5305 | 56.5305 |  | 56.5305 | 100% | 1701 | 96158.3465 | 795.4121 | 44965.0298 |  | 44965.0298 | [7 empty] | 795.4121 | 56.5305 | 44965.0298 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 56.5305 | 56.5305 |  | 56.5305 | [9 empty] | Excavation ( W= 1.63 & d= 2.5 ) |  | M | 54.6288 |  | 54.6288 | 56.5305 | 3088.1924 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 24.5399 | 2.282 | 2.3036 | 129.0026
[22 empty] | Fuel | Material | LTR | 1.76 | 1.7528 | 1.0041 | 32.2506 | 56.7611
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 5.0061 | 9.5882 | 11.2922 | 542.0275
[22 empty] | Fuel | Material | LTR | 1.76 | 0.50061 | 3.5157 | 112.9224 | 198.7434
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 1.1306 | 26.004
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 3.3918 | 5.9696
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 24.5399 | 1.956 | 2.3036 | 110.5736
[22 empty] | Fuel | Material | LTR | 1.76 | 2.454 | 0.7172 | 23.0362 | 40.5437
[22 empty] | Steel Shoring D=2.5 M | Material | M | 35 | 1 | 35 | 56.5305 | 1978.5668
[9 empty] | 56.5305 | 56.5305 |  | 56.5305 | [9 empty] | Pipe Laying & Protection |  | M | 735.7833 |  | 735.7833 | 56.5305 | 41594.185 | 0 | 0 | 0 | 0 | 0
[22 empty] | 630 mm solid HDPE Pipe DR 11 | Material | M | 610 | 1 | 610 | 56.5305 | 34483.5928
[22 empty] | 630 mm HDPE Pipe Installation | SC | M | 60 | 1 | 60 | 56.5305 | 3391.8288
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 6.135 | 40.75 | 9.2145 | 2303.6171
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 6.135 | 24.45 | 9.2145 | 1382.1702
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.18843 | 32.9761
[9 empty] | 56.5305 | 56.5305 |  | 56.5305 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 56.5305 | 282.6524 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 56.5305 | 282.6524
SEW 10 |  | HDPE force main, 630 mm diameter, at a depth of 2.5 – 3.0 m | m | 38.3045 | 2008 | 76915.381 | 824.2248 | 31571.4953 | 38.3045 | 38.3045 |  | 38.3045 | 100% | 2008 | 76915.381 | 824.2248 | 31571.4953 |  | 31571.4953 | [7 empty] | 824.2248 | 38.3045 | 31571.4953 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 38.3045 | 38.3045 |  | 38.3045 | [9 empty] | Excavation ( W= 1.63 & d= 3.0 ) |  | M | 83.4414 |  | 83.4414 | 38.3045 | 3196.1804 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 20.4499 | 2.7384 | 1.8731 | 104.893
[22 empty] | Fuel | Material | LTR | 1.76 | 1.4607 | 1.2049 | 26.2232 | 46.1529
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 4.1718 | 11.5059 | 9.1818 | 440.7268
[22 empty] | Fuel | Material | LTR | 1.76 | 0.41718 | 4.2188 | 91.8181 | 161.5998
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 0.76609 | 17.6201
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 2.2983 | 4.045
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 20.4499 | 2.3472 | 1.8731 | 89.9083
[22 empty] | Fuel | Material | LTR | 1.76 | 2.045 | 0.86064 | 18.7309 | 32.9664
[22 empty] | Steel Shoring D>3.0 M | Material | M | 60 | 1 | 60 | 38.3045 | 2298.2684
[9 empty] | 38.3045 | 38.3045 |  | 38.3045 | [9 empty] | Pipe Laying & Protection |  | M | 735.7833 |  | 735.7833 | 38.3045 | 28183.7925 | 0 | 0 | 0 | 0 | 0
[22 empty] | 630 mm solid HDPE Pipe DR 11 | Material | M | 610 | 1 | 610 | 38.3045 | 23365.7283
[22 empty] | 630 mm HDPE Pipe Installation | SC | M | 60 | 1 | 60 | 38.3045 | 2298.2684
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 6.135 | 40.75 | 6.2436 | 1560.9073
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 6.135 | 24.45 | 6.2436 | 936.5444
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.12768 | 22.3443
[9 empty] | 38.3045 | 38.3045 |  | 38.3045 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 38.3045 | 191.5224 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 38.3045 | 191.5224
SEW 10 |  | Depth variation increase of 0.5 m for 630 mm diameter HDPE force main | m | 2.1842 | 1553 | 3392.0005 | 4.3782 | 9.5628 | 2.1842 | 2.1842 |  | 2.1842 | 100% | 1553 | 3392.0005 | 4.3782 | 9.5628 |  | 9.5628 | [7 empty] | 4.3782 | 2.1842 | 9.5628 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 2.1842 | 2.1842 |  | 2.1842 | [9 empty] | Excavation ( W= 1.63 & d= 0.5 ) |  | M | 4.3782 |  | 4.3782 | 2.1842 | 9.5628 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 122.6994 | 0.4564 | 0.017801 | 0.99685
[22 empty] | Fuel | Material | LTR | 1.76 | 8.7642 | 0.20082 | 0.24921 | 0.43861
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 25.0307 | 1.9176 | 0.087259 | 4.1884
[22 empty] | Fuel | Material | LTR | 1.76 | 2.5031 | 0.70314 | 0.87259 | 1.5358
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 0.043683 | 1.0047
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 0.13105 | 0.23065
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 122.6994 | 0.3912 | 0.017801 | 0.85444
[22 empty] | Fuel | Material | LTR | 1.76 | 12.2699 | 0.14344 | 0.17801 | 0.3133
SEW 10 |  | Depth variation increase of 1.0 m for 630 mm diameter HDPE force main | m | 3.3194 | 1644 | 5457.1594 | 8.1909 | 27.1891 | 3.3194 | 3.3194 |  | 3.3194 | 100% | 1644 | 5457.1594 | 8.1909 | 27.1891 |  | 27.1891 | [7 empty] | 8.1909 | 3.3194 | 27.1891 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 3.3194 | 3.3194 |  | 3.3194 | [9 empty] | Excavation ( W= 1.63 & d= 1.0 ) |  | M | 8.1909 |  | 8.1909 | 3.3194 | 27.1891 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 61.3497 | 0.9128 | 0.054107 | 3.03
[22 empty] | Fuel | Material | LTR | 1.76 | 4.3821 | 0.40163 | 0.7575 | 1.3332
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 12.5153 | 3.8353 | 0.26523 | 12.731
[22 empty] | Fuel | Material | LTR | 1.76 | 1.2515 | 1.4063 | 2.6523 | 4.668
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 0.066389 | 1.5269
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 0.19917 | 0.35053
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 61.3497 | 0.7824 | 0.054107 | 2.5971
[22 empty] | Fuel | Material | LTR | 1.76 | 6.135 | 0.28688 | 0.54107 | 0.95228
SEW 10 |  | Depth variation increase of 1.5 m for 630 mm diameter HDPE force main | m |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | HDPE force main, 250 mm diameter, at a depth of 2.0 – 2.5 m | m | 608.516 | 296 | 180120.7466 | 217.8441 | 132561.658 | 608.516 | 608.516 |  | 608.516 | 100% | 296 | 180120.7466 | 217.8441 | 132561.658 |  | 132561.658 | [7 empty] | 217.8441 | 608.516 | 132561.658 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 608.516 | 608.516 |  | 608.516 | [9 empty] | Excavation ( W= 1.0 & d= 2.5 ) |  | M | 47.2608 |  | 47.2608 | 608.516 | 28758.9642 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 40 | 1.4 | 15.2129 | 851.9224
[22 empty] | Fuel | Material | LTR | 1.76 | 2.8571 | 0.616 | 212.9806 | 374.8459
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 8.16 | 5.8824 | 74.573 | 3579.5061
[22 empty] | Fuel | Material | LTR | 1.76 | 0.816 | 2.1569 | 745.7304 | 1312.4856
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 12.1703 | 279.9174
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 36.511 | 64.2593
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 40 | 1.2 | 15.2129 | 730.2192
[22 empty] | Fuel | Material | LTR | 1.76 | 4 | 0.44 | 152.129 | 267.7471
[22 empty] | Steel Shoring D=2.5 M | Material | M | 35 | 1 | 35 | 608.516 | 21298.0612
[9 empty] | 608.516 | 608.516 |  | 608.516 | [9 empty] | Pipe Laying & Protection |  | M | 165.5833 |  | 165.5833 | 608.516 | 100760.1136 | 0 | 0 | 0 | 0 | 0
[22 empty] | 250 mm solid HDPE Pipe DR 11 | Material | M | 95 | 1 | 95 | 608.516 | 57809.0234
[22 empty] | 250 mm HDPE Pipe Installation | SC | M | 30 | 1 | 30 | 608.516 | 18255.4811
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 10 | 25 | 60.8516 | 15212.9009
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 10 | 15 | 60.8516 | 9127.7405
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 2.0284 | 354.9677
[9 empty] | 608.516 | 608.516 |  | 608.516 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 608.516 | 3042.5802 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 608.516 | 3042.5802
SEW 10 |  | HDPE force main, 250 mm diameter, at a depth of 2.5 – 3.0 m | m |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | Depth variation increase of 0.5 m for 250 mm diameter HDPE force main | m |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | Depth variation increase of 1.0 m for 250 mm diameter HDPE force main | m |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | HDPE force main, 200 mm diameter, at a depth of 2.0 – 2.5 m | m |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | HDPE force main, 200 mm diameter, at a depth of 2.5 – 3.0 m | m |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | HDPE force main, 280 mm diameter, at a depth of 1.5 – 2.0 m | m | 208.489 | 345 | 71928.705 | 198.5051 | 41386.131 | 208.489 | 208.489 |  | 208.489 | 100% | 345 | 71928.705 | 198.5051 | 41386.131 |  | 41386.131 | [7 empty] | 198.5051 | 208.489 | 41386.131 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 208.489 | 208.489 |  | 208.489 | [9 empty] | Excavation ( W= 1.0 & d= 2.0 ) |  | M | 9.9218 |  | 9.9218 | 208.489 | 2068.5804 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 50 | 1.12 | 4.1698 | 233.5077
[22 empty] | Fuel | Material | LTR | 1.76 | 3.5714 | 0.4928 | 58.3769 | 102.7434
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 10.2 | 4.7059 | 20.4401 | 981.1247
[22 empty] | Fuel | Material | LTR | 1.76 | 1.02 | 1.7255 | 204.401 | 359.7457
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 4.1698 | 95.9049
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 12.5093 | 22.0164
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 50 | 0.96 | 4.1698 | 200.1494
[22 empty] | Fuel | Material | LTR | 1.76 | 5 | 0.352 | 41.6978 | 73.3881
[9 empty] | 208.489 | 208.489 |  | 208.489 | [9 empty] | Pipe Laying & Protection |  | M | 183.5833 |  | 183.5833 | 208.489 | 38275.1056 | 0 | 0 | 0 | 0 | 0
[22 empty] | 280 mm solid HDPE Pipe DR 11 | Material | M | 110 | 1 | 110 | 208.489 | 22933.79
[22 empty] | 280 mm HDPE Pipe Installation | SC | M | 33 | 1 | 33 | 208.489 | 6880.137
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 10 | 25 | 20.8489 | 5212.225
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 10 | 15 | 20.8489 | 3127.335
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.69496 | 121.6186
[9 empty] | 208.489 | 208.489 |  | 208.489 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 208.489 | 1042.445 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 208.489 | 1042.445
SEW 10 |  | HDPE force main, 280 mm diameter, at a depth of 2.0 – 2.5 m | m | 57.438 | 369 | 21194.622 | 235.8441 | 13546.4162 | 57.438 | 57.438 |  | 57.438 | 100% | 369 | 21194.622 | 235.8441 | 13546.4162 |  | 13546.4162 | [7 empty] | 235.8441 | 57.438 | 13546.4162 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 57.438 | 57.438 |  | 57.438 | [9 empty] | Excavation ( W= 1.0 & d= 2.5 ) |  | M | 47.2608 |  | 47.2608 | 57.438 | 2714.5667 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 40 | 1.4 | 1.4359 | 80.4132
[22 empty] | Fuel | Material | LTR | 1.76 | 2.8571 | 0.616 | 20.1033 | 35.3818
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 8.16 | 5.8824 | 7.039 | 337.8706
[22 empty] | Fuel | Material | LTR | 1.76 | 0.816 | 2.1569 | 70.3897 | 123.8859
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 1.1488 | 26.4215
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 3.4463 | 6.0655
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 40 | 1.2 | 1.4359 | 68.9256
[22 empty] | Fuel | Material | LTR | 1.76 | 4 | 0.44 | 14.3595 | 25.2727
[22 empty] | Steel Shoring D=2.5 M | Material | M | 35 | 1 | 35 | 57.438 | 2010.33
[9 empty] | 57.438 | 57.438 |  | 57.438 | [9 empty] | Pipe Laying & Protection |  | M | 183.5833 |  | 183.5833 | 57.438 | 10544.6595 | 0 | 0 | 0 | 0 | 0
[22 empty] | 280 mm solid HDPE Pipe DR 11 | Material | M | 110 | 1 | 110 | 57.438 | 6318.18
[22 empty] | 280 mm HDPE Pipe Installation | SC | M | 33 | 1 | 33 | 57.438 | 1895.454
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 10 | 25 | 5.7438 | 1435.95
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 10 | 15 | 5.7438 | 861.57
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.19146 | 33.5055
[9 empty] | 57.438 | 57.438 |  | 57.438 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 57.438 | 287.19 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 57.438 | 287.19
SEW 10 |  | HDPE force main, 280 mm diameter, at a depth of 2.5 – 3.0 m | m | 28.845 | 493 | 14220.585 | 263.1832 | 7591.5192 | 28.845 | 28.845 |  | 28.845 | 100% | 493 | 14220.585 | 263.1832 | 7591.5192 |  | 7591.5192 | [7 empty] | 263.1832 | 28.845 | 7591.5192 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 28.845 | 28.845 |  | 28.845 | [9 empty] | Excavation ( W= 1.0 & d= 3.0 ) |  | M | 74.5999 |  | 74.5999 | 28.845 | 2151.8329 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 33.3333 | 1.68 | 0.86535 | 48.4596
[22 empty] | Fuel | Material | LTR | 1.76 | 2.381 | 0.7392 | 12.1149 | 21.3222
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 6.8 | 7.0588 | 4.2419 | 203.6118
[22 empty] | Fuel | Material | LTR | 1.76 | 0.68 | 2.5882 | 42.4191 | 74.6576
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 0.5769 | 13.2687
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 1.7307 | 3.046
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 33.3333 | 1.44 | 0.86535 | 41.5368
[22 empty] | Fuel | Material | LTR | 1.76 | 3.3333 | 0.528 | 8.6535 | 15.2302
[22 empty] | Steel Shoring D>3.0 M | Material | M | 60 | 1 | 60 | 28.845 | 1730.7
[9 empty] | 28.845 | 28.845 |  | 28.845 | [9 empty] | Pipe Laying & Protection |  | M | 183.5833 |  | 183.5833 | 28.845 | 5295.4612 | 0 | 0 | 0 | 0 | 0
[22 empty] | 280 mm solid HDPE Pipe DR 11 | Material | M | 110 | 1 | 110 | 28.845 | 3172.95
[22 empty] | 280 mm HDPE Pipe Installation | SC | M | 33 | 1 | 33 | 28.845 | 951.885
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 10 | 25 | 2.8845 | 721.125
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 10 | 15 | 2.8845 | 432.675
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.09615 | 16.8262
[9 empty] | 28.845 | 28.845 |  | 28.845 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 28.845 | 144.225 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 28.845 | 144.225
SEW 10 |  | HDPE force main, 355 mm diameter, at a depth of 2.0 – 2.5 m | m |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | HDPE force main, 355 mm diameter, at a depth of 2.5 – 3.0 m | m |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | HDPE force main, 500 mm diameter, at a depth of 1.5 – 2.0 m | m | 25.5901 | 1133 | 28993.5833 | 480.1832 | 12287.9359 | 25.5901 | 25.5901 |  | 25.5901 | 100% | 1133 | 28993.5833 | 480.1832 | 12287.9359 |  | 12287.9359 | [7 empty] | 480.1832 | 25.5901 | 12287.9359 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 25.5901 | 25.5901 |  | 25.5901 | [9 empty] | Excavation ( W= 1.5 & d= 2.0 ) |  | M | 14.5999 |  | 14.5999 | 25.5901 | 373.6118 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 33.3333 | 1.68 | 0.7677 | 42.9914
[22 empty] | Fuel | Material | LTR | 1.76 | 2.381 | 0.7392 | 10.7478 | 18.9162
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 6.8 | 7.0588 | 3.7632 | 180.636
[22 empty] | Fuel | Material | LTR | 1.76 | 0.68 | 2.5882 | 37.6325 | 66.2332
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 0.5118 | 11.7714
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 1.5354 | 2.7023
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 33.3333 | 1.44 | 0.7677 | 36.8497
[22 empty] | Fuel | Material | LTR | 1.76 | 3.3333 | 0.528 | 7.677 | 13.5116
[9 empty] | 25.5901 | 25.5901 |  | 25.5901 | [9 empty] | Pipe Laying & Protection |  | M | 460.5833 |  | 460.5833 | 25.5901 | 11786.3736 | 0 | 0 | 0 | 0 | 0
[22 empty] | 500 mm solid HDPE Pipe DR 11 | Material | M | 345 | 1 | 345 | 25.5901 | 8828.5845
[22 empty] | 500 mm HDPE Pipe Installation | SC | M | 55 | 1 | 55 | 25.5901 | 1407.4555
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 6.6667 | 37.5 | 3.8385 | 959.6287
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 6.6667 | 22.5 | 3.8385 | 575.7772
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.0853 | 14.9276
[9 empty] | 25.5901 | 25.5901 |  | 25.5901 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 25.5901 | 127.9505 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 25.5901 | 127.9505
SEW 10 |  | HDPE force main, 500 mm diameter, at a depth of 2.0 – 2.5 m | m | 70.8772 | 1152 | 81650.4768 | 518.6918 | 36763.3935 | 70.8772 | 70.8772 |  | 70.8772 | 100% | 1152 | 81650.4768 | 518.6918 | 36763.3935 |  | 36763.3935 | [7 empty] | 518.6918 | 70.8772 | 36763.3935 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 70.8772 | 70.8772 |  | 70.8772 | [9 empty] | Excavation ( W= 1.5 & d= 2.5 ) |  | M | 53.1084 |  | 53.1084 | 70.8772 | 3764.1737 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 26.6667 | 2.1 | 2.6579 | 148.842
[22 empty] | Fuel | Material | LTR | 1.76 | 1.9048 | 0.924 | 37.2105 | 65.4905
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 5.44 | 8.8235 | 13.0289 | 625.3866
[22 empty] | Fuel | Material | LTR | 1.76 | 0.544 | 3.2353 | 130.2889 | 229.3084
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 1.4175 | 32.6035
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 4.2526 | 7.4846
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 26.6667 | 1.8 | 2.6579 | 127.5789
[22 empty] | Fuel | Material | LTR | 1.76 | 2.6667 | 0.66 | 26.5789 | 46.7789
[22 empty] | Steel Shoring D=2.5 M | Material | M | 35 | 1 | 35 | 70.8772 | 2480.7003
[9 empty] | 70.8772 | 70.8772 |  | 70.8772 | [9 empty] | Pipe Laying & Protection |  | M | 460.5833 |  | 460.5833 | 70.8772 | 32644.834 | 0 | 0 | 0 | 0 | 0
[22 empty] | 500 mm solid HDPE Pipe DR 11 | Material | M | 345 | 1 | 345 | 70.8772 | 24452.6168
[22 empty] | 500 mm HDPE Pipe Installation | SC | M | 55 | 1 | 55 | 70.8772 | 3898.2433
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 6.6667 | 37.5 | 10.6316 | 2657.8931
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 6.6667 | 22.5 | 10.6316 | 1594.7359
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.23626 | 41.345
[9 empty] | 70.8772 | 70.8772 |  | 70.8772 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 70.8772 | 354.3858 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 70.8772 | 354.3858
SEW 10 |  | HDPE force main, 500 mm diameter, at a depth of 2.50 – 3.00 m | m | 25.3732 | 1282 | 32528.4552 | 547.2003 | 13884.2287 | 25.3732 | 25.3732 |  | 25.3732 | 100% | 1282 | 32528.4552 | 547.2003 | 13884.2287 |  | 13884.2287 | [7 empty] | 547.2003 | 25.3732 | 13884.2287 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 25.3732 | 25.3732 |  | 25.3732 | [9 empty] | Excavation ( W= 1.5 & d= 3.0 ) |  | M | 81.617 |  | 81.617 | 25.3732 | 2070.885 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 22.2222 | 2.52 | 1.1418 | 63.9405
[22 empty] | Fuel | Material | LTR | 1.76 | 1.5873 | 1.1088 | 15.9851 | 28.1338
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 4.5333 | 10.5882 | 5.597 | 268.6575
[22 empty] | Fuel | Material | LTR | 1.76 | 0.45333 | 3.8824 | 55.9703 | 98.5078
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 0.50746 | 11.6717
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 1.5224 | 2.6794
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 22.2222 | 2.16 | 1.1418 | 54.8061
[22 empty] | Fuel | Material | LTR | 1.76 | 2.2222 | 0.792 | 11.4179 | 20.0956
[22 empty] | Steel Shoring D>3.0 M | Material | M | 60 | 1 | 60 | 25.3732 | 1522.3926
[9 empty] | 25.3732 | 25.3732 |  | 25.3732 | [9 empty] | Pipe Laying & Protection |  | M | 460.5833 |  | 460.5833 | 25.3732 | 11686.4776 | 0 | 0 | 0 | 0 | 0
[22 empty] | 500 mm solid HDPE Pipe DR 11 | Material | M | 345 | 1 | 345 | 25.3732 | 8753.7575
[22 empty] | 500 mm HDPE Pipe Installation | SC | M | 55 | 1 | 55 | 25.3732 | 1395.5266
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 6.6667 | 37.5 | 3.806 | 951.4954
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 6.6667 | 22.5 | 3.806 | 570.8972
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.084577 | 14.801
[9 empty] | 25.3732 | 25.3732 |  | 25.3732 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 25.3732 | 126.8661 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 25.3732 | 126.8661
SEW 10 |  | HDPE force main, 500 mm diameter, at a depth of 3.0 – 3.5 m | m | 7.6446 | 1310 | 10014.3736 | 550.7089 | 4209.9271 | 7.6446 | 7.6446 |  | 7.6446 | 100% | 1310 | 10014.3736 | 550.7089 | 4209.9271 |  | 4209.9271 | [7 empty] | 550.7089 | 7.6446 | 4209.9271 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 7.6446 | 7.6446 |  | 7.6446 | [9 empty] | Excavation ( W= 1.5 & d= 3.5 ) |  | M | 85.1256 |  | 85.1256 | 7.6446 | 650.7474 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 19.0476 | 2.94 | 0.40134 | 22.475
[22 empty] | Fuel | Material | LTR | 1.76 | 1.3605 | 1.2936 | 5.6188 | 9.889
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 3.8857 | 12.3529 | 1.9674 | 94.4328
[22 empty] | Fuel | Material | LTR | 1.76 | 0.38857 | 4.5294 | 19.6735 | 34.6254
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 0.15289 | 3.5165
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 0.45867 | 0.80727
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 19.0476 | 2.52 | 0.40134 | 19.2643
[22 empty] | Fuel | Material | LTR | 1.76 | 1.9048 | 0.924 | 4.0134 | 7.0636
[22 empty] | Steel Shoring D>3.0 M | Material | M | 60 | 1 | 60 | 7.6446 | 458.6736
[9 empty] | 7.6446 | 7.6446 |  | 7.6446 | [9 empty] | Pipe Laying & Protection |  | M | 460.5833 |  | 460.5833 | 7.6446 | 3520.9569 | 0 | 0 | 0 | 0 | 0
[22 empty] | 500 mm solid HDPE Pipe DR 11 | Material | M | 345 | 1 | 345 | 7.6446 | 2637.3732
[22 empty] | 500 mm HDPE Pipe Installation | SC | M | 55 | 1 | 55 | 7.6446 | 420.4508
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 6.6667 | 37.5 | 1.1467 | 286.671
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 6.6667 | 22.5 | 1.1467 | 172.0026
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.025482 | 4.4593
[9 empty] | 7.6446 | 7.6446 |  | 7.6446 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 7.6446 | 38.2228 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 7.6446 | 38.2228
SEW 10 |  | HDPE force main, 500 mm diameter, at a depth of 3.5 – 4.0 m | m | 11.618 | 1460 | 16962.3384 | 554.2175 | 6438.9205 | 11.618 | 11.618 |  | 11.618 | 100% | 1460 | 16962.3384 | 554.2175 | 6438.9205 |  | 6438.9205 | [7 empty] | 554.2175 | 11.618 | 6438.9205 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 11.618 | 11.618 |  | 11.618 | [9 empty] | Excavation ( W= 1.5 & d= 4.0 ) |  | M | 88.6341 |  | 88.6341 | 11.618 | 1029.7547 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 16.6667 | 3.36 | 0.69708 | 39.0366
[22 empty] | Fuel | Material | LTR | 1.76 | 1.1905 | 1.4784 | 9.7592 | 17.1761
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 3.4 | 14.1176 | 3.4171 | 164.0194
[22 empty] | Fuel | Material | LTR | 1.76 | 0.34 | 5.1765 | 34.1707 | 60.1404
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 0.23236 | 5.3443
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 0.69708 | 1.2269
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 16.6667 | 2.88 | 0.69708 | 33.46
[22 empty] | Fuel | Material | LTR | 1.76 | 1.6667 | 1.056 | 6.9708 | 12.2687
[22 empty] | Steel Shoring D>3.0 M | Material | M | 60 | 1 | 60 | 11.618 | 697.0824
[9 empty] | 11.618 | 11.618 |  | 11.618 | [9 empty] | Pipe Laying & Protection |  | M | 460.5833 |  | 460.5833 | 11.618 | 5351.0756 | 0 | 0 | 0 | 0 | 0
[22 empty] | 500 mm solid HDPE Pipe DR 11 | Material | M | 345 | 1 | 345 | 11.618 | 4008.2238
[22 empty] | 500 mm HDPE Pipe Installation | SC | M | 55 | 1 | 55 | 11.618 | 638.9922
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 6.6667 | 37.5 | 1.7427 | 435.6765
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 6.6667 | 22.5 | 1.7427 | 261.4059
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.038727 | 6.7772
[9 empty] | 11.618 | 11.618 |  | 11.618 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 11.618 | 58.0902 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 11.618 | 58.0902
SEW 10 |  | Supply and installation of installation parts and accessories for HDPE polyethylene pipes in accordance with the procedures of the competent authorities, specifications and plans. |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | Elbow 11.25°, diameter 315 mm | nr |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | Elbow 33°, diameter 315 mm | nr |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | Elbow 90°, diameter 315 mm | nr | 1.075 | 2002 | 2152.15 | 915.7143 | 984.3929 | 1.075 | 1.075 |  | 1.075 | 100% | 2002 | 2152.15 | 915.7143 | 984.3929 |  | 984.3929 | [7 empty] | 915.7143 | 1.075 | 984.3929 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 1.075 | 1.075 |  | 1.075 | [9 empty] | Supply & Install fittings |  | Ea | 915.7143 |  | 915.7143 | 1.075 | 984.3929 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply 90° elbow, diameter 315 mm | Material | Ea | 830 | 1 | 830 | 1.075 | 892.25
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.35 | 48.5714 | 3.0714 | 52.2143
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.35 | 37.1429 | 3.0714 | 39.9286
SEW 10 |  | Elbow 11.25°, diameter 630 mm | nr |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | Elbow 33°, diameter 630 mm | nr |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | Elbow 90°, diameter 630 mm | nr | 0.15 | 3562 | 534.3 | 2520 | 378 | 0.15 | 0.15 |  | 0.15 | 100% | 3562 | 534.3 | 2520 | 378 |  | 378 | [7 empty] | 2520 | 0.15 | 378 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 0.15 | 0.15 |  | 0.15 | [9 empty] | Supply & Install fittings |  | Ea | 2520 |  | 2520 | 0.15 | 378 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Elbow 90°, diameter 630mm | Material | Ea | 2370 | 1 | 2370 | 0.15 | 355.5
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.2 | 85 | 0.75 | 12.75
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.2 | 65 | 0.75 | 9.75
SEW 10 |  | Elbow 11.25°, diameter 355 mm | nr |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | Elbow 33°, diameter 355 mm | nr |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | Elbow 90°, diameter 355 mm | nr |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | Elbow 45°, diameter 280 mm | nr | 4.9 | 1743 | 8540.7 | 880 | 4312 | 4.9 | 4.9 |  | 4.9 | 100% | 1743 | 8540.7 | 880 | 4312 |  | 4312 | [7 empty] | 880 | 4.9 | 4312 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 4.9 | 4.9 |  | 4.9 | [9 empty] | Supply & Install fittings |  | Ea | 880 |  | 880 | 4.9 | 4312 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Elbow 45°, diameter 280mm | Material | Ea | 820 | 1 | 820 | 4.9 | 4018
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.5 | 34 | 9.8 | 166.6
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.5 | 26 | 9.8 | 127.4
SEW 10 |  | 90° elbow, diameter 280 mm | nr | 2.15 | 1806 | 3882.9 | 921 | 1980.15 | 2.15 | 2.15 |  | 2.15 | 100% | 1806 | 3882.9 | 921 | 1980.15 |  | 1980.15 | [7 empty] | 921 | 2.15 | 1980.15 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 2.15 | 2.15 |  | 2.15 | [9 empty] | Supply & Install fittings |  | Ea | 921 |  | 921 | 2.15 | 1980.15 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Elbow 90°, diameter 280mm | Material | Ea | 861 | 1 | 861 | 2.15 | 1851.15
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.5 | 34 | 4.3 | 73.1
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.5 | 26 | 4.3 | 55.9
SEW 10 |  | Elbow 11.25°, diameter 250 mm | nr | 12 | 1567 | 18804 | 360 | 4320 | 12 | 12 |  | 12 | 100% | 1567 | 18804 | 360 | 4320 |  | 4320 | [7 empty] | 360 | 12 | 4320 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 12 | 12 |  | 12 | [9 empty] | Supply & Install fittings |  | Ea | 360 |  | 360 | 12 | 4320 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Elbow 11.25°, diameter 250 mm | Material | Ea | 300 | 1 | 300 | 12 | 3600
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.5 | 34 | 24 | 408
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.5 | 26 | 24 | 312
SEW 10 |  | Elbow 33°, diameter 250 mm | nr |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | Elbow 90°, diameter 250 mm | nr | 3.1 | 1567 | 4857.7 | 415 | 1286.5 | 3.1 | 3.1 |  | 3.1 | 100% | 1567 | 4857.7 | 415 | 1286.5 |  | 1286.5 | [7 empty] | 415 | 3.1 | 1286.5 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 3.1 | 3.1 |  | 3.1 | [9 empty] | Supply & Install fittings |  | Ea | 415 |  | 415 | 3.1 | 1286.5 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply 90° elbow, diameter 250 mm | Material | Ea | 355 | 1 | 355 | 3.1 | 1100.5
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.5 | 34 | 6.2 | 105.4
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.5 | 26 | 6.2 | 80.6
SEW 10 |  | Elbow 11.25°, diameter 200 mm | nr |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | Elbow 33°, diameter 200 mm | nr |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | Elbow 90°, diameter 200 mm | nr |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | Elbow 45°, diameter 500 mm | nr | 1.05 | 3499 | 3673.95 | 1957 | 2054.85 | 1.05 | 1.05 |  | 1.05 | 100% | 3499 | 3673.95 | 1957 | 2054.85 |  | 2054.85 | [7 empty] | 1957 | 1.05 | 2054.85 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 1.05 | 1.05 |  | 1.05 | [9 empty] | Supply & Install fittings |  | Ea | 1957 |  | 1957 | 1.05 | 2054.85 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Elbow 45°, diameter 500mm | Material | Ea | 1857 | 1 | 1857 | 1.05 | 1949.85
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.3 | 56.6667 | 3.5 | 59.5
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.3 | 43.3333 | 3.5 | 45.5
SEW 10 |  | Elbow 90°, diameter 500 mm | nr | 0.15 | 3537 | 530.55 | 2000 | 300 | 0.15 | 0.15 |  | 0.15 | 100% | 3537 | 530.55 | 2000 | 300 |  | 300 | [7 empty] | 2000 | 0.15 | 300 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 0.15 | 0.15 |  | 0.15 | [9 empty] | Supply & Install fittings |  | Ea | 2000 |  | 2000 | 0.15 | 300 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Elbow 90°, diameter 500mm | Material | Ea | 1900 | 1 | 1900 | 0.15 | 285
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.3 | 56.6667 | 0.5 | 8.5
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.3 | 43.3333 | 0.5 | 6.5
SEW 10 |  | Measurement difference between 45° elbow, diameter 250 mm and 11.25° elbow, diameter 250 mm | nr | 12 | 1598 | 19176 | 395.4 | 4744.8 | 12 | 12 |  | 12 | 100% | 1598 | 19176 | 395.4 | 4744.8 |  | 4744.8 | [7 empty] | 395.4 | 12 | 4744.8 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 12 | 12 |  | 12 | [9 empty] | Supply & Install fittings |  | Ea | 395.4 |  | 395.4 | 12 | 4744.8 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Elbow 45°, diameter 250 mm | Material | Ea | 335.4 | 1 | 335.4 | 12 | 4024.8
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.5 | 34 | 24 | 408
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.5 | 26 | 24 | 312
SEW 10 |  | Measurement difference between 45° elbow, diameter 250 mm and 33° elbow, diameter 250 mm | nr |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | Supply, installation and testing of valves, metal connections, nuts, bolts, piping work inside the room and any other accessories according to the specifications, plans and standards of the competent authorities (rooms are measured separately) |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | Gate lock valve on a 315 mm diameter pipe | nr | 0.2 | 6218 | 1243.6 | 2620 | 524 | 0.2 | 0.2 |  | 0.2 | 100% | 6218 | 1243.6 | 2620 | 524 |  | 524 | [7 empty] | 2620 | 0.2 | 524 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 0.2 | 0.2 |  | 0.2 | [9 empty] | Supply & Install Valves |  | Ea | 2620 |  | 2620 | 0.2 | 524 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Gate Valve 315 MM | Material | Ea | 2200 | 1 | 2200 | 0.2 | 440
[22 empty] | Fitting and Accessories 315 | Material | Ea | 220 | 1 | 220 | 0.2 | 44
[22 empty] | Installation Valve 315mm | SC | Ea | 200 | 1 | 200 | 0.2 | 40
SEW 10 |  | Gate lock valve on 500mm diameter pipe | nr | 2 | 9328 | 18656 | 9431 | 18862 | 2 | 2 |  | 2 | 100% | 9328 | 18656 | 9431 | 18862 |  | 18862 | [7 empty] | 9431 | 2 | 18862 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 2 | 2 |  | 2 | [9 empty] | Supply & Install Valves |  | Ea | 9431 |  | 9431 | 2 | 18862 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Butterfly Valve 500 MM | Material | Ea | 7210 | 1 | 7210 | 2 | 14420
[22 empty] | Fitting and Accessories 500 | Material | Ea | 721 | 1 | 721 | 2 | 1442
[22 empty] | Installation Valve 500mm | SC | Ea | 1500 | 1 | 1500 | 2 | 3000
SEW 10 |  | Gate lock valve on a 630 mm diameter pipe | nr | 2 | 10070 | 20140 | 12225 | 24450 | 2 | 2 |  | 2 | 100% | 10070 | 20140 | 12225 | 24450 |  | 24450 | [7 empty] | 12225 | 2 | 24450 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 2 | 2 |  | 2 | [9 empty] | Supply & Install Valves |  | Ea | 12225 |  | 12225 | 2 | 24450 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Butterfly Valve 630 MM | Material | Ea | 9750 | 1 | 9750 | 2 | 19500
[22 empty] | Fitting and Accessories 630 | Material | Ea | 975 | 1 | 975 | 2 | 1950
[22 empty] | Installation Valve 630mm | SC | Ea | 1500 | 1 | 1500 | 2 | 3000
SEW 10 |  | Gate lock valve on a 250 mm diameter pipe | nr | 1 | 3940 | 3940 | 2020 | 2020 | 1 | 1 |  | 1 | 100% | 3940 | 3940 | 2020 | 2020 |  | 2020 | [7 empty] | 2020 | 1 | 2020 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 1 | 1 |  | 1 | [9 empty] | Supply & Install Valves |  | Ea | 2020 |  | 2020 | 1 | 2020 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Gate Valve 250 MM | Material | Ea | 1700 | 1 | 1700 | 1 | 1700
[22 empty] | Fitting and Accessories 250 | Material | Ea | 170 | 1 | 170 | 1 | 170
[22 empty] | Installation Valve 250mm | SC | Ea | 150 | 1 | 150 | 1 | 150
SEW 10 |  | Gate lock valve on a 200 mm diameter pipe | nr |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | Gate lock valve on a 355 mm diameter pipe | nr |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | Water drain valve on a 315 mm diameter pipe | nr | 1 | 6169 | 6169 | 2620 | 2620 | 1 | 1 |  | 1 | 100% | 6169 | 6169 | 2620 | 2620 |  | 2620 | [7 empty] | 2620 | 1 | 2620 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 1 | 1 |  | 1 | [9 empty] | Supply & Install Valves |  | Ea | 2620 |  | 2620 | 1 | 2620 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Gate Valve 315 MM | Material | Ea | 2200 | 1 | 2200 | 1 | 2200
[22 empty] | Fitting and Accessories 315 | Material | Ea | 220 | 1 | 220 | 1 | 220
[22 empty] | Installation Valve 315mm | SC | Ea | 200 | 1 | 200 | 1 | 200
SEW 10 |  | Water drain valve on a 630 mm diameter pipe | nr | 0.4 | 9945 | 3978 | 12225 | 4890 | 0.4 | 0.4 |  | 0.4 | 100% | 9945 | 3978 | 12225 | 4890 |  | 4890 | [7 empty] | 12225 | 0.4 | 4890 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 0.4 | 0.4 |  | 0.4 | [9 empty] | Supply & Install Valves |  | Ea | 12225 |  | 12225 | 0.4 | 4890 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Butterfly Valve 630 MM | Material | Ea | 9750 | 1 | 9750 | 0.4 | 3900
[22 empty] | Fitting and Accessories 630 | Material | Ea | 975 | 1 | 975 | 0.4 | 390
[22 empty] | Installation Valve 630mm | SC | Ea | 1500 | 1 | 1500 | 0.4 | 600
SEW 10 |  | Water drain valve on 500mm pipe | nr | 0.4 | 9189 | 3675.6 | 9431 | 3772.4 | 0.4 | 0.4 |  | 0.4 | 100% | 9189 | 3675.6 | 9431 | 3772.4 |  | 3772.4 | [7 empty] | 9431 | 0.4 | 3772.4 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 0.4 | 0.4 |  | 0.4 | [9 empty] | Supply & Install Valves |  | Ea | 9431 |  | 9431 | 0.4 | 3772.4 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Butterfly Valve 500 MM | Material | Ea | 7210 | 1 | 7210 | 0.4 | 2884
[22 empty] | Fitting and Accessories 500 | Material | Ea | 721 | 1 | 721 | 0.4 | 288.4
[22 empty] | Installation Valve 500mm | SC | Ea | 1500 | 1 | 1500 | 0.4 | 600
SEW 10 |  | Water drain valve on a 250 mm diameter pipe | nr | 3 | 3991 | 11973 | 2020 | 6060 | 3 | 3 |  | 3 | 100% | 3991 | 11973 | 2020 | 6060 |  | 6060 | [7 empty] | 2020 | 3 | 6060 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 3 | 3 |  | 3 | [9 empty] | Supply & Install Valves |  | Ea | 2020 |  | 2020 | 3 | 6060 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Gate Valve 250 MM | Material | Ea | 1700 | 1 | 1700 | 3 | 5100
[22 empty] | Fitting and Accessories 250 | Material | Ea | 170 | 1 | 170 | 3 | 510
[22 empty] | Installation Valve 250mm | SC | Ea | 150 | 1 | 150 | 3 | 450
SEW 10 |  | Water drain valve on a 200 mm diameter pipe | nr |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | Water drain valve on 280mm pipe | nr | 2.4 | 5917 | 14200.8 | 2240 | 5376 | 2.4 | 2.4 |  | 2.4 | 100% | 5917 | 14200.8 | 2240 | 5376 |  | 5376 | [7 empty] | 2240 | 2.4 | 5376 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 2.4 | 2.4 |  | 2.4 | [9 empty] | Supply & Install Valves |  | Ea | 2240 |  | 2240 | 2.4 | 5376 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Gate Valve 280 MM | Material | Ea | 1870 | 1 | 1870 | 2.4 | 4488
[22 empty] | Fitting and Accessories 280 | Material | Ea | 170 | 1 | 170 | 2.4 | 408
[22 empty] | Installation Valve 280mm | SC | Ea | 200 | 1 | 200 | 2.4 | 480
SEW 10 |  | Water drain valve on a 355 mm diameter pipe | nr |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | Air breathing valve on a 315 mm diameter pipe | nr | 1 | 9347 | 9347 | 3245 | 3245 | 1 | 1 |  | 1 | 100% | 9347 | 9347 | 3245 | 3245 |  | 3245 | [7 empty] | 3245 | 1 | 3245 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 1 | 1 |  | 1 | [9 empty] | Supply & Install Valves |  | Ea | 3245 |  | 3245 | 1 | 3245 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Air Valve 315 MM | Material | Ea | 2825 | 1 | 2825 | 1 | 2825
[22 empty] | Fitting and Accessories 315 | Material | Ea | 220 | 1 | 220 | 1 | 220
[22 empty] | Installation Valve 315mm | SC | Ea | 200 | 1 | 200 | 1 | 200
SEW 10 |  | Air breathing valve on a 630 mm diameter pipe | nr | 2 | 13255 | 26510 | 12625 | 25250 | 2 | 2 |  | 2 | 100% | 13255 | 26510 | 12625 | 25250 |  | 25250 | [7 empty] | 12625 | 2 | 25250 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 2 | 2 |  | 2 | [9 empty] | Supply & Install Valves |  | Ea | 12625 |  | 12625 | 2 | 25250 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Air Valve 630 MM | Material | Ea | 10150 | 1 | 10150 | 2 | 20300
[22 empty] | Fitting and Accessories 630 | Material | Ea | 975 | 1 | 975 | 2 | 1950
[22 empty] | Installation Valve 630mm | SC | Ea | 1500 | 1 | 1500 | 2 | 3000
SEW 10 |  | Air relief valve on 500mm pipe | nr | 2 | 12236 | 24472 | 9971 | 19942 | 2 | 2 |  | 2 | 100% | 12236 | 24472 | 9971 | 19942 |  | 19942 | [7 empty] | 9971 | 2 | 19942 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 2 | 2 |  | 2 | [9 empty] | Supply & Install Valves |  | Ea | 9971 |  | 9971 | 2 | 19942 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Air Valve 500 MM | Material | Ea | 7750 | 1 | 7750 | 2 | 15500
[22 empty] | Fitting and Accessories 500 | Material | Ea | 721 | 1 | 721 | 2 | 1442
[22 empty] | Installation Valve 500mm | SC | Ea | 1500 | 1 | 1500 | 2 | 3000
SEW 10 |  | Air breathing valve on a 250 mm diameter pipe | nr | 2 | 11556 | 23112 | 2190 | 4380 | 2 | 2 |  | 2 | 100% | 11556 | 23112 | 2190 | 4380 |  | 4380 | [7 empty] | 2190 | 2 | 4380 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 2 | 2 |  | 2 | [9 empty] | Supply & Install Valves |  | Ea | 2190 |  | 2190 | 2 | 4380 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Air Valve 250 MM | Material | Ea | 1870 | 1 | 1870 | 2 | 3740
[22 empty] | Fitting and Accessories 250 | Material | Ea | 170 | 1 | 170 | 2 | 340
[22 empty] | Installation Valve 250mm | SC | Ea | 150 | 1 | 150 | 2 | 300
SEW 10 |  | Air breathing valve on a 200 mm diameter pipe | nr |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | Air relief valve on 280mm pipe | nr | 2 | 11046 | 22092 | 2530 | 5060 | 2 | 2 |  | 2 | 100% | 11046 | 22092 | 2530 | 5060 |  | 5060 | [7 empty] | 2530 | 2 | 5060 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 2 | 2 |  | 2 | [9 empty] | Supply & Install Valves |  | Ea | 2530 |  | 2530 | 2 | 5060 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Air Valve 280 MM | Material | Ea | 2160 | 1 | 2160 | 2 | 4320
[22 empty] | Fitting and Accessories 280 | Material | Ea | 170 | 1 | 170 | 2 | 340
[22 empty] | Installation Valve 280mm | SC | Ea | 200 | 1 | 200 | 2 | 400
SEW 10 |  | Air breathing valve on a 355 mm diameter pipe | nr |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | Art (K): Pipe works - manholes and accessories for pipe works |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | Valve chambers |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | Concrete rooms with an obelisk for valves, including excavation, backfilling, waste disposal, water extraction, cleaning concrete, concrete pouring, ordering and commodification works, formwork, ceiling tiles, stairs, water insulation, protection pipe, DI cover, ventilation holes, instruction sign boards, etc., in accordance with the procedures of the competent authorities, specifications and plans. |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | Chamber lock valve on pipe diameter 315 mm | nr | 0.2 | 33107 | 6621.4 | 12286.1796 | 2457.2359 | 0.2 | 0.2 |  | 0.2 | 100% | 33107 | 6621.4 | 12286.1796 | 2457.2359 |  | 2457.2359 | [7 empty] | 12286.1796 | 0.2 | 2457.2359 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 0.2 | 0.2 |  | 0.2 | [9 empty] | Excavate & Disposal (3*3*2.5) |  | Ea | 90.4969 |  | 90.4969 | 0.2 | 18.0994 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 4.4444 | 12.6 | 0.045 | 2.52
[22 empty] | Fuel | Material | LTR | 1.76 | 0.31746 | 5.544 | 0.63 | 1.1088
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.90667 | 52.9412 | 0.22059 | 10.5882
[22 empty] | Fuel | Material | LTR | 1.76 | 0.090667 | 19.4118 | 2.2059 | 3.8824
[9 empty] | 0.2 | 0.2 |  | 0.2 | [9 empty] | Valve Room Installation |  | Ea | 9186.6 |  | 9186.6 | 0.2 | 1837.32 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 1.1111 | 225 | 0.18 | 45
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.2 | 1750 | 1 | 350
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 2.5 | 1000 | 0.08 | 200
[22 empty] | Workmanship plain concrete | SC | M³ | 150 | 1.1111 | 135 | 0.18 | 27
[22 empty] | Workmanship RC concrete | SC | M³ | 450 | 0.2 | 2250 | 1 | 450
[22 empty] | Supply & apply Chamber Cover, frames | Material | Ea | 3500 | 1 | 3500 | 0.2 | 700
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 4 | 20 | 0.05 | 4
[22 empty] | Fuel | Material | HR | 1.76 | 0.26667 | 6.6 | 0.75 | 1.32
[22 empty] | Chamber Pipes Pieces | Material | LS | 150 | 1 | 150 | 0.2 | 30
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.2 | 85 | 1 | 17
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.2 | 65 | 1 | 13
[9 empty] | 0.2 | 0.2 |  | 0.2 | [9 empty] | Internal and external Insulation |  | Ea | 2800 |  | 2800 | 0.2 | 560 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply & apply external waterproofing | SC | M² | 40 | 0.025 | 1600 | 8 | 320
[22 empty] | Supply & apply internal coating | SC | M² | 30 | 0.025 | 1200 | 8 | 240
[9 empty] | 0.2 | 0.2 |  | 0.2 | [9 empty] | Backfilling |  | Ea | 209.0826 |  | 209.0826 | 0.2 | 41.8165 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.083333 | 120 | 2.4 | 24
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 8.3333 | 7.872 | 0.024 | 1.5744
[22 empty] | Fuel | Material | LTR | 1.76 | 0.92593 | 1.9008 | 0.216 | 0.38016
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 1.7 | 28.2353 | 0.11765 | 5.6471
[22 empty] | Fuel | Material | LTR | 1.76 | 0.17 | 10.3529 | 1.1765 | 2.0706
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 4.1667 | 8.64 | 0.048 | 1.728
[22 empty] | Fuel | Material | LTR | 1.76 | 0.46296 | 3.8016 | 0.432 | 0.76032
[22 empty] | Plate Compactor | Machinery | HR | 23 | 1 | 23 | 0.2 | 4.6
[22 empty] | Fuel | Material | LTR | 1.76 | 0.33333 | 5.28 | 0.6 | 1.056
SEW 10 |  | Chamber lock valve on pipe diameter 630 mm | nr | 0.65 | 39904 | 25937.6 | 12286.1796 | 7986.0167 | 0.65 | 0.65 |  | 0.65 | 100% | 39904 | 25937.6 | 12286.1796 | 7986.0167 |  | 7986.0167 | [7 empty] | 12286.1796 | 0.65 | 7986.0167 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 0.65 | 0.65 |  | 0.65 | [9 empty] | Excavate & Disposal (3*3*2.5) |  | Ea | 90.4969 |  | 90.4969 | 0.65 | 58.823 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 4.4444 | 12.6 | 0.14625 | 8.19
[22 empty] | Fuel | Material | LTR | 1.76 | 0.31746 | 5.544 | 2.0475 | 3.6036
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.90667 | 52.9412 | 0.71691 | 34.4118
[22 empty] | Fuel | Material | LTR | 1.76 | 0.090667 | 19.4118 | 7.1691 | 12.6176
[9 empty] | 0.65 | 0.65 |  | 0.65 | [9 empty] | Valve Room Installation |  | Ea | 9186.6 |  | 9186.6 | 0.65 | 5971.29 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 1.1111 | 225 | 0.585 | 146.25
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.2 | 1750 | 3.25 | 1137.5
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 2.5 | 1000 | 0.26 | 650
[22 empty] | Workmanship plain concrete | SC | M³ | 150 | 1.1111 | 135 | 0.585 | 87.75
[22 empty] | Workmanship RC concrete | SC | M³ | 450 | 0.2 | 2250 | 3.25 | 1462.5
[22 empty] | Supply & apply Chamber Cover, frames | Material | Ea | 3500 | 1 | 3500 | 0.65 | 2275
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 4 | 20 | 0.1625 | 13
[22 empty] | Fuel | Material | HR | 1.76 | 0.26667 | 6.6 | 2.4375 | 4.29
[22 empty] | Chamber Pipes Pieces | Material | LS | 150 | 1 | 150 | 0.65 | 97.5
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.2 | 85 | 3.25 | 55.25
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.2 | 65 | 3.25 | 42.25
[9 empty] | 0.65 | 0.65 |  | 0.65 | [9 empty] | Internal and external Insulation |  | Ea | 2800 |  | 2800 | 0.65 | 1820 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply & apply external waterproofing | SC | M² | 40 | 0.025 | 1600 | 26 | 1040
[22 empty] | Supply & apply internal coating | SC | M² | 30 | 0.025 | 1200 | 26 | 780
[9 empty] | 0.65 | 0.65 |  | 0.65 | [9 empty] | Backfilling |  | Ea | 209.0826 |  | 209.0826 | 0.65 | 135.9037 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.083333 | 120 | 7.8 | 78
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 8.3333 | 7.872 | 0.078 | 5.1168
[22 empty] | Fuel | Material | LTR | 1.76 | 0.92593 | 1.9008 | 0.702 | 1.2355
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 1.7 | 28.2353 | 0.38235 | 18.3529
[22 empty] | Fuel | Material | LTR | 1.76 | 0.17 | 10.3529 | 3.8235 | 6.7294
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 4.1667 | 8.64 | 0.156 | 5.616
[22 empty] | Fuel | Material | LTR | 1.76 | 0.46296 | 3.8016 | 1.404 | 2.471
[22 empty] | Plate Compactor | Machinery | HR | 23 | 1 | 23 | 0.65 | 14.95
[22 empty] | Fuel | Material | LTR | 1.76 | 0.33333 | 5.28 | 1.95 | 3.432
SEW 10 |  | Chamber lock valve on a 250 mm diameter pipe | nr | 1 | 30211 | 30211 | 12286.1796 | 12286.1796 | 1 | 1 |  | 1 | 100% | 30211 | 30211 | 12286.1796 | 12286.1796 |  | 12286.1796 | [7 empty] | 12286.1796 | 1 | 12286.1796 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 1 | 1 |  | 1 | [9 empty] | Excavate & Disposal (3*3*2.5) |  | Ea | 90.4969 |  | 90.4969 | 1 | 90.4969 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 4.4444 | 12.6 | 0.225 | 12.6
[22 empty] | Fuel | Material | LTR | 1.76 | 0.31746 | 5.544 | 3.15 | 5.544
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.90667 | 52.9412 | 1.1029 | 52.9412
[22 empty] | Fuel | Material | LTR | 1.76 | 0.090667 | 19.4118 | 11.0294 | 19.4118
[9 empty] | 1 | 1 |  | 1 | [9 empty] | Valve Room Installation |  | Ea | 9186.6 |  | 9186.6 | 1 | 9186.6 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 1.1111 | 225 | 0.9 | 225
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.2 | 1750 | 5 | 1750
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 2.5 | 1000 | 0.4 | 1000
[22 empty] | Workmanship plain concrete | SC | M³ | 150 | 1.1111 | 135 | 0.9 | 135
[22 empty] | Workmanship RC concrete | SC | M³ | 450 | 0.2 | 2250 | 5 | 2250
[22 empty] | Supply & apply Chamber Cover, frames | Material | Ea | 3500 | 1 | 3500 | 1 | 3500
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 4 | 20 | 0.25 | 20
[22 empty] | Fuel | Material | HR | 1.76 | 0.26667 | 6.6 | 3.75 | 6.6
[22 empty] | Chamber Pipes Pieces | Material | LS | 150 | 1 | 150 | 1 | 150
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.2 | 85 | 5 | 85
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.2 | 65 | 5 | 65
[9 empty] | 1 | 1 |  | 1 | [9 empty] | Internal and external Insulation |  | Ea | 2800 |  | 2800 | 1 | 2800 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply & apply external waterproofing | SC | M² | 40 | 0.025 | 1600 | 40 | 1600
[22 empty] | Supply & apply internal coating | SC | M² | 30 | 0.025 | 1200 | 40 | 1200
[9 empty] | 1 | 1 |  | 1 | [9 empty] | Backfilling |  | Ea | 209.0826 |  | 209.0826 | 1 | 209.0826 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.083333 | 120 | 12 | 120
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 8.3333 | 7.872 | 0.12 | 7.872
[22 empty] | Fuel | Material | LTR | 1.76 | 0.92593 | 1.9008 | 1.08 | 1.9008
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 1.7 | 28.2353 | 0.58824 | 28.2353
[22 empty] | Fuel | Material | LTR | 1.76 | 0.17 | 10.3529 | 5.8824 | 10.3529
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 4.1667 | 8.64 | 0.24 | 8.64
[22 empty] | Fuel | Material | LTR | 1.76 | 0.46296 | 3.8016 | 2.16 | 3.8016
[22 empty] | Plate Compactor | Machinery | HR | 23 | 1 | 23 | 1 | 23
[22 empty] | Fuel | Material | LTR | 1.76 | 0.33333 | 5.28 | 3 | 5.28
SEW 10 |  | Chamber lock valve on a 200 mm diameter pipe | nr |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | Chamber lock valve on pipe diameter 355 mm | nr |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | Lock valve chamber on 500mm diameter pipe | nr |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | Water drain valve chamber | nr | 4.75 | 42926 | 203898.5 | 12286.1796 | 58359.353 | 4.75 | 4.75 |  | 4.75 | 100% | 42926 | 203898.5 | 12286.1796 | 58359.353 |  | 58359.353 | [7 empty] | 12286.1796 | 4.75 | 58359.353 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 4.75 | 4.75 |  | 4.75 | [9 empty] | Excavate & Disposal (3*3*2.5) |  | Ea | 90.4969 |  | 90.4969 | 4.75 | 429.8605 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 4.4444 | 12.6 | 1.0687 | 59.85
[22 empty] | Fuel | Material | LTR | 1.76 | 0.31746 | 5.544 | 14.9625 | 26.334
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.90667 | 52.9412 | 5.239 | 251.4706
[22 empty] | Fuel | Material | LTR | 1.76 | 0.090667 | 19.4118 | 52.3897 | 92.2059
[9 empty] | 4.75 | 4.75 |  | 4.75 | [9 empty] | Valve Room Installation |  | Ea | 9186.6 |  | 9186.6 | 4.75 | 43636.35 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 1.1111 | 225 | 4.275 | 1068.75
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.2 | 1750 | 23.75 | 8312.5
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 2.5 | 1000 | 1.9 | 4750
[22 empty] | Workmanship plain concrete | SC | M³ | 150 | 1.1111 | 135 | 4.275 | 641.25
[22 empty] | Workmanship RC concrete | SC | M³ | 450 | 0.2 | 2250 | 23.75 | 10687.5
[22 empty] | Supply & apply Chamber Cover, frames | Material | Ea | 3500 | 1 | 3500 | 4.75 | 16625
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 4 | 20 | 1.1875 | 95
[22 empty] | Fuel | Material | HR | 1.76 | 0.26667 | 6.6 | 17.8125 | 31.35
[22 empty] | Chamber Pipes Pieces | Material | LS | 150 | 1 | 150 | 4.75 | 712.5
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.2 | 85 | 23.75 | 403.75
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.2 | 65 | 23.75 | 308.75
[9 empty] | 4.75 | 4.75 |  | 4.75 | [9 empty] | Internal and external Insulation |  | Ea | 2800 |  | 2800 | 4.75 | 13300 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply & apply external waterproofing | SC | M² | 40 | 0.025 | 1600 | 190 | 7600
[22 empty] | Supply & apply internal coating | SC | M² | 30 | 0.025 | 1200 | 190 | 5700
[9 empty] | 4.75 | 4.75 |  | 4.75 | [9 empty] | Backfilling |  | Ea | 209.0826 |  | 209.0826 | 4.75 | 993.1425 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.083333 | 120 | 57 | 570
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 8.3333 | 7.872 | 0.57 | 37.392
[22 empty] | Fuel | Material | LTR | 1.76 | 0.92593 | 1.9008 | 5.13 | 9.0288
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 1.7 | 28.2353 | 2.7941 | 134.1176
[22 empty] | Fuel | Material | LTR | 1.76 | 0.17 | 10.3529 | 27.9412 | 49.1765
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 4.1667 | 8.64 | 1.14 | 41.04
[22 empty] | Fuel | Material | LTR | 1.76 | 0.46296 | 3.8016 | 10.26 | 18.0576
[22 empty] | Plate Compactor | Machinery | HR | 23 | 1 | 23 | 4.75 | 109.25
[22 empty] | Fuel | Material | LTR | 1.76 | 0.33333 | 5.28 | 14.25 | 25.08
SEW 10 |  | Air vent valve chamber | nr | 3.92 | 0 | 0 | 0 | 0 | 3.92 | 3.92 |  | 3.92 | 100% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 3.92
SEW 10 |  | Art (K): Pipe works - manholes and accessories for pipe works |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | Discharge Chamber |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | Concrete rooms with an obelisk for valves, including excavation, backfilling, waste disposal, water extraction, cleaning concrete, concrete pouring, ordering and commodification works, formwork, ceiling tiles, stairs, water insulation, protection pipe, DI cover, ventilation holes, instruction sign boards, etc., in accordance with the procedures of the competent authorities, specifications and plans. |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | Drainage room 2.45m x5m | nr | 1.55 | 91893 | 142434.15 | 26496.9918 | 41070.3373 | 1.55 | 1.55 |  | 1.55 | 100% | 91893 | 142434.15 | 26496.9918 | 41070.3373 |  | 41070.3373 | [7 empty] | 26496.9918 | 1.55 | 41070.3373 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 1.55 | 1.55 |  | 1.55 | [9 empty] | Excavate & Disposal (2.45*5.0*3.5) |  | Ea | 291.4002 |  | 291.4002 | 1.55 | 451.6702 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 1.3803 | 40.572 | 1.123 | 62.8866
[22 empty] | Fuel | Material | LTR | 1.76 | 0.09859 | 17.8517 | 15.7217 | 27.6701
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.28157 | 170.4706 | 5.5048 | 264.2294
[22 empty] | Fuel | Material | LTR | 1.76 | 0.028157 | 62.5059 | 55.0478 | 96.8841
[9 empty] | 1.55 | 1.55 |  | 1.55 | [9 empty] | Valve Room Installation |  | Ea | 21739.6 |  | 21739.6 | 1.55 | 33696.38 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 0.48309 | 517.5 | 3.2085 | 802.125
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.058531 | 5979.75 | 26.4817 | 9268.6125
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 0.73164 | 3417 | 2.1185 | 5296.35
[22 empty] | Workmanship plain concrete | SC | M³ | 150 | 0.48309 | 310.5 | 3.2085 | 481.275
[22 empty] | Workmanship RC concrete | SC | M³ | 450 | 0.058531 | 7688.25 | 26.4817 | 11916.7875
[22 empty] | Supply & apply Chamber Cover, frames | Material | Ea | 3500 | 1 | 3500 | 1.55 | 5425
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 4 | 20 | 0.3875 | 31
[22 empty] | Fuel | Material | HR | 1.76 | 0.26667 | 6.6 | 5.8125 | 10.23
[22 empty] | Chamber Pipes Pieces | Material | LS | 150 | 1 | 150 | 1.55 | 232.5
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.2 | 85 | 7.75 | 131.75
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.2 | 65 | 7.75 | 100.75
[9 empty] | 1.55 | 1.55 |  | 1.55 | [9 empty] | Internal and external Insulation |  | Ea | 3920 |  | 3920 | 1.55 | 6076 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply & apply external waterproofing | SC | M² | 40 | 0.017857 | 2240 | 86.8 | 3472
[22 empty] | Supply & apply internal coating | SC | M² | 30 | 0.017857 | 1680 | 86.8 | 2604
[9 empty] | 1.55 | 1.55 |  | 1.55 | [9 empty] | Backfilling |  | Ea | 545.9916 |  | 545.9916 | 1.55 | 846.287 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.034807 | 287.3 | 44.5315 | 445.315
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 3.4807 | 18.8469 | 0.44531 | 29.2127
[22 empty] | Fuel | Material | LTR | 1.76 | 0.38674 | 4.5508 | 4.0078 | 7.0538
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.71006 | 67.6 | 2.1829 | 104.78
[22 empty] | Fuel | Material | LTR | 1.76 | 0.071006 | 24.7867 | 21.8292 | 38.4193
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 1.7403 | 20.6856 | 0.89063 | 32.0627
[22 empty] | Fuel | Material | LTR | 1.76 | 0.19337 | 9.1017 | 8.0157 | 14.1076
[22 empty] | Plate Compactor | Machinery | HR | 23 | 0.25 | 92 | 6.2 | 142.6
[22 empty] | Fuel | Material | LTR | 1.76 | 0.083333 | 21.12 | 18.6 | 32.736
SEW 10 |  | Examination using closed-circuit television |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
SEW 10 |  | Conducting a survey using closed television stations, including loaning the scan after a malfunction, shutdown, repair purposes, etc., in accordance with the specifications: Section 330130.16 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
SEW 10 |  | On pipes with an inner diameter of 150 mm | m |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | On pipes with an inner diameter of 200 mm | m |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | On pipes with an inner diameter of 250 mm | m |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | On pipes with an inner diameter of 315 mm | m |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | On pipes with an inner diameter of 355 mm | m |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | On pipes with an inner diameter of 400 mm | m |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | On pipes with an internal diameter of 500 mm | m |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | On pipes with an internal diameter of 600 mm | m |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | On pipes with an inner diameter of 700 mm | m |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | Art (K): Pipeworks - manholes and pipework accessories (continued) |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | Concrete sanitary manholes include excavation, backfilling, waste disposal, dewatering, sanitation concrete, concrete pour, foundations, walls, roof slab, reinforcement, formwork, concrete room frames, brickwork, waterproofing, DI cover with openings and frame, chains, pipes, fittings, spacers, pipe connections, etc., complete in accordance with the plans, specifications and requirements of the concerned authority, dewatering, strengthening and protecting the excavated surfaces all the way up. To the required depths and the disposal of groundwater resulting from drainage around it is measured individually |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | Manhole chambers, diameter 1200 mm |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | (GRP) Maximum depth 1.5 m | nr | 14.45 | 11392 | 164614.4 | 6056.6049 | 87517.9414 | 14.45 | 14.45 |  | 14.45 | 100% | 11392 | 164614.4 | 6056.6049 | 87517.9414 |  | 87517.9414 | [7 empty] | 6056.6049 | 14.45 | 87517.9414 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 14.45 | 14.45 |  | 14.45 | [9 empty] | Excavate & Disposal (2.5*2.5*2.0) |  | Ea | 50.2761 |  | 50.2761 | 14.45 | 726.4893 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 8 | 7 | 1.8063 | 101.15
[22 empty] | Fuel | Material | LTR | 1.76 | 0.57143 | 3.08 | 25.2875 | 44.506
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 1.632 | 29.4118 | 8.8542 | 425
[22 empty] | Fuel | Material | LTR | 1.76 | 0.1632 | 10.7843 | 88.5417 | 155.8333
[9 empty] | 14.45 | 14.45 |  | 14.45 | [9 empty] | Concrete Base 30 cm |  | Ea | 1432.696 |  | 1432.696 | 14.45 | 20702.4572 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 2.2676 | 110.25 | 6.3725 | 1593.1125
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.83333 | 420 | 17.34 | 6069
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 10.4167 | 240 | 1.3872 | 3468
[22 empty] | Workmanship plain concrete | SC | M³ | 150 | 2.2676 | 66.15 | 6.3725 | 955.8675
[22 empty] | Workmanship RC concrete | SC | M³ | 450 | 0.83333 | 540 | 17.34 | 7803
[22 empty] | 2 Layers Bituminous Application | SC | M² | 10 | 0.17763 | 56.296 | 81.3477 | 813.4772
[9 empty] | 14.45 | 14.45 |  | 14.45 | [9 empty] | Manhole Installation |  | Ea | 4362.8 |  | 4362.8 | 14.45 | 63042.46 | 0 | 0 | 0 | 0 | 0
[22 empty] | GRP manhole Dia 1200 mm D=1.5 m W Cover | Material | Ea | 2590 | 1 | 2590 | 14.45 | 37425.5
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 0.5 | 160 | 28.9 | 2312
[22 empty] | Fuel | Material | HR | 1.76 | 0.033333 | 52.8 | 433.5 | 762.96
[22 empty] | Brick & Masonery for Manhole Neck | SC | LS | 1500 | 1 | 1500 | 14.45 | 21675
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.5 | 34 | 28.9 | 491.3
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.5 | 26 | 28.9 | 375.7
[9 empty] | 14.45 | 14.45 |  | 14.45 | [9 empty] | Backfilling |  | Ea | 210.8329 |  | 210.8329 | 14.45 | 3046.5349 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.097664 | 102.392 | 147.9564 | 1479.5644
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 9.7664 | 6.7169 | 1.4796 | 97.0594
[22 empty] | Fuel | Material | LTR | 1.76 | 1.0852 | 1.6219 | 13.3161 | 23.4363
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 1.9923 | 24.0922 | 7.2528 | 348.1328
[22 empty] | Fuel | Material | LTR | 1.76 | 0.19923 | 8.8338 | 72.5277 | 127.6487
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 4.8832 | 7.3722 | 2.9591 | 106.5286
[22 empty] | Fuel | Material | LTR | 1.76 | 0.54258 | 3.2438 | 26.6322 | 46.8726
[22 empty] | Plate Compactor | Machinery | HR | 23 | 0.5 | 46 | 28.9 | 664.7
[22 empty] | Fuel | Material | LTR | 1.76 | 0.16667 | 10.56 | 86.7 | 152.592
SEW 10 |  | At a depth of 1.5 - 2.0 m (GRP) | nr | 8.09 | 14728 | 119149.52 | 6631.8822 | 53651.9268 | 8.09 | 8.09 |  | 8.09 | 100% | 14728 | 119149.52 | 6631.8822 | 53651.9268 |  | 53651.9268 | [7 empty] | 6631.8822 | 8.09 | 53651.9268 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 8.09 | 8.09 |  | 8.09 | [9 empty] | Excavate & Disposal (2.5*2.5*2.5) |  | Ea | 62.8451 |  | 62.8451 | 8.09 | 508.4168 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 6.4 | 8.75 | 1.2641 | 70.7875
[22 empty] | Fuel | Material | LTR | 1.76 | 0.45714 | 3.85 | 17.6969 | 31.1465
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 1.3056 | 36.7647 | 6.1964 | 297.4265
[22 empty] | Fuel | Material | LTR | 1.76 | 0.13056 | 13.4804 | 61.9638 | 109.0564
[9 empty] | 8.09 | 8.09 |  | 8.09 | [9 empty] | Concrete Base 30 cm |  | Ea | 1432.696 |  | 1432.696 | 8.09 | 11590.5106 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 2.2676 | 110.25 | 3.5677 | 891.9225
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.83333 | 420 | 9.708 | 3397.8
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 10.4167 | 240 | 0.77664 | 1941.6
[22 empty] | Workmanship plain concrete | SC | M³ | 150 | 2.2676 | 66.15 | 3.5677 | 535.1535
[22 empty] | Workmanship RC concrete | SC | M³ | 450 | 0.83333 | 540 | 9.708 | 4368.6
[22 empty] | 2 Layers Bituminous Application | SC | M² | 10 | 0.17763 | 56.296 | 45.5435 | 455.4346
[9 empty] | 8.09 | 8.09 |  | 8.09 | [9 empty] | Manhole Installation |  | Ea | 4872.8 |  | 4872.8 | 8.09 | 39420.952 | 0 | 0 | 0 | 0 | 0
[22 empty] | GRP manhole Dia 1200 mm D=2.0 m W Cover | Material | Ea | 3100 | 1 | 3100 | 8.09 | 25079
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 0.5 | 160 | 16.18 | 1294.4
[22 empty] | Fuel | Material | HR | 1.76 | 0.033333 | 52.8 | 242.7 | 427.152
[22 empty] | Brick & Masonery for Manhole Neck | SC | LS | 1500 | 1 | 1500 | 8.09 | 12135
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.5 | 34 | 16.18 | 275.06
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.5 | 26 | 16.18 | 210.34
[9 empty] | 8.09 | 8.09 |  | 8.09 | [9 empty] | Backfilling |  | Ea | 263.5411 |  | 263.5411 | 8.09 | 2132.0473 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.078131 | 127.99 | 103.5439 | 1035.4391
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 7.8131 | 8.3961 | 1.0354 | 67.9248
[22 empty] | Fuel | Material | LTR | 1.76 | 0.86812 | 2.0274 | 9.319 | 16.4014
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 1.5939 | 30.1153 | 5.0757 | 243.6327
[22 empty] | Fuel | Material | LTR | 1.76 | 0.15939 | 11.0423 | 50.7568 | 89.332
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 3.9066 | 9.2153 | 2.0709 | 74.5516
[22 empty] | Fuel | Material | LTR | 1.76 | 0.43406 | 4.0547 | 18.6379 | 32.8027
[22 empty] | Plate Compactor | Machinery | HR | 23 | 0.4 | 57.5 | 20.225 | 465.175
[22 empty] | Fuel | Material | LTR | 1.76 | 0.13333 | 13.2 | 60.675 | 106.788
SEW 10 |  | At a depth of 2.0 - 2.5 m (GRP) | nr | 8.89 | 18316 | 162829.24 | 7197.1594 | 63982.7472 | 8.89 | 8.89 |  | 8.89 | 100% | 18316 | 162829.24 | 7197.1594 | 63982.7472 |  | 63982.7472 | [7 empty] | 7197.1594 | 8.89 | 63982.7472 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 8.89 | 8.89 |  | 8.89 | [9 empty] | Excavate & Disposal (2.5*2.5*3.0) |  | Ea | 75.4141 |  | 75.4141 | 8.89 | 670.4315 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 5.3333 | 10.5 | 1.6669 | 93.345
[22 empty] | Fuel | Material | LTR | 1.76 | 0.38095 | 4.62 | 23.3363 | 41.0718
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 1.088 | 44.1176 | 8.171 | 392.2059
[22 empty] | Fuel | Material | LTR | 1.76 | 0.1088 | 16.1765 | 81.7096 | 143.8088
[9 empty] | 8.89 | 8.89 |  | 8.89 | [9 empty] | Concrete Base 30 cm |  | Ea | 1432.696 |  | 1432.696 | 8.89 | 12736.6674 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 2.2676 | 110.25 | 3.9205 | 980.1225
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.83333 | 420 | 10.668 | 3733.8
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 10.4167 | 240 | 0.85344 | 2133.6
[22 empty] | Workmanship plain concrete | SC | M³ | 150 | 2.2676 | 66.15 | 3.9205 | 588.0735
[22 empty] | Workmanship RC concrete | SC | M³ | 450 | 0.83333 | 540 | 10.668 | 4800.6
[22 empty] | 2 Layers Bituminous Application | SC | M² | 10 | 0.17763 | 56.296 | 50.0471 | 500.4714
[9 empty] | 8.89 | 8.89 |  | 8.89 | [9 empty] | Manhole Installation |  | Ea | 5372.8 |  | 5372.8 | 8.89 | 47764.192 | 0 | 0 | 0 | 0 | 0
[22 empty] | GRP manhole Dia 1200 mm D=2.5 m W Cover | Material | Ea | 3600 | 1 | 3600 | 8.89 | 32004
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 0.5 | 160 | 17.78 | 1422.4
[22 empty] | Fuel | Material | HR | 1.76 | 0.033333 | 52.8 | 266.7 | 469.392
[22 empty] | Brick & Masonery for Manhole Neck | SC | LS | 1500 | 1 | 1500 | 8.89 | 13335
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.5 | 34 | 17.78 | 302.26
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.5 | 26 | 17.78 | 231.14
[9 empty] | 8.89 | 8.89 |  | 8.89 | [9 empty] | Backfilling |  | Ea | 316.2493 |  | 316.2493 | 8.89 | 2811.4562 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.065109 | 153.588 | 136.5397 | 1365.3973
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 6.5109 | 10.0754 | 1.3654 | 89.5701
[22 empty] | Fuel | Material | LTR | 1.76 | 0.72344 | 2.4328 | 12.2886 | 21.6279
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 1.3282 | 36.1384 | 6.6931 | 321.27
[22 empty] | Fuel | Material | LTR | 1.76 | 0.13282 | 13.2507 | 66.9312 | 117.799
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 3.2555 | 11.0583 | 2.7308 | 98.3086
[22 empty] | Fuel | Material | LTR | 1.76 | 0.36172 | 4.8657 | 24.5772 | 43.2558
[22 empty] | Plate Compactor | Machinery | HR | 23 | 0.33333 | 69 | 26.67 | 613.41
[22 empty] | Fuel | Material | LTR | 1.76 | 0.11111 | 15.84 | 80.01 | 140.8176
SEW 10 |  | At a depth of 2.5 - 3.0 m (GRP) | nr | 17.32 | 22092 | 382633.44 | 8162.4366 | 141373.4027 | 17.32 | 17.32 |  | 17.32 | 100% | 22092 | 382633.44 | 8162.4366 | 141373.4027 |  | 141373.4027 | [7 empty] | 8162.4366 | 17.32 | 141373.4027 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 17.32 | 17.32 |  | 17.32 | [9 empty] | Excavate & Disposal (2.5*2.5*3.5) |  | Ea | 87.9831 |  | 87.9831 | 17.32 | 1523.8679 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 4.5714 | 12.25 | 3.7888 | 212.17
[22 empty] | Fuel | Material | LTR | 1.76 | 0.32653 | 5.39 | 53.0425 | 93.3548
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.93257 | 51.4706 | 18.5723 | 891.4706
[22 empty] | Fuel | Material | LTR | 1.76 | 0.093257 | 18.8725 | 185.723 | 326.8725
[9 empty] | 17.32 | 17.32 |  | 17.32 | [9 empty] | Concrete Base 30 cm |  | Ea | 1432.696 |  | 1432.696 | 17.32 | 24814.2947 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 2.2676 | 110.25 | 7.6381 | 1909.53
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.83333 | 420 | 20.784 | 7274.4
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 10.4167 | 240 | 1.6627 | 4156.8
[22 empty] | Workmanship plain concrete | SC | M³ | 150 | 2.2676 | 66.15 | 7.6381 | 1145.718
[22 empty] | Workmanship RC concrete | SC | M³ | 450 | 0.83333 | 540 | 20.784 | 9352.8
[22 empty] | 2 Layers Bituminous Application | SC | M² | 10 | 0.17763 | 56.296 | 97.5047 | 975.0467
[9 empty] | 17.32 | 17.32 |  | 17.32 | [9 empty] | Manhole Installation |  | Ea | 6272.8 |  | 6272.8 | 17.32 | 108644.896 | 0 | 0 | 0 | 0 | 0
[22 empty] | GRP manhole Dia 1200 mm D=3.0 m W Cover | Material | Ea | 4500 | 1 | 4500 | 17.32 | 77940
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 0.5 | 160 | 34.64 | 2771.2
[22 empty] | Fuel | Material | HR | 1.76 | 0.033333 | 52.8 | 519.6 | 914.496
[22 empty] | Brick & Masonery for Manhole Neck | SC | LS | 1500 | 1 | 1500 | 17.32 | 25980
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.5 | 34 | 34.64 | 588.88
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.5 | 26 | 34.64 | 450.32
[9 empty] | 17.32 | 17.32 |  | 17.32 | [9 empty] | Backfilling |  | Ea | 368.9575 |  | 368.9575 | 17.32 | 6390.344 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.055808 | 179.186 | 310.3502 | 3103.5015
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 5.5808 | 11.7546 | 3.1035 | 203.5897
[22 empty] | Fuel | Material | LTR | 1.76 | 0.62009 | 2.8383 | 27.9315 | 49.1595
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 1.1385 | 42.1614 | 15.2132 | 730.2357
[22 empty] | Fuel | Material | LTR | 1.76 | 0.11385 | 15.4592 | 152.1324 | 267.7531
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 2.7904 | 12.9014 | 6.207 | 223.4521
[22 empty] | Fuel | Material | LTR | 1.76 | 0.31004 | 5.6766 | 55.863 | 98.3189
[22 empty] | Plate Compactor | Machinery | HR | 23 | 0.28571 | 80.5 | 60.62 | 1394.26
[22 empty] | Fuel | Material | LTR | 1.76 | 0.095238 | 18.48 | 181.86 | 320.0736
SEW 10 |  | At a depth of 3.0 - 3.5 m (GRP) | nr | 14.88 | 25743 | 383055.84 | 9077.7139 | 135076.3825 | 14.88 | 14.88 |  | 14.88 | 100% | 25743 | 383055.84 | 9077.7139 | 135076.3825 |  | 135076.3825 | [7 empty] | 9077.7139 | 14.88 | 135076.3825 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 14.88 | 14.88 |  | 14.88 | [9 empty] | Excavate & Disposal (2.5*2.5*4.0) |  | Ea | 100.5522 |  | 100.5522 | 14.88 | 1496.2161 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 4 | 14 | 3.72 | 208.32
[22 empty] | Fuel | Material | LTR | 1.76 | 0.28571 | 6.16 | 52.08 | 91.6608
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.816 | 58.8235 | 18.2353 | 875.2941
[22 empty] | Fuel | Material | LTR | 1.76 | 0.0816 | 21.5686 | 182.3529 | 320.9412
[9 empty] | 14.88 | 14.88 |  | 14.88 | [9 empty] | Concrete Base 30 cm |  | Ea | 1432.696 |  | 1432.696 | 14.88 | 21318.5165 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 2.2676 | 110.25 | 6.5621 | 1640.52
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.83333 | 420 | 17.856 | 6249.6
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 10.4167 | 240 | 1.4285 | 3571.2
[22 empty] | Workmanship plain concrete | SC | M³ | 150 | 2.2676 | 66.15 | 6.5621 | 984.312
[22 empty] | Workmanship RC concrete | SC | M³ | 450 | 0.83333 | 540 | 17.856 | 8035.2
[22 empty] | 2 Layers Bituminous Application | SC | M² | 10 | 0.17763 | 56.296 | 83.7684 | 837.6845
[9 empty] | 14.88 | 14.88 |  | 14.88 | [9 empty] | Manhole Installation |  | Ea | 7122.8 |  | 7122.8 | 14.88 | 105987.264 | 0 | 0 | 0 | 0 | 0
[22 empty] | GRP manhole Dia 1200 mm D=3.5 m W Cover | Material | Ea | 5350 | 1 | 5350 | 14.88 | 79608
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 0.5 | 160 | 29.76 | 2380.8
[22 empty] | Fuel | Material | HR | 1.76 | 0.033333 | 52.8 | 446.4 | 785.664
[22 empty] | Brick & Masonery for Manhole Neck | SC | LS | 1500 | 1 | 1500 | 14.88 | 22320
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.5 | 34 | 29.76 | 505.92
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.5 | 26 | 29.76 | 386.88
[9 empty] | 14.88 | 14.88 |  | 14.88 | [9 empty] | Backfilling |  | Ea | 421.6657 |  | 421.6657 | 14.88 | 6274.386 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.048832 | 204.784 | 304.7186 | 3047.1859
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 4.8832 | 13.4338 | 3.0472 | 199.8954
[22 empty] | Fuel | Material | LTR | 1.76 | 0.54258 | 3.2438 | 27.4247 | 48.2674
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.99617 | 48.1845 | 14.9372 | 716.9849
[22 empty] | Fuel | Material | LTR | 1.76 | 0.099617 | 17.6676 | 149.3719 | 262.8945
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 2.4416 | 14.7444 | 6.0944 | 219.3974
[22 empty] | Fuel | Material | LTR | 1.76 | 0.27129 | 6.4876 | 54.8493 | 96.5348
[22 empty] | Plate Compactor | Machinery | HR | 23 | 0.25 | 92 | 59.52 | 1368.96
[22 empty] | Fuel | Material | LTR | 1.76 | 0.083333 | 21.12 | 178.56 | 314.2656
SEW 10 |  | At a depth of 3.5 - 4.0 m (GRP) | nr | 11.67 | 32099 | 374595.33 | 10092.9911 | 117785.2063 | 11.67 | 11.67 |  | 11.67 | 100% | 32099 | 374595.33 | 10092.9911 | 117785.2063 |  | 117785.2063 | [7 empty] | 10092.9911 | 11.67 | 117785.2063 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 11.67 | 11.67 |  | 11.67 | [9 empty] | Excavate & Disposal (2.5*2.5*4.5) |  | Ea | 113.1212 |  | 113.1212 | 11.67 | 1320.1241 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 3.5556 | 15.75 | 3.2822 | 183.8025
[22 empty] | Fuel | Material | LTR | 1.76 | 0.25397 | 6.93 | 45.9506 | 80.8731
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.72533 | 66.1765 | 16.0892 | 772.2794
[22 empty] | Fuel | Material | LTR | 1.76 | 0.072533 | 24.2647 | 160.8915 | 283.1691
[9 empty] | 11.67 | 11.67 |  | 11.67 | [9 empty] | Concrete Base 30 cm |  | Ea | 1432.696 |  | 1432.696 | 11.67 | 16719.5623 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 2.2676 | 110.25 | 5.1465 | 1286.6175
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.83333 | 420 | 14.004 | 4901.4
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 10.4167 | 240 | 1.1203 | 2800.8
[22 empty] | Workmanship plain concrete | SC | M³ | 150 | 2.2676 | 66.15 | 5.1465 | 771.9705
[22 empty] | Workmanship RC concrete | SC | M³ | 450 | 0.83333 | 540 | 14.004 | 6301.8
[22 empty] | 2 Layers Bituminous Application | SC | M² | 10 | 0.17763 | 56.296 | 65.6974 | 656.9743
[9 empty] | 11.67 | 11.67 |  | 11.67 | [9 empty] | Manhole Installation |  | Ea | 8072.8 |  | 8072.8 | 11.67 | 94209.576 | 0 | 0 | 0 | 0 | 0
[22 empty] | GRP manhole Dia 1200 mm D=4.0 m W Cover | Material | Ea | 6300 | 1 | 6300 | 11.67 | 73521
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 0.5 | 160 | 23.34 | 1867.2
[22 empty] | Fuel | Material | HR | 1.76 | 0.033333 | 52.8 | 350.1 | 616.176
[22 empty] | Brick & Masonery for Manhole Neck | SC | LS | 1500 | 1 | 1500 | 11.67 | 17505
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.5 | 34 | 23.34 | 396.78
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.5 | 26 | 23.34 | 303.42
[9 empty] | 11.67 | 11.67 |  | 11.67 | [9 empty] | Backfilling |  | Ea | 474.3739 |  | 474.3739 | 11.67 | 5535.9439 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.043406 | 230.382 | 268.8558 | 2688.5579
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 4.3406 | 15.1131 | 2.6886 | 176.3694
[22 empty] | Fuel | Material | LTR | 1.76 | 0.48229 | 3.6493 | 24.197 | 42.5868
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.88549 | 54.2075 | 13.1792 | 632.6019
[22 empty] | Fuel | Material | LTR | 1.76 | 0.088549 | 19.8761 | 131.7921 | 231.954
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 2.1703 | 16.5875 | 5.3771 | 193.5762
[22 empty] | Fuel | Material | LTR | 1.76 | 0.24115 | 7.2985 | 48.394 | 85.1735
[22 empty] | Plate Compactor | Machinery | HR | 23 | 0.22222 | 103.5 | 52.515 | 1207.845
[22 empty] | Fuel | Material | LTR | 1.76 | 0.074074 | 23.76 | 157.545 | 277.2792
SEW 10 |  | At a depth of 4.0 - 4.5 m (GRP) | nr | 21.71 | 36757 | 797994.47 | 11058.2684 | 240075.0059 | 21.71 | 21.71 |  | 21.71 | 100% | 36757 | 797994.47 | 11058.2684 | 240075.0059 |  | 240075.0059 | [7 empty] | 11058.2684 | 21.71 | 240075.0059 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 21.71 | 21.71 |  | 21.71 | [9 empty] | Excavate & Disposal (2.5*2.5*5.0) |  | Ea | 125.6902 |  | 125.6902 | 21.71 | 2728.7342 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 3.2 | 17.5 | 6.7844 | 379.925
[22 empty] | Fuel | Material | LTR | 1.76 | 0.22857 | 7.7 | 94.9812 | 167.167
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.6528 | 73.5294 | 33.2567 | 1596.3235
[22 empty] | Fuel | Material | LTR | 1.76 | 0.06528 | 26.9608 | 332.5674 | 585.3186
[9 empty] | 21.71 | 21.71 |  | 21.71 | [9 empty] | Concrete Base 30 cm |  | Ea | 1432.696 |  | 1432.696 | 21.71 | 31103.8302 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 2.2676 | 110.25 | 9.5741 | 2393.5275
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.83333 | 420 | 26.052 | 9118.2
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 10.4167 | 240 | 2.0842 | 5210.4
[22 empty] | Workmanship plain concrete | SC | M³ | 150 | 2.2676 | 66.15 | 9.5741 | 1436.1165
[22 empty] | Workmanship RC concrete | SC | M³ | 450 | 0.83333 | 540 | 26.052 | 11723.4
[22 empty] | 2 Layers Bituminous Application | SC | M² | 10 | 0.17763 | 56.296 | 122.2186 | 1222.1862
[9 empty] | 21.71 | 21.71 |  | 21.71 | [9 empty] | Manhole Installation |  | Ea | 8972.8 |  | 8972.8 | 21.71 | 194799.488 | 0 | 0 | 0 | 0 | 0
[22 empty] | GRP manhole Dia 1200 mm D=4.5 m W Cover | Material | Ea | 7200 | 1 | 7200 | 21.71 | 156312
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 0.5 | 160 | 43.42 | 3473.6
[22 empty] | Fuel | Material | HR | 1.76 | 0.033333 | 52.8 | 651.3 | 1146.288
[22 empty] | Brick & Masonery for Manhole Neck | SC | LS | 1500 | 1 | 1500 | 21.71 | 32565
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.5 | 34 | 43.42 | 738.14
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.5 | 26 | 43.42 | 564.46
[9 empty] | 21.71 | 21.71 |  | 21.71 | [9 empty] | Backfilling |  | Ea | 527.0822 |  | 527.0822 | 21.71 | 11442.9536 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.039066 | 255.98 | 555.7326 | 5557.3258
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 3.9066 | 16.7923 | 5.5573 | 364.5606
[22 empty] | Fuel | Material | LTR | 1.76 | 0.43406 | 4.0547 | 50.0159 | 88.028
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.79694 | 60.2306 | 27.2418 | 1307.6061
[22 empty] | Fuel | Material | LTR | 1.76 | 0.079694 | 22.0845 | 272.4179 | 479.4556
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 1.9533 | 18.4306 | 11.1147 | 400.1275
[22 empty] | Fuel | Material | LTR | 1.76 | 0.21703 | 8.1094 | 100.0319 | 176.0561
[22 empty] | Plate Compactor | Machinery | HR | 23 | 0.2 | 115 | 108.55 | 2496.65
[22 empty] | Fuel | Material | LTR | 1.76 | 0.066667 | 26.4 | 325.65 | 573.144
SEW 10 |  | At a depth of 4.5 - 5.0 m (GRP) | nr | 15.6 | 40533 | 632314.8 | 11923.5456 | 186007.3111 | 15.6 | 15.6 |  | 15.6 | 100% | 40533 | 632314.8 | 11923.5456 | 186007.3111 |  | 186007.3111 | [7 empty] | 11923.5456 | 15.6 | 186007.3111 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 15.6 | 15.6 |  | 15.6 | [9 empty] | Excavate & Disposal (2.5*2.5*5.5) |  | Ea | 138.2592 |  | 138.2592 | 15.6 | 2156.8438 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 2.9091 | 19.25 | 5.3625 | 300.3
[22 empty] | Fuel | Material | LTR | 1.76 | 0.20779 | 8.47 | 75.075 | 132.132
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.59345 | 80.8824 | 26.2868 | 1261.7647
[22 empty] | Fuel | Material | LTR | 1.76 | 0.059345 | 29.6569 | 262.8676 | 462.6471
[9 empty] | 15.6 | 15.6 |  | 15.6 | [9 empty] | Concrete Base 30 cm |  | Ea | 1432.696 |  | 1432.696 | 15.6 | 22350.0576 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 2.2676 | 110.25 | 6.8796 | 1719.9
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.83333 | 420 | 18.72 | 6552
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 10.4167 | 240 | 1.4976 | 3744
[22 empty] | Workmanship plain concrete | SC | M³ | 150 | 2.2676 | 66.15 | 6.8796 | 1031.94
[22 empty] | Workmanship RC concrete | SC | M³ | 450 | 0.83333 | 540 | 18.72 | 8424
[22 empty] | 2 Layers Bituminous Application | SC | M² | 10 | 0.17763 | 56.296 | 87.8218 | 878.2176
[9 empty] | 15.6 | 15.6 |  | 15.6 | [9 empty] | Manhole Installation |  | Ea | 9772.8 |  | 9772.8 | 15.6 | 152455.68 | 0 | 0 | 0 | 0 | 0
[22 empty] | GRP manhole Dia 1200 mm D=5.0 m W Cover | Material | Ea | 8000 | 1 | 8000 | 15.6 | 124800
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 0.5 | 160 | 31.2 | 2496
[22 empty] | Fuel | Material | HR | 1.76 | 0.033333 | 52.8 | 468 | 823.68
[22 empty] | Brick & Masonery for Manhole Neck | SC | LS | 1500 | 1 | 1500 | 15.6 | 23400
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.5 | 34 | 31.2 | 530.4
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.5 | 26 | 31.2 | 405.6
[9 empty] | 15.6 | 15.6 |  | 15.6 | [9 empty] | Backfilling |  | Ea | 579.7904 |  | 579.7904 | 15.6 | 9044.7298 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.035514 | 281.578 | 439.2617 | 4392.6168
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 3.5514 | 18.4715 | 4.3926 | 288.1557
[22 empty] | Fuel | Material | LTR | 1.76 | 0.3946 | 4.4602 | 39.5336 | 69.5791
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.72449 | 66.2536 | 21.5324 | 1033.5569
[22 empty] | Fuel | Material | LTR | 1.76 | 0.072449 | 24.293 | 215.3244 | 378.9709
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 1.7757 | 20.2736 | 8.7852 | 316.2684
[22 empty] | Fuel | Material | LTR | 1.76 | 0.1973 | 8.9204 | 79.0671 | 139.1581
[22 empty] | Plate Compactor | Machinery | HR | 23 | 0.18182 | 126.5 | 85.8 | 1973.4
[22 empty] | Fuel | Material | LTR | 1.76 | 0.060606 | 29.04 | 257.4 | 453.024
SEW 10 |  | At a depth of 5.0 - 5.5 m (GRP) | nr | 3.33 | 44436 | 147971.88 | 12838.8228 | 42753.28 | 3.33 | 3.33 |  | 3.33 | 100% | 44436 | 147971.88 | 12838.8228 | 42753.28 |  | 42753.28 | [7 empty] | 12838.8228 | 3.33 | 42753.28 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 3.33 | 3.33 |  | 3.33 | [9 empty] | Excavate & Disposal (2.5*2.5*6.0) |  | Ea | 150.8282 |  | 150.8282 | 3.33 | 502.258 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 2.6667 | 21 | 1.2487 | 69.93
[22 empty] | Fuel | Material | LTR | 1.76 | 0.19048 | 9.24 | 17.4825 | 30.7692
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.544 | 88.2353 | 6.1213 | 293.8235
[22 empty] | Fuel | Material | LTR | 1.76 | 0.0544 | 32.3529 | 61.2132 | 107.7353
[9 empty] | 3.33 | 3.33 |  | 3.33 | [9 empty] | Concrete Base 30 cm |  | Ea | 1432.696 |  | 1432.696 | 3.33 | 4770.8777 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 2.2676 | 110.25 | 1.4685 | 367.1325
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.83333 | 420 | 3.996 | 1398.6
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 10.4167 | 240 | 0.31968 | 799.2
[22 empty] | Workmanship plain concrete | SC | M³ | 150 | 2.2676 | 66.15 | 1.4685 | 220.2795
[22 empty] | Workmanship RC concrete | SC | M³ | 450 | 0.83333 | 540 | 3.996 | 1798.2
[22 empty] | 2 Layers Bituminous Application | SC | M² | 10 | 0.17763 | 56.296 | 18.7466 | 187.4657
[9 empty] | 3.33 | 3.33 |  | 3.33 | [9 empty] | Manhole Installation |  | Ea | 10622.8 |  | 10622.8 | 3.33 | 35373.924 | 0 | 0 | 0 | 0 | 0
[22 empty] | GRP manhole Dia 1200 mm D=5.5 m W Cover | Material | Ea | 8850 | 1 | 8850 | 3.33 | 29470.5
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 0.5 | 160 | 6.66 | 532.8
[22 empty] | Fuel | Material | HR | 1.76 | 0.033333 | 52.8 | 99.9 | 175.824
[22 empty] | Brick & Masonery for Manhole Neck | SC | LS | 1500 | 1 | 1500 | 3.33 | 4995
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.5 | 34 | 6.66 | 113.22
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.5 | 26 | 6.66 | 86.58
[9 empty] | 3.33 | 3.33 |  | 3.33 | [9 empty] | Backfilling |  | Ea | 632.4986 |  | 632.4986 | 3.33 | 2106.2203 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.032555 | 307.176 | 102.2896 | 1022.8961
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 3.2555 | 20.1507 | 1.0229 | 67.102
[22 empty] | Fuel | Material | LTR | 1.76 | 0.36172 | 4.8657 | 9.2061 | 16.2027
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.66411 | 72.2767 | 5.0142 | 240.6814
[22 empty] | Fuel | Material | LTR | 1.76 | 0.066411 | 26.5015 | 50.142 | 88.2499
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 1.6277 | 22.1167 | 2.0458 | 73.6485
[22 empty] | Fuel | Material | LTR | 1.76 | 0.18086 | 9.7313 | 18.4121 | 32.4053
[22 empty] | Plate Compactor | Machinery | HR | 23 | 0.16667 | 138 | 19.98 | 459.54
[22 empty] | Fuel | Material | LTR | 1.76 | 0.055556 | 31.68 | 59.94 | 105.4944
SEW 10 |  | At a depth of 5.5 - 6.0 m (GRP) | nr | 5.37 | 48464 | 260251.68 | 13704.1001 | 73591.0173 | 5.37 | 5.37 |  | 5.37 | 100% | 48464 | 260251.68 | 13704.1001 | 73591.0173 |  | 73591.0173 | [7 empty] | 13704.1001 | 5.37 | 73591.0173 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 5.37 | 5.37 |  | 5.37 | [9 empty] | Excavate & Disposal (2.5*2.5*6.5) |  | Ea | 163.3973 |  | 163.3973 | 5.37 | 877.4433 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 2.4615 | 22.75 | 2.1816 | 122.1675
[22 empty] | Fuel | Material | LTR | 1.76 | 0.17582 | 10.01 | 30.5419 | 53.7537
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.50215 | 95.5882 | 10.6939 | 513.3088
[22 empty] | Fuel | Material | LTR | 1.76 | 0.050215 | 35.049 | 106.9393 | 188.2132
[9 empty] | 5.37 | 5.37 |  | 5.37 | [9 empty] | Concrete Base 30 cm |  | Ea | 1432.696 |  | 1432.696 | 5.37 | 7693.5775 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 2.2676 | 110.25 | 2.3682 | 592.0425
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.83333 | 420 | 6.444 | 2255.4
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 10.4167 | 240 | 0.51552 | 1288.8
[22 empty] | Workmanship plain concrete | SC | M³ | 150 | 2.2676 | 66.15 | 2.3682 | 355.2255
[22 empty] | Workmanship RC concrete | SC | M³ | 450 | 0.83333 | 540 | 6.444 | 2899.8
[22 empty] | 2 Layers Bituminous Application | SC | M² | 10 | 0.17763 | 56.296 | 30.231 | 302.3095
[9 empty] | 5.37 | 5.37 |  | 5.37 | [9 empty] | Manhole Installation |  | Ea | 11422.8 |  | 11422.8 | 5.37 | 61340.436 | 0 | 0 | 0 | 0 | 0
[22 empty] | GRP manhole Dia 1200 mm D=6.0 m W Cover | Material | Ea | 9650 | 1 | 9650 | 5.37 | 51820.5
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 0.5 | 160 | 10.74 | 859.2
[22 empty] | Fuel | Material | HR | 1.76 | 0.033333 | 52.8 | 161.1 | 283.536
[22 empty] | Brick & Masonery for Manhole Neck | SC | LS | 1500 | 1 | 1500 | 5.37 | 8055
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.5 | 34 | 10.74 | 182.58
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.5 | 26 | 10.74 | 139.62
[9 empty] | 5.37 | 5.37 |  | 5.37 | [9 empty] | Backfilling |  | Ea | 685.2068 |  | 685.2068 | 5.37 | 3679.5605 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.03005 | 332.774 | 178.6996 | 1786.9964
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 3.005 | 21.83 | 1.787 | 117.227
[22 empty] | Fuel | Material | LTR | 1.76 | 0.33389 | 5.2711 | 16.083 | 28.306
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.61303 | 78.2998 | 8.7598 | 420.4697
[22 empty] | Fuel | Material | LTR | 1.76 | 0.061303 | 28.7099 | 87.5979 | 154.1722
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 1.5025 | 23.9597 | 3.574 | 128.6637
[22 empty] | Fuel | Material | LTR | 1.76 | 0.16695 | 10.5423 | 32.1659 | 56.612
[22 empty] | Plate Compactor | Machinery | HR | 23 | 0.15385 | 149.5 | 34.905 | 802.815
[22 empty] | Fuel | Material | LTR | 1.76 | 0.051282 | 34.32 | 104.715 | 184.2984
SEW 10 |  | Increasing the depth difference by 0.5 m for 1200 mm diameter manhole chambers (GRP) | nr |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | Increasing the depth difference of 1.0 m for 1200 mm diameter manhole chambers (GRP) | nr |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | Increasing the depth difference by 1.5 m for 1200 mm diameter manhole chambers (GRP) | nr |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | Increasing the depth difference by 2.0 m for 1200 mm diameter manhole chambers (GRP) | nr |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | Increasing the depth difference by 2.5 m for 1200 mm diameter manhole chambers (GRP) | nr |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | Increased depth difference of 3.0 m for 1200 mm diameter manhole chambers (GRP) | nr |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | Increasing the depth difference of 3.5 m for 1200 mm diameter manhole chambers (GRP) | nr |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | Increased depth difference of 4.0 m for 1200 mm diameter manhole chambers (GRP) | nr |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | Increasing the depth difference of 4.5 m for 1200 mm diameter manhole chambers (GRP) | nr |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | Increased depth difference of 5.0 m for 1200 mm diameter manhole chambers (GRP) | nr |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | Backdrop manholes |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | Inspection chambers equipped with one opening (with vertical pipe and concrete skirting equipment), the necessary excavation and concrete construction, a GRP lining, an insulating layer with a protection board, and originally equipped short pipes (built-in), with a frame and cover of a good and tight type, according to the drawings. |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | Manholes with a back drop, diameter 1200 mm |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | At a depth of 2.5 - 3.0 m (GRP) | nr |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | At a depth of 3.0 - 3.5 m (GRP) | nr | 0.04 | 27725 | 1109 | 12577.7139 | 503.1086 | 0.04 | 0.04 |  | 0.04 | 100% | 27725 | 1109 | 12577.7139 | 503.1086 |  | 503.1086 | [7 empty] | 12577.7139 | 0.04 | 503.1086 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 0.04 | 0.04 |  | 0.04 | [9 empty] | Excavate & Disposal (2.5*2.5*4.0) |  | Ea | 100.5522 |  | 100.5522 | 0.04 | 4.0221 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 4 | 14 | 0.01 | 0.56
[22 empty] | Fuel | Material | LTR | 1.76 | 0.28571 | 6.16 | 0.14 | 0.2464
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.816 | 58.8235 | 0.04902 | 2.3529
[22 empty] | Fuel | Material | LTR | 1.76 | 0.0816 | 21.5686 | 0.4902 | 0.86275
[9 empty] | 0.04 | 0.04 |  | 0.04 | [9 empty] | Concrete Base 30 cm |  | Ea | 1432.696 |  | 1432.696 | 0.04 | 57.3078 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 2.2676 | 110.25 | 0.01764 | 4.41
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.83333 | 420 | 0.048 | 16.8
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 10.4167 | 240 | 0.00384 | 9.6
[22 empty] | Workmanship plain concrete | SC | M³ | 150 | 2.2676 | 66.15 | 0.01764 | 2.646
[22 empty] | Workmanship RC concrete | SC | M³ | 450 | 0.83333 | 540 | 0.048 | 21.6
[22 empty] | 2 Layers Bituminous Application | SC | M² | 10 | 0.17763 | 56.296 | 0.22518 | 2.2518
[9 empty] | 0.04 | 0.04 |  | 0.04 | [9 empty] | Manhole Installation |  | Ea | 10622.8 |  | 10622.8 | 0.04 | 424.912 | 0 | 0 | 0 | 0 | 0
[22 empty] | GRP manhole Dia 1200 mm D=3.5 m W Cover | Material | Ea | 5350 | 1 | 5350 | 0.04 | 214
[22 empty] | Manhole Back drop PCs | Material | LS | 3500 | 1 | 3500 | 0.04 | 140
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 0.5 | 160 | 0.08 | 6.4
[22 empty] | Fuel | Material | HR | 1.76 | 0.033333 | 52.8 | 1.2 | 2.112
[22 empty] | Brick & Masonery for Manhole Neck | SC | LS | 1500 | 1 | 1500 | 0.04 | 60
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.5 | 34 | 0.08 | 1.36
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.5 | 26 | 0.08 | 1.04
[9 empty] | 0.04 | 0.04 |  | 0.04 | [9 empty] | Backfilling |  | Ea | 421.6657 |  | 421.6657 | 0.04 | 16.8666 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.048832 | 204.784 | 0.81914 | 8.1914
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 4.8832 | 13.4338 | 0.0081914 | 0.53735
[22 empty] | Fuel | Material | LTR | 1.76 | 0.54258 | 3.2438 | 0.073722 | 0.12975
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.99617 | 48.1845 | 0.040154 | 1.9274
[22 empty] | Fuel | Material | LTR | 1.76 | 0.099617 | 17.6676 | 0.40154 | 0.70671
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 2.4416 | 14.7444 | 0.016383 | 0.58978
[22 empty] | Fuel | Material | LTR | 1.76 | 0.27129 | 6.4876 | 0.14744 | 0.2595
[22 empty] | Plate Compactor | Machinery | HR | 23 | 0.25 | 92 | 0.16 | 3.68
[22 empty] | Fuel | Material | LTR | 1.76 | 0.083333 | 21.12 | 0.48 | 0.8448
SEW 10 |  | At a depth of 3.5 - 4.0 m (GRP) | nr | 1.19 | 24641 | 29322.79 | 13592.9911 | 16175.6594 | 1.19 | 1.19 |  | 1.19 | 100% | 24641 | 29322.79 | 13592.9911 | 16175.6594 |  | 16175.6594 | [7 empty] | 13592.9911 | 1.19 | 16175.6594 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 1.19 | 1.19 |  | 1.19 | [9 empty] | Excavate & Disposal (2.5*2.5*4.5) |  | Ea | 113.1212 |  | 113.1212 | 1.19 | 134.6142 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 3.5556 | 15.75 | 0.33469 | 18.7425
[22 empty] | Fuel | Material | LTR | 1.76 | 0.25397 | 6.93 | 4.6856 | 8.2467
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.72533 | 66.1765 | 1.6406 | 78.75
[22 empty] | Fuel | Material | LTR | 1.76 | 0.072533 | 24.2647 | 16.4062 | 28.875
[9 empty] | 1.19 | 1.19 |  | 1.19 | [9 empty] | Concrete Base 30 cm |  | Ea | 1432.696 |  | 1432.696 | 1.19 | 1704.9082 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 2.2676 | 110.25 | 0.52479 | 131.1975
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.83333 | 420 | 1.428 | 499.8
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 10.4167 | 240 | 0.11424 | 285.6
[22 empty] | Workmanship plain concrete | SC | M³ | 150 | 2.2676 | 66.15 | 0.52479 | 78.7185
[22 empty] | Workmanship RC concrete | SC | M³ | 450 | 0.83333 | 540 | 1.428 | 642.6
[22 empty] | 2 Layers Bituminous Application | SC | M² | 10 | 0.17763 | 56.296 | 6.6992 | 66.9922
[9 empty] | 1.19 | 1.19 |  | 1.19 | [9 empty] | Manhole Installation |  | Ea | 11572.8 |  | 11572.8 | 1.19 | 13771.632 | 0 | 0 | 0 | 0 | 0
[22 empty] | GRP manhole Dia 1200 mm D=4.0 m W Cover | Material | Ea | 6300 | 1 | 6300 | 1.19 | 7497
[22 empty] | Manhole Back drop PCs | Material | LS | 3500 | 1 | 3500 | 1.19 | 4165
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 0.5 | 160 | 2.38 | 190.4
[22 empty] | Fuel | Material | HR | 1.76 | 0.033333 | 52.8 | 35.7 | 62.832
[22 empty] | Brick & Masonery for Manhole Neck | SC | LS | 1500 | 1 | 1500 | 1.19 | 1785
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.5 | 34 | 2.38 | 40.46
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.5 | 26 | 2.38 | 30.94
[9 empty] | 1.19 | 1.19 |  | 1.19 | [9 empty] | Backfilling |  | Ea | 474.3739 |  | 474.3739 | 1.19 | 564.505 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.043406 | 230.382 | 27.4155 | 274.1546
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 4.3406 | 15.1131 | 0.27415 | 17.9845
[22 empty] | Fuel | Material | LTR | 1.76 | 0.48229 | 3.6493 | 2.4674 | 4.3426
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.88549 | 54.2075 | 1.3439 | 64.507
[22 empty] | Fuel | Material | LTR | 1.76 | 0.088549 | 19.8761 | 13.4389 | 23.6526
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 2.1703 | 16.5875 | 0.54831 | 19.7391
[22 empty] | Fuel | Material | LTR | 1.76 | 0.24115 | 7.2985 | 4.9348 | 8.6852
[22 empty] | Plate Compactor | Machinery | HR | 23 | 0.22222 | 103.5 | 5.355 | 123.165
[22 empty] | Fuel | Material | LTR | 1.76 | 0.074074 | 23.76 | 16.065 | 28.2744
SEW 10 |  | At a depth of 4.0 - 4.5 m (GRP) | nr | 0.09 | 47898 | 4310.82 | 14558.2684 | 1310.2442 | 0.09 | 0.09 |  | 0.09 | 100% | 47898 | 4310.82 | 14558.2684 | 1310.2442 |  | 1310.2442 | [7 empty] | 14558.2684 | 0.09 | 1310.2442 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 0.09 | 0.09 |  | 0.09 | [9 empty] | Excavate & Disposal (2.5*2.5*5.0) |  | Ea | 125.6902 |  | 125.6902 | 0.09 | 11.3121 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 3.2 | 17.5 | 0.028125 | 1.575
[22 empty] | Fuel | Material | LTR | 1.76 | 0.22857 | 7.7 | 0.39375 | 0.693
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.6528 | 73.5294 | 0.13787 | 6.6176
[22 empty] | Fuel | Material | LTR | 1.76 | 0.06528 | 26.9608 | 1.3787 | 2.4265
[9 empty] | 0.09 | 0.09 |  | 0.09 | [9 empty] | Concrete Base 30 cm |  | Ea | 1432.696 |  | 1432.696 | 0.09 | 128.9426 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 2.2676 | 110.25 | 0.03969 | 9.9225
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.83333 | 420 | 0.108 | 37.8
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 10.4167 | 240 | 0.00864 | 21.6
[22 empty] | Workmanship plain concrete | SC | M³ | 150 | 2.2676 | 66.15 | 0.03969 | 5.9535
[22 empty] | Workmanship RC concrete | SC | M³ | 450 | 0.83333 | 540 | 0.108 | 48.6
[22 empty] | 2 Layers Bituminous Application | SC | M² | 10 | 0.17763 | 56.296 | 0.50666 | 5.0666
[9 empty] | 0.09 | 0.09 |  | 0.09 | [9 empty] | Manhole Installation |  | Ea | 12472.8 |  | 12472.8 | 0.09 | 1122.552 | 0 | 0 | 0 | 0 | 0
[22 empty] | GRP manhole Dia 1200 mm D=4.5 m W Cover | Material | Ea | 7200 | 1 | 7200 | 0.09 | 648
[22 empty] | Manhole Back drop PCs | Material | LS | 3500 | 1 | 3500 | 0.09 | 315
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 0.5 | 160 | 0.18 | 14.4
[22 empty] | Fuel | Material | HR | 1.76 | 0.033333 | 52.8 | 2.7 | 4.752
[22 empty] | Brick & Masonery for Manhole Neck | SC | LS | 1500 | 1 | 1500 | 0.09 | 135
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.5 | 34 | 0.18 | 3.06
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.5 | 26 | 0.18 | 2.34
[9 empty] | 0.09 | 0.09 |  | 0.09 | [9 empty] | Backfilling |  | Ea | 527.0822 |  | 527.0822 | 0.09 | 47.4374 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.039066 | 255.98 | 2.3038 | 23.0382
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 3.9066 | 16.7923 | 0.023038 | 1.5113
[22 empty] | Fuel | Material | LTR | 1.76 | 0.43406 | 4.0547 | 0.20734 | 0.36493
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.79694 | 60.2306 | 0.11293 | 5.4208
[22 empty] | Fuel | Material | LTR | 1.76 | 0.079694 | 22.0845 | 1.1293 | 1.9876
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 1.9533 | 18.4306 | 0.046076 | 1.6588
[22 empty] | Fuel | Material | LTR | 1.76 | 0.21703 | 8.1094 | 0.41469 | 0.72985
[22 empty] | Plate Compactor | Machinery | HR | 23 | 0.2 | 115 | 0.45 | 10.35
[22 empty] | Fuel | Material | LTR | 1.76 | 0.066667 | 26.4 | 1.35 | 2.376
SEW 10 |  | At a depth of 4.5 - 5.0 m (GRP) | nr | 0.07 | 43681 | 3057.67 | 15423.5456 | 1079.6482 | 0.07 | 0.07 |  | 0.07 | 100% | 43681 | 3057.67 | 15423.5456 | 1079.6482 |  | 1079.6482 | [7 empty] | 15423.5456 | 0.07 | 1079.6482 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 0.07 | 0.07 |  | 0.07 | [9 empty] | Excavate & Disposal (2.5*2.5*5.5) |  | Ea | 138.2592 |  | 138.2592 | 0.07 | 9.6781 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 2.9091 | 19.25 | 0.024062 | 1.3475
[22 empty] | Fuel | Material | LTR | 1.76 | 0.20779 | 8.47 | 0.33687 | 0.5929
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.59345 | 80.8824 | 0.11795 | 5.6618
[22 empty] | Fuel | Material | LTR | 1.76 | 0.059345 | 29.6569 | 1.1795 | 2.076
[9 empty] | 0.07 | 0.07 |  | 0.07 | [9 empty] | Concrete Base 30 cm |  | Ea | 1432.696 |  | 1432.696 | 0.07 | 100.2887 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 2.2676 | 110.25 | 0.03087 | 7.7175
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.83333 | 420 | 0.084 | 29.4
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 10.4167 | 240 | 0.00672 | 16.8
[22 empty] | Workmanship plain concrete | SC | M³ | 150 | 2.2676 | 66.15 | 0.03087 | 4.6305
[22 empty] | Workmanship RC concrete | SC | M³ | 450 | 0.83333 | 540 | 0.084 | 37.8
[22 empty] | 2 Layers Bituminous Application | SC | M² | 10 | 0.17763 | 56.296 | 0.39407 | 3.9407
[9 empty] | 0.07 | 0.07 |  | 0.07 | [9 empty] | Manhole Installation |  | Ea | 13272.8 |  | 13272.8 | 0.07 | 929.096 | 0 | 0 | 0 | 0 | 0
[22 empty] | GRP manhole Dia 1200 mm D=5.0 m W Cover | Material | Ea | 8000 | 1 | 8000 | 0.07 | 560
[22 empty] | Manhole Back drop PCs | Material | LS | 3500 | 1 | 3500 | 0.07 | 245
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 0.5 | 160 | 0.14 | 11.2
[22 empty] | Fuel | Material | HR | 1.76 | 0.033333 | 52.8 | 2.1 | 3.696
[22 empty] | Brick & Masonery for Manhole Neck | SC | LS | 1500 | 1 | 1500 | 0.07 | 105
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.5 | 34 | 0.14 | 2.38
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.5 | 26 | 0.14 | 1.82
[9 empty] | 0.07 | 0.07 |  | 0.07 | [9 empty] | Backfilling |  | Ea | 579.7904 |  | 579.7904 | 0.07 | 40.5853 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.035514 | 281.578 | 1.971 | 19.7105
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 3.5514 | 18.4715 | 0.01971 | 1.293
[22 empty] | Fuel | Material | LTR | 1.76 | 0.3946 | 4.4602 | 0.17739 | 0.31221
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.72449 | 66.2536 | 0.09662 | 4.6378
[22 empty] | Fuel | Material | LTR | 1.76 | 0.072449 | 24.293 | 0.9662 | 1.7005
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 1.7757 | 20.2736 | 0.039421 | 1.4192
[22 empty] | Fuel | Material | LTR | 1.76 | 0.1973 | 8.9204 | 0.35479 | 0.62443
[22 empty] | Plate Compactor | Machinery | HR | 23 | 0.18182 | 126.5 | 0.385 | 8.855
[22 empty] | Fuel | Material | LTR | 1.76 | 0.060606 | 29.04 | 1.155 | 2.0328
SEW 10 |  | At a depth of 5.0 - 5.5 m (GRP) | nr |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | At a depth of 5.5 - 6.0 m (GRP) | nr |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | Manhole rooms |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | Concrete sanitary manholes include excavation, backfilling, waste disposal, dewatering, sanitation concrete, concrete pour, foundations, walls, roof slab, reinforcement, formwork, concrete room frames, brickwork, waterproofing, DI cover with openings and frame, chains, pipes, fittings, spacers, pipe connections, etc., complete in accordance with the plans, specifications and requirements of the concerned authority, dewatering, strengthening and protecting the excavated surfaces all the way up. To the required depths and the disposal of groundwater resulting from drainage around it is measured individually |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | Manhole chambers with a diameter of 1500 mm |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | At a depth of 1.5 - 2.0 m (GRP) | nr | 0.018069 | 24547 | 443.5389 | 8320.3097 | 150.3394 | 0.018069 | 0.018069 |  | 0.018069 | 100% | 24547 | 443.5389 | 8320.3097 | 150.3394 |  | 150.3394 | [7 empty] | 8320.3097 | 0.018069 | 150.3394 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 0.018069 | 0.018069 |  | 0.018069 | [9 empty] | Excavate & Disposal (3.0*3.0*2.5) |  | Ea | 90.4969 |  | 90.4969 | 0.018069 | 1.6352 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 4.4444 | 12.6 | 0.0040655 | 0.22767
[22 empty] | Fuel | Material | LTR | 1.76 | 0.31746 | 5.544 | 0.056917 | 0.10017
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.90667 | 52.9412 | 0.019929 | 0.95659
[22 empty] | Fuel | Material | LTR | 1.76 | 0.090667 | 19.4118 | 0.19929 | 0.35075
[9 empty] | 0.018069 | 0.018069 |  | 0.018069 | [9 empty] | Concrete Base 30 cm |  | Ea | 1883.8375 |  | 1883.8375 | 0.018069 | 34.039 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 1.7361 | 144 | 0.010408 | 2.6019
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.63012 | 555.45 | 0.028675 | 10.0364
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 7.8765 | 317.4 | 0.002294 | 5.7351
[22 empty] | Workmanship plain concrete | SC | M³ | 150 | 1.7361 | 86.4 | 0.010408 | 1.5612
[22 empty] | Workmanship RC concrete | SC | M³ | 450 | 0.63012 | 714.15 | 0.028675 | 12.904
[22 empty] | 2 Layers Bituminous Application | SC | M² | 10 | 0.15052 | 66.4375 | 0.12005 | 1.2005
[9 empty] | 0.018069 | 0.018069 |  | 0.018069 | [9 empty] | Manhole Installation |  | Ea | 6002.8 |  | 6002.8 | 0.018069 | 108.4644 | 0 | 0 | 0 | 0 | 0
[22 empty] | GRP manhole Dia 1500 mm D=2.0 m W Cover | Material | Ea | 4230 | 1 | 4230 | 0.018069 | 76.4317
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 0.5 | 160 | 0.036138 | 2.891
[22 empty] | Fuel | Material | HR | 1.76 | 0.033333 | 52.8 | 0.54207 | 0.95404
[22 empty] | Brick & Masonery for Manhole Neck | SC | LS | 1500 | 1 | 1500 | 0.018069 | 27.1034
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.5 | 34 | 0.036138 | 0.61434
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.5 | 26 | 0.036138 | 0.46979
[9 empty] | 0.018069 | 0.018069 |  | 0.018069 | [9 empty] | Backfilling |  | Ea | 343.1752 |  | 343.1752 | 0.018069 | 6.2008 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.055296 | 180.8438 | 0.32677 | 3.2677
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 5.5296 | 11.8633 | 0.0032677 | 0.21436
[22 empty] | Fuel | Material | LTR | 1.76 | 0.6144 | 2.8646 | 0.029409 | 0.05176
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 1.128 | 42.5515 | 0.016018 | 0.76886
[22 empty] | Fuel | Material | LTR | 1.76 | 0.1128 | 15.6022 | 0.16018 | 0.28192
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 2.7648 | 13.0207 | 0.0065353 | 0.23527
[22 empty] | Fuel | Material | LTR | 1.76 | 0.3072 | 5.7291 | 0.058818 | 0.10352
[22 empty] | Plate Compactor | Machinery | HR | 23 | 0.4 | 57.5 | 0.045172 | 1.039
[22 empty] | Fuel | Material | LTR | 1.76 | 0.13333 | 13.2 | 0.13552 | 0.23851
SEW 10 |  | At a depth of 2.0 - 2.5 m (GRP) | nr | 0.45 | 30652 | 13793.4 | 8887.0441 | 3999.1698 | 0.45 | 0.45 |  | 0.45 | 100% | 30652 | 13793.4 | 8887.0441 | 3999.1698 |  | 3999.1698 | [7 empty] | 8887.0441 | 0.45 | 3999.1698 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 0.45 | 0.45 |  | 0.45 | [9 empty] | Excavate & Disposal (3.0*3.0*3.0) |  | Ea | 108.5963 |  | 108.5963 | 0.45 | 48.8683 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 3.7037 | 15.12 | 0.1215 | 6.804
[22 empty] | Fuel | Material | LTR | 1.76 | 0.26455 | 6.6528 | 1.701 | 2.9938
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.75556 | 63.5294 | 0.59559 | 28.5882
[22 empty] | Fuel | Material | LTR | 1.76 | 0.075556 | 23.2941 | 5.9559 | 10.4824
[9 empty] | 0.45 | 0.45 |  | 0.45 | [9 empty] | Concrete Base 30 cm |  | Ea | 1883.8375 |  | 1883.8375 | 0.45 | 847.7269 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 1.7361 | 144 | 0.2592 | 64.8
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.63012 | 555.45 | 0.71415 | 249.9525
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 7.8765 | 317.4 | 0.057132 | 142.83
[22 empty] | Workmanship plain concrete | SC | M³ | 150 | 1.7361 | 86.4 | 0.2592 | 38.88
[22 empty] | Workmanship RC concrete | SC | M³ | 450 | 0.63012 | 714.15 | 0.71415 | 321.3675
[22 empty] | 2 Layers Bituminous Application | SC | M² | 10 | 0.15052 | 66.4375 | 2.9897 | 29.8969
[9 empty] | 0.45 | 0.45 |  | 0.45 | [9 empty] | Manhole Installation |  | Ea | 6482.8 |  | 6482.8 | 0.45 | 2917.26 | 0 | 0 | 0 | 0 | 0
[22 empty] | GRP manhole Dia 1500 mm D=2.5 m W Cover | Material | Ea | 4710 | 1 | 4710 | 0.45 | 2119.5
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 0.5 | 160 | 0.9 | 72
[22 empty] | Fuel | Material | HR | 1.76 | 0.033333 | 52.8 | 13.5 | 23.76
[22 empty] | Brick & Masonery for Manhole Neck | SC | LS | 1500 | 1 | 1500 | 0.45 | 675
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.5 | 34 | 0.9 | 15.3
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.5 | 26 | 0.9 | 11.7
[9 empty] | 0.45 | 0.45 |  | 0.45 | [9 empty] | Backfilling |  | Ea | 411.8103 |  | 411.8103 | 0.45 | 185.3146 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.04608 | 217.0125 | 9.7656 | 97.6556
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 4.608 | 14.236 | 0.097656 | 6.4062
[22 empty] | Fuel | Material | LTR | 1.76 | 0.512 | 3.4375 | 0.8789 | 1.5469
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.94004 | 51.0618 | 0.4787 | 22.9778
[22 empty] | Fuel | Material | LTR | 1.76 | 0.094004 | 18.7226 | 4.787 | 8.4252
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 2.304 | 15.6249 | 0.19531 | 7.0312
[22 empty] | Fuel | Material | LTR | 1.76 | 0.256 | 6.875 | 1.7578 | 3.0937
[22 empty] | Plate Compactor | Machinery | HR | 23 | 0.33333 | 69 | 1.35 | 31.05
[22 empty] | Fuel | Material | LTR | 1.76 | 0.11111 | 15.84 | 4.05 | 7.128
SEW 10 |  | At a depth of 2.5 - 3.0 m (GRP) | nr | 0.18 | 36757 | 6616.26 | 9413.7785 | 1694.4801 | 0.18 | 0.18 |  | 0.18 | 100% | 36757 | 6616.26 | 9413.7785 | 1694.4801 |  | 1694.4801 | [7 empty] | 9413.7785 | 0.18 | 1694.4801 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 0.18 | 0.18 |  | 0.18 | [9 empty] | Excavate & Disposal (3.0*3.0*3.5) |  | Ea | 126.6957 |  | 126.6957 | 0.18 | 22.8052 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 3.1746 | 17.64 | 0.0567 | 3.1752
[22 empty] | Fuel | Material | LTR | 1.76 | 0.22676 | 7.7616 | 0.7938 | 1.3971
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.64762 | 74.1176 | 0.27794 | 13.3412
[22 empty] | Fuel | Material | LTR | 1.76 | 0.064762 | 27.1765 | 2.7794 | 4.8918
[9 empty] | 0.18 | 0.18 |  | 0.18 | [9 empty] | Concrete Base 30 cm |  | Ea | 1883.8375 |  | 1883.8375 | 0.18 | 339.0907 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 1.7361 | 144 | 0.10368 | 25.92
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.63012 | 555.45 | 0.28566 | 99.981
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 7.8765 | 317.4 | 0.022853 | 57.132
[22 empty] | Workmanship plain concrete | SC | M³ | 150 | 1.7361 | 86.4 | 0.10368 | 15.552
[22 empty] | Workmanship RC concrete | SC | M³ | 450 | 0.63012 | 714.15 | 0.28566 | 128.547
[22 empty] | 2 Layers Bituminous Application | SC | M² | 10 | 0.15052 | 66.4375 | 1.1959 | 11.9587
[9 empty] | 0.18 | 0.18 |  | 0.18 | [9 empty] | Manhole Installation |  | Ea | 6922.8 |  | 6922.8 | 0.18 | 1246.104 | 0 | 0 | 0 | 0 | 0
[22 empty] | GRP manhole Dia 1500 mm D=3.0 m W Cover | Material | Ea | 5150 | 1 | 5150 | 0.18 | 927
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 0.5 | 160 | 0.36 | 28.8
[22 empty] | Fuel | Material | HR | 1.76 | 0.033333 | 52.8 | 5.4 | 9.504
[22 empty] | Brick & Masonery for Manhole Neck | SC | LS | 1500 | 1 | 1500 | 0.18 | 270
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.5 | 34 | 0.36 | 6.12
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.5 | 26 | 0.36 | 4.68
[9 empty] | 0.18 | 0.18 |  | 0.18 | [9 empty] | Backfilling |  | Ea | 480.4453 |  | 480.4453 | 0.18 | 86.4802 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.039497 | 253.1813 | 4.5573 | 45.5726
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 3.9497 | 16.6087 | 0.045573 | 2.9896
[22 empty] | Fuel | Material | LTR | 1.76 | 0.43886 | 4.0104 | 0.41015 | 0.72187
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.80575 | 59.5721 | 0.2234 | 10.723
[22 empty] | Fuel | Material | LTR | 1.76 | 0.080575 | 21.8431 | 2.234 | 3.9318
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 1.9749 | 18.2291 | 0.091145 | 3.2812
[22 empty] | Fuel | Material | LTR | 1.76 | 0.21943 | 8.0208 | 0.82031 | 1.4437
[22 empty] | Plate Compactor | Machinery | HR | 23 | 0.28571 | 80.5 | 0.63 | 14.49
[22 empty] | Fuel | Material | LTR | 1.76 | 0.095238 | 18.48 | 1.89 | 3.3264
SEW 10 |  | At a depth of 3.0 - 3.5 m (GRP) | nr | 6.78 | 42863 | 290611.14 | 10150.513 | 68820.4779 | 6.78 | 6.78 |  | 6.78 | 100% | 42863 | 290611.14 | 10150.513 | 68820.4779 |  | 68820.4779 | [7 empty] | 10150.513 | 6.78 | 68820.4779 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 6.78 | 6.78 |  | 6.78 | [9 empty] | Excavate & Disposal (3.0*3.0*4.0) |  | Ea | 144.7951 |  | 144.7951 | 6.78 | 981.7108 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 2.7778 | 20.16 | 2.4408 | 136.6848
[22 empty] | Fuel | Material | LTR | 1.76 | 0.19841 | 8.8704 | 34.1712 | 60.1413
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.56667 | 84.7059 | 11.9647 | 574.3059
[22 empty] | Fuel | Material | LTR | 1.76 | 0.056667 | 31.0588 | 119.6471 | 210.5788
[9 empty] | 6.78 | 6.78 |  | 6.78 | [9 empty] | Concrete Base 30 cm |  | Ea | 1883.8375 |  | 1883.8375 | 6.78 | 12772.4182 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 1.7361 | 144 | 3.9053 | 976.32
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.63012 | 555.45 | 10.7599 | 3765.951
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 7.8765 | 317.4 | 0.86079 | 2151.972
[22 empty] | Workmanship plain concrete | SC | M³ | 150 | 1.7361 | 86.4 | 3.9053 | 585.792
[22 empty] | Workmanship RC concrete | SC | M³ | 450 | 0.63012 | 714.15 | 10.7599 | 4841.937
[22 empty] | 2 Layers Bituminous Application | SC | M² | 10 | 0.15052 | 66.4375 | 45.0446 | 450.4463
[9 empty] | 6.78 | 6.78 |  | 6.78 | [9 empty] | Manhole Installation |  | Ea | 7572.8 |  | 7572.8 | 6.78 | 51343.584 | 0 | 0 | 0 | 0 | 0
[22 empty] | GRP manhole Dia 1500 mm D=3.5 m W Cover | Material | Ea | 5800 | 1 | 5800 | 6.78 | 39324
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 0.5 | 160 | 13.56 | 1084.8
[22 empty] | Fuel | Material | HR | 1.76 | 0.033333 | 52.8 | 203.4 | 357.984
[22 empty] | Brick & Masonery for Manhole Neck | SC | LS | 1500 | 1 | 1500 | 6.78 | 10170
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.5 | 34 | 13.56 | 230.52
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.5 | 26 | 13.56 | 176.28
[9 empty] | 6.78 | 6.78 |  | 6.78 | [9 empty] | Backfilling |  | Ea | 549.0804 |  | 549.0804 | 6.78 | 3722.7648 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.03456 | 289.35 | 196.1793 | 1961.793
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 3.456 | 18.9814 | 1.9618 | 128.6936
[22 empty] | Fuel | Material | LTR | 1.76 | 0.384 | 4.5833 | 17.6561 | 31.0748
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.70503 | 68.0824 | 9.6166 | 461.5984
[22 empty] | Fuel | Material | LTR | 1.76 | 0.070503 | 24.9635 | 96.1663 | 169.2527
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 1.728 | 20.8332 | 3.9236 | 141.2491
[22 empty] | Fuel | Material | LTR | 1.76 | 0.192 | 9.1666 | 35.3123 | 62.1496
[22 empty] | Plate Compactor | Machinery | HR | 23 | 0.25 | 92 | 27.12 | 623.76
[22 empty] | Fuel | Material | LTR | 1.76 | 0.083333 | 21.12 | 81.36 | 143.1936
SEW 10 |  | At a depth of 3.5 - 4.0 m (GRP) | nr | 1.78 | 49093 | 87385.54 | 10987.2474 | 19557.3004 | 1.78 | 1.78 |  | 1.78 | 100% | 49093 | 87385.54 | 10987.2474 | 19557.3004 |  | 19557.3004 | [7 empty] | 10987.2474 | 1.78 | 19557.3004 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 1.78 | 1.78 |  | 1.78 | [9 empty] | Excavate & Disposal (3.0*3.0*4.5) |  | Ea | 162.8945 |  | 162.8945 | 1.78 | 289.9522 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 2.4691 | 22.68 | 0.7209 | 40.3704
[22 empty] | Fuel | Material | LTR | 1.76 | 0.17637 | 9.9792 | 10.0926 | 17.763
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.5037 | 95.2941 | 3.5338 | 169.6235
[22 empty] | Fuel | Material | LTR | 1.76 | 0.05037 | 34.9412 | 35.3382 | 62.1953
[9 empty] | 1.78 | 1.78 |  | 1.78 | [9 empty] | Concrete Base 30 cm |  | Ea | 1883.8375 |  | 1883.8375 | 1.78 | 3353.2307 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 1.7361 | 144 | 1.0253 | 256.32
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.63012 | 555.45 | 2.8249 | 988.701
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 7.8765 | 317.4 | 0.22599 | 564.972
[22 empty] | Workmanship plain concrete | SC | M³ | 150 | 1.7361 | 86.4 | 1.0253 | 153.792
[22 empty] | Workmanship RC concrete | SC | M³ | 450 | 0.63012 | 714.15 | 2.8249 | 1271.187
[22 empty] | 2 Layers Bituminous Application | SC | M² | 10 | 0.15052 | 66.4375 | 11.8259 | 118.2587
[9 empty] | 1.78 | 1.78 |  | 1.78 | [9 empty] | Manhole Installation |  | Ea | 8322.8 |  | 8322.8 | 1.78 | 14814.584 | 0 | 0 | 0 | 0 | 0
[22 empty] | GRP manhole Dia 1500 mm D=4.0 m W Cover | Material | Ea | 6550 | 1 | 6550 | 1.78 | 11659
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 0.5 | 160 | 3.56 | 284.8
[22 empty] | Fuel | Material | HR | 1.76 | 0.033333 | 52.8 | 53.4 | 93.984
[22 empty] | Brick & Masonery for Manhole Neck | SC | LS | 1500 | 1 | 1500 | 1.78 | 2670
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.5 | 34 | 3.56 | 60.52
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.5 | 26 | 3.56 | 46.28
[9 empty] | 1.78 | 1.78 |  | 1.78 | [9 empty] | Backfilling |  | Ea | 617.7154 |  | 617.7154 | 1.78 | 1099.5334 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.03072 | 325.5188 | 57.9423 | 579.4234
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 3.072 | 21.354 | 0.57942 | 38.0102
[22 empty] | Fuel | Material | LTR | 1.76 | 0.34134 | 5.1562 | 5.2148 | 9.1781
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.62669 | 76.5926 | 2.8403 | 136.3349
[22 empty] | Fuel | Material | LTR | 1.76 | 0.062669 | 28.084 | 28.4031 | 49.9895
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 1.536 | 23.4374 | 1.1588 | 41.7185
[22 empty] | Fuel | Material | LTR | 1.76 | 0.17067 | 10.3124 | 10.4296 | 18.3561
[22 empty] | Plate Compactor | Machinery | HR | 23 | 0.22222 | 103.5 | 8.01 | 184.23
[22 empty] | Fuel | Material | LTR | 1.76 | 0.074074 | 23.76 | 24.03 | 42.2928
SEW 10 |  | At a depth of 4.0 - 4.5 m (GRP) | nr | 6.19 | 55199 | 341681.81 | 11873.9818 | 73499.9475 | 6.19 | 6.19 |  | 6.19 | 100% | 55199 | 341681.81 | 11873.9818 | 73499.9475 |  | 73499.9475 | [7 empty] | 11873.9818 | 6.19 | 73499.9475 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 6.19 | 6.19 |  | 6.19 | [9 empty] | Excavate & Disposal (3.0*3.0*5.0) |  | Ea | 180.9939 |  | 180.9939 | 6.19 | 1120.3521 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 2.2222 | 25.2 | 2.7855 | 155.988
[22 empty] | Fuel | Material | LTR | 1.76 | 0.15873 | 11.088 | 38.997 | 68.6347
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.45333 | 105.8824 | 13.6544 | 655.4118
[22 empty] | Fuel | Material | LTR | 1.76 | 0.045333 | 38.8235 | 136.5441 | 240.3176
[9 empty] | 6.19 | 6.19 |  | 6.19 | [9 empty] | Concrete Base 30 cm |  | Ea | 1883.8375 |  | 1883.8375 | 6.19 | 11660.9541 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 1.7361 | 144 | 3.5654 | 891.36
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.63012 | 555.45 | 9.8235 | 3438.2355
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 7.8765 | 317.4 | 0.78588 | 1964.706
[22 empty] | Workmanship plain concrete | SC | M³ | 150 | 1.7361 | 86.4 | 3.5654 | 534.816
[22 empty] | Workmanship RC concrete | SC | M³ | 450 | 0.63012 | 714.15 | 9.8235 | 4420.5885
[22 empty] | 2 Layers Bituminous Application | SC | M² | 10 | 0.15052 | 66.4375 | 41.1248 | 411.2481
[9 empty] | 6.19 | 6.19 |  | 6.19 | [9 empty] | Manhole Installation |  | Ea | 9122.8 |  | 9122.8 | 6.19 | 56470.132 | 0 | 0 | 0 | 0 | 0
[22 empty] | GRP manhole Dia 1500 mm D=4.5 m W Cover | Material | Ea | 7350 | 1 | 7350 | 6.19 | 45496.5
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 0.5 | 160 | 12.38 | 990.4
[22 empty] | Fuel | Material | HR | 1.76 | 0.033333 | 52.8 | 185.7 | 326.832
[22 empty] | Brick & Masonery for Manhole Neck | SC | LS | 1500 | 1 | 1500 | 6.19 | 9285
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.5 | 34 | 12.38 | 210.46
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.5 | 26 | 12.38 | 160.94
[9 empty] | 6.19 | 6.19 |  | 6.19 | [9 empty] | Backfilling |  | Ea | 686.3504 |  | 686.3504 | 6.19 | 4248.5092 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.027648 | 361.6875 | 223.8846 | 2238.8456
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 2.7648 | 23.7267 | 2.2388 | 146.8683
[22 empty] | Fuel | Material | LTR | 1.76 | 0.3072 | 5.7291 | 20.1496 | 35.4633
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.56402 | 85.1029 | 10.9747 | 526.7872
[22 empty] | Fuel | Material | LTR | 1.76 | 0.056402 | 31.2044 | 109.7473 | 193.1553
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 1.3824 | 26.0415 | 4.4777 | 161.1969
[22 empty] | Fuel | Material | LTR | 1.76 | 0.1536 | 11.4583 | 40.2992 | 70.9266
[22 empty] | Plate Compactor | Machinery | HR | 23 | 0.2 | 115 | 30.95 | 711.85
[22 empty] | Fuel | Material | LTR | 1.76 | 0.066667 | 26.4 | 92.85 | 163.416
SEW 10 |  | At a depth of 4.5 - 5.0 m (GRP) | nr | 12.46 | 61304 | 763847.84 | 12760.7163 | 158998.5246 | 12.46 | 12.46 |  | 12.46 | 100% | 61304 | 763847.84 | 12760.7163 | 158998.5246 |  | 158998.5246 | [7 empty] | 12760.7163 | 12.46 | 158998.5246 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 12.46 | 12.46 |  | 12.46 | [9 empty] | Excavate & Disposal (3.0*3.0*5.5) |  | Ea | 199.0933 |  | 199.0933 | 12.46 | 2480.7022 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 2.0202 | 27.72 | 6.1677 | 345.3912
[22 empty] | Fuel | Material | LTR | 1.76 | 0.1443 | 12.1968 | 86.3478 | 151.9721
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.41212 | 116.4706 | 30.2338 | 1451.2235
[22 empty] | Fuel | Material | LTR | 1.76 | 0.041212 | 42.7059 | 302.3382 | 532.1153
[9 empty] | 12.46 | 12.46 |  | 12.46 | [9 empty] | Concrete Base 30 cm |  | Ea | 1883.8375 |  | 1883.8375 | 12.46 | 23472.6152 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 1.7361 | 144 | 7.177 | 1794.24
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.63012 | 555.45 | 19.774 | 6920.907
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 7.8765 | 317.4 | 1.5819 | 3954.804
[22 empty] | Workmanship plain concrete | SC | M³ | 150 | 1.7361 | 86.4 | 7.177 | 1076.544
[22 empty] | Workmanship RC concrete | SC | M³ | 450 | 0.63012 | 714.15 | 19.774 | 8898.309
[22 empty] | 2 Layers Bituminous Application | SC | M² | 10 | 0.15052 | 66.4375 | 82.7811 | 827.8112
[9 empty] | 12.46 | 12.46 |  | 12.46 | [9 empty] | Manhole Installation |  | Ea | 9922.8 |  | 9922.8 | 12.46 | 123638.088 | 0 | 0 | 0 | 0 | 0
[22 empty] | GRP manhole Dia 1500 mm D=5.0 m W Cover | Material | Ea | 8150 | 1 | 8150 | 12.46 | 101549
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 0.5 | 160 | 24.92 | 1993.6
[22 empty] | Fuel | Material | HR | 1.76 | 0.033333 | 52.8 | 373.8 | 657.888
[22 empty] | Brick & Masonery for Manhole Neck | SC | LS | 1500 | 1 | 1500 | 12.46 | 18690
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.5 | 34 | 24.92 | 423.64
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.5 | 26 | 24.92 | 323.96
[9 empty] | 12.46 | 12.46 |  | 12.46 | [9 empty] | Backfilling |  | Ea | 754.9855 |  | 754.9855 | 12.46 | 9407.1192 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.025135 | 397.8563 | 495.7289 | 4957.2889
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 2.5135 | 26.0994 | 4.9573 | 325.1982
[22 empty] | Fuel | Material | LTR | 1.76 | 0.27927 | 6.302 | 44.6156 | 78.5235
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.51275 | 93.6132 | 24.3004 | 1166.4209
[22 empty] | Fuel | Material | LTR | 1.76 | 0.051275 | 34.3249 | 243.0044 | 427.6877
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 1.2567 | 28.6457 | 9.9146 | 356.9248
[22 empty] | Fuel | Material | LTR | 1.76 | 0.13964 | 12.6041 | 89.2312 | 157.0469
[22 empty] | Plate Compactor | Machinery | HR | 23 | 0.18182 | 126.5 | 68.53 | 1576.19
[22 empty] | Fuel | Material | LTR | 1.76 | 0.060606 | 29.04 | 205.59 | 361.8384
SEW 10 |  | At a depth of 5.0 - 5.5 m (GRP) | nr | 10.82 | 67346 | 728683.72 | 13705.1659 | 148289.8949 | 10.82 | 10.82 |  | 10.82 | 100% | 67346 | 728683.72 | 13705.1659 | 148289.8949 |  | 148289.8949 | [7 empty] | 13705.1659 | 10.82 | 148289.8949 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 10.82 | 10.82 |  | 10.82 | [9 empty] | Excavate & Disposal (3.0*3.0*6.0) |  | Ea | 274.9079 |  | 274.9079 | 10.82 | 2974.503 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 50T | Machinery | HR | 131.2 | 1.8519 | 70.848 | 5.8428 | 766.5754
[22 empty] | Fuel | Material | LTR | 1.76 | 0.05787 | 30.4128 | 186.9696 | 329.0665
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.37778 | 127.0588 | 28.6412 | 1374.7765
[22 empty] | Fuel | Material | LTR | 1.76 | 0.037778 | 46.5882 | 286.4118 | 504.0847
[9 empty] | 10.82 | 10.82 |  | 10.82 | [9 empty] | Concrete Base 30 cm |  | Ea | 1883.8375 |  | 1883.8375 | 10.82 | 20383.1217 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 1.7361 | 144 | 6.2323 | 1558.08
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.63012 | 555.45 | 17.1713 | 6009.969
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 7.8765 | 317.4 | 1.3737 | 3434.268
[22 empty] | Workmanship plain concrete | SC | M³ | 150 | 1.7361 | 86.4 | 6.2323 | 934.848
[22 empty] | Workmanship RC concrete | SC | M³ | 450 | 0.63012 | 714.15 | 17.1713 | 7727.103
[22 empty] | 2 Layers Bituminous Application | SC | M² | 10 | 0.15052 | 66.4375 | 71.8854 | 718.8537
[9 empty] | 10.82 | 10.82 |  | 10.82 | [9 empty] | Manhole Installation |  | Ea | 10722.8 |  | 10722.8 | 10.82 | 116020.696 | 0 | 0 | 0 | 0 | 0
[22 empty] | GRP manhole Dia 1500 mm D=5.5 m W Cover | Material | Ea | 8950 | 1 | 8950 | 10.82 | 96839
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 0.5 | 160 | 21.64 | 1731.2
[22 empty] | Fuel | Material | HR | 1.76 | 0.033333 | 52.8 | 324.6 | 571.296
[22 empty] | Brick & Masonery for Manhole Neck | SC | LS | 1500 | 1 | 1500 | 10.82 | 16230
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.5 | 34 | 21.64 | 367.88
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.5 | 26 | 21.64 | 281.32
[9 empty] | 10.82 | 10.82 |  | 10.82 | [9 empty] | Backfilling |  | Ea | 823.6205 |  | 823.6205 | 10.82 | 8911.5742 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.02304 | 434.025 | 469.615 | 4696.1505
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 2.304 | 28.472 | 4.6962 | 308.0675
[22 empty] | Fuel | Material | LTR | 1.76 | 0.256 | 6.875 | 42.2654 | 74.387
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.47002 | 102.1235 | 23.0203 | 1104.9766
[22 empty] | Fuel | Material | LTR | 1.76 | 0.047002 | 37.4453 | 230.2035 | 405.1581
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 1.152 | 31.2498 | 9.3923 | 338.1228
[22 empty] | Fuel | Material | LTR | 1.76 | 0.128 | 13.7499 | 84.5307 | 148.774
[22 empty] | Plate Compactor | Machinery | HR | 23 | 0.16667 | 138 | 64.92 | 1493.16
[22 empty] | Fuel | Material | LTR | 1.76 | 0.055556 | 31.68 | 194.76 | 342.7776
SEW 10 |  | At a depth of 5.5 - 6.0 m (GRP) | nr | 0.49 | 73640 | 36083.6 | 14646.7099 | 7176.8879 | 0.49 | 0.49 |  | 0.49 | 100% | 73640 | 36083.6 | 14646.7099 | 7176.8879 |  | 7176.8879 | [7 empty] | 14646.7099 | 0.49 | 7176.8879 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 0.49 | 0.49 |  | 0.49 | [9 empty] | Excavate & Disposal (3.0*3.0*6.5) |  | Ea | 297.8168 |  | 297.8168 | 0.49 | 145.9303 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 50T | Machinery | HR | 131.2 | 1.7094 | 76.752 | 0.28665 | 37.6085
[22 empty] | Fuel | Material | LTR | 1.76 | 0.053419 | 32.9472 | 9.1728 | 16.1441
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.34872 | 137.6471 | 1.4051 | 67.4471
[22 empty] | Fuel | Material | LTR | 1.76 | 0.034872 | 50.4706 | 14.0515 | 24.7306
[9 empty] | 0.49 | 0.49 |  | 0.49 | [9 empty] | Concrete Base 30 cm |  | Ea | 1883.8375 |  | 1883.8375 | 0.49 | 923.0804 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 1.7361 | 144 | 0.28224 | 70.56
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.63012 | 555.45 | 0.77763 | 272.1705
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 7.8765 | 317.4 | 0.06221 | 155.526
[22 empty] | Workmanship plain concrete | SC | M³ | 150 | 1.7361 | 86.4 | 0.28224 | 42.336
[22 empty] | Workmanship RC concrete | SC | M³ | 450 | 0.63012 | 714.15 | 0.77763 | 349.9335
[22 empty] | 2 Layers Bituminous Application | SC | M² | 10 | 0.15052 | 66.4375 | 3.2554 | 32.5544
[9 empty] | 0.49 | 0.49 |  | 0.49 | [9 empty] | Manhole Installation |  | Ea | 11572.8 |  | 11572.8 | 0.49 | 5670.672 | 0 | 0 | 0 | 0 | 0
[22 empty] | GRP manhole Dia 1500 mm D=6.0 m W Cover | Material | Ea | 9800 | 1 | 9800 | 0.49 | 4802
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 0.5 | 160 | 0.98 | 78.4
[22 empty] | Fuel | Material | HR | 1.76 | 0.033333 | 52.8 | 14.7 | 25.872
[22 empty] | Brick & Masonery for Manhole Neck | SC | LS | 1500 | 1 | 1500 | 0.49 | 735
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.5 | 34 | 0.98 | 16.66
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.5 | 26 | 0.98 | 12.74
[9 empty] | 0.49 | 0.49 |  | 0.49 | [9 empty] | Backfilling |  | Ea | 892.2556 |  | 892.2556 | 0.49 | 437.2052 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.021268 | 470.1937 | 23.0395 | 230.3949
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 2.1268 | 30.8447 | 0.23039 | 15.1139
[22 empty] | Fuel | Material | LTR | 1.76 | 0.23631 | 7.4479 | 2.0736 | 3.6495
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.43386 | 110.6338 | 1.1294 | 54.2106
[22 empty] | Fuel | Material | LTR | 1.76 | 0.043386 | 40.5657 | 11.2939 | 19.8772
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 1.0634 | 33.854 | 0.46079 | 16.5884
[22 empty] | Fuel | Material | LTR | 1.76 | 0.11815 | 14.8957 | 4.1471 | 7.2989
[22 empty] | Plate Compactor | Machinery | HR | 23 | 0.15385 | 149.5 | 3.185 | 73.255
[22 empty] | Fuel | Material | LTR | 1.76 | 0.051282 | 34.32 | 9.555 | 16.8168
SEW 10 |  | At a depth of 6.0 - 6.5 m (GRP) | nr | 6.27 | 79745 | 500001.15 | 15588.254 | 97738.3523 | 6.27 | 6.27 |  | 6.27 | 100% | 79745 | 500001.15 | 15588.254 | 97738.3523 |  | 97738.3523 | [7 empty] | 15588.254 | 6.27 | 97738.3523 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 6.27 | 6.27 |  | 6.27 | [9 empty] | Excavate & Disposal (3.0*3.0*7.0) |  | Ea | 320.7258 |  | 320.7258 | 6.27 | 2010.951 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 50T | Machinery | HR | 131.2 | 1.5873 | 82.656 | 3.9501 | 518.2531
[22 empty] | Fuel | Material | LTR | 1.76 | 0.049603 | 35.4816 | 126.4032 | 222.4696
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.32381 | 148.2353 | 19.3632 | 929.4353
[22 empty] | Fuel | Material | LTR | 1.76 | 0.032381 | 54.3529 | 193.6324 | 340.7929
[9 empty] | 6.27 | 6.27 |  | 6.27 | [9 empty] | Concrete Base 30 cm |  | Ea | 1883.8375 |  | 1883.8375 | 6.27 | 11811.6611 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 1.7361 | 144 | 3.6115 | 902.88
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.63012 | 555.45 | 9.9505 | 3482.6715
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 7.8765 | 317.4 | 0.79604 | 1990.098
[22 empty] | Workmanship plain concrete | SC | M³ | 150 | 1.7361 | 86.4 | 3.6115 | 541.728
[22 empty] | Workmanship RC concrete | SC | M³ | 450 | 0.63012 | 714.15 | 9.9505 | 4477.7205
[22 empty] | 2 Layers Bituminous Application | SC | M² | 10 | 0.15052 | 66.4375 | 41.6563 | 416.5631
[9 empty] | 6.27 | 6.27 |  | 6.27 | [9 empty] | Manhole Installation |  | Ea | 12422.8 |  | 12422.8 | 6.27 | 77890.956 | 0 | 0 | 0 | 0 | 0
[22 empty] | GRP manhole Dia 1500 mm D=6.5 m W Cover | Material | Ea | 10650 | 1 | 10650 | 6.27 | 66775.5
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 0.5 | 160 | 12.54 | 1003.2
[22 empty] | Fuel | Material | HR | 1.76 | 0.033333 | 52.8 | 188.1 | 331.056
[22 empty] | Brick & Masonery for Manhole Neck | SC | LS | 1500 | 1 | 1500 | 6.27 | 9405
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.5 | 34 | 12.54 | 213.18
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.5 | 26 | 12.54 | 163.02
[9 empty] | 6.27 | 6.27 |  | 6.27 | [9 empty] | Backfilling |  | Ea | 960.8906 |  | 960.8906 | 6.27 | 6024.7842 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.019749 | 506.3625 | 317.4893 | 3174.8929
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 1.9749 | 33.2174 | 3.1749 | 208.273
[22 empty] | Fuel | Material | LTR | 1.76 | 0.21943 | 8.0208 | 28.574 | 50.2903
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.40287 | 119.1441 | 15.5632 | 747.0336
[22 empty] | Fuel | Material | LTR | 1.76 | 0.040287 | 43.6862 | 155.632 | 273.9123
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 0.98743 | 36.4581 | 6.3498 | 228.5923
[22 empty] | Fuel | Material | LTR | 1.76 | 0.10971 | 16.0416 | 57.1481 | 100.5806
[22 empty] | Plate Compactor | Machinery | HR | 23 | 0.14286 | 161 | 43.89 | 1009.47
[22 empty] | Fuel | Material | LTR | 1.76 | 0.047619 | 36.96 | 131.67 | 231.7392
SEW 10 |  | At a depth of 6.5 - 7.0 m (GRP) | nr | 2 | 101964 | 203928 | 16629.798 | 33259.596 | 2 | 2 |  | 2 | 100% | 101964 | 203928 | 16629.798 | 33259.596 |  | 33259.596 | [7 empty] | 16629.798 | 2 | 33259.596 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 2 | 2 |  | 2 | [9 empty] | Excavate & Disposal (3.0*3.0*7.5) |  | Ea | 343.6348 |  | 343.6348 | 2 | 687.2696 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 50T | Machinery | HR | 131.2 | 1.4815 | 88.56 | 1.35 | 177.12
[22 empty] | Fuel | Material | LTR | 1.76 | 0.046296 | 38.016 | 43.2 | 76.032
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.30222 | 158.8235 | 6.6176 | 317.6471
[22 empty] | Fuel | Material | LTR | 1.76 | 0.030222 | 58.2353 | 66.1765 | 116.4706
[9 empty] | 2 | 2 |  | 2 | [9 empty] | Concrete Base 30 cm |  | Ea | 1883.8375 |  | 1883.8375 | 2 | 3767.675 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 1.7361 | 144 | 1.152 | 288
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.63012 | 555.45 | 3.174 | 1110.9
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 7.8765 | 317.4 | 0.25392 | 634.8
[22 empty] | Workmanship plain concrete | SC | M³ | 150 | 1.7361 | 86.4 | 1.152 | 172.8
[22 empty] | Workmanship RC concrete | SC | M³ | 450 | 0.63012 | 714.15 | 3.174 | 1428.3
[22 empty] | 2 Layers Bituminous Application | SC | M² | 10 | 0.15052 | 66.4375 | 13.2875 | 132.875
[9 empty] | 2 | 2 |  | 2 | [9 empty] | Manhole Installation |  | Ea | 13372.8 |  | 13372.8 | 2 | 26745.6 | 0 | 0 | 0 | 0 | 0
[22 empty] | GRP manhole Dia 1500 mm D=7.0 m W Cover | Material | Ea | 11600 | 1 | 11600 | 2 | 23200
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 0.5 | 160 | 4 | 320
[22 empty] | Fuel | Material | HR | 1.76 | 0.033333 | 52.8 | 60 | 105.6
[22 empty] | Brick & Masonery for Manhole Neck | SC | LS | 1500 | 1 | 1500 | 2 | 3000
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.5 | 34 | 4 | 68
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.5 | 26 | 4 | 52
[9 empty] | 2 | 2 |  | 2 | [9 empty] | Backfilling |  | Ea | 1029.5257 |  | 1029.5257 | 2 | 2059.0513 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.018432 | 542.5312 | 108.5062 | 1085.0625
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 1.8432 | 35.59 | 1.0851 | 71.1801
[22 empty] | Fuel | Material | LTR | 1.76 | 0.2048 | 8.5937 | 9.7656 | 17.1874
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.37602 | 127.6544 | 5.3189 | 255.3088
[22 empty] | Fuel | Material | LTR | 1.76 | 0.037602 | 46.8066 | 53.1893 | 93.6132
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 0.92161 | 39.0622 | 2.1701 | 78.1245
[22 empty] | Fuel | Material | LTR | 1.76 | 0.1024 | 17.1874 | 19.5311 | 34.3748
[22 empty] | Plate Compactor | Machinery | HR | 23 | 0.13333 | 172.5 | 15 | 345
[22 empty] | Fuel | Material | LTR | 1.76 | 0.044444 | 39.6 | 45 | 79.2
SEW 10 |  | At a depth of 7.0 - 7.5 m (GRP) | nr |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | Backdrop manholes |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | Inspection chambers equipped with one opening (with vertical pipe and concrete skirting equipment), the necessary excavation and concrete construction, a GRP lining, an insulating layer with a protection board, and originally equipped short pipes (built-in), with a frame and cover of a good and tight type, according to the drawings. |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | Manholes with a back drop, diameter 1500 mm |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | At a depth of 4.0 - 4.5 m (GRP) | nr |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | At a depth of 4.5 - 5.0 m (GRP) | nr | 2 | 66024 | 132048 | 16260.7163 | 32521.4325 | 2 | 2 |  | 2 | 100% | 66024 | 132048 | 16260.7163 | 32521.4325 |  | 32521.4325 | [7 empty] | 16260.7163 | 2 | 32521.4325 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 2 | 2 |  | 2 | [9 empty] | Excavate & Disposal (3.0*3.0*5.5) |  | Ea | 199.0933 |  | 199.0933 | 2 | 398.1865 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 2.0202 | 27.72 | 0.99 | 55.44
[22 empty] | Fuel | Material | LTR | 1.76 | 0.1443 | 12.1968 | 13.86 | 24.3936
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.41212 | 116.4706 | 4.8529 | 232.9412
[22 empty] | Fuel | Material | LTR | 1.76 | 0.041212 | 42.7059 | 48.5294 | 85.4118
[9 empty] | 2 | 2 |  | 2 | [9 empty] | Concrete Base 30 cm |  | Ea | 1883.8375 |  | 1883.8375 | 2 | 3767.675 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 1.7361 | 144 | 1.152 | 288
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.63012 | 555.45 | 3.174 | 1110.9
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 7.8765 | 317.4 | 0.25392 | 634.8
[22 empty] | Workmanship plain concrete | SC | M³ | 150 | 1.7361 | 86.4 | 1.152 | 172.8
[22 empty] | Workmanship RC concrete | SC | M³ | 450 | 0.63012 | 714.15 | 3.174 | 1428.3
[22 empty] | 2 Layers Bituminous Application | SC | M² | 10 | 0.15052 | 66.4375 | 13.2875 | 132.875
[9 empty] | 2 | 2 |  | 2 | [9 empty] | Manhole Installation |  | Ea | 13422.8 |  | 13422.8 | 2 | 26845.6 | 0 | 0 | 0 | 0 | 0
[22 empty] | GRP manhole Dia 1500 mm D=5.0 m W Cover | Material | Ea | 8150 | 1 | 8150 | 2 | 16300
[22 empty] | Manhole Back drop PCs | Material | LS | 3500 | 1 | 3500 | 2 | 7000
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 0.5 | 160 | 4 | 320
[22 empty] | Fuel | Material | HR | 1.76 | 0.033333 | 52.8 | 60 | 105.6
[22 empty] | Brick & Masonery for Manhole Neck | SC | LS | 1500 | 1 | 1500 | 2 | 3000
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.5 | 34 | 4 | 68
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.5 | 26 | 4 | 52
[9 empty] | 2 | 2 |  | 2 | [9 empty] | Backfilling |  | Ea | 754.9855 |  | 754.9855 | 2 | 1509.971 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.025135 | 397.8563 | 79.5713 | 795.7125
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 2.5135 | 26.0994 | 0.79571 | 52.1987
[22 empty] | Fuel | Material | LTR | 1.76 | 0.27927 | 6.302 | 7.1614 | 12.6041
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.51275 | 93.6132 | 3.9006 | 187.2265
[22 empty] | Fuel | Material | LTR | 1.76 | 0.051275 | 34.3249 | 39.0055 | 68.6497
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 1.2567 | 28.6457 | 1.5914 | 57.2913
[22 empty] | Fuel | Material | LTR | 1.76 | 0.13964 | 12.6041 | 14.3228 | 25.2082
[22 empty] | Plate Compactor | Machinery | HR | 23 | 0.18182 | 126.5 | 11 | 253
[22 empty] | Fuel | Material | LTR | 1.76 | 0.060606 | 29.04 | 33 | 58.08
SEW 10 |  | At a depth of 5.0 - 5.5 m (GRP) | nr | 2.29 | 72533 | 166100.57 | 17205.1659 | 39399.8299 | 2.29 | 2.29 |  | 2.29 | 100% | 72533 | 166100.57 | 17205.1659 | 39399.8299 |  | 39399.8299 | [7 empty] | 17205.1659 | 2.29 | 39399.8299 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 2.29 | 2.29 |  | 2.29 | [9 empty] | Excavate & Disposal (3.0*3.0*6.0) |  | Ea | 274.9079 |  | 274.9079 | 2.29 | 629.539 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 50T | Machinery | HR | 131.2 | 1.8519 | 70.848 | 1.2366 | 162.2419
[22 empty] | Fuel | Material | LTR | 1.76 | 0.05787 | 30.4128 | 39.5712 | 69.6453
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.37778 | 127.0588 | 6.0618 | 290.9647
[22 empty] | Fuel | Material | LTR | 1.76 | 0.037778 | 46.5882 | 60.6176 | 106.6871
[9 empty] | 2.29 | 2.29 |  | 2.29 | [9 empty] | Concrete Base 30 cm |  | Ea | 1883.8375 |  | 1883.8375 | 2.29 | 4313.9879 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 1.7361 | 144 | 1.319 | 329.76
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.63012 | 555.45 | 3.6342 | 1271.9805
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 7.8765 | 317.4 | 0.29074 | 726.846
[22 empty] | Workmanship plain concrete | SC | M³ | 150 | 1.7361 | 86.4 | 1.319 | 197.856
[22 empty] | Workmanship RC concrete | SC | M³ | 450 | 0.63012 | 714.15 | 3.6342 | 1635.4035
[22 empty] | 2 Layers Bituminous Application | SC | M² | 10 | 0.15052 | 66.4375 | 15.2142 | 152.1419
[9 empty] | 2.29 | 2.29 |  | 2.29 | [9 empty] | Manhole Installation |  | Ea | 14222.8 |  | 14222.8 | 2.29 | 32570.212 | 0 | 0 | 0 | 0 | 0
[22 empty] | GRP manhole Dia 1500 mm D=5.5 m W Cover | Material | Ea | 8950 | 1 | 8950 | 2.29 | 20495.5
[22 empty] | Manhole Back drop PCs | Material | LS | 3500 | 1 | 3500 | 2.29 | 8015
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 0.5 | 160 | 4.58 | 366.4
[22 empty] | Fuel | Material | HR | 1.76 | 0.033333 | 52.8 | 68.7 | 120.912
[22 empty] | Brick & Masonery for Manhole Neck | SC | LS | 1500 | 1 | 1500 | 2.29 | 3435
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.5 | 34 | 4.58 | 77.86
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.5 | 26 | 4.58 | 59.54
[9 empty] | 2.29 | 2.29 |  | 2.29 | [9 empty] | Backfilling |  | Ea | 823.6205 |  | 823.6205 | 2.29 | 1886.091 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.02304 | 434.025 | 99.3917 | 993.9173
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 2.304 | 28.472 | 0.99392 | 65.201
[22 empty] | Fuel | Material | LTR | 1.76 | 0.256 | 6.875 | 8.9453 | 15.7436
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.47002 | 102.1235 | 4.8721 | 233.8629
[22 empty] | Fuel | Material | LTR | 1.76 | 0.047002 | 37.4453 | 48.7214 | 85.7497
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 1.152 | 31.2498 | 1.9878 | 71.562
[22 empty] | Fuel | Material | LTR | 1.76 | 0.128 | 13.7499 | 17.8905 | 31.4873
[22 empty] | Plate Compactor | Machinery | HR | 23 | 0.16667 | 138 | 13.74 | 316.02
[22 empty] | Fuel | Material | LTR | 1.76 | 0.055556 | 31.68 | 41.22 | 72.5472
SEW 10 |  | At a depth of 5.5 - 6.0 m (GRP) | nr | 0.11 | 79305 | 8723.55 | 18146.7099 | 1996.1381 | 0.11 | 0.11 |  | 0.11 | 100% | 79305 | 8723.55 | 18146.7099 | 1996.1381 |  | 1996.1381 | [7 empty] | 18146.7099 | 0.11 | 1996.1381 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 0.11 | 0.11 |  | 0.11 | [9 empty] | Excavate & Disposal (3.0*3.0*6.5) |  | Ea | 297.8168 |  | 297.8168 | 0.11 | 32.7599 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 50T | Machinery | HR | 131.2 | 1.7094 | 76.752 | 0.06435 | 8.4427
[22 empty] | Fuel | Material | LTR | 1.76 | 0.053419 | 32.9472 | 2.0592 | 3.6242
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.34872 | 137.6471 | 0.31544 | 15.1412
[22 empty] | Fuel | Material | LTR | 1.76 | 0.034872 | 50.4706 | 3.1544 | 5.5518
[9 empty] | 0.11 | 0.11 |  | 0.11 | [9 empty] | Concrete Base 30 cm |  | Ea | 1883.8375 |  | 1883.8375 | 0.11 | 207.2221 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 1.7361 | 144 | 0.06336 | 15.84
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.63012 | 555.45 | 0.17457 | 61.0995
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 7.8765 | 317.4 | 0.013966 | 34.914
[22 empty] | Workmanship plain concrete | SC | M³ | 150 | 1.7361 | 86.4 | 0.06336 | 9.504
[22 empty] | Workmanship RC concrete | SC | M³ | 450 | 0.63012 | 714.15 | 0.17457 | 78.5565
[22 empty] | 2 Layers Bituminous Application | SC | M² | 10 | 0.15052 | 66.4375 | 0.73081 | 7.3081
[9 empty] | 0.11 | 0.11 |  | 0.11 | [9 empty] | Manhole Installation |  | Ea | 15072.8 |  | 15072.8 | 0.11 | 1658.008 | 0 | 0 | 0 | 0 | 0
[22 empty] | GRP manhole Dia 1500 mm D=6.0 m W Cover | Material | Ea | 9800 | 1 | 9800 | 0.11 | 1078
[22 empty] | Manhole Back drop PCs | Material | LS | 3500 | 1 | 3500 | 0.11 | 385
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 0.5 | 160 | 0.22 | 17.6
[22 empty] | Fuel | Material | HR | 1.76 | 0.033333 | 52.8 | 3.3 | 5.808
[22 empty] | Brick & Masonery for Manhole Neck | SC | LS | 1500 | 1 | 1500 | 0.11 | 165
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.5 | 34 | 0.22 | 3.74
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.5 | 26 | 0.22 | 2.86
[9 empty] | 0.11 | 0.11 |  | 0.11 | [9 empty] | Backfilling |  | Ea | 892.2556 |  | 892.2556 | 0.11 | 98.1481 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.021268 | 470.1937 | 5.1721 | 51.7213
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 2.1268 | 30.8447 | 0.051721 | 3.3929
[22 empty] | Fuel | Material | LTR | 1.76 | 0.23631 | 7.4479 | 0.46549 | 0.81927
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.43386 | 110.6338 | 0.25354 | 12.1697
[22 empty] | Fuel | Material | LTR | 1.76 | 0.043386 | 40.5657 | 2.5354 | 4.4622
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 1.0634 | 33.8539 | 0.10344 | 3.7239
[22 empty] | Fuel | Material | LTR | 1.76 | 0.11815 | 14.8957 | 0.93098 | 1.6385
[22 empty] | Plate Compactor | Machinery | HR | 23 | 0.15385 | 149.5 | 0.715 | 16.445
[22 empty] | Fuel | Material | LTR | 1.76 | 0.051282 | 34.32 | 2.145 | 3.7752
SEW 10 |  | At a depth of 6.5 - 7.0 m (GRP) | nr |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | At a depth of 7.0 - 7.5 m (GRP) | nr |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | Increasing the depth difference by 0.5 m for 1500 mm diameter back-fall holes (GRP) | nr |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | Increase the depth difference of 1.0 m for 1500 mm diameter back-fall holes (GRP) | nr |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | Increasing the depth difference of 1.5 m for 1500 mm diameter back-fall holes (GRP) | nr |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | Increased depth difference of 2.0 m when falling back holes with a diameter of 1500 mm (GRP) | nr |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | Sanitary manholes from GRP include excavation, backfilling, waste disposal, dewatering, cleaning concrete, concrete pour, footings, DI cover with openings and frame, chains, pipes, fittings, spacers, pipe connections, etc., complete in accordance with the plans, specifications, and requirements of the concerned authority, dewatering, strengthening and protecting the excavated surfaces up to the required depths, and the disposal of groundwater resulting from dewatering around them is measured individually. |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | Manhole chambers, diameter 1800 mm |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | At a depth of 1.5 - 2.0 m (GRP) | nr |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | At a depth of 2.0 - 2.5 m (GRP) | nr | 0.71 | 28575 | 20288.25 | 10735.7624 | 7622.3913 | 0.71 | 0.71 |  | 0.71 | 100% | 28575 | 20288.25 | 10735.7624 | 7622.3913 |  | 7622.3913 | [7 empty] | 10735.7624 | 0.71 | 7622.3913 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 0.71 | 0.71 |  | 0.71 | [9 empty] | Excavate & Disposal (3.5*3.5*3.0) |  | Ea | 147.8117 |  | 147.8117 | 0.71 | 104.9463 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 2.7211 | 20.58 | 0.26092 | 14.6118
[22 empty] | Fuel | Material | LTR | 1.76 | 0.19436 | 9.0552 | 3.6529 | 6.4292
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.5551 | 86.4706 | 1.279 | 61.3941
[22 empty] | Fuel | Material | LTR | 1.76 | 0.05551 | 31.7059 | 12.7904 | 22.5112
[9 empty] | 0.71 | 0.71 |  | 0.71 | [9 empty] | Concrete Base 30 cm |  | Ea | 2396.566 |  | 2396.566 | 0.71 | 1701.5619 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 1.3717 | 182.25 | 0.51759 | 129.3975
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.4931 | 709.8 | 1.4399 | 503.958
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 6.1637 | 405.6 | 0.11519 | 287.976
[22 empty] | Workmanship plain concrete | SC | M³ | 150 | 1.3717 | 109.35 | 0.51759 | 77.6385
[22 empty] | Workmanship RC concrete | SC | M³ | 450 | 0.4931 | 912.6 | 1.4399 | 647.946
[22 empty] | 2 Layers Bituminous Application | SC | M² | 10 | 0.12993 | 76.966 | 5.4646 | 54.6459
[9 empty] | 0.71 | 0.71 |  | 0.71 | [9 empty] | Manhole Installation |  | Ea | 7667.8 |  | 7667.8 | 0.71 | 5444.138 | 0 | 0 | 0 | 0 | 0
[22 empty] | GRP manhole Dia 1800 mm D=2.5 m W Cover | Material | Ea | 5895 | 1 | 5895 | 0.71 | 4185.45
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 0.5 | 160 | 1.42 | 113.6
[22 empty] | Fuel | Material | HR | 1.76 | 0.033333 | 52.8 | 21.3 | 37.488
[22 empty] | Brick & Masonery for Manhole Neck | SC | LS | 1500 | 1 | 1500 | 0.71 | 1065
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.5 | 34 | 1.42 | 24.14
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.5 | 26 | 1.42 | 18.46
[9 empty] | 0.71 | 0.71 |  | 0.71 | [9 empty] | Backfilling |  | Ea | 523.5847 |  | 523.5847 | 0.71 | 371.7451 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.034341 | 291.198 | 20.6751 | 206.7506
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 3.4341 | 19.1026 | 0.20675 | 13.5628
[22 empty] | Fuel | Material | LTR | 1.76 | 0.38157 | 4.6126 | 1.8608 | 3.2749
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.70055 | 68.5172 | 1.0135 | 48.6472
[22 empty] | Fuel | Material | LTR | 1.76 | 0.070055 | 25.123 | 10.1348 | 17.8373
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 1.717 | 20.9663 | 0.4135 | 14.886
[22 empty] | Fuel | Material | LTR | 1.76 | 0.19078 | 9.2252 | 3.7215 | 6.5499
[22 empty] | Plate Compactor | Machinery | HR | 23 | 0.33333 | 69 | 2.13 | 48.99
[22 empty] | Fuel | Material | LTR | 1.76 | 0.11111 | 15.84 | 6.39 | 11.2464
SEW 10 |  | At a depth of 2.5 - 3.0 m (GRP) | nr | 0.08 | 34366 | 2749.28 | 11657.6618 | 932.6129 | 0.08 | 0.08 |  | 0.08 | 100% | 34366 | 2749.28 | 11657.6618 | 932.6129 |  | 932.6129 | [7 empty] | 11657.6618 | 0.08 | 932.6129 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 0.08 | 0.08 |  | 0.08 | [9 empty] | Excavate & Disposal (3.5*3.5*3.5) |  | Ea | 172.4469 |  | 172.4469 | 0.08 | 13.7958 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 2.3324 | 24.01 | 0.0343 | 1.9208
[22 empty] | Fuel | Material | LTR | 1.76 | 0.1666 | 10.5644 | 0.4802 | 0.84515
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.4758 | 100.8824 | 0.16814 | 8.0706
[22 empty] | Fuel | Material | LTR | 1.76 | 0.04758 | 36.9902 | 1.6814 | 2.9592
[9 empty] | 0.08 | 0.08 |  | 0.08 | [9 empty] | Concrete Base 30 cm |  | Ea | 2396.566 |  | 2396.566 | 0.08 | 191.7253 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 1.3717 | 182.25 | 0.05832 | 14.58
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.4931 | 709.8 | 0.16224 | 56.784
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 6.1637 | 405.6 | 0.012979 | 32.448
[22 empty] | Workmanship plain concrete | SC | M³ | 150 | 1.3717 | 109.35 | 0.05832 | 8.748
[22 empty] | Workmanship RC concrete | SC | M³ | 450 | 0.4931 | 912.6 | 0.16224 | 73.008
[22 empty] | 2 Layers Bituminous Application | SC | M² | 10 | 0.12993 | 76.966 | 0.61573 | 6.1573
[9 empty] | 0.08 | 0.08 |  | 0.08 | [9 empty] | Manhole Installation |  | Ea | 8477.8 |  | 8477.8 | 0.08 | 678.224 | 0 | 0 | 0 | 0 | 0
[22 empty] | GRP manhole Dia 1800 mm D=3.0 m W Cover | Material | Ea | 6705 | 1 | 6705 | 0.08 | 536.4
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 0.5 | 160 | 0.16 | 12.8
[22 empty] | Fuel | Material | HR | 1.76 | 0.033333 | 52.8 | 2.4 | 4.224
[22 empty] | Brick & Masonery for Manhole Neck | SC | LS | 1500 | 1 | 1500 | 0.08 | 120
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.5 | 34 | 0.16 | 2.72
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.5 | 26 | 0.16 | 2.08
[9 empty] | 0.08 | 0.08 |  | 0.08 | [9 empty] | Backfilling |  | Ea | 610.8488 |  | 610.8488 | 0.08 | 48.8679 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.029435 | 339.731 | 2.7178 | 27.1785
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 2.9435 | 22.2864 | 0.027178 | 1.7829
[22 empty] | Fuel | Material | LTR | 1.76 | 0.32706 | 5.3813 | 0.24461 | 0.43051
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.60048 | 79.9367 | 0.13323 | 6.3949
[22 empty] | Fuel | Material | LTR | 1.76 | 0.060048 | 29.3101 | 1.3323 | 2.3448
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 1.4718 | 24.4606 | 0.054357 | 1.9569
[22 empty] | Fuel | Material | LTR | 1.76 | 0.16353 | 10.7627 | 0.48921 | 0.86101
[22 empty] | Plate Compactor | Machinery | HR | 23 | 0.28571 | 80.5 | 0.28 | 6.44
[22 empty] | Fuel | Material | LTR | 1.76 | 0.095238 | 18.48 | 0.84 | 1.4784
SEW 10 |  | At a depth of 3.0 - 3.5 m (GRP) | nr |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | At a depth of 3.5 - 4.0 m (GRP) | nr | 0.45 | 40030 | 18013.5 | 13676.4606 | 6154.4073 | 0.45 | 0.45 |  | 0.45 | 100% | 40030 | 18013.5 | 13676.4606 | 6154.4073 |  | 6154.4073 | [7 empty] | 13676.4606 | 0.45 | 6154.4073 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 0.45 | 0.45 |  | 0.45 | [9 empty] | Excavate & Disposal (3.5*3.5*4.5) |  | Ea | 221.7175 |  | 221.7175 | 0.45 | 99.7729 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 1.8141 | 30.87 | 0.24806 | 13.8915
[22 empty] | Fuel | Material | LTR | 1.76 | 0.12958 | 13.5828 | 3.4729 | 6.1123
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.37007 | 129.7059 | 1.216 | 58.3676
[22 empty] | Fuel | Material | LTR | 1.76 | 0.037007 | 47.5588 | 12.1599 | 21.4015
[9 empty] | 0.45 | 0.45 |  | 0.45 | [9 empty] | Concrete Base 30 cm |  | Ea | 2396.566 |  | 2396.566 | 0.45 | 1078.4547 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 1.3717 | 182.25 | 0.32805 | 82.0125
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.4931 | 709.8 | 0.9126 | 319.41
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 6.1637 | 405.6 | 0.073008 | 182.52
[22 empty] | Workmanship plain concrete | SC | M³ | 150 | 1.3717 | 109.35 | 0.32805 | 49.2075
[22 empty] | Workmanship RC concrete | SC | M³ | 450 | 0.4931 | 912.6 | 0.9126 | 410.67
[22 empty] | 2 Layers Bituminous Application | SC | M² | 10 | 0.12993 | 76.966 | 3.4635 | 34.6347
[9 empty] | 0.45 | 0.45 |  | 0.45 | [9 empty] | Manhole Installation |  | Ea | 10272.8 |  | 10272.8 | 0.45 | 4622.76 | 0 | 0 | 0 | 0 | 0
[22 empty] | GRP manhole Dia 1800 mm D=4.0 m W Cover | Material | Ea | 8500 | 1 | 8500 | 0.45 | 3825
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 0.5 | 160 | 0.9 | 72
[22 empty] | Fuel | Material | HR | 1.76 | 0.033333 | 52.8 | 13.5 | 23.76
[22 empty] | Brick & Masonery for Manhole Neck | SC | LS | 1500 | 1 | 1500 | 0.45 | 675
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.5 | 34 | 0.9 | 15.3
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.5 | 26 | 0.9 | 11.7
[9 empty] | 0.45 | 0.45 |  | 0.45 | [9 empty] | Backfilling |  | Ea | 785.3771 |  | 785.3771 | 0.45 | 353.4197 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.022894 | 436.797 | 19.6559 | 196.5586
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 2.2894 | 28.6539 | 0.19656 | 12.8942
[22 empty] | Fuel | Material | LTR | 1.76 | 0.25438 | 6.9189 | 1.769 | 3.1135
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.46704 | 102.7758 | 0.96352 | 46.2491
[22 empty] | Fuel | Material | LTR | 1.76 | 0.046704 | 37.6844 | 9.6352 | 16.958
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 1.1447 | 31.4494 | 0.39312 | 14.1522
[22 empty] | Fuel | Material | LTR | 1.76 | 0.12719 | 13.8377 | 3.5381 | 6.227
[22 empty] | Plate Compactor | Machinery | HR | 23 | 0.22222 | 103.5 | 2.025 | 46.575
[22 empty] | Fuel | Material | LTR | 1.76 | 0.074074 | 23.76 | 6.075 | 10.692
SEW 10 |  | At a depth of 4.0 - 4.5 m (GRP) | nr | 0.04 | 51485 | 2059.4 | 14738.36 | 589.5344 | 0.04 | 0.04 |  | 0.04 | 100% | 51485 | 2059.4 | 14738.36 | 589.5344 |  | 589.5344 | [7 empty] | 14738.36 | 0.04 | 589.5344 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 0.04 | 0.04 |  | 0.04 | [9 empty] | Excavate & Disposal (3.5*3.5*5.0) |  | Ea | 246.3528 |  | 246.3528 | 0.04 | 9.8541 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 1.6327 | 34.3 | 0.0245 | 1.372
[22 empty] | Fuel | Material | LTR | 1.76 | 0.11662 | 15.092 | 0.343 | 0.60368
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.33306 | 144.1176 | 0.1201 | 5.7647
[22 empty] | Fuel | Material | LTR | 1.76 | 0.033306 | 52.8431 | 1.201 | 2.1137
[9 empty] | 0.04 | 0.04 |  | 0.04 | [9 empty] | Concrete Base 30 cm |  | Ea | 2396.566 |  | 2396.566 | 0.04 | 95.8626 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 1.3717 | 182.25 | 0.02916 | 7.29
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.4931 | 709.8 | 0.08112 | 28.392
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 6.1637 | 405.6 | 0.0064896 | 16.224
[22 empty] | Workmanship plain concrete | SC | M³ | 150 | 1.3717 | 109.35 | 0.02916 | 4.374
[22 empty] | Workmanship RC concrete | SC | M³ | 450 | 0.4931 | 912.6 | 0.08112 | 36.504
[22 empty] | 2 Layers Bituminous Application | SC | M² | 10 | 0.12993 | 76.966 | 0.30786 | 3.0786
[9 empty] | 0.04 | 0.04 |  | 0.04 | [9 empty] | Manhole Installation |  | Ea | 11222.8 |  | 11222.8 | 0.04 | 448.912 | 0 | 0 | 0 | 0 | 0
[22 empty] | GRP manhole Dia 1800 mm D=4.5 m W Cover | Material | Ea | 9450 | 1 | 9450 | 0.04 | 378
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 0.5 | 160 | 0.08 | 6.4
[22 empty] | Fuel | Material | HR | 1.76 | 0.033333 | 52.8 | 1.2 | 2.112
[22 empty] | Brick & Masonery for Manhole Neck | SC | LS | 1500 | 1 | 1500 | 0.04 | 60
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.5 | 34 | 0.08 | 1.36
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.5 | 26 | 0.08 | 1.04
[9 empty] | 0.04 | 0.04 |  | 0.04 | [9 empty] | Backfilling |  | Ea | 872.6412 |  | 872.6412 | 0.04 | 34.9056 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.020605 | 485.33 | 1.9413 | 19.4132
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 2.0605 | 31.8376 | 0.019413 | 1.2735
[22 empty] | Fuel | Material | LTR | 1.76 | 0.22894 | 7.6876 | 0.17472 | 0.30751
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.42033 | 114.1953 | 0.095163 | 4.5678
[22 empty] | Fuel | Material | LTR | 1.76 | 0.042033 | 41.8716 | 0.95163 | 1.6749
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 1.0302 | 34.9438 | 0.038826 | 1.3978
[22 empty] | Fuel | Material | LTR | 1.76 | 0.11447 | 15.3753 | 0.34944 | 0.61501
[22 empty] | Plate Compactor | Machinery | HR | 23 | 0.2 | 115 | 0.2 | 4.6
[22 empty] | Fuel | Material | LTR | 1.76 | 0.066667 | 26.4 | 0.6 | 1.056
SEW 10 |  | At a depth of 4.5 - 5.0 m (GRP) | nr | 0.17 | 57276 | 9736.92 | 15900.2594 | 2703.0441 | 0.17 | 0.17 |  | 0.17 | 100% | 57276 | 9736.92 | 15900.2594 | 2703.0441 |  | 2703.0441 | [7 empty] | 15900.2594 | 0.17 | 2703.0441 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 0.17 | 0.17 |  | 0.17 | [9 empty] | Excavate & Disposal (3.5*3.5*5.5) |  | Ea | 270.9881 |  | 270.9881 | 0.17 | 46.068 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 1.4842 | 37.73 | 0.11454 | 6.4141
[22 empty] | Fuel | Material | LTR | 1.76 | 0.10602 | 16.6012 | 1.6035 | 2.8222
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.30278 | 158.5294 | 0.56146 | 26.95
[22 empty] | Fuel | Material | LTR | 1.76 | 0.030278 | 58.1275 | 5.6146 | 9.8817
[9 empty] | 0.17 | 0.17 |  | 0.17 | [9 empty] | Concrete Base 30 cm |  | Ea | 2396.566 |  | 2396.566 | 0.17 | 407.4162 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 1.3717 | 182.25 | 0.12393 | 30.9825
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.4931 | 709.8 | 0.34476 | 120.666
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 6.1637 | 405.6 | 0.027581 | 68.952
[22 empty] | Workmanship plain concrete | SC | M³ | 150 | 1.3717 | 109.35 | 0.12393 | 18.5895
[22 empty] | Workmanship RC concrete | SC | M³ | 450 | 0.4931 | 912.6 | 0.34476 | 155.142
[22 empty] | 2 Layers Bituminous Application | SC | M² | 10 | 0.12993 | 76.966 | 1.3084 | 13.0842
[9 empty] | 0.17 | 0.17 |  | 0.17 | [9 empty] | Manhole Installation |  | Ea | 12272.8 |  | 12272.8 | 0.17 | 2086.376 | 0 | 0 | 0 | 0 | 0
[22 empty] | GRP manhole Dia 1800 mm D=5.0 m W Cover | Material | Ea | 10500 | 1 | 10500 | 0.17 | 1785
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 0.5 | 160 | 0.34 | 27.2
[22 empty] | Fuel | Material | HR | 1.76 | 0.033333 | 52.8 | 5.1 | 8.976
[22 empty] | Brick & Masonery for Manhole Neck | SC | LS | 1500 | 1 | 1500 | 0.17 | 255
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.5 | 34 | 0.34 | 5.78
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.5 | 26 | 0.34 | 4.42
[9 empty] | 0.17 | 0.17 |  | 0.17 | [9 empty] | Backfilling |  | Ea | 959.9053 |  | 959.9053 | 0.17 | 163.1839 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.018731 | 533.863 | 9.0757 | 90.7567
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 1.8731 | 35.0214 | 0.090757 | 5.9536
[22 empty] | Fuel | Material | LTR | 1.76 | 0.20813 | 8.4564 | 0.81681 | 1.4376
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.38212 | 125.6148 | 0.44489 | 21.3545
[22 empty] | Fuel | Material | LTR | 1.76 | 0.038212 | 46.0588 | 4.4489 | 7.83
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 0.93657 | 38.4381 | 0.18151 | 6.5345
[22 empty] | Fuel | Material | LTR | 1.76 | 0.10406 | 16.9128 | 1.6336 | 2.8752
[22 empty] | Plate Compactor | Machinery | HR | 23 | 0.18182 | 126.5 | 0.935 | 21.505
[22 empty] | Fuel | Material | LTR | 1.76 | 0.060606 | 29.04 | 2.805 | 4.9368
SEW 10 |  | At a depth of 5.0 - 5.5 m (GRP) | nr | 0.79 | 62941 | 49723.39 | 17040.7156 | 13462.1653 | 0.79 | 0.79 |  | 0.79 | 100% | 62941 | 49723.39 | 17040.7156 | 13462.1653 |  | 13462.1653 | [7 empty] | 17040.7156 | 0.79 | 13462.1653 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 0.79 | 0.79 |  | 0.79 | [9 empty] | Excavate & Disposal (3.5*3.5*6.0) |  | Ea | 374.1801 |  | 374.1801 | 0.79 | 295.6023 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 50T | Machinery | HR | 131.2 | 1.3605 | 96.432 | 0.58065 | 76.1813
[22 empty] | Fuel | Material | LTR | 1.76 | 0.042517 | 41.3952 | 18.5808 | 32.7022
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.27755 | 172.9412 | 2.8463 | 136.6235
[22 empty] | Fuel | Material | LTR | 1.76 | 0.027755 | 63.4118 | 28.4632 | 50.0953
[9 empty] | 0.79 | 0.79 |  | 0.79 | [9 empty] | Concrete Base 30 cm |  | Ea | 2396.566 |  | 2396.566 | 0.79 | 1893.2871 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 1.3717 | 182.25 | 0.57591 | 143.9775
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.4931 | 709.8 | 1.6021 | 560.742
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 6.1637 | 405.6 | 0.12817 | 320.424
[22 empty] | Workmanship plain concrete | SC | M³ | 150 | 1.3717 | 109.35 | 0.57591 | 86.3865
[22 empty] | Workmanship RC concrete | SC | M³ | 450 | 0.4931 | 912.6 | 1.6021 | 720.954
[22 empty] | 2 Layers Bituminous Application | SC | M² | 10 | 0.12993 | 76.966 | 6.0803 | 60.8031
[9 empty] | 0.79 | 0.79 |  | 0.79 | [9 empty] | Manhole Installation |  | Ea | 13222.8 |  | 13222.8 | 0.79 | 10446.012 | 0 | 0 | 0 | 0 | 0
[22 empty] | GRP manhole Dia 1800 mm D=5.5 m W Cover | Material | Ea | 11450 | 1 | 11450 | 0.79 | 9045.5
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 0.5 | 160 | 1.58 | 126.4
[22 empty] | Fuel | Material | HR | 1.76 | 0.033333 | 52.8 | 23.7 | 41.712
[22 empty] | Brick & Masonery for Manhole Neck | SC | LS | 1500 | 1 | 1500 | 0.79 | 1185
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.5 | 34 | 1.58 | 26.86
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.5 | 26 | 1.58 | 20.54
[9 empty] | 0.79 | 0.79 |  | 0.79 | [9 empty] | Backfilling |  | Ea | 1047.1694 |  | 1047.1694 | 0.79 | 827.2638 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.01717 | 582.396 | 46.0093 | 460.0928
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 1.717 | 38.2052 | 0.46009 | 30.1821
[22 empty] | Fuel | Material | LTR | 1.76 | 0.19078 | 9.2252 | 4.1408 | 7.2879
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.35028 | 137.0344 | 2.2554 | 108.2571
[22 empty] | Fuel | Material | LTR | 1.76 | 0.035028 | 50.2459 | 22.5536 | 39.6943
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 0.85852 | 41.9325 | 0.92019 | 33.1267
[22 empty] | Fuel | Material | LTR | 1.76 | 0.095391 | 18.4503 | 8.2817 | 14.5757
[22 empty] | Plate Compactor | Machinery | HR | 23 | 0.16667 | 138 | 4.74 | 109.02
[22 empty] | Fuel | Material | LTR | 1.76 | 0.055556 | 31.68 | 14.22 | 25.0272
SEW 10 |  | At a depth of 5.5 - 6.0 m (GRP) | nr | 0.77 | 68731 | 52922.87 | 18259.1614 | 14059.5543 | 0.77 | 0.77 |  | 0.77 | 100% | 68731 | 52922.87 | 18259.1614 | 14059.5543 |  | 14059.5543 | [7 empty] | 18259.1614 | 0.77 | 14059.5543 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 0.77 | 0.77 |  | 0.77 | [9 empty] | Excavate & Disposal (3.5*3.5*6.5) |  | Ea | 405.3618 |  | 405.3618 | 0.77 | 312.1286 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 50T | Machinery | HR | 131.2 | 1.2559 | 104.468 | 0.61311 | 80.4404
[22 empty] | Fuel | Material | LTR | 1.76 | 0.039246 | 44.8448 | 19.6196 | 34.5305
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.2562 | 187.3529 | 3.0055 | 144.2618
[22 empty] | Fuel | Material | LTR | 1.76 | 0.02562 | 68.6961 | 30.0545 | 52.896
[9 empty] | 0.77 | 0.77 |  | 0.77 | [9 empty] | Concrete Base 30 cm |  | Ea | 2396.566 |  | 2396.566 | 0.77 | 1845.3558 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 1.3717 | 182.25 | 0.56133 | 140.3325
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.4931 | 709.8 | 1.5616 | 546.546
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 6.1637 | 405.6 | 0.12492 | 312.312
[22 empty] | Workmanship plain concrete | SC | M³ | 150 | 1.3717 | 109.35 | 0.56133 | 84.1995
[22 empty] | Workmanship RC concrete | SC | M³ | 450 | 0.4931 | 912.6 | 1.5616 | 702.702
[22 empty] | 2 Layers Bituminous Application | SC | M² | 10 | 0.12993 | 76.966 | 5.9264 | 59.2638
[9 empty] | 0.77 | 0.77 |  | 0.77 | [9 empty] | Manhole Installation |  | Ea | 14322.8 |  | 14322.8 | 0.77 | 11028.556 | 0 | 0 | 0 | 0 | 0
[22 empty] | GRP manhole Dia 1800 mm D=6.0 m W Cover | Material | Ea | 12550 | 1 | 12550 | 0.77 | 9663.5
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 0.5 | 160 | 1.54 | 123.2
[22 empty] | Fuel | Material | HR | 1.76 | 0.033333 | 52.8 | 23.1 | 40.656
[22 empty] | Brick & Masonery for Manhole Neck | SC | LS | 1500 | 1 | 1500 | 0.77 | 1155
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.5 | 34 | 1.54 | 26.18
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.5 | 26 | 1.54 | 20.02
[9 empty] | 0.77 | 0.77 |  | 0.77 | [9 empty] | Backfilling |  | Ea | 1134.4335 |  | 1134.4335 | 0.77 | 873.5138 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.01585 | 630.929 | 48.5815 | 485.8153
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 1.585 | 41.3889 | 0.48582 | 31.8695
[22 empty] | Fuel | Material | LTR | 1.76 | 0.17611 | 9.9939 | 4.3723 | 7.6953
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.32333 | 148.4539 | 2.3814 | 114.3095
[22 empty] | Fuel | Material | LTR | 1.76 | 0.032333 | 54.4331 | 23.8145 | 41.9135
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 0.79248 | 45.4269 | 0.97163 | 34.9787
[22 empty] | Fuel | Material | LTR | 1.76 | 0.088054 | 19.9878 | 8.7447 | 15.3906
[22 empty] | Plate Compactor | Machinery | HR | 23 | 0.15385 | 149.5 | 5.005 | 115.115
[22 empty] | Fuel | Material | LTR | 1.76 | 0.051282 | 34.32 | 15.015 | 26.4264
SEW 10 |  | Increasing the depth difference by 0.5 m for 1800 mm diameter manhole chambers (GRP) | nr |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | Increasing the depth difference by 1.0 m for 1800 mm diameter manhole chambers (GRP) | nr |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | Increasing the depth difference by 1.5 m for 1800 mm diameter manhole chambers (GRP) | nr |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | Increasing the depth difference by 2.0 m for 1800 mm diameter manhole chambers (GRP) | nr |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | Increasing the depth difference by 2.5 m for 1800 mm diameter manhole chambers (GRP) | nr |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | Increased depth difference of 3.0 m for 1800 mm diameter manhole chambers (GRP) | nr |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | Increased depth difference of 3.5 m for 1800 mm diameter manhole chambers (GRP) | nr |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | Increased depth difference of 4.0 m for 1800 mm diameter manhole chambers (GRP) | nr |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | Increased depth difference of 4.5 m for 1800 mm diameter manhole chambers (GRP) | nr |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | Backdrop manholes |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | Inspection chambers equipped with one opening (with vertical pipe and concrete skirting equipment), the necessary excavation and concrete construction, a GRP lining, an insulating layer with a protection board, and originally equipped short pipes (built-in), with a frame and cover of a good and tight type, according to the drawings. |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | Manholes with a back drop, diameter 1800 mm |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | At a depth of 5.0 - 5.5 m (GRP) | nr | 0.12 | 67787 | 8134.44 | 20540.7156 | 2464.8859 | 0.12 | 0.12 |  | 0.12 | 100% | 67787 | 8134.44 | 20540.7156 | 2464.8859 |  | 2464.8859 | [7 empty] | 20540.7156 | 0.12 | 2464.8859 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 0.12 | 0.12 |  | 0.12 | [9 empty] | Excavate & Disposal (3.5*3.5*6.0) |  | Ea | 374.1801 |  | 374.1801 | 0.12 | 44.9016 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 50T | Machinery | HR | 131.2 | 1.3605 | 96.432 | 0.0882 | 11.5718
[22 empty] | Fuel | Material | LTR | 1.76 | 0.042517 | 41.3952 | 2.8224 | 4.9674
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.27755 | 172.9412 | 0.43235 | 20.7529
[22 empty] | Fuel | Material | LTR | 1.76 | 0.027755 | 63.4118 | 4.3235 | 7.6094
[9 empty] | 0.12 | 0.12 |  | 0.12 | [9 empty] | Concrete Base 30 cm |  | Ea | 2396.566 |  | 2396.566 | 0.12 | 287.5879 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 1.3717 | 182.25 | 0.08748 | 21.87
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.4931 | 709.8 | 0.24336 | 85.176
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 6.1637 | 405.6 | 0.019469 | 48.672
[22 empty] | Workmanship plain concrete | SC | M³ | 150 | 1.3717 | 109.35 | 0.08748 | 13.122
[22 empty] | Workmanship RC concrete | SC | M³ | 450 | 0.4931 | 912.6 | 0.24336 | 109.512
[22 empty] | 2 Layers Bituminous Application | SC | M² | 10 | 0.12993 | 76.966 | 0.92359 | 9.2359
[9 empty] | 0.12 | 0.12 |  | 0.12 | [9 empty] | Manhole Installation |  | Ea | 16722.8 |  | 16722.8 | 0.12 | 2006.736 | 0 | 0 | 0 | 0 | 0
[22 empty] | GRP manhole Dia 1800 mm D=5.5 m W Cover | Material | Ea | 11450 | 1 | 11450 | 0.12 | 1374
[22 empty] | Manhole Back drop PCs | Material | LS | 3500 | 1 | 3500 | 0.12 | 420
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 0.5 | 160 | 0.24 | 19.2
[22 empty] | Fuel | Material | HR | 1.76 | 0.033333 | 52.8 | 3.6 | 6.336
[22 empty] | Brick & Masonery for Manhole Neck | SC | LS | 1500 | 1 | 1500 | 0.12 | 180
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.5 | 34 | 0.24 | 4.08
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.5 | 26 | 0.24 | 3.12
[9 empty] | 0.12 | 0.12 |  | 0.12 | [9 empty] | Backfilling |  | Ea | 1047.1694 |  | 1047.1694 | 0.12 | 125.6603 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.01717 | 582.396 | 6.9888 | 69.8875
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 1.717 | 38.2052 | 0.069888 | 4.5846
[22 empty] | Fuel | Material | LTR | 1.76 | 0.19078 | 9.2252 | 0.62899 | 1.107
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.35028 | 137.0344 | 0.34259 | 16.4441
[22 empty] | Fuel | Material | LTR | 1.76 | 0.035028 | 50.2459 | 3.4259 | 6.0295
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 0.85852 | 41.9325 | 0.13978 | 5.0319
[22 empty] | Fuel | Material | LTR | 1.76 | 0.095391 | 18.4503 | 1.258 | 2.214
[22 empty] | Plate Compactor | Machinery | HR | 23 | 0.16667 | 138 | 0.72 | 16.56
[22 empty] | Fuel | Material | LTR | 1.76 | 0.055556 | 31.68 | 2.16 | 3.8016
SEW 10 |  | Increasing the depth difference by 0.5 m for sinkholes with a back fall of 1800 mm diameter (GRP) | nr |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | Sanitary manholes from GRP include excavation, backfilling, waste disposal, dewatering, cleaning concrete, concrete pour, footings, DI cover with openings and frame, chains, pipes, fittings, spacers, pipe connections, etc., complete in accordance with the plans, specifications, and requirements of the concerned authority, dewatering, strengthening and protecting the excavated surfaces up to the required depths, and the disposal of groundwater resulting from dewatering around them is measured individually. |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | Manhole chambers with a diameter of 2000 mm |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | At a depth of 5.5 - 6.0 m (GRP) | nr | 0.28 | 71627 | 20055.56 | 20663.7134 | 5785.8397 | 0.28 | 0.28 |  | 0.28 | 100% | 71627 | 20055.56 | 20663.7134 | 5785.8397 |  | 5785.8397 | [7 empty] | 20663.7134 | 0.28 | 5785.8397 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 0.28 | 0.28 |  | 0.28 | [9 empty] | Excavate & Disposal (3.8*3.8*6.5) |  | Ea | 477.8306 |  | 477.8306 | 0.28 | 133.7926 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 50T | Machinery | HR | 131.2 | 1.0654 | 123.1443 | 0.26281 | 34.4804
[22 empty] | Fuel | Material | LTR | 1.76 | 0.033294 | 52.862 | 8.4099 | 14.8013
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.21734 | 220.8471 | 1.2883 | 61.8372
[22 empty] | Fuel | Material | LTR | 1.76 | 0.021734 | 80.9773 | 12.8827 | 22.6736
[9 empty] | 0.28 | 0.28 |  | 0.28 | [9 empty] | Concrete Base 30 cm |  | Ea | 2772.6 |  | 2772.6 | 0.28 | 776.328 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 1.1891 | 210.25 | 0.23548 | 58.87
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.42517 | 823.2 | 0.65856 | 230.496
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 5.3146 | 470.4 | 0.052685 | 131.712
[22 empty] | Workmanship plain concrete | SC | M³ | 150 | 1.1891 | 126.15 | 0.23548 | 35.322
[22 empty] | Workmanship RC concrete | SC | M³ | 450 | 0.42517 | 1058.4 | 0.65856 | 296.352
[22 empty] | 2 Layers Bituminous Application | SC | M² | 10 | 0.11876 | 84.2 | 2.3576 | 23.576
[9 empty] | 0.28 | 0.28 |  | 0.28 | [9 empty] | Manhole Installation |  | Ea | 16122.8 |  | 16122.8 | 0.28 | 4514.384 | 0 | 0 | 0 | 0 | 0
[22 empty] | GRP manhole Dia 2000 mm D=6.0 m W Cover | Material | Ea | 14350 | 1 | 14350 | 0.28 | 4018
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 0.5 | 160 | 0.56 | 44.8
[22 empty] | Fuel | Material | HR | 1.76 | 0.033333 | 52.8 | 8.4 | 14.784
[22 empty] | Brick & Masonery for Manhole Neck | SC | LS | 1500 | 1 | 1500 | 0.28 | 420
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.5 | 34 | 0.56 | 9.52
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.5 | 26 | 0.56 | 7.28
[9 empty] | 0.28 | 0.28 |  | 0.28 | [9 empty] | Backfilling |  | Ea | 1290.4828 |  | 1290.4828 | 0.28 | 361.3352 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.013615 | 734.5 | 20.566 | 205.66
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 1.3615 | 48.1832 | 0.20566 | 13.4913
[22 empty] | Fuel | Material | LTR | 1.76 | 0.15127 | 11.6345 | 1.8509 | 3.2577
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.27774 | 172.8235 | 1.0081 | 48.3906
[22 empty] | Fuel | Material | LTR | 1.76 | 0.027774 | 63.3686 | 10.0814 | 17.7432
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 0.68074 | 52.884 | 0.41132 | 14.8075
[22 empty] | Fuel | Material | LTR | 1.76 | 0.075637 | 23.269 | 3.7019 | 6.5153
[22 empty] | Plate Compactor | Machinery | HR | 23 | 0.15385 | 149.5 | 1.82 | 41.86
[22 empty] | Fuel | Material | LTR | 1.76 | 0.051282 | 34.32 | 5.46 | 9.6096
SEW 10 |  | At a depth of 6.5 - 7.0 m (GRP) | nr | 0.12 | 83585 | 10030.2 | 24435.7616 | 2932.2914 | 0.12 | 0.12 |  | 0.12 | 100% | 83585 | 10030.2 | 24435.7616 | 2932.2914 |  | 2932.2914 | [7 empty] | 24435.7616 | 0.12 | 2932.2914 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 0.12 | 0.12 |  | 0.12 | [9 empty] | Excavate & Disposal (3.8*3.8*7.5) |  | Ea | 551.343 |  | 551.343 | 0.12 | 66.1612 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 50T | Machinery | HR | 131.2 | 0.92336 | 142.0896 | 0.12996 | 17.0508
[22 empty] | Fuel | Material | LTR | 1.76 | 0.028855 | 60.9946 | 4.1587 | 7.3193
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.18837 | 254.8235 | 0.63706 | 30.5788
[22 empty] | Fuel | Material | LTR | 1.76 | 0.018837 | 93.4353 | 6.3706 | 11.2122
[9 empty] | 0.12 | 0.12 |  | 0.12 | [9 empty] | Concrete Base 30 cm |  | Ea | 2772.6 |  | 2772.6 | 0.12 | 332.712 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 1.1891 | 210.25 | 0.10092 | 25.23
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.42517 | 823.2 | 0.28224 | 98.784
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 5.3146 | 470.4 | 0.022579 | 56.448
[22 empty] | Workmanship plain concrete | SC | M³ | 150 | 1.1891 | 126.15 | 0.10092 | 15.138
[22 empty] | Workmanship RC concrete | SC | M³ | 450 | 0.42517 | 1058.4 | 0.28224 | 127.008
[22 empty] | 2 Layers Bituminous Application | SC | M² | 10 | 0.11876 | 84.2 | 1.0104 | 10.104
[9 empty] | 0.12 | 0.12 |  | 0.12 | [9 empty] | Manhole Installation |  | Ea | 19622.8 |  | 19622.8 | 0.12 | 2354.736 | 0 | 0 | 0 | 0 | 0
[22 empty] | GRP manhole Dia 2000 mm D=7.0 m W Cover | Material | Ea | 17850 | 1 | 17850 | 0.12 | 2142
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 0.5 | 160 | 0.24 | 19.2
[22 empty] | Fuel | Material | HR | 1.76 | 0.033333 | 52.8 | 3.6 | 6.336
[22 empty] | Brick & Masonery for Manhole Neck | SC | LS | 1500 | 1 | 1500 | 0.12 | 180
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.5 | 34 | 0.24 | 4.08
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.5 | 26 | 0.24 | 3.12
[9 empty] | 0.12 | 0.12 |  | 0.12 | [9 empty] | Backfilling |  | Ea | 1489.0186 |  | 1489.0186 | 0.12 | 178.6822 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.011799 | 847.5 | 10.17 | 101.7
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 1.1799 | 55.596 | 0.1017 | 6.6715
[22 empty] | Fuel | Material | LTR | 1.76 | 0.1311 | 13.4244 | 0.9153 | 1.6109
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.24071 | 199.4118 | 0.49853 | 23.9294
[22 empty] | Fuel | Material | LTR | 1.76 | 0.024071 | 73.1176 | 4.9853 | 8.7741
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 0.58997 | 61.02 | 0.2034 | 7.3224
[22 empty] | Fuel | Material | LTR | 1.76 | 0.065552 | 26.8488 | 1.8306 | 3.2219
[22 empty] | Plate Compactor | Machinery | HR | 23 | 0.13333 | 172.5 | 0.9 | 20.7
[22 empty] | Fuel | Material | LTR | 1.76 | 0.044444 | 39.6 | 2.7 | 4.752
SEW 10 |  | Increasing the depth difference by 0.5 m for 2000 mm diameter manholes (GRP) | nr | 0.28 | 5970 | 1671.6 | 136.0241 | 38.0867 | 0.28 | 0.28 |  | 0.28 | 100% | 5970 | 1671.6 | 136.0241 | 38.0867 |  | 38.0867 | [7 empty] | 136.0241 | 0.28 | 38.0867 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 0.28 | 0.28 |  | 0.28 | [9 empty] | Excavate & Disposal (3.8*3.8*0.5) |  | Ea | 36.7562 |  | 36.7562 | 0.28 | 10.2917 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 50T | Machinery | HR | 131.2 | 13.8504 | 9.4726 | 0.020216 | 2.6523
[22 empty] | Fuel | Material | LTR | 1.76 | 0.43283 | 4.0663 | 0.64691 | 1.1386
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 2.8255 | 16.9882 | 0.099098 | 4.7567
[22 empty] | Fuel | Material | LTR | 1.76 | 0.28255 | 6.229 | 0.99098 | 1.7441
[9 empty] | 0.28 | 0.28 |  | 0.28 | [9 empty] | Backfilling |  | Ea | 99.2679 |  | 99.2679 | 0.28 | 27.795 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.17699 | 56.5 | 1.582 | 15.82
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 17.6991 | 3.7064 | 0.01582 | 1.0378
[22 empty] | Fuel | Material | LTR | 1.76 | 1.9666 | 0.89496 | 0.14238 | 0.25059
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 3.6106 | 13.2941 | 0.077549 | 3.7224
[22 empty] | Fuel | Material | LTR | 1.76 | 0.36106 | 4.8745 | 0.77549 | 1.3649
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 8.8496 | 4.068 | 0.03164 | 1.139
[22 empty] | Fuel | Material | LTR | 1.76 | 0.98328 | 1.7899 | 0.28476 | 0.50118
[22 empty] | Plate Compactor | Machinery | HR | 23 | 2 | 11.5 | 0.14 | 3.22
[22 empty] | Fuel | Material | LTR | 1.76 | 0.66667 | 2.64 | 0.42 | 0.7392
SEW 10 |  | Increasing the depth difference by 1.5 m for 2000 mm diameter manholes (GRP) | nr |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | Backdrop manholes |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | Inspection chambers equipped with one opening (with vertical pipe and concrete skirting equipment), the necessary excavation and concrete construction, a GRP lining, an insulating layer with a protection board, and originally equipped short pipes (built-in), with a frame and cover of a good and tight type, according to the drawings. |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | Manholes with a back drop, diameter 2000 mm |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | At a depth of 6.0 - 6.5 m (GRP) | nr |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | At a depth of 6.5 - 7 m (GRP) | nr | 0.24 | 83585 | 20060.4 | 27935.7616 | 6704.5828 | 0.24 | 0.24 |  | 0.24 | 100% | 83585 | 20060.4 | 27935.7616 | 6704.5828 |  | 6704.5828 | [7 empty] | 27935.7616 | 0.24 | 6704.5828 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 0.24 | 0.24 |  | 0.24 | [9 empty] | Excavate & Disposal (3.8*3.8*7.5) |  | Ea | 551.343 |  | 551.343 | 0.24 | 132.3223 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 50T | Machinery | HR | 131.2 | 0.92336 | 142.0896 | 0.25992 | 34.1015
[22 empty] | Fuel | Material | LTR | 1.76 | 0.028855 | 60.9946 | 8.3174 | 14.6387
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.18837 | 254.8235 | 1.2741 | 61.1576
[22 empty] | Fuel | Material | LTR | 1.76 | 0.018837 | 93.4353 | 12.7412 | 22.4245
[9 empty] | 0.24 | 0.24 |  | 0.24 | [9 empty] | Concrete Base 30 cm |  | Ea | 2772.6 |  | 2772.6 | 0.24 | 665.424 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 1.1891 | 210.25 | 0.20184 | 50.46
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.42517 | 823.2 | 0.56448 | 197.568
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 5.3146 | 470.4 | 0.045158 | 112.896
[22 empty] | Workmanship plain concrete | SC | M³ | 150 | 1.1891 | 126.15 | 0.20184 | 30.276
[22 empty] | Workmanship RC concrete | SC | M³ | 450 | 0.42517 | 1058.4 | 0.56448 | 254.016
[22 empty] | 2 Layers Bituminous Application | SC | M² | 10 | 0.11876 | 84.2 | 2.0208 | 20.208
[9 empty] | 0.24 | 0.24 |  | 0.24 | [9 empty] | Manhole Installation |  | Ea | 23122.8 |  | 23122.8 | 0.24 | 5549.472 | 0 | 0 | 0 | 0 | 0
[22 empty] | GRP manhole Dia 2000 mm D=7.0 m W Cover | Material | Ea | 17850 | 1 | 17850 | 0.24 | 4284
[22 empty] | Manhole Back drop PCs | Material | LS | 3500 | 1 | 3500 | 0.24 | 840
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 0.5 | 160 | 0.48 | 38.4
[22 empty] | Fuel | Material | HR | 1.76 | 0.033333 | 52.8 | 7.2 | 12.672
[22 empty] | Brick & Masonery for Manhole Neck | SC | LS | 1500 | 1 | 1500 | 0.24 | 360
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.5 | 34 | 0.48 | 8.16
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.5 | 26 | 0.48 | 6.24
[9 empty] | 0.24 | 0.24 |  | 0.24 | [9 empty] | Backfilling |  | Ea | 1489.0186 |  | 1489.0186 | 0.24 | 357.3645 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.011799 | 847.5 | 20.34 | 203.4
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 1.1799 | 55.596 | 0.2034 | 13.343
[22 empty] | Fuel | Material | LTR | 1.76 | 0.1311 | 13.4244 | 1.8306 | 3.2219
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.24071 | 199.4118 | 0.99706 | 47.8588
[22 empty] | Fuel | Material | LTR | 1.76 | 0.024071 | 73.1176 | 9.9706 | 17.5482
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 0.58997 | 61.02 | 0.4068 | 14.6448
[22 empty] | Fuel | Material | LTR | 1.76 | 0.065552 | 26.8488 | 3.6612 | 6.4437
[22 empty] | Plate Compactor | Machinery | HR | 23 | 0.13333 | 172.5 | 1.8 | 41.4
[22 empty] | Fuel | Material | LTR | 1.76 | 0.044444 | 39.6 | 5.4 | 9.504
SEW 10 |  | Increase the depth difference by 0.5 m for 2000 mm diameter back-fall holes (GRP) | nr | 0.12 | 6429 | 771.48 | 136.0241 | 16.3229 | 0.12 | 0.12 |  | 0.12 | 100% | 6429 | 771.48 | 136.0241 | 16.3229 |  | 16.3229 | [7 empty] | 136.0241 | 0.12 | 16.3229 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 0.12 | 0.12 |  | 0.12 | [9 empty] | Excavate & Disposal (3.8*3.8*0.5) |  | Ea | 36.7562 |  | 36.7562 | 0.12 | 4.4107 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 50T | Machinery | HR | 131.2 | 13.8504 | 9.4726 | 0.008664 | 1.1367
[22 empty] | Fuel | Material | LTR | 1.76 | 0.43283 | 4.0663 | 0.27725 | 0.48796
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 2.8255 | 16.9882 | 0.042471 | 2.0386
[22 empty] | Fuel | Material | LTR | 1.76 | 0.28255 | 6.229 | 0.42471 | 0.74748
[9 empty] | 0.12 | 0.12 |  | 0.12 | [9 empty] | Backfilling |  | Ea | 99.2679 |  | 99.2679 | 0.12 | 11.9121 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.17699 | 56.5 | 0.678 | 6.78
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 17.6991 | 3.7064 | 0.00678 | 0.44477
[22 empty] | Fuel | Material | LTR | 1.76 | 1.9666 | 0.89496 | 0.06102 | 0.1074
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 3.6106 | 13.2941 | 0.033235 | 1.5953
[22 empty] | Fuel | Material | LTR | 1.76 | 0.36106 | 4.8745 | 0.33235 | 0.58494
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 8.8496 | 4.068 | 0.01356 | 0.48816
[22 empty] | Fuel | Material | LTR | 1.76 | 0.98328 | 1.7899 | 0.12204 | 0.21479
[22 empty] | Plate Compactor | Machinery | HR | 23 | 2 | 11.5 | 0.06 | 1.38
[22 empty] | Fuel | Material | LTR | 1.76 | 0.66667 | 2.64 | 0.18 | 0.3168
SEW 10 |  | Increase the depth difference of 1.0 m for 2000 mm diameter back-fall holes (GRP) | nr |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | Art (K): Pipeworks - manholes and pipework accessories (continued) |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
SEW 10 |  | The other decorated rooms |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
SEW 10 |  | Home connections room with the possibility of connecting to private properties, accompanying concrete works, water path work inside the rooms (BENCHING), a pre-cast opening cover, a cover and a high-strength steel frame according to what is stated on the plans (reserve quantity enclosed). |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
SEW 10 |  | Maximum depth 1.5 metres | nr |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | Backfill materials under and around pipes |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
SEW 10 |  | Materials for granular bedding or powdered gravel are well compacted under and around the pipe to different depths in accordance with the plans, specifications and requirements of the concerned authority. |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
SEW 10 |  | On pipes with an inner diameter of 150 mm | m | 368.1557 | 83 | 30556.919 | 56.1518 | 20672.5949 | 368.1557 | 368.1557 |  | 368.1557 | 100% | 83 | 30556.919 | 56.1518 | 20672.5949 |  | 20672.5949 | [7 empty] | 56.1518 | 368.1557 | 20672.5949 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 368.1557 | 368.1557 |  | 368.1557 | [9 empty] | Granular Material (W=1.0) |  | M | 56.1518 |  | 56.1518 | 368.1557 | 20672.5949 | 0 | 0 | 0 | 0 | 0
[22 empty] | Granular bedding backfilling material | Material | M³ | 70 | 1.3655 | 51.2636 | 269.6142 | 18872.9932
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 136.5491 | 0.48041 | 2.6961 | 176.8669
[22 empty] | Fuel | Material | LTR | 1.76 | 15.1721 | 0.116 | 24.2653 | 42.7069
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 18.5707 | 2.5847 | 19.8246 | 951.5795
[22 empty] | Fuel | Material | LTR | 1.76 | 1.8571 | 0.94773 | 198.2457 | 348.9125
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 68.2745 | 0.52728 | 5.3923 | 194.1222
[22 empty] | Fuel | Material | LTR | 1.76 | 7.5861 | 0.232 | 48.5306 | 85.4138
SEW 10 |  | On pipes with an inner diameter of 200 mm | m | 1846.7769 | 95 | 175443.8008 | 58.9322 | 108834.6172 | 1846.7769 | 1846.7769 |  | 1846.7769 | 100% | 95 | 175443.8008 | 58.9322 | 108834.6172 |  | 108834.6172 | [7 empty] | 58.9322 | 1846.7769 | 108834.6172 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 1846.7769 | 1846.7769 |  | 1846.7769 | [9 empty] | Granular Material (W=1.0) |  | M | 58.9322 |  | 58.9322 | 1846.7769 | 108834.6172 | 0 | 0 | 0 | 0 | 0
[22 empty] | Granular bedding backfilling material | Material | M³ | 70 | 1.3011 | 53.802 | 1419.4327 | 99360.2881
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 130.1067 | 0.5042 | 14.1943 | 931.1478
[22 empty] | Fuel | Material | LTR | 1.76 | 14.4563 | 0.12175 | 127.7489 | 224.8381
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 17.6945 | 2.7127 | 104.3701 | 5009.7624
[22 empty] | Fuel | Material | LTR | 1.76 | 1.7695 | 0.99466 | 1043.7005 | 1836.9129
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 65.0533 | 0.55339 | 28.3887 | 1021.9915
[22 empty] | Fuel | Material | LTR | 1.76 | 7.2281 | 0.24349 | 255.4979 | 449.6763
SEW 10 |  | On pipes with an inner diameter of 250 mm | m | 530.566 | 108 | 57301.128 | 61.4117 | 32582.942 | 530.566 | 530.566 |  | 530.566 | 100% | 108 | 57301.128 | 61.4117 | 32582.942 |  | 32582.942 | [7 empty] | 61.4117 | 530.566 | 32582.942 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 530.566 | 530.566 |  | 530.566 | [9 empty] | Granular Material (W=1.0) |  | M | 61.4117 |  | 61.4117 | 530.566 | 32582.942 | 0 | 0 | 0 | 0 | 0
[22 empty] | Granular bedding backfilling material | Material | M³ | 70 | 1.2485 | 56.0656 | 424.9502 | 29746.5144
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 124.8537 | 0.52541 | 4.2495 | 278.7673
[22 empty] | Fuel | Material | LTR | 1.76 | 13.8726 | 0.12687 | 38.2455 | 67.3121
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 16.9801 | 2.8268 | 31.2463 | 1499.8243
[22 empty] | Fuel | Material | LTR | 1.76 | 1.698 | 1.0365 | 312.4634 | 549.9356
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 62.4268 | 0.57668 | 8.499 | 305.9641
[22 empty] | Fuel | Material | LTR | 1.76 | 6.9363 | 0.25374 | 76.491 | 134.6242
SEW 10 |  | On pipes with an inner diameter of 315 mm | m | 231.677 | 124 | 28727.9542 | 64.1851 | 14870.2049 | 231.677 | 231.677 |  | 231.677 | 100% | 124 | 28727.9542 | 64.1851 | 14870.2049 |  | 14870.2049 | [7 empty] | 64.1851 | 231.677 | 14870.2049 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 231.677 | 231.677 |  | 231.677 | [9 empty] | Granular Material (W=1.0) |  | M | 64.1851 |  | 64.1851 | 231.677 | 14870.2049 | 0 | 0 | 0 | 0 | 0
[22 empty] | Granular bedding backfilling material | Material | M³ | 70 | 1.1946 | 58.5976 | 193.9388 | 13575.7159
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 119.4588 | 0.54914 | 1.9394 | 127.2239
[22 empty] | Fuel | Material | LTR | 1.76 | 13.2732 | 0.1326 | 17.4545 | 30.7199
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 16.2464 | 2.9545 | 14.2602 | 684.4899
[22 empty] | Fuel | Material | LTR | 1.76 | 1.6246 | 1.0833 | 142.6021 | 250.9796
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 59.7294 | 0.60272 | 3.8788 | 139.6359
[22 empty] | Fuel | Material | LTR | 1.76 | 6.6366 | 0.2652 | 34.909 | 61.4398
SEW 10 |  | On pipes with an inner diameter of 355 mm | m |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | On pipes with an inner diameter of 400 mm | m | 248.8512 | 148 | 36829.985 | 82.3793 | 20500.1991 | 248.8512 | 248.8512 |  | 248.8512 | 100% | 148 | 36829.985 | 82.3793 | 20500.1991 |  | 20500.1991 | [7 empty] | 82.3793 | 248.8512 | 20500.1991 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 248.8512 | 248.8512 |  | 248.8512 | [9 empty] | Granular Material (W=1.2) |  | M | 82.3793 |  | 82.3793 | 248.8512 | 20500.1991 | 0 | 0 | 0 | 0 | 0
[22 empty] | Granular bedding backfilling material | Material | M³ | 70 | 0.93075 | 75.208 | 267.3658 | 18715.6048
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 93.0752 | 0.70481 | 2.6737 | 175.392
[22 empty] | Fuel | Material | LTR | 1.76 | 10.3417 | 0.17018 | 24.0629 | 42.3507
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 12.6582 | 3.792 | 19.6592 | 943.6439
[22 empty] | Fuel | Material | LTR | 1.76 | 1.2658 | 1.3904 | 196.5925 | 346.0028
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 46.5376 | 0.77357 | 5.3473 | 192.5034
[22 empty] | Fuel | Material | LTR | 1.76 | 5.1708 | 0.34037 | 48.1258 | 84.7015
SEW 10 |  | On pipes with an internal diameter of 500 mm | m | 127.3835 | 177 | 22546.8883 | 111.4659 | 14198.9205 | 127.3835 | 127.3835 |  | 127.3835 | 100% | 177 | 22546.8883 | 111.4659 | 14198.9205 |  | 14198.9205 | [7 empty] | 111.4659 | 127.3835 | 14198.9205 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 127.3835 | 127.3835 |  | 127.3835 | [9 empty] | Granular Material (W=1.5) |  | M | 111.4659 |  | 111.4659 | 127.3835 | 14198.9205 | 0 | 0 | 0 | 0 | 0
[22 empty] | Granular bedding backfilling material | Material | M³ | 70 | 0.68788 | 101.7625 | 185.1838 | 12962.8685
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 68.7876 | 0.95366 | 1.8518 | 121.4806
[22 empty] | Fuel | Material | LTR | 1.76 | 7.6431 | 0.23027 | 16.6665 | 29.3331
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 9.3551 | 5.1309 | 13.6165 | 653.59
[22 empty] | Fuel | Material | LTR | 1.76 | 0.93551 | 1.8813 | 136.1646 | 239.6497
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 34.3938 | 1.0467 | 3.7037 | 133.3324
[22 empty] | Fuel | Material | LTR | 1.76 | 3.8215 | 0.46055 | 33.3331 | 58.6662
SEW 10 |  | On pipes with an internal diameter of 600 mm | m | 175.5932 | 212 | 37225.769 | 125.5472 | 22045.2412 | 175.5932 | 175.5932 |  | 175.5932 | 100% | 212 | 37225.769 | 125.5472 | 22045.2412 |  | 22045.2412 | [7 empty] | 125.5472 | 175.5932 | 22045.2412 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 175.5932 | 175.5932 |  | 175.5932 | [9 empty] | Granular Material (W=1.6) |  | M | 125.5472 |  | 125.5472 | 175.5932 | 22045.2412 | 0 | 0 | 0 | 0 | 0
[22 empty] | Granular bedding backfilling material | Material | M³ | 70 | 0.61072 | 114.618 | 287.5164 | 20126.1471
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 61.0724 | 1.0741 | 2.8752 | 188.6108
[22 empty] | Fuel | Material | LTR | 1.76 | 6.7858 | 0.25936 | 25.8765 | 45.5426
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 8.3059 | 5.7791 | 21.1409 | 1014.7637
[22 empty] | Fuel | Material | LTR | 1.76 | 0.83059 | 2.119 | 211.4091 | 372.08
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 30.5362 | 1.1789 | 5.7503 | 207.0118
[22 empty] | Fuel | Material | LTR | 1.76 | 3.3929 | 0.51873 | 51.7529 | 91.0852
SEW 10 |  | On pipes with an inner diameter of 700 mm | m | 183.9419 | 248 | 45617.6036 | 139.9582 | 25744.1874 | 183.9419 | 183.9419 |  | 183.9419 | 100% | 248 | 45617.6036 | 139.9582 | 25744.1874 |  | 25744.1874 | [7 empty] | 139.9582 | 183.9419 | 25744.1874 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 183.9419 | 183.9419 |  | 183.9419 | [9 empty] | Granular Material (W=1.7) |  | M | 139.9582 |  | 139.9582 | 183.9419 | 25744.1874 | 0 | 0 | 0 | 0 | 0
[22 empty] | Granular bedding backfilling material | Material | M³ | 70 | 0.54784 | 127.7745 | 335.7584 | 23503.0907
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 54.784 | 1.1974 | 3.3576 | 220.2575
[22 empty] | Fuel | Material | LTR | 1.76 | 6.0871 | 0.28914 | 30.2183 | 53.1841
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 7.4506 | 6.4424 | 24.6881 | 1185.0298
[22 empty] | Fuel | Material | LTR | 1.76 | 0.74506 | 2.3622 | 246.8812 | 434.5109
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 27.392 | 1.3143 | 6.7152 | 241.7461
[22 empty] | Fuel | Material | LTR | 1.76 | 3.0436 | 0.57827 | 60.4365 | 106.3683
SEW 10 |  | Concrete anchor blocks to prevent pipe movement (Thrust Blocks) |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
SEW 10 |  | Concrete anchor blocks to prevent movement at elbows or other installation parts of various diameters, including formwork, reinforcement, concrete, etc., in accordance with the requirements of the concerned authority, specifications, and plans. |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
SEW 10 |  | Block volume from 0-1 cubic meter |  | 25.4 | 755 | 19177 | 675 | 17145 | 25.4 | 25.4 |  | 25.4 | 100% | 755 | 19177 | 675 | 17145 |  | 17145 | [7 empty] | 675 | 25.4 | 17145 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 25.4 | 25.4 |  | 25.4 | [9 empty] | Thrust Block (0.75 m³) |  | Ea | 675 |  | 675 | 25.4 | 17145 | 0 | 0 | 0 | 0 | 0
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 1.3333 | 262.5 | 19.05 | 6667.5
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 16.6667 | 150 | 1.524 | 3810
[22 empty] | Workmanship Thrust Block | SC | M³ | 350 | 1.3333 | 262.5 | 19.05 | 6667.5
SEW 10 |  | The block size is 1-2 cubic metres |  | 1.2 | 1133 | 1359.6 | 1350 | 1620 | 1.2 | 1.2 |  | 1.2 | 100% | 1133 | 1359.6 | 1350 | 1620 |  | 1620 | [7 empty] | 1350 | 1.2 | 1620 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 1.2 | 1.2 |  | 1.2 | [9 empty] | Thrust Block (1.5 m³) |  | Ea | 1350 |  | 1350 | 1.2 | 1620 | 0 | 0 | 0 | 0 | 0
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.66667 | 525 | 1.8 | 630
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 8.3333 | 300 | 0.144 | 360
[22 empty] | Workmanship Thrust Block | SC | M³ | 350 | 0.66667 | 525 | 1.8 | 630
SEW 10 |  | Block volume of 6 cubic metres |  | 6.8 | 4532 | 30817.6 | 5400 | 36720 | 6.8 | 6.8 |  | 6.8 | 100% | 4532 | 30817.6 | 5400 | 36720 |  | 36720 | [7 empty] | 5400 | 6.8 | 36720 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 6.8 | 6.8 |  | 6.8 | [9 empty] | Thrust Block (6.0 m³) |  | Ea | 5400 |  | 5400 | 6.8 | 36720 | 0 | 0 | 0 | 0 | 0
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.16667 | 2100 | 40.8 | 14280
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 2.0833 | 1200 | 3.264 | 8160
[22 empty] | Workmanship Thrust Block | SC | M³ | 350 | 0.16667 | 2100 | 40.8 | 14280
SEW 10 |  | PS1 sewage pumping station 428 l/s |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | Sewage pumps, including the motor control center (MCC), control panel, flow meters, pressure transducers, level control switches, simple walls, GRP pipes and other connecting pipes, testing, delivery, installation parts, and the necessary mechanical and electrical work in accordance with the standards of the concerned authority, specifications and plans (the pumping station building and the motor control center building are measured separately) | sum | 0.29787 | 3433660 | 1022780.9259 | 2820451.1194 | 840125 | 0.29787 | 0.29787 |  | 0.29787 | 100% | 3433660 | 1022780.9259 | 2820451.1194 | 840125 |  | 840125 | [7 empty] | 2820451.1194 | 0.29787 | 840125 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 0.29787 | 0.29787 |  | 0.29787 | [9 empty] | PS1 sewage pumping station |  | LS | 2820451.1194 |  | 2820451.1194 | 0.29787 | 840125 | 0 | 0 | 0 | 0 | 0
[22 empty] | Sewage pumping station 428 l/s | SC | LS | 2820451.1194 | 1 | 2820451.1194 | 0.29787 | 840125
SEW 10 |  | Variable-speed sewage pumps: 2 working and 1 spare (in a well). Each pump in Well A has a flow of 86 liters per second. A pump in Well B has a flow of 325 liters per second and a vertical pressure of 25 m. It includes a motor control center. | sum | 0.23 | 5158373 | 1186425.79 | 3601579.3478 | 828363.25 | 0.23 | 0.23 |  | 0.23 | 100% | 5158373 | 1186425.79 | 3601579.3478 | 828363.25 |  | 828363.25 | [7 empty] | 3601579.3478 | 0.23 | 828363.25 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 0.23 | 0.23 |  | 0.23 | [9 empty] | Variable-speed sewage pumps system |  | LS | 3601579.3478 |  | 3601579.3478 | 0.23 | 828363.25 | 0 | 0 | 0 | 0 | 0
[22 empty] | 2 pumps discarge 86 l/s & 325 l/s head 25 m | SC | LS | 3601579.3478 | 1 | 3601579.3478 | 0.23 | 828363.25
SEW 10 |  | Odor control system | sum | 1 | 226585 | 226585 | 145500 | 145500 | 1 | 1 |  | 1 | 100% | 226585 | 226585 | 145500 | 145500 |  | 145500 | [7 empty] | 145500 | 1 | 145500 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 1 | 1 |  | 1 | [9 empty] | Odour control system |  | LS | 145500 |  | 145500 | 1 | 145500 | 0 | 0 | 0 | 0 | 0
[22 empty] | Odor Control Unit & Connection | SC | LS | 145500 | 1 | 145500 | 1 | 145500
SEW 10 |  | In-line Booster Station | nr | 1 | 236027 | 236027 | 164793.75 | 164793.75 | 1 | 1 |  | 1 | 100% | 236027 | 236027 | 164793.75 | 164793.75 |  | 164793.75 | [7 empty] | 164793.75 | 1 | 164793.75 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 1 | 1 |  | 1 | [9 empty] | In-line Booster Station |  | LS | 164793.75 |  | 164793.75 | 1 | 164793.75 | 0 | 0 | 0 | 0 | 0
[22 empty] | In-line Booster Station | SC | LS | 164793.75 | 1 | 164793.75 | 1 | 164793.75
SEW 10 |  | Valves and fittings |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
SEW 10 |  | Supply, installation and testing of valves, including mounting flanges, connections, nuts, bolts, piping work inside the room and external piping (unless measured in another item) and all other accessories in accordance with the specifications, drawings and standards of the concerned authority. |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
SEW 10 |  | Valves, fittings and flow meters in different sizes |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | The mesh is 35mm raked bar SS 316 | sum | 0.28 | 31470 | 8811.6 | 21972.5 | 6152.3 | 0.28 | 0.28 |  | 0.28 | 100% | 31470 | 8811.6 | 21972.5 | 6152.3 |  | 6152.3 | [7 empty] | 21972.5 | 0.28 | 6152.3 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 0.28 | 0.28 |  | 0.28 | [9 empty] | The mesh is 35mm raked bar SS 316 |  | LS | 21972.5 |  | 21972.5 | 0.28 | 6152.3 | 0 | 0 | 0 | 0 | 0
[22 empty] | Grid mesh 35mm raked bar SS 316 | SC | LS | 21972.5 | 1 | 21972.5 | 0.28 | 6152.3
SEW 10 |  | 100 kVA generator standby generator |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
SEW 10 |  | 100 kVA generator standby generator with an umbrella tank in accordance with what is stated in the specifications, plans and the authority’s approval. | sum | 0.69 | 1778749 | 1227336.81 | 345270 | 238236.3 | 0.69 | 0.69 |  | 0.69 | 100% | 1778749 | 1227336.81 | 345270 | 238236.3 |  | 238236.3 | [7 empty] | 345270 | 0.69 | 238236.3 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 0.69 | 0.69 |  | 0.69 | [9 empty] | 100 KVA generator with umbrella tank |  | LS | 345270 |  | 345270 | 0.69 | 238236.3 | 0 | 0 | 0 | 0 | 0
[22 empty] | 100 KVA generator with umbrella tank | SC | LS | 345270 | 1 | 345270 | 0.69 | 238236.3
SEW 10 |  | (Continued) PS1 Wastewater Pumping Station |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
SEW 10 |  | Pump well and valve chambers |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
SEW 10 |  | Cast-in-place concrete valve chamber and the structural structure of the well, including excavation, backfilling, waste disposal, dewatering (if needed), pouring, concrete works, supports, formwork, masonry work, waterproofing, GRP cover, columns, rust-resistant covers, guide bars, GRP supports, strainers, distribution boxes, tests, delivery, etc., in accordance with the requirements of the concerned authority, plans and specifications. |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
SEW 10 |  | The structural structure of the well, which consists of two wells with internal dimensions of 12 m each, at a depth of approximately 11 m. | sum | 0.14 | 868577 | 121600.78 | 662420.3793 | 92738.8531 | 0.14 | 0.14 |  | 0.14 | 100% | 868577 | 121600.78 | 662420.3793 | 92738.8531 |  | 92738.8531 | [7 empty] | 662420.3793 | 0.14 | 92738.8531 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 0.14 | 0.14 |  | 0.14 | [9 empty] | 2 wells internal dimensions 12m, depth 11m |  | LS | 662420.3793 |  | 662420.3793 | 0.14 | 92738.8531 | 0 | 0 | 0 | 0 | 0
[22 empty] | 2 wells internal dimensions 12m, depth 11m | SC | LS | 662420.3793 | 1 | 662420.3793 | 0.14 | 92738.8531
SEW 10 |  | Concrete wall, 1000 mm thick, 5 m long and 5 m high, for construction inside a well. | sum | 1 | 67661 | 67661 | 30875 | 30875 | 1 | 1 |  | 1 | 100% | 67661 | 67661 | 30875 | 30875 |  | 30875 | [7 empty] | 30875 | 1 | 30875 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 1 | 1 |  | 1 | [9 empty] | Concrete Wall |  | LS | 30875 |  | 30875 | 1 | 30875 | 0 | 0 | 0 | 0 | 0
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.04 | 8750 | 25 | 8750
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 0.26667 | 9375 | 3.75 | 9375
[22 empty] | Workmanship RC concrete | SC | M³ | 450 | 0.04 | 11250 | 25 | 11250
[22 empty] | Supply and apply construction joints | SC | LS | 1500 | 1 | 1500 | 1 | 1500
SEW 10 |  | Grid chamber 35mm raked bar SS 316 | sum | 0.14 | 31470 | 4405.8 | 21972.5 | 3076.15 | 0.14 | 0.14 |  | 0.14 | 100% | 31470 | 4405.8 | 21972.5 | 3076.15 |  | 3076.15 | [7 empty] | 21972.5 | 0.14 | 3076.15 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 0.14 | 0.14 |  | 0.14 | [9 empty] | Grid mesh 35mm raked bar SS 316 |  | LS | 21972.5 |  | 21972.5 | 0.14 | 3076.15 | 0 | 0 | 0 | 0 | 0
[22 empty] | Grid mesh 35mm raked bar SS 316 | SC | LS | 21972.5 | 1 | 21972.5 | 0.14 | 3076.15
SEW 10 |  | Valve chamber | sum | 0.14 | 399671 | 55953.94 | 214682.1916 | 30055.5068 | 0.14 | 0.14 |  | 0.14 | 100% | 399671 | 55953.94 | 214682.1916 | 30055.5068 |  | 30055.5068 | [7 empty] | 214682.1916 | 0.14 | 30055.5068 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 0.14 | 0.14 |  | 0.14 | [9 empty] | Valve chamber remaining work |  | LS | 214682.1916 |  | 214682.1916 | 0.14 | 30055.5068 | 0 | 0 | 0 | 0 | 0
[22 empty] | Valve chamber | SC | LS | 214682.1916 | 1 | 214682.1916 | 0.14 | 30055.5068
SEW 10 |  | Flow meter room | sum | 0.14 | 236656 | 33131.84 | 104088.4115 | 14572.3776 | 0.14 | 0.14 |  | 0.14 | 100% | 236656 | 33131.84 | 104088.4115 | 14572.3776 |  | 14572.3776 | [7 empty] | 104088.4115 | 0.14 | 14572.3776 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 0.14 | 0.14 |  | 0.14 | [9 empty] | Flow meter room remaining work |  | LS | 104088.4115 |  | 104088.4115 | 0.14 | 14572.3776 | 0 | 0 | 0 | 0 | 0
[22 empty] | Flow meter room | SC | LS | 104088.4115 | 1 | 104088.4115 | 0.14 | 14572.3776
SEW 10 |  | Engine Control Center Building |  |  |  | 0 | 0
SEW 10 |  | The MCC engine control center building includes a generator, a fuel storage area, and sanitary facilities. It includes earthworks, foundations, concrete works, reinforcement, supports, formwork, brickwork, waterproofing, all finishing works, stairs, barriers, supports, ventilation openings, wires, circuits, 35W lighting, simple accessories for energy, the telephone system, control equipment, outlets, wires, fire alarms, air conditioners, ventilation equipment, distribution boxes, etc., complete in accordance with the requirements of the concerned authority, specifications and plans. |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
SEW 10 |  | Engine Control Center Building | sum | 0.075 | 84970 | 6372.75 | 77660.2699 | 5824.5202 | 0.075 | 0.075 |  | 0.075 | 100% | 84970 | 6372.75 | 77660.2699 | 5824.5202 |  | 5824.5202 | [7 empty] | 77660.2699 | 0.075 | 5824.5202 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 0.075 | 0.075 |  | 0.075 | [9 empty] | Engine Control Center Building remaining work |  | LS | 77660.2699 |  | 77660.2699 | 0.075 | 5824.5202 | 0 | 0 | 0 | 0 | 0
[22 empty] | Engine Control Center Building | SC | LS | 77660.2699 | 1 | 77660.2699 | 0.075 | 5824.5202
SEW 10 |  | The base for the odor control system |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | Concrete base below odor control system | sum | 1 | 13595 | 13595 | 9540 | 9540 | 1 | 1 |  | 1 | 100% | 13595 | 13595 | 9540 | 9540 |  | 9540 | [7 empty] | 9540 | 1 | 9540 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 1 | 1 |  | 1 | [9 empty] | Concrete base below odor control system |  | LS | 9540 |  | 9540 | 1 | 9540 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 0.27778 | 900 | 3.6 | 900
[22 empty] | Workmanship plain concrete | SC | M³ | 150 | 0.27778 | 540 | 3.6 | 540
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.11111 | 3150 | 9 | 3150
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 1.3889 | 1800 | 0.72 | 1800
[22 empty] | Workmanship Thrust Block | SC | M³ | 350 | 0.11111 | 3150 | 9 | 3150
SEW 10 |  | Perimeter walls |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
SEW 10 |  | Perimeter walls, including earthworks, foundations, bricks, construction works, and complete finishes in accordance with the plans, specifications, and requirements of the concerned authority. |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
SEW 10 |  | Perimeter walls | m | 136.0005 | 2266 | 308177.133 | 906.3355 | 123262.0852 | 136.0005 | 136.0005 |  | 136.0005 | 100% | 2266 | 308177.133 | 906.3355 | 123262.0852 |  | 123262.0852 | [7 empty] | 906.3355 | 136.0005 | 123262.0852 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 136.0005 | 136.0005 |  | 136.0005 | [9 empty] | Excavate & Disposal (D=1.50, W=1.00, B=1.00) |  | M | 6.3355 |  | 6.3355 | 136.0005 | 861.6352 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 53.3333 | 1.05 | 2.55 | 142.8005
[22 empty] | Fuel | Material | LTR | 1.76 | 3.8095 | 0.462 | 35.7001 | 62.8322
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 13.6 | 3.5294 | 10 | 480.0018
[22 empty] | Fuel | Material | LTR | 1.76 | 1.36 | 1.2941 | 100.0004 | 176.0006
[9 empty] | 136.0005 | 136.0005 |  | 136.0005 | [9 empty] | Perimeter walls foundations |  | M | 540 |  | 540 | 136.0005 | 73440.27 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 5 | 50 | 27.2001 | 6800.025
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 2.5 | 140 | 54.4002 | 19040.07
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 25 | 100 | 5.44 | 13600.05
[22 empty] | Workmanship plain concrete | SC | M³ | 150 | 5 | 30 | 27.2001 | 4080.015
[22 empty] | Workmanship RC concrete | SC | M³ | 450 | 2.5 | 180 | 54.4002 | 24480.09
[22 empty] | 2 Layers Bituminous Application | SC | M² | 10 | 0.25 | 40 | 544.002 | 5440.02
[9 empty] | 136.0005 | 136.0005 |  | 136.0005 | [9 empty] | Brick walls with posts (2.5m) |  | M | 360 |  | 360 | 136.0005 | 48960.18 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply concrete bricks 40*20*20 | Material | M | 150 | 1 | 150 | 136.0005 | 20400.075
[22 empty] | Masonry mortar | Material | M | 90 | 1 | 90 | 136.0005 | 12240.045
[22 empty] | Apply masonary works | SC | M | 120 | 1 | 120 | 136.0005 | 16320.06
SEW 10 |  | Main entry gates with two swing doors or a sliding door | nr | 1 | 22658 | 22658 | 18500 | 18500 | 1 | 1 |  | 1 | 100% | 22658 | 22658 | 18500 | 18500 |  | 18500 | [7 empty] | 18500 | 1 | 18500 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 1 | 1 |  | 1 | [9 empty] | Main entry gates |  | LS | 18500 |  | 18500 | 1 | 18500 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply & apply sliding door | SC | LS | 18500 | 1 | 18500 | 1 | 18500
SEW 10 |  | Single door personal entry gate | nr | 1 | 8182 | 8182 | 4750 | 4750 | 1 | 1 |  | 1 | 100% | 8182 | 8182 | 4750 | 4750 |  | 4750 | [7 empty] | 4750 | 1 | 4750 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 1 | 1 |  | 1 | [9 empty] | Single door |  | LS | 4750 |  | 4750 | 1 | 4750 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply & apply single door | SC | LS | 4750 | 1 | 4750 | 1 | 4750
SEW 10 |  | (Continued) PS1 Wastewater Pumping Station |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
SEW 10 |  | Lighting |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
SEW 10 |  | Lighting works, including poles and foundation works for poles, switches, control devices, cables and cable tubes, grounding, accessories and installation parts, are complete in accordance with the plans, specifications and requirements of the concerned authority. |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
SEW 10 |  | Flood Lights with single stand, 250 watts | sum | 1 | 314702 | 314702 | 219500 | 219500 | 1 | 1 |  | 1 | 100% | 314702 | 314702 | 219500 | 219500 |  | 219500 | [7 empty] | 219500 | 1 | 219500 | 219500 | 219500 | 219500 | 219500 | 878000 |  | 5 | Original Pay item
[9 empty] | 1 | 1 |  | 1 | [9 empty] | Lighting Poles |  | LS | 219500 |  | 219500 | 1 | 219500 | 0 | 0 | 0 | 0 | 0
[22 empty] | 8 nos Flood Lights with single stand, 250 watts | SC | LS | 219500 | 1 | 219500 | 1 | 219500
SEW 10 |  | Ducts ferry works |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
SEW 10 |  | Supply and installation of uPVC culverts in trenches, including tension ropes, warning tapes, excavation and backfilling with sandy or granular materials, compaction, waste disposal work, returning the thing to its original state, testing, and all requirements of the concerned authority, specifications and plans. |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
SEW 10 |  | One exit path with a depth not exceeding 1.5 metres | m | 28 | 104 | 2912 | 56.1307 | 1571.6598 | 28 | 28 |  | 28 | 100% | 104 | 2912 | 56.1307 | 1571.6598 |  | 1571.6598 | [7 empty] | 56.1307 | 28 | 1571.6598 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 28 | 28 |  | 28 | [9 empty] | Excavate & Disposal ( W= 1.5 M * d= 1.5 ) |  | M | 10.5257 |  | 10.5257 | 28 | 294.7194 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 44.4444 | 1.26 | 0.63 | 35.28
[22 empty] | Fuel | Material | LTR | 1.76 | 3.1746 | 0.5544 | 8.82 | 15.5232
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 9.0667 | 5.2941 | 3.0882 | 148.2353
[22 empty] | Fuel | Material | LTR | 1.76 | 0.90667 | 1.9412 | 30.8824 | 54.3529
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 44.4444 | 1.08 | 0.63 | 30.24
[22 empty] | Fuel | Material | LTR | 1.76 | 4.4444 | 0.396 | 6.3 | 11.088
[9 empty] | 28 | 28 |  | 28 | [9 empty] | Duct bank (0.25*0.25) |  | M | 31.34 |  | 31.34 | 28 | 877.52 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 16 | 15.625 | 1.75 | 437.5
[22 empty] | UPVC Pipe 50 mm | Material | M | 4 | 1 | 4 | 28 | 112
[22 empty] | UPVC Fitting 50 mm | Material | M | 2 | 1 | 2 | 28 | 56
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 16 | 9.375 | 1.75 | 262.5
[22 empty] | Skilled Labor | Manpower | HR | 17 | 50 | 0.34 | 0.56 | 9.52
[9 empty] | 28 | 28 |  | 28 | [9 empty] | Backfilling |  | M | 14.265 |  | 14.265 | 28 | 399.4204 | 0 | 0 | 0 | 0 | 0
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 45.7143 | 1.435 | 0.6125 | 40.18
[22 empty] | Fuel | Material | LTR | 1.76 | 5.0794 | 0.3465 | 5.5125 | 9.702
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 9.3257 | 5.1471 | 3.0025 | 144.1176
[22 empty] | Fuel | Material | LTR | 1.76 | 0.93257 | 1.8873 | 30.0245 | 52.8431
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 22.8571 | 1.575 | 1.225 | 44.1
[22 empty] | Fuel | Material | LTR | 1.76 | 2.5397 | 0.693 | 11.025 | 19.404
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 32 | 1.5 | 0.875 | 42
[22 empty] | Fuel | Material | LTR | 1.76 | 3.2 | 0.55 | 8.75 | 15.4
[22 empty] | Plate Compactor | Machinery | HR | 23 | 25 | 0.92 | 1.12 | 25.76
[22 empty] | Fuel | Material | LTR | 1.76 | 8.3333 | 0.2112 | 3.36 | 5.9136
SEW 10 |  | A path of two exits with a depth not exceeding 1.5 metres | m | 28 | 120 | 3360 | 78.5391 | 2199.0951 | 28 | 28 |  | 28 | 100% | 120 | 3360 | 78.5391 | 2199.0951 |  | 2199.0951 | [7 empty] | 78.5391 | 28 | 2199.0951 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 28 | 28 |  | 28 | [9 empty] | Excavate & Disposal ( W= 1.6 M * d= 1.5 ) |  | M | 11.2274 |  | 11.2274 | 28 | 314.3674 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 41.6667 | 1.344 | 0.672 | 37.632
[22 empty] | Fuel | Material | LTR | 1.76 | 2.9762 | 0.59136 | 9.408 | 16.5581
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 8.5 | 5.6471 | 3.2941 | 158.1176
[22 empty] | Fuel | Material | LTR | 1.76 | 0.85 | 2.0706 | 32.9412 | 57.9765
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 41.6667 | 1.152 | 0.672 | 32.256
[22 empty] | Fuel | Material | LTR | 1.76 | 4.1667 | 0.4224 | 6.72 | 11.8272
[9 empty] | 28 | 28 |  | 28 | [9 empty] | Duct bank (0.40*0.25) |  | M | 52.34 |  | 52.34 | 28 | 1465.52 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 10 | 25 | 2.8 | 700
[22 empty] | UPVC Pipe 50 mm | Material | M | 4 | 0.5 | 8 | 56 | 224
[22 empty] | UPVC Fitting 50 mm | Material | M | 2 | 0.5 | 4 | 56 | 112
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 10 | 15 | 2.8 | 420
[22 empty] | Skilled Labor | Manpower | HR | 17 | 50 | 0.34 | 0.56 | 9.52
[9 empty] | 28 | 28 |  | 28 | [9 empty] | Backfilling |  | M | 14.9717 |  | 14.9717 | 28 | 419.2077 | 0 | 0 | 0 | 0 | 0
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 43.4783 | 1.5088 | 0.644 | 42.2464
[22 empty] | Fuel | Material | LTR | 1.76 | 4.8309 | 0.36432 | 5.796 | 10.201
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 8.8696 | 5.4118 | 3.1569 | 151.5294
[22 empty] | Fuel | Material | LTR | 1.76 | 0.88696 | 1.9843 | 31.5686 | 55.5608
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 21.7391 | 1.656 | 1.288 | 46.368
[22 empty] | Fuel | Material | LTR | 1.76 | 2.4155 | 0.72864 | 11.592 | 20.4019
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 30 | 1.6 | 0.93333 | 44.8
[22 empty] | Fuel | Material | LTR | 1.76 | 3 | 0.58667 | 9.3333 | 16.4267
[22 empty] | Plate Compactor | Machinery | HR | 23 | 25 | 0.92 | 1.12 | 25.76
[22 empty] | Fuel | Material | LTR | 1.76 | 8.3333 | 0.2112 | 3.36 | 5.9136
SEW 10 |  | A path of 8 exits with a depth not exceeding 1.5 metres | m | 20 | 380 | 7600 | 187.2255 | 3744.5097 | 20 | 20 |  | 20 | 100% | 380 | 7600 | 187.2255 | 3744.5097 |  | 3744.5097 | [7 empty] | 187.2255 | 20 | 3744.5097 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 20 | 20 |  | 20 | [9 empty] | Excavate & Disposal ( W= 1.7 M * d= 1.5 ) |  | M | 11.9291 |  | 11.9291 | 20 | 238.5824 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 39.2157 | 1.428 | 0.51 | 28.56
[22 empty] | Fuel | Material | LTR | 1.76 | 2.8011 | 0.62832 | 7.14 | 12.5664
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 8 | 6 | 2.5 | 120
[22 empty] | Fuel | Material | LTR | 1.76 | 0.8 | 2.2 | 25 | 44
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 39.2157 | 1.224 | 0.51 | 24.48
[22 empty] | Fuel | Material | LTR | 1.76 | 3.9216 | 0.4488 | 5.1 | 8.976
[9 empty] | 20 | 20 |  | 20 | [9 empty] | Duct bank |  | M | 160.34 |  | 160.34 | 20 | 3206.8 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 3.5714 | 70 | 5.6 | 1400
[22 empty] | UPVC Pipe 50 mm | Material | M | 4 | 0.125 | 32 | 160 | 640
[22 empty] | UPVC Fitting 50 mm | Material | M | 2 | 0.125 | 16 | 160 | 320
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 3.5714 | 42 | 5.6 | 840
[22 empty] | Skilled Labor | Manpower | HR | 17 | 50 | 0.34 | 0.4 | 6.8
[9 empty] | 20 | 20 |  | 20 | [9 empty] | Backfilling |  | M | 14.9564 |  | 14.9564 | 20 | 299.1273 | 0 | 0 | 0 | 0 | 0
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 44.0529 | 1.4891 | 0.454 | 29.7824
[22 empty] | Fuel | Material | LTR | 1.76 | 4.8948 | 0.35957 | 4.086 | 7.1914
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 8.9868 | 5.3412 | 2.2255 | 106.8235
[22 empty] | Fuel | Material | LTR | 1.76 | 0.89868 | 1.9584 | 22.2549 | 39.1686
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 22.0264 | 1.6344 | 0.908 | 32.688
[22 empty] | Fuel | Material | LTR | 1.76 | 2.4474 | 0.71914 | 8.172 | 14.3827
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 28.2353 | 1.7 | 0.70833 | 34
[22 empty] | Fuel | Material | LTR | 1.76 | 2.8235 | 0.62333 | 7.0833 | 12.4667
[22 empty] | Plate Compactor | Machinery | HR | 23 | 25 | 0.92 | 0.8 | 18.4
[22 empty] | Fuel | Material | LTR | 1.76 | 8.3333 | 0.2112 | 2.4 | 4.224
SEW 10 |  | Earthing work |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | Pit for grounding work | nr | 1 | 1385 | 1385 | 1137.4 | 1137.4 | 1 | 1 |  | 1 | 100% | 1385 | 1385 | 1137.4 | 1137.4 |  | 1137.4 | [7 empty] | 1137.4 | 1 | 1137.4 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 1 | 1 |  | 1 | [9 empty] | Pit for grounding work |  | Ea | 1137.4 |  | 1137.4 | 1 | 1137.4 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pit for grounding work | SC | LS | 1137.4 | 1 | 1137.4 | 1 | 1137.4
SEW 10 |  | Cable pulling pit measuring 600x600 mm | nr | 3 | 1762 | 5286 | 1447 | 4341 | 3 | 3 |  | 3 | 100% | 1762 | 5286 | 1447 | 4341 |  | 4341 | [7 empty] | 1447 | 3 | 4341 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 3 | 3 |  | 3 | [9 empty] | Cable pulling pit measuring 600x600 mm |  | Ea | 1447 |  | 1447 | 3 | 4341 | 0 | 0 | 0 | 0 | 0
[22 empty] | Cable pulling pit measuring 600x600 mm | SC | LS | 1447 | 1 | 1447 | 3 | 4341
SEW 10 |  | Cosmetic coordination works |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | Concrete interlock pavement tiles, including subsoil and sand layer with compaction according to specifications and plans. |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | Pavement tiles for the perimeter of buildings | m² | 675 | 86 | 58050 | 54.3824 | 36708.12 | 675 | 675 |  | 675 | 100% | 86 | 58050 | 54.3824 | 36708.12 |  | 36708.12 | [7 empty] | 54.3824 | 675 | 36708.12 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 675 | 675 |  | 675 | [9 empty] | Base layer preparation |  | M² | 4.3824 |  | 4.3824 | 675 | 2958.12 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backhoe loader | Machinery | HR | 44 | 20 | 2.2 | 33.75 | 1485
[22 empty] | Fuel | Material | LTR | 1.76 | 2 | 0.88 | 337.5 | 594
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 100 | 0.48 | 6.75 | 324
[22 empty] | Fuel | Material | LTR | 1.76 | 10 | 0.176 | 67.5 | 118.8
[22 empty] | Roller Compactor 10 Ton | Machinery | HR | 40 | 100 | 0.4 | 6.75 | 270
[22 empty] | Fuel | Material | LTR | 1.76 | 7.1429 | 0.2464 | 94.5 | 166.32
[9 empty] | 675 | 675 |  | 675 | [9 empty] | Fix Interlock tiles (10 cm sand bedding) |  | M² | 50 |  | 50 | 675 | 33750 | 0 | 0 | 0 | 0 | 0
[22 empty] | Polyethylene sheet | Machinery | M² | 2 | 1 | 2 | 675 | 1350
[22 empty] | Sand Supply | Material | M³ | 30 | 10 | 3 | 67.5 | 2025
[22 empty] | Interlock tiles Supply | Material | M² | 25 | 1 | 25 | 675 | 16875
[22 empty] | Interlock tiles Installation | SC | M² | 20 | 1 | 20 | 675 | 13500
SEW 10 |  | Paving tiles for entrance ways | m² | 45 | 86 | 3870 | 54.3824 | 2447.208 | 45 | 45 |  | 45 | 100% | 86 | 3870 | 54.3824 | 2447.208 |  | 2447.208 | [7 empty] | 54.3824 | 45 | 2447.208 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 45 | 45 |  | 45 | [9 empty] | Base layer preparation |  | M² | 4.3824 |  | 4.3824 | 45 | 197.208 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backhoe loader | Machinery | HR | 44 | 20 | 2.2 | 2.25 | 99
[22 empty] | Fuel | Material | LTR | 1.76 | 2 | 0.88 | 22.5 | 39.6
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 100 | 0.48 | 0.45 | 21.6
[22 empty] | Fuel | Material | LTR | 1.76 | 10 | 0.176 | 4.5 | 7.92
[22 empty] | Roller Compactor 10 Ton | Machinery | HR | 40 | 100 | 0.4 | 0.45 | 18
[22 empty] | Fuel | Material | LTR | 1.76 | 7.1429 | 0.2464 | 6.3 | 11.088
[9 empty] | 45 | 45 |  | 45 | [9 empty] | Fix Interlock tiles (10 cm sand bedding) |  | M² | 50 |  | 50 | 45 | 2250 | 0 | 0 | 0 | 0 | 0
[22 empty] | Polyethylene sheet | Material | M² | 2 | 1 | 2 | 45 | 90
[22 empty] | Sand Supply | Material | M³ | 30 | 10 | 3 | 4.5 | 135
[22 empty] | Interlock tiles Supply | Material | M² | 25 | 1 | 25 | 45 | 1125
[22 empty] | Interlock tiles Installation | SC | M² | 20 | 1 | 20 | 45 | 900
SEW 10 |  | Water drainage network at the pumping station |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
SEW 10 |  | The internal water drainage network within the scope of the pumping station building, which includes drainage pipes, installation parts, chambers, and connections with the main drainage network in accordance with the requirements of the concerned authority, specifications and plans. |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
SEW 10 |  | Surface channel for water drainage within the pumping station building complex | m | 45 | 189 | 8505 | 182.4833 | 8211.75 | 45 | 45 |  | 45 | 100% | 189 | 8505 | 182.4833 | 8211.75 |  | 8211.75 | [7 empty] | 182.4833 | 45 | 8211.75 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 45 | 45 |  | 45 | [9 empty] | Excavation of drainage Channel |  | M | 3.3 |  | 3.3 | 45 | 148.5 | 0 | 0 | 0 | 0 | 0
[22 empty] | Concrete Cutter | Machinery | HR | 40 | 20 | 2 | 2.25 | 90
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 10 | 1.3 | 4.5 | 58.5
[9 empty] | 45 | 45 |  | 45 | [9 empty] | Surface preperation |  | M | 8.3333 |  | 8.3333 | 45 | 375 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 30 | 8.3333 | 1.5 | 375
[9 empty] | 45 | 45 |  | 45 | [9 empty] | Channel Installation with Connections |  | M | 170.85 |  | 170.85 | 45 | 7688.25 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Floor Surface Channel with grating | Material | M | 150 | 1 | 150 | 45 | 6750
[22 empty] | Supply Pipes Connections | Material | M | 20 | 1 | 20 | 45 | 900
[22 empty] | Skilled labor | Manpower | HR | 17 | 20 | 0.85 | 2.25 | 38.25
SEW 10 |  | Additional excavation and backfilling works, drilling into rock | m³ | 1 | 113 | 113 | 30.658 | 30.658 | 1 | 1 |  | 1 | 100% | 113 | 113 | 30.658 | 30.658 |  | 30.658 | [7 empty] | 30.658 | 1 | 30.658 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 1 | 1 |  | 1 | [9 empty] | Rock Excavation & Disposal |  | M³ | 22.3553 |  | 22.3553 | 1 | 22.3553 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Hydraulic Hammer 50T | Machinery | HR | 150.4 | 15 | 10.0267 | 0.066667 | 10.0267
[22 empty] | Fuel | Material | LTR | 1.76 | 0.46875 | 3.7547 | 2.1333 | 3.7547
[22 empty] | Excavator with Bucket 50T | Machinery | HR | 131.2 | 50 | 2.624 | 0.02 | 2.624
[22 empty] | Fuel | Material | LTR | 1.76 | 1.5625 | 1.1264 | 0.64 | 1.1264
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 13.6 | 3.5294 | 0.073529 | 3.5294
[22 empty] | Fuel | Material | LTR | 1.76 | 1.36 | 1.2941 | 0.73529 | 1.2941
[9 empty] | 1 | 1 |  | 1 | [9 empty] | Backfilling & Compaction |  | M³ | 8.3027 |  | 8.3027 | 1 | 8.3027 | 0 | 0 | 0 | 0 | 0
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 100 | 0.656 | 0.01 | 0.656
[22 empty] | Fuel | Material | LTR | 1.76 | 11.1111 | 0.1584 | 0.09 | 0.1584
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 13.6 | 3.5294 | 0.073529 | 3.5294
[22 empty] | Fuel | Material | LTR | 1.76 | 1.36 | 1.2941 | 0.73529 | 1.2941
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 50 | 0.72 | 0.02 | 0.72
[22 empty] | Fuel | Material | LTR | 1.76 | 5.5556 | 0.3168 | 0.18 | 0.3168
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 80 | 0.6 | 0.0125 | 0.6
[22 empty] | Fuel | Material | LTR | 1.76 | 8 | 0.22 | 0.125 | 0.22
[22 empty] | Roller Compactor 10 Ton | Machinery | HR | 40 | 80 | 0.5 | 0.0125 | 0.5
[22 empty] | Fuel | Material | LTR | 1.76 | 5.7143 | 0.308 | 0.175 | 0.308
SEW 10 |  | PS 2 sewage pumping station - 55 liters per sec |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | comments: |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | 1- Establishing the entire pump station, including internal connecting pipes, fittings, valves, etc |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | 2- The description of the items for the pumps is in accordance with the flow requirements of the first stage only, while the rest of the pumps shown in the drawings will be constructed according to the flow requirements of the final stage in parallel with the construction of the other stages. |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | Sewage pumps and motor control center |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
SEW 10 |  | Sewage pumps, including the motor control center (MCC), control panel, flow meters, pressure transducers, level control switches, simple walls, GRP pipes and other connecting pipes, testing, delivery, installation parts, and the necessary mechanical and electrical work in accordance with the standards of the concerned authority, specifications and plans (the pumping station building and the motor control center building are measured separately) |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
SEW 10 |  | Variable-speed sewage and wastewater pumps: 1 working and 1 spare (in a well). Each pump has a flow of 55 liters per second and a vertical pressure of 35 m and includes a motor control center. | sum | 0.3 | 1652185 | 495655.5 | 1153556.25 | 346066.875 | 0.3 | 0.3 |  | 0.3 | 100% | 1652185 | 495655.5 | 1153556.25 | 346066.875 |  | 346066.875 | [7 empty] | 1153556.25 | 0.3 | 346066.875 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 0.3 | 0.3 |  | 0.3 | [9 empty] | Variable speed sewage pumps system |  | LS | 1153556.25 |  | 1153556.25 | 0.3 | 346066.875 | 0 | 0 | 0 | 0 | 0
[22 empty] | 2 pumps discarge 55 l/s head 35 m | SC | LS | 1153556.25 | 1 | 1153556.25 | 0.3 | 346066.875
SEW 10 |  | Odor control system | sum | 1 | 226585 | 226585 | 145500 | 145500 | 1 | 1 |  | 1 | 100% | 226585 | 226585 | 145500 | 145500 |  | 145500 | [7 empty] | 145500 | 1 | 145500 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 1 | 1 |  | 1 | [9 empty] | Odour control system |  | LS | 145500 |  | 145500 | 1 | 145500 | 0 | 0 | 0 | 0 | 0
[22 empty] | Odor Control Unit & Connection | SC | LS | 145500 | 1 | 145500 | 1 | 145500
SEW 10 |  | In-line Booster Station | nr | 1 | 2596290 | 2596290 | 1812500 | 1812500 | 1 | 1 |  | 1 | 100% | 2596290 | 2596290 | 1812500 | 1812500 |  | 1812500 | [7 empty] | 1812500 | 1 | 1812500 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 1 | 1 |  | 1 | [9 empty] | In-line Booster Station |  | Ea | 1812500 |  | 1812500 | 1 | 1812500 | 0 | 0 | 0 | 0 | 0
[22 empty] | In-line Booster Station V | SC | LS | 1812500 | 1 | 1812500 | 1 | 1812500
SEW 10 |  | 100 kVA generator standby generator |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
SEW 10 |  | With an umbrella tank in accordance with what is stated in the specifications, plans and the authority’s approval. |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | Valves and fittings |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
SEW 10 |  | Supply, installation and testing of valves, including mounting flanges, connections, nuts, bolts, piping work inside the room and external piping (unless measured in another item) and all other accessories in accordance with the specifications, drawings and standards of the concerned authority. |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
SEW 10 |  | Valves, fittings and flow meters in different sizes | sum | 0.23 | 94411 | 21714.53 | 65500 | 15065 | 0.23 | 0.23 |  | 0.23 | 100% | 94411 | 21714.53 | 65500 | 15065 |  | 15065 | [7 empty] | 65500 | 0.23 | 15065 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 0.23 | 0.23 |  | 0.23 | [9 empty] | Valves, fittings and flow meters different sizes |  | LS | 65500 |  | 65500 | 0.23 | 15065 | 0 | 0 | 0 | 0 | 0
[22 empty] | Valves, fittings and flow meters different sizes | SC | LS | 65500 | 1 | 65500 | 0.23 | 15065
SEW 10 |  | The mesh is 35mm raked bar SS 316 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | Pump well and valve chambers |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
SEW 10 |  | Cast-in-place concrete valve chamber and the structural structure of the well, including excavation, backfilling, waste disposal, dewatering (if needed), pouring, concrete works, supports, formwork, masonry work, waterproofing, GRP cover, columns, rust-resistant covers, guide bars, GRP supports, strainers, distribution boxes, tests, delivery, etc., in accordance with the requirements of the concerned authority, plans and specifications. |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
SEW 10 |  | The structural structure of the well, which consists of two wells with internal dimensions of 3 m each, at a depth of approximately 9 m. | sum | 0.63 | 212423 | 133826.49 | 157093.517 | 98968.9157 | 0.63 | 0.63 |  | 0.63 | 100% | 212423 | 133826.49 | 157093.517 | 98968.9157 |  | 98968.9157 | [7 empty] | 157093.517 | 0.63 | 98968.9157 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 0.63 | 0.63 |  | 0.63 | [9 empty] | Valves, fittings and flow meters different sizes |  | LS | 157093.517 |  | 157093.517 | 0.63 | 98968.9157 | 0 | 0 | 0 | 0 | 0
[22 empty] | 2 wells internal dimensions 3m, depth 9m | SC | LS | 157093.517 | 1 | 157093.517 | 0.63 | 98968.9157
SEW 10 |  | Grid chamber 35mm raked bar SS 316 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | Valve chamber | sum | 0.4 | 399671 | 159868.4 | 214682.1916 | 85872.8766 | 0.4 | 0.4 |  | 0.4 | 100% | 399671 | 159868.4 | 214682.1916 | 85872.8766 |  | 85872.8766 | [7 empty] | 214682.1916 | 0.4 | 85872.8766 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 0.4 | 0.4 |  | 0.4 | [9 empty] | Valve chamber remaining work |  | LS | 214682.1916 |  | 214682.1916 | 0.4 | 85872.8766 | 0 | 0 | 0 | 0 | 0
[22 empty] | Valve chamber | SC | LS | 214682.1916 | 1 | 214682.1916 | 0.4 | 85872.8766
SEW 10 |  | Flow meter room | sum | 0.63 | 236656 | 149093.28 | 104088.4115 | 65575.6992 | 0.63 | 0.63 |  | 0.63 | 100% | 236656 | 149093.28 | 104088.4115 | 65575.6992 |  | 65575.6992 | [7 empty] | 104088.4115 | 0.63 | 65575.6992 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 0.63 | 0.63 |  | 0.63 | [9 empty] | Flow meter room remaining work |  | LS | 104088.4115 |  | 104088.4115 | 0.63 | 65575.6992 | 0 | 0 | 0 | 0 | 0
[22 empty] | Flow meter room | SC | LS | 104088.4115 | 1 | 104088.4115 | 0.63 | 65575.6992
SEW 10 |  | PS2 sewage pumping station |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
SEW 10 |  | Engine Control Center Building |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
SEW 10 |  | The engine control center building includes a generator, fuel storage space, and sanitary facilities. It includes earthworks, foundations, concrete works, reinforcement, supports, formwork, brickwork, waterproofing, all finishing works, stairs, barriers, supports, ventilation openings, wires, circuits, lighting, and simple accessories related to energy, the telephone system, control equipment, outlets, wires, fire alarms, air conditioners, ventilation equipment, distribution boxes, etc., complete in accordance with the requirements of the concerned authority, specifications, and plans. |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
SEW 10 |  | Engine Control Center Building | sum | 0.075 | 918930 | 68919.75 | 754820 | 56611.5 | 0.075 | 0.075 |  | 0.075 | 100% | 918930 | 68919.75 | 754820 | 56611.5 |  | 56611.5 | [7 empty] | 754820 | 0.075 | 56611.5 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 0.075 | 0.075 |  | 0.075 | [9 empty] | Engine Control Center Building remaining work |  | LS | 754820 |  | 754820 | 0.075 | 56611.5 | 0 | 0 | 0 | 0 | 0
[22 empty] | Engine Control Center Building | SC | LS | 754820 | 1 | 754820 | 0.075 | 56611.5
SEW 10 |  | The base for the odor control system |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
SEW 10 |  | Concrete base below odor control system | sum | 1 | 13595 | 13595 | 9540 | 9540 | 1 | 1 |  | 1 | 100% | 13595 | 13595 | 9540 | 9540 |  | 9540 | [7 empty] | 9540 | 1 | 9540 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 1 | 1 |  | 1 | [9 empty] | Concrete base below odor control system |  | LS | 9540 |  | 9540 | 1 | 9540 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 0.27778 | 900 | 3.6 | 900
[22 empty] | Workmanship plain concrete | SC | M³ | 150 | 0.27778 | 540 | 3.6 | 540
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.11111 | 3150 | 9 | 3150
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 1.3889 | 1800 | 0.72 | 1800
[22 empty] | Workmanship Thrust Block | SC | M³ | 350 | 0.11111 | 3150 | 9 | 3150
SEW 10 |  | Perimeter walls |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
SEW 10 |  | Perimeter walls, including earthworks, foundations, bricks, construction works, and complete finishes in accordance with the plans, specifications, and requirements of the concerned authority. |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
SEW 10 |  | Perimeter walls | m | 120 | 2266 | 271920 | 906.3355 | 108760.2635 | 120 | 120 |  | 120 | 100% | 2266 | 271920 | 906.3355 | 108760.2635 |  | 108760.2635 | [7 empty] | 906.3355 | 120 | 108760.2635 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 120 | 120 |  | 120 | [9 empty] | Excavate & Disposal (D=1.50, W=1.00, B=1.00) |  | M | 6.3355 |  | 6.3355 | 120 | 760.2635 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 53.3333 | 1.05 | 2.25 | 126
[22 empty] | Fuel | Material | LTR | 1.76 | 3.8095 | 0.462 | 31.5 | 55.44
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 13.6 | 3.5294 | 8.8235 | 423.5294
[22 empty] | Fuel | Material | LTR | 1.76 | 1.36 | 1.2941 | 88.2353 | 155.2941
[9 empty] | 120 | 120 |  | 120 | [9 empty] | Perimeter walls foundations |  | M | 540 |  | 540 | 120 | 64800 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 5 | 50 | 24 | 6000
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 2.5 | 140 | 48 | 16800
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 25 | 100 | 4.8 | 12000
[22 empty] | Workmanship plain concrete | SC | M³ | 150 | 5 | 30 | 24 | 3600
[22 empty] | Workmanship RC concrete | SC | M³ | 450 | 2.5 | 180 | 48 | 21600
[22 empty] | 2 Layers Bituminous Application | SC | M² | 10 | 0.25 | 40 | 480 | 4800
[9 empty] | 120 | 120 |  | 120 | [9 empty] | Brick walls with posts (2.5m) |  | M | 360 |  | 360 | 120 | 43200 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply concrete bricks 40*20*20 | Material | M | 150 | 1 | 150 | 120 | 18000
[22 empty] | Masonry mortar | Material | M | 90 | 1 | 90 | 120 | 10800
[22 empty] | Apply masonary works | SC | M | 120 | 1 | 120 | 120 | 14400
SEW 10 |  | Main entry gates with two swing doors or a sliding door | nr | 1 | 22658 | 22658 | 18500 | 18500 | 1 | 1 |  | 1 | 100% | 22658 | 22658 | 18500 | 18500 |  | 18500 | [7 empty] | 18500 | 1 | 18500 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 1 | 1 |  | 1 | [9 empty] | Main entry gates |  | LS | 18500 |  | 18500 | 1 | 18500 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply & apply sliding door | SC | LS | 18500 | 1 | 18500 | 1 | 18500
SEW 10 |  | Single door personal entry gate | nr | 1 | 8182 | 8182 | 4750 | 4750 | 1 | 1 |  | 1 | 100% | 8182 | 8182 | 4750 | 4750 |  | 4750 | [7 empty] | 4750 | 1 | 4750 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 1 | 1 |  | 1 | [9 empty] | Single door |  | LS | 4750 |  | 4750 | 1 | 4750 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply & apply single door | SC | LS | 4750 | 1 | 4750 | 1 | 4750
SEW 10 |  | Lighting |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
SEW 10 |  | Lighting works, including poles and foundation works for poles, switches, control devices, cables and cable tubes, grounding, accessories and installation parts, are complete in accordance with the plans, specifications and requirements of the concerned authority. |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
SEW 10 |  | Flood Lights with a single stand, with a lighting intensity of 250 watts | sum | 1 | 314702 | 314702 | 219500 | 219500 | 1 | 1 |  | 1 | 100% | 314702 | 314702 | 219500 | 219500 |  | 219500 | [7 empty] | 219500 | 1 | 219500 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 1 | 1 |  | 1 | [9 empty] | Lighting Poles |  | LS | 219500 |  | 219500 | 1 | 219500 | 0 | 0 | 0 | 0 | 0
[22 empty] | 8 nos Flood Lights with single stand, 250 watts | SC | LS | 219500 | 1 | 219500 | 1 | 219500
SEW 10 |  | Ducts ferry works |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
SEW 10 |  | Supply and installation of uPVC culverts in trenches, including tension ropes, warning tapes, excavation and backfilling with sandy or granular materials, compaction, waste disposal work, returning the thing to its original state, testing, and all requirements of the concerned authority, specifications and plans. |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
SEW 10 |  | One exit path with a depth not exceeding 1.5 metres | m | 25 | 104 | 2600 | 56.1307 | 1403.2677 | 25 | 25 |  | 25 | 100% | 104 | 2600 | 56.1307 | 1403.2677 |  | 1403.2677 | [7 empty] | 56.1307 | 25 | 1403.2677 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 25 | 25 |  | 25 | [9 empty] | Excavate & Disposal ( W= 1.5 M * d= 1.5 ) |  | M | 10.5257 |  | 10.5257 | 25 | 263.1424 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 44.4444 | 1.26 | 0.5625 | 31.5
[22 empty] | Fuel | Material | LTR | 1.76 | 3.1746 | 0.5544 | 7.875 | 13.86
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 9.0667 | 5.2941 | 2.7574 | 132.3529
[22 empty] | Fuel | Material | LTR | 1.76 | 0.90667 | 1.9412 | 27.5735 | 48.5294
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 44.4444 | 1.08 | 0.5625 | 27
[22 empty] | Fuel | Material | LTR | 1.76 | 4.4444 | 0.396 | 5.625 | 9.9
[9 empty] | 25 | 25 |  | 25 | [9 empty] | Duct bank (0.25*0.25) |  | M | 31.34 |  | 31.34 | 25 | 783.5 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 16 | 15.625 | 1.5625 | 390.625
[22 empty] | UPVC Pipe 50 mm | Material | M | 4 | 1 | 4 | 25 | 100
[22 empty] | UPVC Fitting 50 mm | Material | M | 2 | 1 | 2 | 25 | 50
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 16 | 9.375 | 1.5625 | 234.375
[22 empty] | Skilled Labor | Manpower | HR | 17 | 50 | 0.34 | 0.5 | 8.5
[9 empty] | 25 | 25 |  | 25 | [9 empty] | Backfilling |  | M | 14.265 |  | 14.265 | 25 | 356.6253 | 0 | 0 | 0 | 0 | 0
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 45.7143 | 1.435 | 0.54688 | 35.875
[22 empty] | Fuel | Material | LTR | 1.76 | 5.0794 | 0.3465 | 4.9219 | 8.6625
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 9.3257 | 5.1471 | 2.6808 | 128.6765
[22 empty] | Fuel | Material | LTR | 1.76 | 0.93257 | 1.8873 | 26.8076 | 47.1814
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 22.8571 | 1.575 | 1.0938 | 39.375
[22 empty] | Fuel | Material | LTR | 1.76 | 2.5397 | 0.693 | 9.8438 | 17.325
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 32 | 1.5 | 0.78125 | 37.5
[22 empty] | Fuel | Material | LTR | 1.76 | 3.2 | 0.55 | 7.8125 | 13.75
[22 empty] | Plate Compactor | Machinery | HR | 23 | 25 | 0.92 | 1 | 23
[22 empty] | Fuel | Material | LTR | 1.76 | 8.3333 | 0.2112 | 3 | 5.28
SEW 10 |  | A path of two exits with a depth not exceeding 1.5 metres | m | 25 | 120 | 3000 | 78.5391 | 1963.4778 | 25 | 25 |  | 25 | 100% | 120 | 3000 | 78.5391 | 1963.4778 |  | 1963.4778 | [7 empty] | 78.5391 | 25 | 1963.4778 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 25 | 25 |  | 25 | [9 empty] | Excavate & Disposal ( W= 1.6 M * d= 1.5 ) |  | M | 11.2274 |  | 11.2274 | 25 | 280.6852 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 41.6667 | 1.344 | 0.6 | 33.6
[22 empty] | Fuel | Material | LTR | 1.76 | 2.9762 | 0.59136 | 8.4 | 14.784
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 8.5 | 5.6471 | 2.9412 | 141.1765
[22 empty] | Fuel | Material | LTR | 1.76 | 0.85 | 2.0706 | 29.4118 | 51.7647
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 41.6667 | 1.152 | 0.6 | 28.8
[22 empty] | Fuel | Material | LTR | 1.76 | 4.1667 | 0.4224 | 6 | 10.56
[9 empty] | 25 | 25 |  | 25 | [9 empty] | Duct bank (0.40*0.25) |  | M | 52.34 |  | 52.34 | 25 | 1308.5 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 10 | 25 | 2.5 | 625
[22 empty] | UPVC Pipe 50 mm | Material | M | 4 | 0.5 | 8 | 50 | 200
[22 empty] | UPVC Fitting 50 mm | Material | M | 2 | 0.5 | 4 | 50 | 100
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 10 | 15 | 2.5 | 375
[22 empty] | Skilled Labor | Manpower | HR | 17 | 50 | 0.34 | 0.5 | 8.5
[9 empty] | 25 | 25 |  | 25 | [9 empty] | Backfilling |  | M | 14.9717 |  | 14.9717 | 25 | 374.2926 | 0 | 0 | 0 | 0 | 0
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 43.4783 | 1.5088 | 0.575 | 37.72
[22 empty] | Fuel | Material | LTR | 1.76 | 4.8309 | 0.36432 | 5.175 | 9.108
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 8.8696 | 5.4118 | 2.8186 | 135.2941
[22 empty] | Fuel | Material | LTR | 1.76 | 0.88696 | 1.9843 | 28.1863 | 49.6078
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 21.7391 | 1.656 | 1.15 | 41.4
[22 empty] | Fuel | Material | LTR | 1.76 | 2.4155 | 0.72864 | 10.35 | 18.216
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 30 | 1.6 | 0.83333 | 40
[22 empty] | Fuel | Material | LTR | 1.76 | 3 | 0.58667 | 8.3333 | 14.6667
[22 empty] | Plate Compactor | Machinery | HR | 23 | 25 | 0.92 | 1 | 23
[22 empty] | Fuel | Material | LTR | 1.76 | 8.3333 | 0.2112 | 3 | 5.28
SEW 10 |  | A path of 8 exits with a depth not exceeding 1.5 metres | m | 20 | 380 | 7600 | 187.2255 | 3744.5097 | 20 | 20 |  | 20 | 100% | 380 | 7600 | 187.2255 | 3744.5097 |  | 3744.5097 | [7 empty] | 187.2255 | 20 | 3744.5097 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 20 | 20 |  | 20 | [9 empty] | Excavate & Disposal ( W= 1.7 M * d= 1.5 ) |  | M | 11.9291 |  | 11.9291 | 20 | 238.5824 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 39.2157 | 1.428 | 0.51 | 28.56
[22 empty] | Fuel | Material | LTR | 1.76 | 2.8011 | 0.62832 | 7.14 | 12.5664
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 8 | 6 | 2.5 | 120
[22 empty] | Fuel | Material | LTR | 1.76 | 0.8 | 2.2 | 25 | 44
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 39.2157 | 1.224 | 0.51 | 24.48
[22 empty] | Fuel | Material | LTR | 1.76 | 3.9216 | 0.4488 | 5.1 | 8.976
[9 empty] | 20 | 20 |  | 20 | [9 empty] | Duct bank |  | M | 160.34 |  | 160.34 | 20 | 3206.8 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 3.5714 | 70 | 5.6 | 1400
[22 empty] | UPVC Pipe 50 mm | Material | M | 4 | 0.125 | 32 | 160 | 640
[22 empty] | UPVC Fitting 50 mm | Material | M | 2 | 0.125 | 16 | 160 | 320
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 3.5714 | 42 | 5.6 | 840
[22 empty] | Skilled Labor | Manpower | HR | 17 | 50 | 0.34 | 0.4 | 6.8
[9 empty] | 20 | 20 |  | 20 | [9 empty] | Backfilling |  | M | 14.9564 |  | 14.9564 | 20 | 299.1273 | 0 | 0 | 0 | 0 | 0
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 44.0529 | 1.4891 | 0.454 | 29.7824
[22 empty] | Fuel | Material | LTR | 1.76 | 4.8948 | 0.35957 | 4.086 | 7.1914
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 8.9868 | 5.3412 | 2.2255 | 106.8235
[22 empty] | Fuel | Material | LTR | 1.76 | 0.89868 | 1.9584 | 22.2549 | 39.1686
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 22.0264 | 1.6344 | 0.908 | 32.688
[22 empty] | Fuel | Material | LTR | 1.76 | 2.4474 | 0.71914 | 8.172 | 14.3827
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 28.2353 | 1.7 | 0.70833 | 34
[22 empty] | Fuel | Material | LTR | 1.76 | 2.8235 | 0.62333 | 7.0833 | 12.4667
[22 empty] | Plate Compactor | Machinery | HR | 23 | 25 | 0.92 | 0.8 | 18.4
[22 empty] | Fuel | Material | LTR | 1.76 | 8.3333 | 0.2112 | 2.4 | 4.224
SEW 10 |  | Earthing work |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | Pit for grounding work | nr | 1 | 1385 | 1385 | 1137.4 | 1137.4 | 1 | 1 |  | 1 | 100% | 1385 | 1385 | 1137.4 | 1137.4 |  | 1137.4 | [7 empty] | 1137.4 | 1 | 1137.4 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 1 | 1 |  | 1 | [9 empty] | Pit for grounding work |  | Ea | 1137.4 |  | 1137.4 | 1 | 1137.4 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pit for grounding work | SC | LS | 1137.4 | 1 | 1137.4 | 1 | 1137.4
SEW 10 |  | Cable pulling pit measuring 600x600 mm | nr | 3 | 1762 | 5286 | 1447 | 4341 | 3 | 3 |  | 3 | 100% | 1762 | 5286 | 1447 | 4341 |  | 4341 | [7 empty] | 1447 | 3 | 4341 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 3 | 3 |  | 3 | [9 empty] | Cable pulling pit measuring 600x600 mm |  | Ea | 1447 |  | 1447 | 3 | 4341 | 0 | 0 | 0 | 0 | 0
[22 empty] | Cable pulling pit measuring 600x600 mm | SC | LS | 1447 | 1 | 1447 | 3 | 4341
SEW 10 |  | (Continued) PS2 Wastewater Pumping Station |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
SEW 10 |  | Cosmetic coordination works |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
SEW 10 |  | Concrete interlock pavement tiles, including subsoil and sand layer with compaction according to specifications and plans. |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
SEW 10 |  | Pavement tiles for the perimeter of buildings | m² | 495 | 86 | 42570 | 54.3824 | 26919.288 | 495 | 495 |  | 495 | 100% | 86 | 42570 | 54.3824 | 26919.288 |  | 26919.288 | [7 empty] | 54.3824 | 495 | 26919.288 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 495 | 495 |  | 495 | [9 empty] | Base layer preparation |  | M² | 4.3824 |  | 4.3824 | 495 | 2169.288 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backhoe loader | Machinery | HR | 44 | 20 | 2.2 | 24.75 | 1089
[22 empty] | Fuel | Material | LTR | 1.76 | 2 | 0.88 | 247.5 | 435.6
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 100 | 0.48 | 4.95 | 237.6
[22 empty] | Fuel | Material | LTR | 1.76 | 10 | 0.176 | 49.5 | 87.12
[22 empty] | Roller Compactor 10 Ton | Machinery | HR | 40 | 100 | 0.4 | 4.95 | 198
[22 empty] | Fuel | Material | LTR | 1.76 | 7.1429 | 0.2464 | 69.3 | 121.968
[9 empty] | 495 | 495 |  | 495 | [9 empty] | Fix Interlock tiles (10 cm sand bedding) |  | M² | 50 |  | 50 | 495 | 24750 | 0 | 0 | 0 | 0 | 0
[22 empty] | Polyethylene sheet | Machinery | M² | 2 | 1 | 2 | 495 | 990
[22 empty] | Sand Supply | Material | M³ | 30 | 10 | 3 | 49.5 | 1485
[22 empty] | Interlock tiles Supply | Material | M² | 25 | 1 | 25 | 495 | 12375
[22 empty] | Interlock tiles Installation | SC | M² | 20 | 1 | 20 | 495 | 9900
SEW 10 |  | Paving tiles for entrance ways | m² | 200 | 86 | 17200 | 54.3824 | 10876.48 | 200 | 200 |  | 200 | 100% | 86 | 17200 | 54.3824 | 10876.48 |  | 10876.48 | [7 empty] | 54.3824 | 200 | 10876.48 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 200 | 200 |  | 200 | [9 empty] | Base layer preparation |  | M² | 4.3824 |  | 4.3824 | 200 | 876.48 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backhoe loader | Machinery | HR | 44 | 20 | 2.2 | 10 | 440
[22 empty] | Fuel | Material | LTR | 1.76 | 2 | 0.88 | 100 | 176
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 100 | 0.48 | 2 | 96
[22 empty] | Fuel | Material | LTR | 1.76 | 10 | 0.176 | 20 | 35.2
[22 empty] | Roller Compactor 10 Ton | Machinery | HR | 40 | 100 | 0.4 | 2 | 80
[22 empty] | Fuel | Material | LTR | 1.76 | 7.1429 | 0.2464 | 28 | 49.28
[9 empty] | 200 | 200 |  | 200 | [9 empty] | Fix Interlock tiles (10 cm sand bedding) |  | M² | 50 |  | 50 | 200 | 10000 | 0 | 0 | 0 | 0 | 0
[22 empty] | Polyethylene sheet | Machinery | M² | 2 | 1 | 2 | 200 | 400
[22 empty] | Sand Supply | Material | M³ | 30 | 10 | 3 | 20 | 600
[22 empty] | Interlock tiles Supply | Material | M² | 25 | 1 | 25 | 200 | 5000
[22 empty] | Interlock tiles Installation | SC | M² | 20 | 1 | 20 | 200 | 4000
SEW 10 |  | Water drainage network at the pumping station |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
SEW 10 |  | The internal water drainage network within the scope of the pumping station building, which includes drainage pipes, installation parts, chambers, and connections with the main drainage network in accordance with the requirements of the concerned authority, specifications and plans. |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
SEW 10 |  | Surface channel for water drainage within the pumping station building complex | m | 45 | 189 | 8505 | 182.4833 | 8211.75 | 45 | 45 |  | 45 | 100% | 189 | 8505 | 182.4833 | 8211.75 |  | 8211.75 | [7 empty] | 182.4833 | 45 | 8211.75 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 45 | 45 |  | 45 | [9 empty] | Excavation of drainage Channel |  | M | 3.3 |  | 3.3 | 45 | 148.5 | 0 | 0 | 0 | 0 | 0
[22 empty] | Concrete Cutter | Machinery | HR | 40 | 20 | 2 | 2.25 | 90
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 10 | 1.3 | 4.5 | 58.5
[9 empty] | 45 | 45 |  | 45 | [9 empty] | Surface preperation |  | M | 8.3333 |  | 8.3333 | 45 | 375 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 30 | 8.3333 | 1.5 | 375
[9 empty] | 45 | 45 |  | 45 | [9 empty] | Channel Installation with Connections |  | M | 170.85 |  | 170.85 | 45 | 7688.25 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Floor Surface Channel with grating | Material | M | 150 | 1 | 150 | 45 | 6750
[22 empty] | Supply Pipes Connections | Material | M | 20 | 1 | 20 | 45 | 900
[22 empty] | Skilled labor | Manpower | HR | 17 | 20 | 0.85 | 2.25 | 38.25
SEW 10 |  | Additional works for sewage networks (Extra over) |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | Excavation work to various depths in the rock, including disposal of waste, warning tapes, dewatering, and washing in accordance with special procedures. | m³ | 1 | 113 | 113 | 30.658 | 30.658 | 1 | 1 |  | 1 | 100% | 113 | 113 | 30.658 | 30.658 |  | 30.658 | [7 empty] | 30.658 | 1 | 30.658 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 1 | 1 |  | 1 | [9 empty] | Rock Excavation & Disposal |  | M³ | 22.3553 |  | 22.3553 | 1 | 22.3553 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Hydraulic Hammer 50T | Machinery | HR | 150.4 | 15 | 10.0267 | 0.066667 | 10.0267
[22 empty] | Fuel | Material | LTR | 1.76 | 0.46875 | 3.7547 | 2.1333 | 3.7547
[22 empty] | Excavator with Bucket 50T | Machinery | HR | 131.2 | 50 | 2.624 | 0.02 | 2.624
[22 empty] | Fuel | Material | LTR | 1.76 | 1.5625 | 1.1264 | 0.64 | 1.1264
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 13.6 | 3.5294 | 0.073529 | 3.5294
[22 empty] | Fuel | Material | LTR | 1.76 | 1.36 | 1.2941 | 0.73529 | 1.2941
[9 empty] | 1 | 1 |  | 1 | [9 empty] | Backfilling & Compaction |  | M³ | 8.3027 |  | 8.3027 | 1 | 8.3027 | 0 | 0 | 0 | 0 | 0
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 100 | 0.656 | 0.01 | 0.656
[22 empty] | Fuel | Material | LTR | 1.76 | 11.1111 | 0.1584 | 0.09 | 0.1584
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 13.6 | 3.5294 | 0.073529 | 3.5294
[22 empty] | Fuel | Material | LTR | 1.76 | 1.36 | 1.2941 | 0.73529 | 1.2941
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 50 | 0.72 | 0.02 | 0.72
[22 empty] | Fuel | Material | LTR | 1.76 | 5.5556 | 0.3168 | 0.18 | 0.3168
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 80 | 0.6 | 0.0125 | 0.6
[22 empty] | Fuel | Material | LTR | 1.76 | 8 | 0.22 | 0.125 | 0.22
[22 empty] | Roller Compactor 10 Ton | Machinery | HR | 40 | 80 | 0.5 | 0.0125 | 0.5
[22 empty] | Fuel | Material | LTR | 1.76 | 5.7143 | 0.308 | 0.175 | 0.308
SEW 10 |  | PS3 sewage pumping station - 145 liters per sect |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | comments: |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | 1- Establishing the entire pump station, including internal connecting pipes, fittings, valves, etc |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | Sewage pumps and motor control center |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | Sewage pumps, including the motor control center (MCC), control panel, flow meters, pressure transducers, level control switches, simple walls, GRP pipes and other connecting pipes, testing, delivery, installation parts, and the necessary mechanical and electrical work in accordance with the standards of the concerned authority, specifications and plans (the pumping station building and the motor control center building are measured separately) |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | Variable-speed sewage pumps: 1 working and 1 spare (in well, total 4). Each pump in well A has a flow of 30 liters per second, and a pump in well B has a flow of 115 liters per second and a vertical pressure of 17 m. It includes a motor control center. | sum | 0.3 | 3671521 | 1101456.3 | 2563458.3333 | 769037.5 | 0.3 | 0.3 |  | 0.3 | 100% | 3671521 | 1101456.3 | 2563458.3333 | 769037.5 |  | 769037.5 | [7 empty] | 2563458.3333 | 0.3 | 769037.5 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 0.3 | 0.3 |  | 0.3 | [9 empty] | 2 pumps discarge 30 l/s & 115 l/s head 17 m |  | LS | 2563458.3333 |  | 2563458.3333 | 0.3 | 769037.5 | 0 | 0 | 0 | 0 | 0
[22 empty] | 2 pumps discarge 30 l/s & 115 l/s head 17 m | SC | LS | 2563458.3333 | 1 | 2563458.3333 | 0.3 | 769037.5
SEW 10 |  | Odor control system | sum | 1 | 226585 | 226585 | 145500 | 145500 | 1 | 1 |  | 1 | 100% | 226585 | 226585 | 145500 | 145500 |  | 145500 | [7 empty] | 145500 | 1 | 145500 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 1 | 1 |  | 1 | [9 empty] | Odour control system |  | LS | 145500 |  | 145500 | 1 | 145500 | 0 | 0 | 0 | 0 | 0
[22 empty] | Odor Control Unit & Connection | SC | LS | 145500 | 1 | 145500 | 1 | 145500
SEW 10 |  | In-line Booster Station | nr | 1 | 2596290 | 2596290 | 1812500 | 1812500 | 1 | 1 |  | 1 | 100% | 2596290 | 2596290 | 1812500 | 1812500 |  | 1812500 | [7 empty] | 1812500 | 1 | 1812500 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 1 | 1 |  | 1 | [9 empty] | In-line Booster Station |  | Ea | 1812500 |  | 1812500 | 1 | 1812500 | 0 | 0 | 0 | 0 | 0
[22 empty] | In-line Booster Station V | SC | LS | 1812500 | 1 | 1812500 | 1 | 1812500
SEW 10 |  | 100 kVA generator standby generator With an umbrella tank in accordance with what is stated in the specifications, plans and the authority’s approval. |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | Valves and fittings |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
SEW 10 |  | Supply, installation and testing of valves, including mounting flanges, connections, nuts, bolts, piping work inside the room and external piping (unless measured in another item) and all other accessories in accordance with the specifications, drawings and standards of the concerned authority. |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
SEW 10 |  | Valves, fittings and flow meters in different sizes | sum | 0.23 | 94411 | 21714.53 | 65500 | 15065 | 0.23 | 0.23 |  | 0.23 | 100% | 94411 | 21714.53 | 65500 | 15065 |  | 15065 | [7 empty] | 65500 | 0.23 | 15065 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 0.23 | 0.23 |  | 0.23 | [9 empty] | Valves, fittings and flow meters different sizes |  | LS | 65500 |  | 65500 | 0.23 | 15065 | 0 | 0 | 0 | 0 | 0
[22 empty] | Valves, fittings and flow meters different sizes | SC | LS | 65500 | 1 | 65500 | 0.23 | 15065
SEW 10 |  | The mesh is 35mm raked bar SS 316 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | Pump well and valve chambers |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
SEW 10 |  | Cast-in-place concrete valve chamber and the structural structure of the well, including excavation, backfilling, waste disposal, dewatering (if needed), pouring, concrete works, supports, formwork, masonry work, waterproofing, GRP cover, columns, rust-resistant covers, guide bars, GRP supports, strainers, distribution boxes, tests, delivery, etc., in accordance with the requirements of the concerned authority, plans and specifications. |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
SEW 10 |  | The structural structure of the well, which consists of two wells with internal dimensions of 5x5 m each, at a depth of approximately 11 m. | sum | 0.48 | 868577 | 416916.96 | 438304.67 | 210386.2416 | 0.48 | 0.48 |  | 0.48 | 100% | 868577 | 416916.96 | 438304.67 | 210386.2416 |  | 210386.2416 | [7 empty] | 438304.67 | 0.48 | 210386.2416 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 0.48 | 0.48 |  | 0.48 | [9 empty] | 2 wells internal dimensions 5m, depth 11m |  | LS | 438304.67 |  | 438304.67 | 0.48 | 210386.2416 | 0 | 0 | 0 | 0 | 0
[22 empty] | 2 wells internal dimensions 5m, depth 11m | SC | LS | 438304.67 | 1 | 438304.67 | 0.48 | 210386.2416
SEW 10 |  | Concrete wall, 1000 mm thick, 5 m long and 5 m high, for construction inside a well. | sum | 0.48 | 67661 | 32477.28 | 30875 | 14820 | 0.48 | 0.48 |  | 0.48 | 100% | 67661 | 32477.28 | 30875 | 14820 |  | 14820 | [7 empty] | 30875 | 0.48 | 14820 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 0.48 | 0.48 |  | 0.48 | [9 empty] | Concrete Wall |  | LS | 30875 |  | 30875 | 0.48 | 14820 | 0 | 0 | 0 | 0 | 0
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.04 | 8750 | 12 | 4200
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 0.26667 | 9375 | 1.8 | 4500
[22 empty] | Workmanship RC concrete | SC | M³ | 450 | 0.04 | 11250 | 12 | 5400
[22 empty] | Supply and apply construction joints | SC | LS | 1500 | 1 | 1500 | 0.48 | 720
SEW 10 |  | (Continued) PS3 Wastewater Pumping Station |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
SEW 10 |  | Grid chamber 35mm raked bar SS 316 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | Valve chamber | sum | 0.48 | 399671 | 191842.08 | 214682.1916 | 103047.452 | 0.48 | 0.48 |  | 0.48 | 100% | 399671 | 191842.08 | 214682.1916 | 103047.452 |  | 103047.452 | [7 empty] | 214682.1916 | 0.48 | 103047.452 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 0.48 | 0.48 |  | 0.48 | [9 empty] | Valve chamber remaining work |  | LS | 214682.1916 |  | 214682.1916 | 0.48 | 103047.452 | 0 | 0 | 0 | 0 | 0
[22 empty] | Valve chamber | SC | LS | 214682.1916 | 1 | 214682.1916 | 0.48 | 103047.452
SEW 10 |  | Flow meter room | sum | 0.38 | 236656 | 89929.28 | 104088.4115 | 39553.5964 | 0.38 | 0.38 |  | 0.38 | 100% | 236656 | 89929.28 | 104088.4115 | 39553.5964 |  | 39553.5964 | [7 empty] | 104088.4115 | 0.38 | 39553.5964 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 0.38 | 0.38 |  | 0.38 | [9 empty] | Flow meter room remaining work |  | LS | 104088.4115 |  | 104088.4115 | 0.38 | 39553.5964 | 0 | 0 | 0 | 0 | 0
[22 empty] | Flow meter room | SC | LS | 104088.4115 | 1 | 104088.4115 | 0.38 | 39553.5964
SEW 10 |  | Engine Control Center Building |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
SEW 10 |  | The engine control center building includes a generator, fuel storage space, and sanitary facilities. It includes earthworks, foundations, concrete works, reinforcement, supports, formwork, brickwork, waterproofing, all finishing works, stairs, barriers, supports, ventilation openings, wires, circuits, lighting, and simple accessories related to energy, the telephone system, control equipment, outlets, wires, fire alarms, air conditioners, ventilation equipment, distribution boxes, etc., complete in accordance with the requirements of the concerned authority, specifications, and plans. |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
SEW 10 |  | Engine Control Center Building | sum | 0.075 | 84970 | 6372.75 | 77660.2699 | 5824.5202 | 0.075 | 0.075 |  | 0.075 | 100% | 84970 | 6372.75 | 77660.2699 | 5824.5202 |  | 5824.5202 | [7 empty] | 77660.2699 | 0.075 | 5824.5202 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 0.075 | 0.075 |  | 0.075 | [9 empty] | Engine Control Center Building remaining work |  | LS | 77660.2699 |  | 77660.2699 | 0.075 | 5824.5202 | 0 | 0 | 0 | 0 | 0
[22 empty] | Engine Control Center Building | SC | LS | 77660.2699 | 1 | 77660.2699 | 0.075 | 5824.5202
SEW 10 |  | The base for the odor control system |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
SEW 10 |  | Concrete base below odor control system | sum | 1 | 13595 | 13595 | 9540 | 9540 | 1 | 1 |  | 1 | 100% | 13595 | 13595 | 9540 | 9540 |  | 9540 | [7 empty] | 9540 | 1 | 9540 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 1 | 1 |  | 1 | [9 empty] | Concrete base below odor control system |  | LS | 9540 |  | 9540 | 1 | 9540 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 0.27778 | 900 | 3.6 | 900
[22 empty] | Workmanship plain concrete | SC | M³ | 150 | 0.27778 | 540 | 3.6 | 540
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.11111 | 3150 | 9 | 3150
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 1.3889 | 1800 | 0.72 | 1800
[22 empty] | Workmanship Thrust Block | SC | M³ | 350 | 0.11111 | 3150 | 9 | 3150
SEW 10 |  | Perimeter walls |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
SEW 10 |  | Perimeter walls, including earthworks, foundations, bricks, construction works, and complete finishes in accordance with the plans, specifications, and requirements of the concerned authority. |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
SEW 10 |  | Perimeter walls | m | 120 | 2266 | 271920 | 906.3355 | 108760.2635 | 120 | 120 |  | 120 | 100% | 2266 | 271920 | 906.3355 | 108760.2635 |  | 108760.2635 | [7 empty] | 906.3355 | 120 | 108760.2635 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 120 | 120 |  | 120 | [9 empty] | Excavate & Disposal (D=1.50, W=1.00, B=1.00) |  | M | 6.3355 |  | 6.3355 | 120 | 760.2635 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 53.3333 | 1.05 | 2.25 | 126
[22 empty] | Fuel | Material | LTR | 1.76 | 3.8095 | 0.462 | 31.5 | 55.44
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 13.6 | 3.5294 | 8.8235 | 423.5294
[22 empty] | Fuel | Material | LTR | 1.76 | 1.36 | 1.2941 | 88.2353 | 155.2941
[9 empty] | 120 | 120 |  | 120 | [9 empty] | Perimeter walls foundations |  | M | 540 |  | 540 | 120 | 64800 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 5 | 50 | 24 | 6000
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 2.5 | 140 | 48 | 16800
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 25 | 100 | 4.8 | 12000
[22 empty] | Workmanship plain concrete | SC | M³ | 150 | 5 | 30 | 24 | 3600
[22 empty] | Workmanship RC concrete | SC | M³ | 450 | 2.5 | 180 | 48 | 21600
[22 empty] | 2 Layers Bituminous Application | SC | M² | 10 | 0.25 | 40 | 480 | 4800
[9 empty] | 120 | 120 |  | 120 | [9 empty] | Brick walls with posts (2.5m) |  | M | 360 |  | 360 | 120 | 43200 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply concrete bricks 40*20*20 | Material | M | 150 | 1 | 150 | 120 | 18000
[22 empty] | Masonry mortar | Material | M | 90 | 1 | 90 | 120 | 10800
[22 empty] | Apply masonary works | SC | M | 120 | 1 | 120 | 120 | 14400
SEW 10 |  | Main entry gates with two swing doors or a sliding door | nr | 1 | 22658 | 22658 | 18500 | 18500 | 1 | 1 |  | 1 | 100% | 22658 | 22658 | 18500 | 18500 |  | 18500 | [7 empty] | 18500 | 1 | 18500 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 1 | 1 |  | 1 | [9 empty] | Main entry gates |  | LS | 18500 |  | 18500 | 1 | 18500 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply & apply sliding door | SC | LS | 18500 | 1 | 18500 | 1 | 18500
SEW 10 |  | Single door personal entry gate | nr | 1 | 8182 | 8182 | 4750 | 4750 | 1 | 1 |  | 1 | 100% | 8182 | 8182 | 4750 | 4750 |  | 4750 | [7 empty] | 4750 | 1 | 4750 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 1 | 1 |  | 1 | [9 empty] | Single door |  | LS | 4750 |  | 4750 | 1 | 4750 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply & apply single door | SC | LS | 4750 | 1 | 4750 | 1 | 4750
SEW 10 |  | Lighting |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
SEW 10 |  | Lighting works, including poles and foundation works for poles, switches, control devices, cables and cable tubes, grounding, accessories and installation parts, are complete in accordance with the plans, specifications and requirements of the concerned authority. |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
SEW 10 |  | Flood Lights with single stand, 250 watts | sum | 1 | 314702 | 314702 | 219500 | 219500 | 1 | 1 |  | 1 | 100% | 314702 | 314702 | 219500 | 219500 |  | 219500 | [7 empty] | 219500 | 1 | 219500 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 1 | 1 |  | 1 | [9 empty] | Lighting Poles |  | LS | 219500 |  | 219500 | 1 | 219500 | 0 | 0 | 0 | 0 | 0
[22 empty] | 8 nos Flood Lights with single stand, 250 watts | SC | LS | 219500 | 1 | 219500 | 1 | 219500
SEW 10 |  | (Continued) PS3 Wastewater Pumping Station |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
SEW 10 |  | Ducts ferry works |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
SEW 10 |  | Supply and installation of uPVC culverts in trenches, including tension ropes, warning tapes, excavation and backfilling with sandy or granular materials, compaction, waste disposal work, returning the thing to its original state, testing, and all requirements of the concerned authority, specifications and plans. |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
SEW 10 |  | One exit path with a depth not exceeding 1.5 metres | m | 25 | 104 | 2600 | 56.1307 | 1403.2677 | 25 | 25 |  | 25 | 100% | 104 | 2600 | 56.1307 | 1403.2677 |  | 1403.2677 | [7 empty] | 56.1307 | 25 | 1403.2677 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 25 | 25 |  | 25 | [9 empty] | Excavate & Disposal ( W= 1.5 M * d= 1.5 ) |  | M | 10.5257 |  | 10.5257 | 25 | 263.1424 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 44.4444 | 1.26 | 0.5625 | 31.5
[22 empty] | Fuel | Material | LTR | 1.76 | 3.1746 | 0.5544 | 7.875 | 13.86
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 9.0667 | 5.2941 | 2.7574 | 132.3529
[22 empty] | Fuel | Material | LTR | 1.76 | 0.90667 | 1.9412 | 27.5735 | 48.5294
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 44.4444 | 1.08 | 0.5625 | 27
[22 empty] | Fuel | Material | LTR | 1.76 | 4.4444 | 0.396 | 5.625 | 9.9
[9 empty] | 25 | 25 |  | 25 | [9 empty] | Duct bank (0.25*0.25) |  | M | 31.34 |  | 31.34 | 25 | 783.5 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 16 | 15.625 | 1.5625 | 390.625
[22 empty] | UPVC Pipe 50 mm | Material | M | 4 | 1 | 4 | 25 | 100
[22 empty] | UPVC Fitting 50 mm | Material | M | 2 | 1 | 2 | 25 | 50
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 16 | 9.375 | 1.5625 | 234.375
[22 empty] | Skilled Labor | Manpower | HR | 17 | 50 | 0.34 | 0.5 | 8.5
[9 empty] | 25 | 25 |  | 25 | [9 empty] | Backfilling |  | M | 14.265 |  | 14.265 | 25 | 356.6253 | 0 | 0 | 0 | 0 | 0
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 45.7143 | 1.435 | 0.54688 | 35.875
[22 empty] | Fuel | Material | LTR | 1.76 | 5.0794 | 0.3465 | 4.9219 | 8.6625
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 9.3257 | 5.1471 | 2.6808 | 128.6765
[22 empty] | Fuel | Material | LTR | 1.76 | 0.93257 | 1.8873 | 26.8076 | 47.1814
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 22.8571 | 1.575 | 1.0938 | 39.375
[22 empty] | Fuel | Material | LTR | 1.76 | 2.5397 | 0.693 | 9.8438 | 17.325
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 32 | 1.5 | 0.78125 | 37.5
[22 empty] | Fuel | Material | LTR | 1.76 | 3.2 | 0.55 | 7.8125 | 13.75
[22 empty] | Plate Compactor | Machinery | HR | 23 | 25 | 0.92 | 1 | 23
[22 empty] | Fuel | Material | LTR | 1.76 | 8.3333 | 0.2112 | 3 | 5.28
SEW 10 |  | A path of two exits with a depth not exceeding 1.5 metres | m | 25 | 120 | 3000 | 78.5391 | 1963.4778 | 25 | 25 |  | 25 | 100% | 120 | 3000 | 78.5391 | 1963.4778 |  | 1963.4778 | [7 empty] | 78.5391 | 25 | 1963.4778 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 25 | 25 |  | 25 | [9 empty] | Excavate & Disposal ( W= 1.6 M * d= 1.5 ) |  | M | 11.2274 |  | 11.2274 | 25 | 280.6852 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 41.6667 | 1.344 | 0.6 | 33.6
[22 empty] | Fuel | Material | LTR | 1.76 | 2.9762 | 0.59136 | 8.4 | 14.784
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 8.5 | 5.6471 | 2.9412 | 141.1765
[22 empty] | Fuel | Material | LTR | 1.76 | 0.85 | 2.0706 | 29.4118 | 51.7647
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 41.6667 | 1.152 | 0.6 | 28.8
[22 empty] | Fuel | Material | LTR | 1.76 | 4.1667 | 0.4224 | 6 | 10.56
[9 empty] | 25 | 25 |  | 25 | [9 empty] | Duct bank (0.40*0.25) |  | M | 52.34 |  | 52.34 | 25 | 1308.5 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 10 | 25 | 2.5 | 625
[22 empty] | UPVC Pipe 50 mm | Material | M | 4 | 0.5 | 8 | 50 | 200
[22 empty] | UPVC Fitting 50 mm | Material | M | 2 | 0.5 | 4 | 50 | 100
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 10 | 15 | 2.5 | 375
[22 empty] | Skilled Labor | Manpower | HR | 17 | 50 | 0.34 | 0.5 | 8.5
[9 empty] | 25 | 25 |  | 25 | [9 empty] | Backfilling |  | M | 14.9717 |  | 14.9717 | 25 | 374.2926 | 0 | 0 | 0 | 0 | 0
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 43.4783 | 1.5088 | 0.575 | 37.72
[22 empty] | Fuel | Material | LTR | 1.76 | 4.8309 | 0.36432 | 5.175 | 9.108
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 8.8696 | 5.4118 | 2.8186 | 135.2941
[22 empty] | Fuel | Material | LTR | 1.76 | 0.88696 | 1.9843 | 28.1863 | 49.6078
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 21.7391 | 1.656 | 1.15 | 41.4
[22 empty] | Fuel | Material | LTR | 1.76 | 2.4155 | 0.72864 | 10.35 | 18.216
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 30 | 1.6 | 0.83333 | 40
[22 empty] | Fuel | Material | LTR | 1.76 | 3 | 0.58667 | 8.3333 | 14.6667
[22 empty] | Plate Compactor | Machinery | HR | 23 | 25 | 0.92 | 1 | 23
[22 empty] | Fuel | Material | LTR | 1.76 | 8.3333 | 0.2112 | 3 | 5.28
SEW 10 |  | A path of 8 exits with a depth not exceeding 1.5 metres | m | 20 | 380 | 7600 | 187.2255 | 3744.5097 | 20 | 20 |  | 20 | 100% | 380 | 7600 | 187.2255 | 3744.5097 |  | 3744.5097 | [7 empty] | 187.2255 | 20 | 3744.5097 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 20 | 20 |  | 20 | [9 empty] | Excavate & Disposal ( W= 1.7 M * d= 1.5 ) |  | M | 11.9291 |  | 11.9291 | 20 | 238.5824 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 39.2157 | 1.428 | 0.51 | 28.56
[22 empty] | Fuel | Material | LTR | 1.76 | 2.8011 | 0.62832 | 7.14 | 12.5664
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 8 | 6 | 2.5 | 120
[22 empty] | Fuel | Material | LTR | 1.76 | 0.8 | 2.2 | 25 | 44
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 39.2157 | 1.224 | 0.51 | 24.48
[22 empty] | Fuel | Material | LTR | 1.76 | 3.9216 | 0.4488 | 5.1 | 8.976
[9 empty] | 20 | 20 |  | 20 | [9 empty] | Duct bank |  | M | 160.34 |  | 160.34 | 20 | 3206.8 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 3.5714 | 70 | 5.6 | 1400
[22 empty] | UPVC Pipe 50 mm | Material | M | 4 | 0.125 | 32 | 160 | 640
[22 empty] | UPVC Fitting 50 mm | Material | M | 2 | 0.125 | 16 | 160 | 320
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 3.5714 | 42 | 5.6 | 840
[22 empty] | Skilled Labor | Manpower | HR | 17 | 50 | 0.34 | 0.4 | 6.8
[9 empty] | 20 | 20 |  | 20 | [9 empty] | Backfilling |  | M | 14.9564 |  | 14.9564 | 20 | 299.1273 | 0 | 0 | 0 | 0 | 0
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 44.0529 | 1.4891 | 0.454 | 29.7824
[22 empty] | Fuel | Material | LTR | 1.76 | 4.8948 | 0.35957 | 4.086 | 7.1914
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 8.9868 | 5.3412 | 2.2255 | 106.8235
[22 empty] | Fuel | Material | LTR | 1.76 | 0.89868 | 1.9584 | 22.2549 | 39.1686
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 22.0264 | 1.6344 | 0.908 | 32.688
[22 empty] | Fuel | Material | LTR | 1.76 | 2.4474 | 0.71914 | 8.172 | 14.3827
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 28.2353 | 1.7 | 0.70833 | 34
[22 empty] | Fuel | Material | LTR | 1.76 | 2.8235 | 0.62333 | 7.0833 | 12.4667
[22 empty] | Plate Compactor | Machinery | HR | 23 | 25 | 0.92 | 0.8 | 18.4
[22 empty] | Fuel | Material | LTR | 1.76 | 8.3333 | 0.2112 | 2.4 | 4.224
SEW 10 |  | Earthing work |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
SEW 10 |  | Pit for grounding work | nr | 1 | 1385 | 1385 | 1137.4 | 1137.4 | 1 | 1 |  | 1 | 100% | 1385 | 1385 | 1137.4 | 1137.4 |  | 1137.4 | [7 empty] | 1137.4 | 1 | 1137.4 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 1 | 1 |  | 1 | [9 empty] | Pit for grounding work |  | Ea | 1137.4 |  | 1137.4 | 1 | 1137.4 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pit for grounding work | SC | LS | 1137.4 | 1 | 1137.4 | 1 | 1137.4
SEW 10 |  | Cable pulling pit measuring 600x600 mm | nr | 3 | 1762 | 5286 | 1447 | 4341 | 3 | 3 |  | 3 | 100% | 1762 | 5286 | 1447 | 4341 |  | 4341 | [7 empty] | 1447 | 3 | 4341 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 3 | 3 |  | 3 | [9 empty] | Cable pulling pit measuring 600x600 mm |  | Ea | 1447 |  | 1447 | 3 | 4341 | 0 | 0 | 0 | 0 | 0
[22 empty] | Cable pulling pit measuring 600x600 mm | SC | LS | 1447 | 1 | 1447 | 3 | 4341
SEW 10 |  | Cosmetic coordination works |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
SEW 10 |  | Concrete interlock pavement tiles, including subsoil and sand layer with compaction according to specifications and plans. |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
SEW 10 |  | Pavement tiles for the perimeter of buildings | m² | 495 | 86 | 42570 | 54.3824 | 26919.288 | 495 | 495 |  | 495 | 100% | 86 | 42570 | 54.3824 | 26919.288 |  | 26919.288 | [7 empty] | 54.3824 | 495 | 26919.288 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 495 | 495 |  | 495 | [9 empty] | Base layer preparation |  | M² | 4.3824 |  | 4.3824 | 495 | 2169.288 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backhoe loader | Machinery | HR | 44 | 20 | 2.2 | 24.75 | 1089
[22 empty] | Fuel | Material | LTR | 1.76 | 2 | 0.88 | 247.5 | 435.6
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 100 | 0.48 | 4.95 | 237.6
[22 empty] | Fuel | Material | LTR | 1.76 | 10 | 0.176 | 49.5 | 87.12
[22 empty] | Roller Compactor 10 Ton | Machinery | HR | 40 | 100 | 0.4 | 4.95 | 198
[22 empty] | Fuel | Material | LTR | 1.76 | 7.1429 | 0.2464 | 69.3 | 121.968
[9 empty] | 495 | 495 |  | 495 | [9 empty] | Fix Interlock tiles (10 cm sand bedding) |  | M² | 50 |  | 50 | 495 | 24750 | 0 | 0 | 0 | 0 | 0
[22 empty] | Polyethylene sheet | Machinery | M² | 2 | 1 | 2 | 495 | 990
[22 empty] | Sand Supply | Material | M³ | 30 | 10 | 3 | 49.5 | 1485
[22 empty] | Interlock tiles Supply | Material | M² | 25 | 1 | 25 | 495 | 12375
[22 empty] | Interlock tiles Installation | SC | M² | 20 | 1 | 20 | 495 | 9900
SEW 10 |  | Paving tiles for entrance ways | m² | 120 | 86 | 10320 | 54.3824 | 6525.888 | 120 | 120 |  | 120 | 100% | 86 | 10320 | 54.3824 | 6525.888 |  | 6525.888 | [7 empty] | 54.3824 | 120 | 6525.888 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 120 | 120 |  | 120 | [9 empty] | Base layer preparation |  | M² | 4.3824 |  | 4.3824 | 120 | 525.888 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backhoe loader | Machinery | HR | 44 | 20 | 2.2 | 6 | 264
[22 empty] | Fuel | Material | LTR | 1.76 | 2 | 0.88 | 60 | 105.6
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 100 | 0.48 | 1.2 | 57.6
[22 empty] | Fuel | Material | LTR | 1.76 | 10 | 0.176 | 12 | 21.12
[22 empty] | Roller Compactor 10 Ton | Machinery | HR | 40 | 100 | 0.4 | 1.2 | 48
[22 empty] | Fuel | Material | LTR | 1.76 | 7.1429 | 0.2464 | 16.8 | 29.568
[9 empty] | 120 | 120 |  | 120 | [9 empty] | Fix Interlock tiles (10 cm sand bedding) |  | M² | 50 |  | 50 | 120 | 6000 | 0 | 0 | 0 | 0 | 0
[22 empty] | Polyethylene sheet | Machinery | M² | 2 | 1 | 2 | 120 | 240
[22 empty] | Sand Supply | Material | M³ | 30 | 10 | 3 | 12 | 360
[22 empty] | Interlock tiles Supply | Material | M² | 25 | 1 | 25 | 120 | 3000
[22 empty] | Interlock tiles Installation | SC | M² | 20 | 1 | 20 | 120 | 2400
SEW 10 |  | Water drainage network at the pumping station |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
SEW 10 |  | The internal water drainage network within the scope of the pumping station building, which includes drainage pipes, installation parts, chambers, and connections with the main drainage network in accordance with the requirements of the concerned authority, specifications and plans. |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
SEW 10 |  | Surface channel for water drainage within the pumping station building complex | m | 45 | 298 | 13410 | 182.4833 | 8211.75 | 45 | 45 |  | 45 | 100% | 298 | 13410 | 182.4833 | 8211.75 |  | 8211.75 | [7 empty] | 182.4833 | 45 | 8211.75 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 45 | 45 |  | 45 | [9 empty] | Excavation of drainage Channel |  | M | 3.3 |  | 3.3 | 45 | 148.5 | 0 | 0 | 0 | 0 | 0
[22 empty] | Concrete Cutter | Machinery | HR | 40 | 20 | 2 | 2.25 | 90
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 10 | 1.3 | 4.5 | 58.5
[9 empty] | 45 | 45 |  | 45 | [9 empty] | Surface preperation |  | M | 8.3333 |  | 8.3333 | 45 | 375 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 30 | 8.3333 | 1.5 | 375
[9 empty] | 45 | 45 |  | 45 | [9 empty] | Channel Installation with Connections |  | M | 170.85 |  | 170.85 | 45 | 7688.25 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Floor Surface Channel with grating | Material | M | 150 | 1 | 150 | 45 | 6750
[22 empty] | Supply Pipes Connections | Material | M | 20 | 1 | 20 | 45 | 900
[22 empty] | Skilled labor | Manpower | HR | 17 | 20 | 0.85 | 2.25 | 38.25
SEW 10 |  | Additional works for sewage networks (Extra over) |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
SEW 10 |  | Excavation work for various depths or limestone, including disposal of waste, warning tapes, dewatering and washing according to special procedures. | m³ | 1 | 32 | 32 | 19.742 | 19.742 | 1 | 1 |  | 1 | 100% | 32 | 32 | 19.742 | 19.742 |  | 19.742 | [7 empty] | 19.742 | 1 | 19.742 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 1 | 1 |  | 1 | [9 empty] | Excavation & Disposal |  | M³ | 13.0472 |  | 13.0472 | 1 | 13.0472 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Hydraulic Hammer 50T | Machinery | HR | 150.4 | 25 | 6.016 | 0.04 | 6.016
[22 empty] | Fuel | Material | LTR | 1.76 | 0.78125 | 2.2528 | 1.28 | 2.2528
[22 empty] | Excavator with Bucket 50T | Machinery | HR | 131.2 | 120 | 1.0933 | 0.0083333 | 1.0933
[22 empty] | Fuel | Material | LTR | 1.76 | 3.75 | 0.46933 | 0.26667 | 0.46933
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 20.4 | 2.3529 | 0.04902 | 2.3529
[22 empty] | Fuel | Material | LTR | 1.76 | 2.04 | 0.86275 | 0.4902 | 0.86275
[9 empty] | 1 | 1 |  | 1 | [9 empty] | Backfilling & Compaction |  | M³ | 6.6949 |  | 6.6949 | 1 | 6.6949 | 0 | 0 | 0 | 0 | 0
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 100 | 0.656 | 0.01 | 0.656
[22 empty] | Fuel | Material | LTR | 1.76 | 11.1111 | 0.1584 | 0.09 | 0.1584
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 20.4 | 2.3529 | 0.04902 | 2.3529
[22 empty] | Fuel | Material | LTR | 1.76 | 2.04 | 0.86275 | 0.4902 | 0.86275
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 50 | 0.72 | 0.02 | 0.72
[22 empty] | Fuel | Material | LTR | 1.76 | 5.5556 | 0.3168 | 0.18 | 0.3168
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 80 | 0.6 | 0.0125 | 0.6
[22 empty] | Fuel | Material | LTR | 1.76 | 8 | 0.22 | 0.125 | 0.22
[22 empty] | Roller Compactor 10 Ton | Machinery | HR | 40 | 80 | 0.5 | 0.0125 | 0.5
[22 empty] | Fuel | Material | LTR | 1.76 | 5.7143 | 0.308 | 0.175 | 0.308
SEW 10 |  | PS4 sewage pumping station 100 liters per sec |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
SEW 10 |  | comments: |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | 1- Establishing the entire pump station, including internal connecting pipes, fittings, valves, etc | nr | 0.38898 | 188821 | 73447.4264 | 131835 | 51281.0623 | 0.38898 | 0.38898 |  | 0.38898 | 100% | 188821 | 73447.4264 | 131835 | 51281.0623 |  | 51281.0623 | [7 empty] | 131835 | 0.38898 | 51281.0623 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 0.38898 | 0.38898 |  | 0.38898 | [9 empty] | Pump Station |  | LS | 131835 |  | 131835 | 0.38898 | 51281.0623 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pump station inc connect pipes, fittings, valves | SC | LS | 131835 | 1 | 131835 | 0.38898 | 51281.0623
SEW 10 |  | Sewage pumps and motor control center |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
SEW 10 |  | Sewage pumps, including the motor control center (MCC), control panel, flow meters, pressure transducers, level control switches, simple walls, GRP pipes and other connecting pipes, testing, delivery, installation parts, and the necessary mechanical and electrical work in accordance with the standards of the concerned authority, specifications and plans (the pumping station building and the motor control center building are measured separately) |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
SEW 10 |  | Variable-speed sewage and wastewater pumps: 2 working and 1 spare (in well) 1. Each pump has a flow of 100 liters per second and a vertical pressure of 22 m and includes a motor control center. | sum | 0.3 | 1500079 | 450023.7 | 1047355.8333 | 314206.75 | 0.3 | 0.3 |  | 0.3 | 100% | 1500079 | 450023.7 | 1047355.8333 | 314206.75 |  | 314206.75 | [7 empty] | 1047355.8333 | 0.3 | 314206.75 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 0.3 | 0.3 |  | 0.3 | [9 empty] | 3 pumps discarge 100 l/s head 22 m |  | LS | 1047355.8333 |  | 1047355.8333 | 0.3 | 314206.75 | 0 | 0 | 0 | 0 | 0
[22 empty] | 3 pumps discarge 100 l/s head 22 m | SC | LS | 1047355.8333 | 1 | 1047355.8333 | 0.3 | 314206.75
SEW 10 |  | Odor control system | sum | 1 | 226585 | 226585 | 145500 | 145500 | 1 | 1 |  | 1 | 100% | 226585 | 226585 | 145500 | 145500 |  | 145500 | [7 empty] | 145500 | 1 | 145500 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 1 | 1 |  | 1 | [9 empty] | Odour control system |  | LS | 145500 |  | 145500 | 1 | 145500 | 0 | 0 | 0 | 0 | 0
[22 empty] | Odor Control Unit & Connection | SC | LS | 145500 | 1 | 145500 | 1 | 145500
SEW 10 |  | In-line Booster Station | nr | 1 | 1022781 | 1022781 | 715000 | 715000 | 1 | 1 |  | 1 | 100% | 1022781 | 1022781 | 715000 | 715000 |  | 715000 | [7 empty] | 715000 | 1 | 715000 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 1 | 1 |  | 1 | [9 empty] | In-line Booster Station |  | Ea | 715000 |  | 715000 | 1 | 715000 | 0 | 0 | 0 | 0 | 0
[22 empty] | In-line Booster Station K | SC | LS | 715000 | 1 | 715000 | 1 | 715000
SEW 10 |  | Valves and fittings |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
SEW 10 |  | Supply, installation and testing of valves, including mounting flanges, connections, nuts, bolts, piping work inside the room and external piping (unless measured in another item) and all other accessories in accordance with the specifications, drawings and standards of the concerned authority. |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
SEW 10 |  | Valves, fittings and flow meters in different sizes | sum | 0.28 | 94411 | 26435.08 | 65500 | 18340 | 0.28 | 0.28 |  | 0.28 | 100% | 94411 | 26435.08 | 65500 | 18340 |  | 18340 | [7 empty] | 65500 | 0.28 | 18340 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 0.28 | 0.28 |  | 0.28 | [9 empty] | Valves, fittings and flow meters different sizes |  | LS | 65500 |  | 65500 | 0.28 | 18340 | 0 | 0 | 0 | 0 | 0
[22 empty] | Valves, fittings and flow meters different sizes | SC | LS | 65500 | 1 | 65500 | 0.28 | 18340
SEW 10 |  | The mesh is 35mm raked bar SS 316 | sum | 1 | 31470 | 31470 | 21972.5 | 21972.5 | 1 | 1 |  | 1 | 100% | 31470 | 31470 | 21972.5 | 21972.5 |  | 21972.5 | [7 empty] | 21972.5 | 1 | 21972.5 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 1 | 1 |  | 1 | [9 empty] | The mesh is 35mm raked bar SS 316 |  | LS | 21972.5 |  | 21972.5 | 1 | 21972.5 | 0 | 0 | 0 | 0 | 0
[22 empty] | Grid mesh 35mm raked bar SS 316 | SC | LS | 21972.5 | 1 | 21972.5 | 1 | 21972.5
SEW 10 |  | 100 kVA generator standby generator |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
SEW 10 |  | 100 kVA generator standby generator with an umbrella tank in accordance with what is stated in the specifications, plans and the authority’s approval. | nr | 0.85 | 1388390 | 1180131.5 | 345270 | 293479.5 | 0.85 | 0.85 |  | 0.85 | 100% | 1388390 | 1180131.5 | 345270 | 293479.5 |  | 293479.5 | [7 empty] | 345270 | 0.85 | 293479.5 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 0.85 | 0.85 |  | 0.85 | [9 empty] | 100 KVA generator with umbrella tank |  | LS | 345270 |  | 345270 | 0.85 | 293479.5 | 0 | 0 | 0 | 0 | 0
[22 empty] | 100 KVA generator with umbrella tank | SC | LS | 345270 | 1 | 345270 | 0.85 | 293479.5
SEW 10 |  | (Continued) PS4 Wastewater Pumping Station |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
SEW 10 |  | Pump well and valve chambers |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
SEW 10 |  | Cast-in-place concrete valve chamber and the structural structure of the well, including excavation, backfilling, waste disposal, dewatering (if needed), pouring, concrete works, supports, formwork, masonry work, waterproofing, GRP cover, columns, rust-resistant covers, guide bars, GRP supports, strainers, distribution boxes, tests, delivery, etc., in accordance with the requirements of the concerned authority, plans and specifications. |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
SEW 10 |  | The structural structure of the well, which consists of 1 well with internal dimensions of 4 m each, at a depth of approximately 11 m. | sum | 0.51 | 416036 | 212178.36 | 272802.6305 | 139129.3416 | 0.51 | 0.51 |  | 0.51 | 100% | 416036 | 212178.36 | 272802.6305 | 139129.3416 |  | 139129.3416 | [7 empty] | 272802.6305 | 0.51 | 139129.3416 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 0.51 | 0.51 |  | 0.51 | [9 empty] | 1 wells internal dimensions 4m, depth 11m |  | LS | 272802.6305 |  | 272802.6305 | 0.51 | 139129.3416 | 0 | 0 | 0 | 0 | 0
[22 empty] | 1 wells internal dimensions 4m, depth 11m | SC | LS | 272802.6305 | 1 | 272802.6305 | 0.51 | 139129.3416
SEW 10 |  | Grid chamber 35mm raked bar SS 316 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
SEW 10 |  | Valve chamber | sum | 0.51 | 399671 | 203832.21 | 214682.1916 | 109487.9177 | 0.51 | 0.51 |  | 0.51 | 100% | 399671 | 203832.21 | 214682.1916 | 109487.9177 |  | 109487.9177 | [7 empty] | 214682.1916 | 0.51 | 109487.9177 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 0.51 | 0.51 |  | 0.51 | [9 empty] | Valve chamber remaining work |  | LS | 214682.1916 |  | 214682.1916 | 0.51 | 109487.9177 | 0 | 0 | 0 | 0 | 0
[22 empty] | Valve chamber | SC | LS | 214682.1916 | 1 | 214682.1916 | 0.51 | 109487.9177
SEW 10 |  | Flow meter room | sum | 0.51 | 236656 | 120694.56 | 104088.4115 | 53085.0899 | 0.51 | 0.51 |  | 0.51 | 100% | 236656 | 120694.56 | 104088.4115 | 53085.0899 |  | 53085.0899 | [7 empty] | 104088.4115 | 0.51 | 53085.0899 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 0.51 | 0.51 |  | 0.51 | [9 empty] | Flow meter room remaining work |  | LS | 104088.4115 |  | 104088.4115 | 0.51 | 53085.0899 | 0 | 0 | 0 | 0 | 0
[22 empty] | Flow meter room | SC | LS | 104088.4115 | 1 | 104088.4115 | 0.51 | 53085.0899
SEW 10 |  | (Continued) PS4 Wastewater Pumping Station |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
SEW 10 |  | Engine Control Center Building |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
SEW 10 |  | The engine control center building includes a generator, fuel storage space, and sanitary facilities. It includes earthworks, foundations, concrete works, reinforcement, supports, formwork, brickwork, waterproofing, all finishing works, stairs, barriers, supports, ventilation openings, wires, circuits, lighting, and simple accessories related to energy, the telephone system, control equipment, outlets, wires, fire alarms, air conditioners, ventilation equipment, distribution boxes, etc., complete in accordance with the requirements of the concerned authority, specifications, and plans. |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
SEW 10 |  | Engine Control Center Building | sum | 0.075 | 918930 | 68919.75 | 754820 | 56611.5 | 0.075 | 0.075 |  | 0.075 | 100% | 918930 | 68919.75 | 754820 | 56611.5 |  | 56611.5 | [7 empty] | 754820 | 0.075 | 56611.5 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 0.075 | 0.075 |  | 0.075 | [9 empty] | Engine Control Center Building remaining work |  | LS | 754820 |  | 754820 | 0.075 | 56611.5 | 0 | 0 | 0 | 0 | 0
[22 empty] | Engine Control Center Building | SC | LS | 754820 | 1 | 754820 | 0.075 | 56611.5
SEW 10 |  | The base for the odor control system |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
SEW 10 |  | Concrete base below odor control system | sum | 1 | 13595 | 13595 | 9540 | 9540 | 1 | 1 |  | 1 | 100% | 13595 | 13595 | 9540 | 9540 |  | 9540 | [7 empty] | 9540 | 1 | 9540 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 1 | 1 |  | 1 | [9 empty] | Concrete base below odor control system |  | LS | 9540 |  | 9540 | 1 | 9540 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 0.27778 | 900 | 3.6 | 900
[22 empty] | Workmanship plain concrete | SC | M³ | 150 | 0.27778 | 540 | 3.6 | 540
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.11111 | 3150 | 9 | 3150
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 1.3889 | 1800 | 0.72 | 1800
[22 empty] | Workmanship Thrust Block | SC | M³ | 350 | 0.11111 | 3150 | 9 | 3150
SEW 10 |  | Perimeter walls |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
SEW 10 |  | Perimeter walls, including earthworks, foundations, bricks, construction works, and complete finishes in accordance with the plans, specifications, and requirements of the concerned authority. |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
SEW 10 |  | Perimeter walls | m | 120 | 2266 | 271920 | 906.3355 | 108760.2635 | 120 | 120 |  | 120 | 100% | 2266 | 271920 | 906.3355 | 108760.2635 |  | 108760.2635 | [7 empty] | 906.3355 | 120 | 108760.2635 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 120 | 120 |  | 120 | [9 empty] | Excavate & Disposal (D=1.50, W=1.00, B=1.00) |  | M | 6.3355 |  | 6.3355 | 120 | 760.2635 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 53.3333 | 1.05 | 2.25 | 126
[22 empty] | Fuel | Material | LTR | 1.76 | 3.8095 | 0.462 | 31.5 | 55.44
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 13.6 | 3.5294 | 8.8235 | 423.5294
[22 empty] | Fuel | Material | LTR | 1.76 | 1.36 | 1.2941 | 88.2353 | 155.2941
[9 empty] | 120 | 120 |  | 120 | [9 empty] | Perimeter walls foundations |  | M | 540 |  | 540 | 120 | 64800 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 5 | 50 | 24 | 6000
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 2.5 | 140 | 48 | 16800
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 25 | 100 | 4.8 | 12000
[22 empty] | Workmanship plain concrete | SC | M³ | 150 | 5 | 30 | 24 | 3600
[22 empty] | Workmanship RC concrete | SC | M³ | 450 | 2.5 | 180 | 48 | 21600
[22 empty] | 2 Layers Bituminous Application | SC | M² | 10 | 0.25 | 40 | 480 | 4800
[9 empty] | 120 | 120 |  | 120 | [9 empty] | Brick walls with posts (2.5m) |  | M | 360 |  | 360 | 120 | 43200 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply concrete bricks 40*20*20 | Material | M | 150 | 1 | 150 | 120 | 18000
[22 empty] | Masonry mortar | Material | M | 90 | 1 | 90 | 120 | 10800
[22 empty] | Apply masonary works | SC | M | 120 | 1 | 120 | 120 | 14400
SEW 10 |  | Main entry gates with two swing doors or a sliding door | nr | 1 | 22658 | 22658 | 18500 | 18500 | 1 | 1 |  | 1 | 100% | 22658 | 22658 | 18500 | 18500 |  | 18500 | [7 empty] | 18500 | 1 | 18500 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 1 | 1 |  | 1 | [9 empty] | Main entry gates |  | LS | 18500 |  | 18500 | 1 | 18500 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply & apply sliding door | SC | LS | 18500 | 1 | 18500 | 1 | 18500
SEW 10 |  | Single door personal entry gate | nr | 1 | 8182 | 8182 | 4750 | 4750 | 1 | 1 |  | 1 | 100% | 8182 | 8182 | 4750 | 4750 |  | 4750 | [7 empty] | 4750 | 1 | 4750 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 1 | 1 |  | 1 | [9 empty] | Single door |  | LS | 4750 |  | 4750 | 1 | 4750 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply & apply single door | SC | LS | 4750 | 1 | 4750 | 1 | 4750
SEW 10 |  | Lighting |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
SEW 10 |  | Lighting works, including poles and foundation works for poles, switches, control devices, cables and cable tubes, grounding, accessories and installation parts, are complete in accordance with the plans, specifications and requirements of the concerned authority. |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
SEW 10 |  | Flood Lights with single stand, 250 watts | sum | 1 | 314702 | 314702 | 219500 | 219500 | 1 | 1 |  | 1 | 100% | 314702 | 314702 | 219500 | 219500 |  | 219500 | [7 empty] | 219500 | 1 | 219500 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 1 | 1 |  | 1 | [9 empty] | Lighting Poles |  | LS | 219500 |  | 219500 | 1 | 219500 | 0 | 0 | 0 | 0 | 0
[22 empty] | 8 nos Flood Lights with single stand, 250 watts | SC | LS | 219500 | 1 | 219500 | 1 | 219500
SEW 10 |  | Ducts ferry works |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
SEW 10 |  | Supply and installation of uPVC culverts in trenches, including tension ropes, warning tapes, excavation and backfilling with sandy or granular materials, compaction, waste disposal work, returning the thing to its original state, testing, and all requirements of the concerned authority, specifications and plans. |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
SEW 10 |  | One exit path with a depth not exceeding 1.5 metres | m | 9 | 104 | 936 | 56.1307 | 505.1764 | 9 | 9 |  | 9 | 100% | 104 | 936 | 56.1307 | 505.1764 |  | 505.1764 | [7 empty] | 56.1307 | 9 | 505.1764 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 9 | 9 |  | 9 | [9 empty] | Excavate & Disposal ( W= 1.5 M * d= 1.5 ) |  | M | 10.5257 |  | 10.5257 | 9 | 94.7312 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 44.4444 | 1.26 | 0.2025 | 11.34
[22 empty] | Fuel | Material | LTR | 1.76 | 3.1746 | 0.5544 | 2.835 | 4.9896
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 9.0667 | 5.2941 | 0.99265 | 47.6471
[22 empty] | Fuel | Material | LTR | 1.76 | 0.90667 | 1.9412 | 9.9265 | 17.4706
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 44.4444 | 1.08 | 0.2025 | 9.72
[22 empty] | Fuel | Material | LTR | 1.76 | 4.4444 | 0.396 | 2.025 | 3.564
[9 empty] | 9 | 9 |  | 9 | [9 empty] | Duct bank (0.25*0.25) |  | M | 31.34 |  | 31.34 | 9 | 282.06 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 16 | 15.625 | 0.5625 | 140.625
[22 empty] | UPVC Pipe 50 mm | Material | M | 4 | 1 | 4 | 9 | 36
[22 empty] | UPVC Fitting 50 mm | Material | M | 2 | 1 | 2 | 9 | 18
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 16 | 9.375 | 0.5625 | 84.375
[22 empty] | Skilled Labor | Manpower | HR | 17 | 50 | 0.34 | 0.18 | 3.06
[9 empty] | 9 | 9 |  | 9 | [9 empty] | Backfilling |  | M | 14.265 |  | 14.265 | 9 | 128.3851 | 0 | 0 | 0 | 0 | 0
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 45.7143 | 1.435 | 0.19687 | 12.915
[22 empty] | Fuel | Material | LTR | 1.76 | 5.0794 | 0.3465 | 1.7719 | 3.1185
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 9.3257 | 5.1471 | 0.96507 | 46.3235
[22 empty] | Fuel | Material | LTR | 1.76 | 0.93257 | 1.8873 | 9.6507 | 16.9853
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 22.8571 | 1.575 | 0.39375 | 14.175
[22 empty] | Fuel | Material | LTR | 1.76 | 2.5397 | 0.693 | 3.5438 | 6.237
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 32 | 1.5 | 0.28125 | 13.5
[22 empty] | Fuel | Material | LTR | 1.76 | 3.2 | 0.55 | 2.8125 | 4.95
[22 empty] | Plate Compactor | Machinery | HR | 23 | 25 | 0.92 | 0.36 | 8.28
[22 empty] | Fuel | Material | LTR | 1.76 | 8.3333 | 0.2112 | 1.08 | 1.9008
SEW 10 |  | A path of two exits with a depth not exceeding 1.5 metres | m | 9 | 120 | 1080 | 78.5391 | 706.852 | 9 | 9 |  | 9 | 100% | 120 | 1080 | 78.5391 | 706.852 |  | 706.852 | [7 empty] | 78.5391 | 9 | 706.852 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 9 | 9 |  | 9 | [9 empty] | Excavate & Disposal ( W= 1.6 M * d= 1.5 ) |  | M | 11.2274 |  | 11.2274 | 9 | 101.0467 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 41.6667 | 1.344 | 0.216 | 12.096
[22 empty] | Fuel | Material | LTR | 1.76 | 2.9762 | 0.59136 | 3.024 | 5.3222
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 8.5 | 5.6471 | 1.0588 | 50.8235
[22 empty] | Fuel | Material | LTR | 1.76 | 0.85 | 2.0706 | 10.5882 | 18.6353
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 41.6667 | 1.152 | 0.216 | 10.368
[22 empty] | Fuel | Material | LTR | 1.76 | 4.1667 | 0.4224 | 2.16 | 3.8016
[9 empty] | 9 | 9 |  | 9 | [9 empty] | Duct bank (0.40*0.25) |  | M | 52.34 |  | 52.34 | 9 | 471.06 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 10 | 25 | 0.9 | 225
[22 empty] | UPVC Pipe 50 mm | Material | M | 4 | 0.5 | 8 | 18 | 72
[22 empty] | UPVC Fitting 50 mm | Material | M | 2 | 0.5 | 4 | 18 | 36
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 10 | 15 | 0.9 | 135
[22 empty] | Skilled Labor | Manpower | HR | 17 | 50 | 0.34 | 0.18 | 3.06
[9 empty] | 9 | 9 |  | 9 | [9 empty] | Backfilling |  | M | 14.9717 |  | 14.9717 | 9 | 134.7453 | 0 | 0 | 0 | 0 | 0
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 43.4783 | 1.5088 | 0.207 | 13.5792
[22 empty] | Fuel | Material | LTR | 1.76 | 4.8309 | 0.36432 | 1.863 | 3.2789
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 8.8696 | 5.4118 | 1.0147 | 48.7059
[22 empty] | Fuel | Material | LTR | 1.76 | 0.88696 | 1.9843 | 10.1471 | 17.8588
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 21.7391 | 1.656 | 0.414 | 14.904
[22 empty] | Fuel | Material | LTR | 1.76 | 2.4155 | 0.72864 | 3.726 | 6.5578
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 30 | 1.6 | 0.3 | 14.4
[22 empty] | Fuel | Material | LTR | 1.76 | 3 | 0.58667 | 3 | 5.28
[22 empty] | Plate Compactor | Machinery | HR | 23 | 25 | 0.92 | 0.36 | 8.28
[22 empty] | Fuel | Material | LTR | 1.76 | 8.3333 | 0.2112 | 1.08 | 1.9008
SEW 10 |  | A path of 8 exits with a depth not exceeding 1.5 metres | m | 20 | 380 | 7600 | 187.2255 | 3744.5097 | 20 | 20 |  | 20 | 100% | 380 | 7600 | 187.2255 | 3744.5097 |  | 3744.5097 | [7 empty] | 187.2255 | 20 | 3744.5097 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 20 | 20 |  | 20 | [9 empty] | Excavate & Disposal ( W= 1.7 M * d= 1.5 ) |  | M | 11.9291 |  | 11.9291 | 20 | 238.5824 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 39.2157 | 1.428 | 0.51 | 28.56
[22 empty] | Fuel | Material | LTR | 1.76 | 2.8011 | 0.62832 | 7.14 | 12.5664
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 8 | 6 | 2.5 | 120
[22 empty] | Fuel | Material | LTR | 1.76 | 0.8 | 2.2 | 25 | 44
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 39.2157 | 1.224 | 0.51 | 24.48
[22 empty] | Fuel | Material | LTR | 1.76 | 3.9216 | 0.4488 | 5.1 | 8.976
[9 empty] | 20 | 20 |  | 20 | [9 empty] | Duct bank |  | M | 160.34 |  | 160.34 | 20 | 3206.8 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 3.5714 | 70 | 5.6 | 1400
[22 empty] | UPVC Pipe 50 mm | Material | M | 4 | 0.125 | 32 | 160 | 640
[22 empty] | UPVC Fitting 50 mm | Material | M | 2 | 0.125 | 16 | 160 | 320
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 3.5714 | 42 | 5.6 | 840
[22 empty] | Skilled Labor | Manpower | HR | 17 | 50 | 0.34 | 0.4 | 6.8
[9 empty] | 20 | 20 |  | 20 | [9 empty] | Backfilling |  | M | 14.9564 |  | 14.9564 | 20 | 299.1273 | 0 | 0 | 0 | 0 | 0
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 44.0529 | 1.4891 | 0.454 | 29.7824
[22 empty] | Fuel | Material | LTR | 1.76 | 4.8948 | 0.35957 | 4.086 | 7.1914
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 8.9868 | 5.3412 | 2.2255 | 106.8235
[22 empty] | Fuel | Material | LTR | 1.76 | 0.89868 | 1.9584 | 22.2549 | 39.1686
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 22.0264 | 1.6344 | 0.908 | 32.688
[22 empty] | Fuel | Material | LTR | 1.76 | 2.4474 | 0.71914 | 8.172 | 14.3827
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 28.2353 | 1.7 | 0.70833 | 34
[22 empty] | Fuel | Material | LTR | 1.76 | 2.8235 | 0.62333 | 7.0833 | 12.4667
[22 empty] | Plate Compactor | Machinery | HR | 23 | 25 | 0.92 | 0.8 | 18.4
[22 empty] | Fuel | Material | LTR | 1.76 | 8.3333 | 0.2112 | 2.4 | 4.224
SEW 10 |  | Earthing work |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
SEW 10 |  | Pit for grounding work | nr | 1 | 1385 | 1385 | 1137.4 | 1137.4 | 1 | 1 |  | 1 | 100% | 1385 | 1385 | 1137.4 | 1137.4 |  | 1137.4 | [7 empty] | 1137.4 | 1 | 1137.4 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 1 | 1 |  | 1 | [9 empty] | Pit for grounding work |  | Ea | 1137.4 |  | 1137.4 | 1 | 1137.4 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pit for grounding work | SC | LS | 1137.4 | 1 | 1137.4 | 1 | 1137.4
SEW 10 |  | Cable pulling pit measuring 600x600 mm | nr | 2 | 1762 | 3524 | 1447 | 2894 | 2 | 2 |  | 2 | 100% | 1762 | 3524 | 1447 | 2894 |  | 2894 | [7 empty] | 1447 | 2 | 2894 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 2 | 2 |  | 2 | [9 empty] | Cable pulling pit measuring 600x600 mm |  | Ea | 1447 |  | 1447 | 2 | 2894 | 0 | 0 | 0 | 0 | 0
[22 empty] | Cable pulling pit measuring 600x600 mm | SC | LS | 1447 | 1 | 1447 | 2 | 2894
SEW 10 |  | (Continued) PS4 Wastewater Pumping Station |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
SEW 10 |  | Cosmetic coordination works |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
SEW 10 |  | Concrete interlock pavement tiles, including subsoil and sand layer with compaction according to specifications and plans. |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
SEW 10 |  | Pavement tiles for the perimeter of buildings | m² | 277 | 86 | 23822 | 54.3824 | 15063.9248 | 277 | 277 |  | 277 | 100% | 86 | 23822 | 54.3824 | 15063.9248 |  | 15063.9248 | [7 empty] | 54.3824 | 277 | 15063.9248 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 277 | 277 |  | 277 | [9 empty] | Base layer preparation |  | M² | 4.3824 |  | 4.3824 | 277 | 1213.9248 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backhoe loader | Machinery | HR | 44 | 20 | 2.2 | 13.85 | 609.4
[22 empty] | Fuel | Material | LTR | 1.76 | 2 | 0.88 | 138.5 | 243.76
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 100 | 0.48 | 2.77 | 132.96
[22 empty] | Fuel | Material | LTR | 1.76 | 10 | 0.176 | 27.7 | 48.752
[22 empty] | Roller Compactor 10 Ton | Machinery | HR | 40 | 100 | 0.4 | 2.77 | 110.8
[22 empty] | Fuel | Material | LTR | 1.76 | 7.1429 | 0.2464 | 38.78 | 68.2528
[9 empty] | 277 | 277 |  | 277 | [9 empty] | Fix Interlock tiles (10 cm sand bedding) |  | M² | 50 |  | 50 | 277 | 13850 | 0 | 0 | 0 | 0 | 0
[22 empty] | Polyethylene sheet | Machinery | M² | 2 | 1 | 2 | 277 | 554
[22 empty] | Sand Supply | Material | M³ | 30 | 10 | 3 | 27.7 | 831
[22 empty] | Interlock tiles Supply | Material | M² | 25 | 1 | 25 | 277 | 6925
[22 empty] | Interlock tiles Installation | SC | M² | 20 | 1 | 20 | 277 | 5540
SEW 10 |  | Paving tiles for entrance ways | m² | 43.65 | 86 | 3753.9 | 54.3824 | 2373.7918 | 43.65 | 43.65 |  | 43.65 | 100% | 86 | 3753.9 | 54.3824 | 2373.7918 |  | 2373.7918 | [7 empty] | 54.3824 | 43.65 | 2373.7918 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 43.65 | 43.65 |  | 43.65 | [9 empty] | Base layer preparation |  | M² | 4.3824 |  | 4.3824 | 43.65 | 191.2918 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backhoe loader | Machinery | HR | 44 | 20 | 2.2 | 2.1825 | 96.03
[22 empty] | Fuel | Material | LTR | 1.76 | 2 | 0.88 | 21.825 | 38.412
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 100 | 0.48 | 0.4365 | 20.952
[22 empty] | Fuel | Material | LTR | 1.76 | 10 | 0.176 | 4.365 | 7.6824
[22 empty] | Roller Compactor 10 Ton | Machinery | HR | 40 | 100 | 0.4 | 0.4365 | 17.46
[22 empty] | Fuel | Material | LTR | 1.76 | 7.1429 | 0.2464 | 6.111 | 10.7554
[9 empty] | 43.65 | 43.65 |  | 43.65 | [9 empty] | Fix Interlock tiles (10 cm sand bedding) |  | M² | 50 |  | 50 | 43.65 | 2182.5 | 0 | 0 | 0 | 0 | 0
[22 empty] | Polyethylene sheet | Machinery | M² | 2 | 1 | 2 | 43.65 | 87.3
[22 empty] | Sand Supply | Material | M³ | 30 | 10 | 3 | 4.365 | 130.95
[22 empty] | Interlock tiles Supply | Material | M² | 25 | 1 | 25 | 43.65 | 1091.25
[22 empty] | Interlock tiles Installation | SC | M² | 20 | 1 | 20 | 43.65 | 873
SEW 10 |  | Water drainage network at the pumping station |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
SEW 10 |  | The internal water drainage network within the scope of the pumping station building, which includes drainage pipes, installation parts, chambers, and connections with the main drainage network in accordance with the requirements of the concerned authority, specifications and plans. |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
SEW 10 |  | Surface channel for water drainage within the pumping station building complex | m | 120 | 298 | 35760 | 70.4938 | 8459.25 | 120 | 120 |  | 120 | 100% | 298 | 35760 | 70.4938 | 8459.25 |  | 8459.25 | [7 empty] | 70.4938 | 120 | 8459.25 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 120 | 120 |  | 120 | [9 empty] | Excavation of drainage Channel |  | M | 3.3 |  | 3.3 | 120 | 396 | 0 | 0 | 0 | 0 | 0
[22 empty] | Concrete Cutter | Machinery | HR | 40 | 20 | 2 | 6 | 240
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 10 | 1.3 | 12 | 156
[9 empty] | 120 | 45 |  | 45 | [9 empty] | Surface preperation |  | M | 8.3333 |  | 8.3333 | 45 | 375 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 30 | 8.3333 | 1.5 | 375
[9 empty] | 120 | 45 |  | 45 | [9 empty] | Channel Installation with Connections |  | M | 170.85 |  | 170.85 | 45 | 7688.25 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Floor Surface Channel with grating | Material | M | 150 | 1 | 150 | 45 | 6750
[22 empty] | Supply Pipes Connections | Material | M | 20 | 1 | 20 | 45 | 900
[22 empty] | Skilled labor | Manpower | HR | 17 | 20 | 0.85 | 2.25 | 38.25
SEW 10 |  | Additional works for sewage networks (Extra over) |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
SEW 10 |  | Excavation work at various depths, including disposal of waste, warning tapes, dewatering, and washing in accordance with special procedures. | m³ | 1 | 32 | 32 | 19.742 | 19.742 | 1 | 1 |  | 1 | 100% | 32 | 32 | 19.742 | 19.742 |  | 19.742 | [7 empty] | 19.742 | 1 | 19.742 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 1 | 1 |  | 1 | [9 empty] | Excavation & Disposal |  | M³ | 13.0472 |  | 13.0472 | 1 | 13.0472 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Hydraulic Hammer 50T | Machinery | HR | 150.4 | 25 | 6.016 | 0.04 | 6.016
[22 empty] | Fuel | Material | LTR | 1.76 | 0.78125 | 2.2528 | 1.28 | 2.2528
[22 empty] | Excavator with Bucket 50T | Machinery | HR | 131.2 | 120 | 1.0933 | 0.0083333 | 1.0933
[22 empty] | Fuel | Material | LTR | 1.76 | 3.75 | 0.46933 | 0.26667 | 0.46933
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 20.4 | 2.3529 | 0.04902 | 2.3529
[22 empty] | Fuel | Material | LTR | 1.76 | 2.04 | 0.86275 | 0.4902 | 0.86275
[9 empty] | 1 | 1 |  | 1 | [9 empty] | Backfilling & Compaction |  | M³ | 6.6949 |  | 6.6949 | 1 | 6.6949 | 0 | 0 | 0 | 0 | 0
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 100 | 0.656 | 0.01 | 0.656
[22 empty] | Fuel | Material | LTR | 1.76 | 11.1111 | 0.1584 | 0.09 | 0.1584
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 20.4 | 2.3529 | 0.04902 | 2.3529
[22 empty] | Fuel | Material | LTR | 1.76 | 2.04 | 0.86275 | 0.4902 | 0.86275
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 50 | 0.72 | 0.02 | 0.72
[22 empty] | Fuel | Material | LTR | 1.76 | 5.5556 | 0.3168 | 0.18 | 0.3168
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 80 | 0.6 | 0.0125 | 0.6
[22 empty] | Fuel | Material | LTR | 1.76 | 8 | 0.22 | 0.125 | 0.22
[22 empty] | Roller Compactor 10 Ton | Machinery | HR | 40 | 80 | 0.5 | 0.0125 | 0.5
[22 empty] | Fuel | Material | LTR | 1.76 | 5.7143 | 0.308 | 0.175 | 0.308
Category (I): Piping works - pipes
Circular pipes
Supply and installation of uPVC pipes in trenches, including excavation, backfilling, compaction, waste removal, facility protection, reinforcement work, warning tapes, testing, and commissioning upon completion in accordance with plans, specifications, and requirements of the concerned authority (backfill work under and around the pipe is measured individually)
STR11 |  | 250 mm diameter pipes at a depth of 0 - 1.5 m. | m | 7.5155 | 268 | 2014.154 | 115.1661 | 865.5305 | 7.5155 | 7.5155 |  | 7.5155 | 100% | 268 | 2014.154 | 115.1661 | 865.5305 |  | 865.5305 | [7 empty] | 115.1661 | 7.5155 | 865.5305 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 7.5155 | 7.5155 |  | 7.5155 | [9 empty] | Excavation ( W= 1.0 & d= 1.5 ) |  | M | 7.5827 |  | 7.5827 | 7.5155 | 56.988 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 66.6667 | 0.84 | 0.11273 | 6.313
[22 empty] | Fuel | Material | LTR | 1.76 | 4.7619 | 0.3696 | 1.5783 | 2.7777
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 13.6 | 3.5294 | 0.55261 | 26.5253
[22 empty] | Fuel | Material | LTR | 1.76 | 1.36 | 1.2941 | 5.5261 | 9.7259
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 0.15031 | 3.4571
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 0.45093 | 0.79364
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 66.6667 | 0.72 | 0.11273 | 5.4112
[22 empty] | Fuel | Material | LTR | 1.76 | 6.6667 | 0.264 | 1.1273 | 1.9841
[9 empty] | 7.5155 | 7.5155 |  | 7.5155 | [9 empty] | Pipe Laying & Protection |  | M | 102.5833 |  | 102.5833 | 7.5155 | 770.965 | 0 | 0 | 0 | 0 | 0
[22 empty] | UPVC Pipe 250 mm | Material | M | 52 | 1 | 52 | 7.5155 | 390.806
[22 empty] | UPVC Fitting 250 mm | Material | M | 5 | 1 | 5 | 7.5155 | 37.5775
[22 empty] | Skilled Labor | Manpower | HR | 17 | 6 | 2.8333 | 1.2526 | 21.2939
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 6 | 2.1667 | 1.2526 | 16.2836
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 10 | 25 | 0.75155 | 187.8875
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 10 | 15 | 0.75155 | 112.7325
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.025052 | 4.384
[9 empty] | 7.5155 | 7.5155 |  | 7.5155 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 7.5155 | 37.5775 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 7.5155 | 37.5775
STR11 |  | 250 mm diameter pipes at a depth of 1.5 - 2.0 m. | m | 9.3065 | 291 | 2708.1915 | 117.5051 | 1093.5613 | 9.3065 | 9.3065 |  | 9.3065 | 100% | 291 | 2708.1915 | 117.5051 | 1093.5613 |  | 1093.5613 | [7 empty] | 117.5051 | 9.3065 | 1093.5613 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 9.3065 | 9.3065 |  | 9.3065 | [9 empty] | Excavation ( W= 1.0 & d= 2.0 ) |  | M | 9.9218 |  | 9.9218 | 9.3065 | 92.337 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 50 | 1.12 | 0.18613 | 10.4233
[22 empty] | Fuel | Material | LTR | 1.76 | 3.5714 | 0.4928 | 2.6058 | 4.5862
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 10.2 | 4.7059 | 0.9124 | 43.7953
[22 empty] | Fuel | Material | LTR | 1.76 | 1.02 | 1.7255 | 9.124 | 16.0583
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 0.18613 | 4.281
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 0.55839 | 0.98277
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 50 | 0.96 | 0.18613 | 8.9342
[22 empty] | Fuel | Material | LTR | 1.76 | 5 | 0.352 | 1.8613 | 3.2759
[9 empty] | 9.3065 | 9.3065 |  | 9.3065 | [9 empty] | Pipe Laying & Protection |  | M | 102.5833 |  | 102.5833 | 9.3065 | 954.6918 | 0 | 0 | 0 | 0 | 0
[22 empty] | UPVC Pipe 250 mm | Material | M | 52 | 1 | 52 | 9.3065 | 483.938
[22 empty] | UPVC Fitting 250 mm | Material | M | 5 | 1 | 5 | 9.3065 | 46.5325
[22 empty] | Skilled Labor | Manpower | HR | 17 | 6 | 2.8333 | 1.5511 | 26.3684
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 6 | 2.1667 | 1.5511 | 20.1641
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 10 | 25 | 0.93065 | 232.6625
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 10 | 15 | 0.93065 | 139.5975
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.031022 | 5.4288
[9 empty] | 9.3065 | 9.3065 |  | 9.3065 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 9.3065 | 46.5325 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 9.3065 | 46.5325
STR11 |  | 250 mm diameter pipes at a depth of 2.0 - 2.5 m, | m |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | 160 mm diameter pipes at a depth of 2.0 - 2.5 m, | m |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | 200 mm diameter pipes at a depth of 2.0 - 2.5 m, | m |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | 300 mm diameter pipes at a depth of 0 - 1.5 m, | m | 6429.0565 | 386 | 2481615.809 | 146.1661 | 939709.8758 | 6429.0565 | 6429.0565 |  | 6429.0565 | 100% | 386 | 2481615.809 | 146.1661 | 939709.8758 |  | 939709.8758 | [7 empty] | 146.1661 | 6429.0565 | 939709.8758 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 6429.0565 | 6429.0565 |  | 6429.0565 | [9 empty] | Excavation ( W= 1.0 & d= 1.5 ) |  | M | 7.5827 |  | 7.5827 | 6429.0565 | 48749.7958 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 66.6667 | 0.84 | 96.4358 | 5400.4075
[22 empty] | Fuel | Material | LTR | 1.76 | 4.7619 | 0.3696 | 1350.1019 | 2376.1793
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 13.6 | 3.5294 | 472.7247 | 22690.7876
[22 empty] | Fuel | Material | LTR | 1.76 | 1.36 | 1.2941 | 4727.2474 | 8319.9555
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 128.5811 | 2957.366
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 385.7434 | 678.9084
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 66.6667 | 0.72 | 96.4358 | 4628.9207
[22 empty] | Fuel | Material | LTR | 1.76 | 6.6667 | 0.264 | 964.3585 | 1697.2709
[9 empty] | 6429.0565 | 6429.0565 |  | 6429.0565 | [9 empty] | Pipe Laying & Protection |  | M | 133.5833 |  | 133.5833 | 6429.0565 | 858814.7975 | 0 | 0 | 0 | 0 | 0
[22 empty] | UPVC Pipe 300 mm | Material | M | 80 | 1 | 80 | 6429.0565 | 514324.52
[22 empty] | UPVC Fitting 300 mm | Material | M | 8 | 1 | 8 | 6429.0565 | 51432.452
[22 empty] | Skilled Labor | Manpower | HR | 17 | 6 | 2.8333 | 1071.5094 | 18215.6601
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 6 | 2.1667 | 1071.5094 | 13929.6224
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 10 | 25 | 642.9056 | 160726.4125
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 10 | 15 | 642.9056 | 96435.8475
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 21.4302 | 3750.283
[9 empty] | 6429.0565 | 6429.0565 |  | 6429.0565 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 6429.0565 | 32145.2825 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 6429.0565 | 32145.2825
STR11 |  | 300 mm diameter pipes at a depth of 1.5 - 2.0 m. | m | 1056.1224 | 399 | 421392.8376 | 148.5051 | 156839.5688 | 1056.1224 | 1056.1224 |  | 1056.1224 | 100% | 399 | 421392.8376 | 148.5051 | 156839.5688 |  | 156839.5688 | [7 empty] | 148.5051 | 1056.1224 | 156839.5688 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 1056.1224 | 1056.1224 |  | 1056.1224 | [9 empty] | Excavation ( W= 1.0 & d= 2.0 ) |  | M | 9.9218 |  | 9.9218 | 1056.1224 | 10478.6062 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 50 | 1.12 | 21.1224 | 1182.8571
[22 empty] | Fuel | Material | LTR | 1.76 | 3.5714 | 0.4928 | 295.7143 | 520.4571
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 10.2 | 4.7059 | 103.5414 | 4969.9878
[22 empty] | Fuel | Material | LTR | 1.76 | 1.02 | 1.7255 | 1035.4141 | 1822.3288
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 21.1224 | 485.8163
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 63.3673 | 111.5265
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 50 | 0.96 | 21.1224 | 1013.8775
[22 empty] | Fuel | Material | LTR | 1.76 | 5 | 0.352 | 211.2245 | 371.7551
[9 empty] | 1056.1224 | 1056.1224 |  | 1056.1224 | [9 empty] | Pipe Laying & Protection |  | M | 133.5833 |  | 133.5833 | 1056.1224 | 141080.3506 | 0 | 0 | 0 | 0 | 0
[22 empty] | UPVC Pipe 300 mm | Material | M | 80 | 1 | 80 | 1056.1224 | 84489.792
[22 empty] | UPVC Fitting 300 mm | Material | M | 8 | 1 | 8 | 1056.1224 | 8448.9792
[22 empty] | Skilled Labor | Manpower | HR | 17 | 6 | 2.8333 | 176.0204 | 2992.3468
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 6 | 2.1667 | 176.0204 | 2288.2652
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 10 | 25 | 105.6122 | 26403.06
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 10 | 15 | 105.6122 | 15841.836
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 3.5204 | 616.0714
[9 empty] | 1056.1224 | 1056.1224 |  | 1056.1224 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 1056.1224 | 5280.612 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 1056.1224 | 5280.612
STR11 |  | 300 mm diameter pipes at a depth of 2.0 - 2.5 m, | m | 194.8948 | 417 | 81271.1316 | 185.8441 | 36220.0583 | 194.8948 | 194.8948 |  | 194.8948 | 100% | 417 | 81271.1316 | 185.8441 | 36220.0583 |  | 36220.0583 | [7 empty] | 185.8441 | 194.8948 | 36220.0583 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 194.8948 | 194.8948 |  | 194.8948 | [9 empty] | Excavation ( W= 1.0 & d= 2.5 ) |  | M | 47.2608 |  | 47.2608 | 194.8948 | 9210.8872 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 40 | 1.4 | 4.8724 | 272.8527
[22 empty] | Fuel | Material | LTR | 1.76 | 2.8571 | 0.616 | 68.2132 | 120.0552
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 8.16 | 5.8824 | 23.8842 | 1146.44
[22 empty] | Fuel | Material | LTR | 1.76 | 0.816 | 2.1569 | 238.8417 | 420.3613
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 3.8979 | 89.6516
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 11.6937 | 20.5809
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 40 | 1.2 | 4.8724 | 233.8738
[22 empty] | Fuel | Material | LTR | 1.76 | 4 | 0.44 | 48.7237 | 85.7537
[22 empty] | Steel Shoring D=2.5 M | Material | M | 35 | 1 | 35 | 194.8948 | 6821.318
[9 empty] | 194.8948 | 194.8948 |  | 194.8948 | [9 empty] | Pipe Laying & Protection |  | M | 133.5833 |  | 133.5833 | 194.8948 | 26034.697 | 0 | 0 | 0 | 0 | 0
[22 empty] | UPVC Pipe 300 mm | Material | M | 80 | 1 | 80 | 194.8948 | 15591.584
[22 empty] | UPVC Fitting 300 mm | Material | M | 8 | 1 | 8 | 194.8948 | 1559.1584
[22 empty] | Skilled Labor | Manpower | HR | 17 | 6 | 2.8333 | 32.4825 | 552.2019
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 6 | 2.1667 | 32.4825 | 422.2721
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 10 | 25 | 19.4895 | 4872.37
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 10 | 15 | 19.4895 | 2923.422
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.64965 | 113.6886
[9 empty] | 194.8948 | 194.8948 |  | 194.8948 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 194.8948 | 974.474 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 194.8948 | 974.474
STR11 |  | 300 mm diameter pipes at a depth of 2.5 - 3.0 m, | m | 168.2758 | 543 | 91373.7594 | 213.1832 | 35873.5722 | 168.2758 | 168.2758 |  | 168.2758 | 100% | 543 | 91373.7594 | 213.1832 | 35873.5722 |  | 35873.5722 | [7 empty] | 213.1832 | 168.2758 | 35873.5722 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 168.2758 | 168.2758 |  | 168.2758 | [9 empty] | Excavation ( W= 1.0 & d= 3.0 ) |  | M | 74.5999 |  | 74.5999 | 168.2758 | 12553.3509 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 33.3333 | 1.68 | 5.0483 | 282.7033
[22 empty] | Fuel | Material | LTR | 1.76 | 2.381 | 0.7392 | 70.6758 | 124.3895
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 6.8 | 7.0588 | 24.7464 | 1187.8292
[22 empty] | Fuel | Material | LTR | 1.76 | 0.68 | 2.5882 | 247.4644 | 435.5374
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 3.3655 | 77.4069
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 10.0965 | 17.7699
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 33.3333 | 1.44 | 5.0483 | 242.3172
[22 empty] | Fuel | Material | LTR | 1.76 | 3.3333 | 0.528 | 50.4827 | 88.8496
[22 empty] | Steel Shoring D>3.0 M | Material | M | 60 | 1 | 60 | 168.2758 | 10096.548
[9 empty] | 168.2758 | 168.2758 |  | 168.2758 | [9 empty] | Pipe Laying & Protection |  | M | 133.5833 |  | 133.5833 | 168.2758 | 22478.8423 | 0 | 0 | 0 | 0 | 0
[22 empty] | UPVC Pipe 300 mm | Material | M | 80 | 1 | 80 | 168.2758 | 13462.064
[22 empty] | UPVC Fitting 300 mm | Material | M | 8 | 1 | 8 | 168.2758 | 1346.2064
[22 empty] | Skilled Labor | Manpower | HR | 17 | 6 | 2.8333 | 28.046 | 476.7814
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 6 | 2.1667 | 28.046 | 364.5976
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 10 | 25 | 16.8276 | 4206.895
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 10 | 15 | 16.8276 | 2524.137
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.56092 | 98.1609
[9 empty] | 168.2758 | 168.2758 |  | 168.2758 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 168.2758 | 841.379 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 168.2758 | 841.379
STR11 |  | 300 mm diameter pipes at a depth of 3.0 - 3.5 m, | m | 6.88 | 568 | 3907.84 | 215.5222 | 1482.793 | 6.88 | 6.88 |  | 6.88 | 100% | 568 | 3907.84 | 215.5222 | 1482.793 |  | 1482.793 | [7 empty] | 215.5222 | 6.88 | 1482.793 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 6.88 | 6.88 |  | 6.88 | [9 empty] | Excavation ( W= 1.0 & d= 3.5 ) |  | M | 76.9389 |  | 76.9389 | 6.88 | 529.3396 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 28.5714 | 1.96 | 0.2408 | 13.4848
[22 empty] | Fuel | Material | LTR | 1.76 | 2.0408 | 0.8624 | 3.3712 | 5.9333
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 5.8286 | 8.2353 | 1.1804 | 56.6588
[22 empty] | Fuel | Material | LTR | 1.76 | 0.58286 | 3.0196 | 11.8039 | 20.7749
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 0.1376 | 3.1648
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 0.4128 | 0.72653
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 28.5714 | 1.68 | 0.2408 | 11.5584
[22 empty] | Fuel | Material | LTR | 1.76 | 2.8571 | 0.616 | 2.408 | 4.2381
[22 empty] | Steel Shoring D>3.0 M | Material | M | 60 | 1 | 60 | 6.88 | 412.8
[9 empty] | 6.88 | 6.88 |  | 6.88 | [9 empty] | Pipe Laying & Protection |  | M | 133.5833 |  | 133.5833 | 6.88 | 919.0533 | 0 | 0 | 0 | 0 | 0
[22 empty] | UPVC Pipe 300 mm | Material | M | 80 | 1 | 80 | 6.88 | 550.4
[22 empty] | UPVC Fitting 300 mm | Material | M | 8 | 1 | 8 | 6.88 | 55.04
[22 empty] | Skilled Labor | Manpower | HR | 17 | 6 | 2.8333 | 1.1467 | 19.4933
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 6 | 2.1667 | 1.1467 | 14.9067
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 10 | 25 | 0.688 | 172
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 10 | 15 | 0.688 | 103.2
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.022933 | 4.0133
[9 empty] | 6.88 | 6.88 |  | 6.88 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 6.88 | 34.4 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 6.88 | 34.4
STR11 |  | 300 mm diameter pipes at a depth of 3.5 - 4.0 m, | m | 6.38 | 716 | 4568.08 | 217.8613 | 1389.955 | 6.38 | 6.38 |  | 6.38 | 100% | 716 | 4568.08 | 217.8613 | 1389.955 |  | 1389.955 | [7 empty] | 217.8613 | 6.38 | 1389.955 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 6.38 | 6.38 |  | 6.38 | [9 empty] | Excavation ( W= 1.0 & d= 4.0 ) |  | M | 79.2779 |  | 79.2779 | 6.38 | 505.7933 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 25 | 2.24 | 0.2552 | 14.2912
[22 empty] | Fuel | Material | LTR | 1.76 | 1.7857 | 0.9856 | 3.5728 | 6.2881
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 5.1 | 9.4118 | 1.251 | 60.0471
[22 empty] | Fuel | Material | LTR | 1.76 | 0.51 | 3.451 | 12.5098 | 22.0173
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 0.1276 | 2.9348
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 0.3828 | 0.67373
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 25 | 1.92 | 0.2552 | 12.2496
[22 empty] | Fuel | Material | LTR | 1.76 | 2.5 | 0.704 | 2.552 | 4.4915
[22 empty] | Steel Shoring D>3.0 M | Material | M | 60 | 1 | 60 | 6.38 | 382.8
[9 empty] | 6.38 | 6.38 |  | 6.38 | [9 empty] | Pipe Laying & Protection |  | M | 133.5833 |  | 133.5833 | 6.38 | 852.2617 | 0 | 0 | 0 | 0 | 0
[22 empty] | UPVC Pipe 300 mm | Material | M | 80 | 1 | 80 | 6.38 | 510.4
[22 empty] | UPVC Fitting 300 mm | Material | M | 8 | 1 | 8 | 6.38 | 51.04
[22 empty] | Skilled Labor | Manpower | HR | 17 | 6 | 2.8333 | 1.0633 | 18.0767
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 6 | 2.1667 | 1.0633 | 13.8233
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 10 | 25 | 0.638 | 159.5
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 10 | 15 | 0.638 | 95.7
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.021267 | 3.7217
[9 empty] | 6.38 | 6.38 |  | 6.38 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 6.38 | 31.9 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 6.38 | 31.9
Circular pipes
Supply and installation of GRP pipes in trenches, including excavation, backfilling, compaction, waste removal, surface protection, reinforcement work, dividers, warning tapes, testing and commissioning upon completion in accordance with the plans, specifications and requirements of the concerned authority (backfilling work under and around the pipe is measured individually)
STR11 |  | Pipes with an inner diameter of 350 mm at a depth of 0 - 1.5 m | m | 22.5 | 386 | 8685 | 208.1661 | 4683.7364 | 22.5 | 22.5 |  | 22.5 | 100% | 386 | 8685 | 208.1661 | 4683.7364 |  | 4683.7364 | [7 empty] | 208.1661 | 22.5 | 4683.7364 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 22.5 | 22.5 |  | 22.5 | [9 empty] | Excavation ( W= 1.0 & d= 1.5 ) |  | M | 7.5827 |  | 7.5827 | 22.5 | 170.6114 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 66.6667 | 0.84 | 0.3375 | 18.9
[22 empty] | Fuel | Material | LTR | 1.76 | 4.7619 | 0.3696 | 4.725 | 8.316
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 13.6 | 3.5294 | 1.6544 | 79.4118
[22 empty] | Fuel | Material | LTR | 1.76 | 1.36 | 1.2941 | 16.5441 | 29.1176
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 0.45 | 10.35
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 1.35 | 2.376
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 66.6667 | 0.72 | 0.3375 | 16.2
[22 empty] | Fuel | Material | LTR | 1.76 | 6.6667 | 0.264 | 3.375 | 5.94
[9 empty] | 22.5 | 22.5 |  | 22.5 | [9 empty] | Pipe Laying & Protection |  | M | 195.5833 |  | 195.5833 | 22.5 | 4400.625 | 0 | 0 | 0 | 0 | 0
[22 empty] | GRP Pipe 350 mm | Material | M | 105 | 1 | 105 | 22.5 | 2362.5
[22 empty] | GRP Fitting 350 mm | Material | M | 10 | 1 | 10 | 22.5 | 225
[22 empty] | Workmanship GRP pipe 350 mm | SC | M | 40 | 1 | 40 | 22.5 | 900
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 10 | 25 | 2.25 | 562.5
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 10 | 15 | 2.25 | 337.5
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.075 | 13.125
[9 empty] | 22.5 | 22.5 |  | 22.5 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 22.5 | 112.5 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 22.5 | 112.5
STR11 |  | Pipes with an inner diameter of 350 mm at a depth of 1.5 - 2.0 m | m | 47.305 | 403 | 19063.9351 | 210.5051 | 9957.9546 | 47.305 | 47.305 |  | 47.305 | 100% | 403 | 19063.9351 | 210.5051 | 9957.9546 |  | 9957.9546 | [7 empty] | 210.5051 | 47.305 | 9957.9546 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 47.305 | 47.305 |  | 47.305 | [9 empty] | Excavation ( W= 1.0 & d= 2.0 ) |  | M | 9.9218 |  | 9.9218 | 47.305 | 469.3499 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 50 | 1.12 | 0.9461 | 52.9817
[22 empty] | Fuel | Material | LTR | 1.76 | 3.5714 | 0.4928 | 13.2454 | 23.3119
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 10.2 | 4.7059 | 4.6377 | 222.612
[22 empty] | Fuel | Material | LTR | 1.76 | 1.02 | 1.7255 | 46.3775 | 81.6244
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 0.9461 | 21.7603
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 2.8383 | 4.9954
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 50 | 0.96 | 0.9461 | 45.4128
[22 empty] | Fuel | Material | LTR | 1.76 | 5 | 0.352 | 9.461 | 16.6514
[9 empty] | 47.305 | 47.305 |  | 47.305 | [9 empty] | Pipe Laying & Protection |  | M | 195.5833 |  | 195.5833 | 47.305 | 9252.0794 | 0 | 0 | 0 | 0 | 0
[22 empty] | GRP Pipe 350 mm | Material | M | 105 | 1 | 105 | 47.305 | 4967.0302
[22 empty] | GRP Fitting 350 mm | Material | M | 10 | 1 | 10 | 47.305 | 473.0505
[22 empty] | Workmanship GRP pipe 350 mm | SC | M | 40 | 1 | 40 | 47.305 | 1892.202
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 10 | 25 | 4.7305 | 1182.6262
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 10 | 15 | 4.7305 | 709.5757
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.15768 | 27.5946
[9 empty] | 47.305 | 47.305 |  | 47.305 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 47.305 | 236.5252 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 47.305 | 236.5252
STR11 |  | Pipes with an inner diameter of 350 mm at a depth of 2.0 - 2.5 m | m | 17.707 | 418 | 7401.5051 | 247.8441 | 4388.564 | 17.707 | 17.707 |  | 17.707 | 100% | 418 | 7401.5051 | 247.8441 | 4388.564 |  | 4388.564 | [7 empty] | 247.8441 | 17.707 | 4388.564 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 17.707 | 17.707 |  | 17.707 | [9 empty] | Excavation ( W= 1.0 & d= 2.5 ) |  | M | 47.2608 |  | 47.2608 | 17.707 | 836.8449 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 40 | 1.4 | 0.44267 | 24.7897
[22 empty] | Fuel | Material | LTR | 1.76 | 2.8571 | 0.616 | 6.1974 | 10.9075
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 8.16 | 5.8824 | 2.17 | 104.1585
[22 empty] | Fuel | Material | LTR | 1.76 | 0.816 | 2.1569 | 21.6997 | 38.1915
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 0.35414 | 8.1452
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 1.0624 | 1.8699
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 40 | 1.2 | 0.44267 | 21.2483
[22 empty] | Fuel | Material | LTR | 1.76 | 4 | 0.44 | 4.4267 | 7.7911
[22 empty] | Steel Shoring D=2.5 M | Material | M | 35 | 1 | 35 | 17.707 | 619.7433
[9 empty] | 17.707 | 17.707 |  | 17.707 | [9 empty] | Pipe Laying & Protection |  | M | 195.5833 |  | 195.5833 | 17.707 | 3463.1843 | 0 | 0 | 0 | 0 | 0
[22 empty] | GRP Pipe 350 mm | Material | M | 105 | 1 | 105 | 17.707 | 1859.2298
[22 empty] | GRP Fitting 350 mm | Material | M | 10 | 1 | 10 | 17.707 | 177.0695
[22 empty] | Workmanship GRP pipe 350 mm | SC | M | 40 | 1 | 40 | 17.707 | 708.278
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 10 | 25 | 1.7707 | 442.6738
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 10 | 15 | 1.7707 | 265.6043
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.059023 | 10.3291
[9 empty] | 17.707 | 17.707 |  | 17.707 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 17.707 | 88.5348 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 17.707 | 88.5348
STR11 |  | Pipes with an inner diameter of 350 mm at a depth of 2.5 - 3.0 m | m | 35.75 | 545 | 19483.75 | 275.1832 | 9837.7991 | 35.75 | 35.75 |  | 35.75 | 100% | 545 | 19483.75 | 275.1832 | 9837.7991 |  | 9837.7991 | [7 empty] | 275.1832 | 35.75 | 9837.7991 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 35.75 | 35.75 |  | 35.75 | [9 empty] | Excavation ( W= 1.0 & d= 3.0 ) |  | M | 74.5999 |  | 74.5999 | 35.75 | 2666.945 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 33.3333 | 1.68 | 1.0725 | 60.06
[22 empty] | Fuel | Material | LTR | 1.76 | 2.381 | 0.7392 | 15.015 | 26.4264
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 6.8 | 7.0588 | 5.2574 | 252.3529
[22 empty] | Fuel | Material | LTR | 1.76 | 0.68 | 2.5882 | 52.5735 | 92.5294
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 0.715 | 16.445
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 2.145 | 3.7752
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 33.3333 | 1.44 | 1.0725 | 51.48
[22 empty] | Fuel | Material | LTR | 1.76 | 3.3333 | 0.528 | 10.725 | 18.876
[22 empty] | Steel Shoring D>3.0 M | Material | M | 60 | 1 | 60 | 35.75 | 2145
[9 empty] | 35.75 | 35.75 |  | 35.75 | [9 empty] | Pipe Laying & Protection |  | M | 195.5833 |  | 195.5833 | 35.75 | 6992.1042 | 0 | 0 | 0 | 0 | 0
[22 empty] | GRP Pipe 350 mm | Material | M | 105 | 1 | 105 | 35.75 | 3753.75
[22 empty] | GRP Fitting 350 mm | Material | M | 10 | 1 | 10 | 35.75 | 357.5
[22 empty] | Workmanship GRP pipe 350 mm | SC | M | 40 | 1 | 40 | 35.75 | 1430
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 10 | 25 | 3.575 | 893.75
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 10 | 15 | 3.575 | 536.25
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.11917 | 20.8542
[9 empty] | 35.75 | 35.75 |  | 35.75 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 35.75 | 178.75 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 35.75 | 178.75
STR11 |  | Pipes with an inner diameter of 350 mm at a depth of 3.0 - 3.5 m | m | 7.85 | 569 | 4466.65 | 277.5222 | 2178.5495 | 7.85 | 7.85 |  | 7.85 | 100% | 569 | 4466.65 | 277.5222 | 2178.5495 |  | 2178.5495 | [7 empty] | 277.5222 | 7.85 | 2178.5495 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 7.85 | 7.85 |  | 7.85 | [9 empty] | Excavation ( W= 1.0 & d= 3.5 ) |  | M | 76.9389 |  | 76.9389 | 7.85 | 603.9704 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 28.5714 | 1.96 | 0.27475 | 15.386
[22 empty] | Fuel | Material | LTR | 1.76 | 2.0408 | 0.8624 | 3.8465 | 6.7698
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 5.8286 | 8.2353 | 1.3468 | 64.6471
[22 empty] | Fuel | Material | LTR | 1.76 | 0.58286 | 3.0196 | 13.4681 | 23.7039
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 0.157 | 3.611
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 0.471 | 0.82896
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 28.5714 | 1.68 | 0.27475 | 13.188
[22 empty] | Fuel | Material | LTR | 1.76 | 2.8571 | 0.616 | 2.7475 | 4.8356
[22 empty] | Steel Shoring D>3.0 M | Material | M | 60 | 1 | 60 | 7.85 | 471
[9 empty] | 7.85 | 7.85 |  | 7.85 | [9 empty] | Pipe Laying & Protection |  | M | 195.5833 |  | 195.5833 | 7.85 | 1535.3292 | 0 | 0 | 0 | 0 | 0
[22 empty] | GRP Pipe 350 mm | Material | M | 105 | 1 | 105 | 7.85 | 824.25
[22 empty] | GRP Fitting 350 mm | Material | M | 10 | 1 | 10 | 7.85 | 78.5
[22 empty] | Workmanship GRP pipe 350 mm | SC | M | 40 | 1 | 40 | 7.85 | 314
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 10 | 25 | 0.785 | 196.25
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 10 | 15 | 0.785 | 117.75
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.026167 | 4.5792
[9 empty] | 7.85 | 7.85 |  | 7.85 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 7.85 | 39.25 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 7.85 | 39.25
STR11 |  | Pipes with an inner diameter of 350 mm at a depth of 3.5 - 4.0 m | m | 6.8459 | 720 | 4929.084 | 279.8613 | 1915.9163 | 6.8459 | 6.8459 |  | 6.8459 | 100% | 720 | 4929.084 | 279.8613 | 1915.9163 |  | 1915.9163 | [7 empty] | 279.8613 | 6.8459 | 1915.9163 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 6.8459 | 6.8459 |  | 6.8459 | [9 empty] | Excavation ( W= 1.0 & d= 4.0 ) |  | M | 79.2779 |  | 79.2779 | 6.8459 | 542.7328 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 25 | 2.24 | 0.27384 | 15.3349
[22 empty] | Fuel | Material | LTR | 1.76 | 1.7857 | 0.9856 | 3.8337 | 6.7474
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 5.1 | 9.4118 | 1.3423 | 64.4325
[22 empty] | Fuel | Material | LTR | 1.76 | 0.51 | 3.451 | 13.4234 | 23.6252
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 0.13692 | 3.1491
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 0.41076 | 0.72293
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 25 | 1.92 | 0.27384 | 13.1442
[22 empty] | Fuel | Material | LTR | 1.76 | 2.5 | 0.704 | 2.7384 | 4.8195
[22 empty] | Steel Shoring D>3.0 M | Material | M | 60 | 1 | 60 | 6.8459 | 410.757
[9 empty] | 6.8459 | 6.8459 |  | 6.8459 | [9 empty] | Pipe Laying & Protection |  | M | 195.5833 |  | 195.5833 | 6.8459 | 1338.9537 | 0 | 0 | 0 | 0 | 0
[22 empty] | GRP Pipe 350 mm | Material | M | 105 | 1 | 105 | 6.8459 | 718.8247
[22 empty] | GRP Fitting 350 mm | Material | M | 10 | 1 | 10 | 6.8459 | 68.4595
[22 empty] | Workmanship GRP pipe 350 mm | SC | M | 40 | 1 | 40 | 6.8459 | 273.838
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 10 | 25 | 0.68459 | 171.1487
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 10 | 15 | 0.68459 | 102.6892
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.02282 | 3.9935
[9 empty] | 6.8459 | 6.8459 |  | 6.8459 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 6.8459 | 34.2297 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 6.8459 | 34.2297
STR11 |  | Pipes with an inner diameter of 400 mm at a depth of 0 - 1.5 m | m |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Pipes with an inner diameter of 400 mm at a depth of 1.5 - 2.0 m | m | 97.274 | 535 | 52041.5633 | 274.3763 | 26689.6704 | 97.274 | 97.274 |  | 97.274 | 100% | 535 | 52041.5633 | 274.3763 | 26689.6704 |  | 26689.6704 | [7 empty] | 274.3763 | 97.274 | 26689.6704 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 97.274 | 97.274 |  | 97.274 | [9 empty] | Excavation ( W= 1.20 & d= 2.0 ) |  | M | 11.793 |  | 11.793 | 97.274 | 1147.1524 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 41.6667 | 1.344 | 2.3346 | 130.7362
[22 empty] | Fuel | Material | LTR | 1.76 | 2.9762 | 0.59136 | 32.684 | 57.5239
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 8.5 | 5.6471 | 11.444 | 549.3117
[22 empty] | Fuel | Material | LTR | 1.76 | 0.85 | 2.0706 | 114.4399 | 201.4143
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 1.9455 | 44.746
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 5.8364 | 10.2721
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 41.6667 | 1.152 | 2.3346 | 112.0596
[22 empty] | Fuel | Material | LTR | 1.76 | 4.1667 | 0.4224 | 23.3457 | 41.0885
[9 empty] | 97.274 | 97.274 |  | 97.274 | [9 empty] | Pipe Laying & Protection |  | M | 257.5833 |  | 257.5833 | 97.274 | 25056.1483 | 0 | 0 | 0 | 0 | 0
[22 empty] | GRP Pipe 400 mm | Material | M | 144 | 1 | 144 | 97.274 | 14007.4488
[22 empty] | GRP Fitting 400 mm | Material | M | 15 | 1 | 15 | 97.274 | 1459.1093
[22 empty] | Workmanship GRP pipe 400 mm | SC | M | 50 | 1 | 50 | 97.274 | 4863.6975
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 8.3333 | 30 | 11.6729 | 2918.2185
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 8.3333 | 18 | 11.6729 | 1750.9311
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.32425 | 56.7431
[9 empty] | 97.274 | 97.274 |  | 97.274 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 97.274 | 486.3698 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 97.274 | 486.3698
STR11 |  | Pipes with an inner diameter of 400 mm at a depth of 2.0 - 2.5 m | m | 119.3031 | 550 | 65616.705 | 312.1832 | 37244.4226 | 119.3031 | 119.3031 |  | 119.3031 | 100% | 550 | 65616.705 | 312.1832 | 37244.4226 |  | 37244.4226 | [7 empty] | 312.1832 | 119.3031 | 37244.4226 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 119.3031 | 119.3031 |  | 119.3031 | [9 empty] | Excavation ( W= 1.20 & d= 2.5 ) |  | M | 49.5999 |  | 49.5999 | 119.3031 | 5917.4169 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 33.3333 | 1.68 | 3.5791 | 200.4292
[22 empty] | Fuel | Material | LTR | 1.76 | 2.381 | 0.7392 | 50.1073 | 88.1889
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 6.8 | 7.0588 | 17.5446 | 842.1395
[22 empty] | Fuel | Material | LTR | 1.76 | 0.68 | 2.5882 | 175.4457 | 308.7845
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 2.3861 | 54.8794
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 7.1582 | 12.5984
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 33.3333 | 1.44 | 3.5791 | 171.7965
[22 empty] | Fuel | Material | LTR | 1.76 | 3.3333 | 0.528 | 35.7909 | 62.992
[22 empty] | Steel Shoring D=2.5 M | Material | M | 35 | 1 | 35 | 119.3031 | 4175.6085
[9 empty] | 119.3031 | 119.3031 |  | 119.3031 | [9 empty] | Pipe Laying & Protection |  | M | 257.5833 |  | 257.5833 | 119.3031 | 30730.4902 | 0 | 0 | 0 | 0 | 0
[22 empty] | GRP Pipe 400 mm | Material | M | 144 | 1 | 144 | 119.3031 | 17179.6464
[22 empty] | GRP Fitting 400 mm | Material | M | 15 | 1 | 15 | 119.3031 | 1789.5465
[22 empty] | Workmanship GRP pipe 400 mm | SC | M | 50 | 1 | 50 | 119.3031 | 5965.155
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 8.3333 | 30 | 14.3164 | 3579.093
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 8.3333 | 18 | 14.3164 | 2147.4558
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.39768 | 69.5935
[9 empty] | 119.3031 | 119.3031 |  | 119.3031 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 119.3031 | 596.5155 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 119.3031 | 596.5155
STR11 |  | Pipes with an inner diameter of 400 mm at a depth of 2.5 - 3.0 m | m | 98.0814 | 680 | 66695.318 | 339.99 | 33346.6825 | 98.0814 | 98.0814 |  | 98.0814 | 100% | 680 | 66695.318 | 339.99 | 33346.6825 |  | 33346.6825 | [7 empty] | 339.99 | 98.0814 | 33346.6825 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 98.0814 | 98.0814 |  | 98.0814 | [9 empty] | Excavation ( W= 1.20 & d= 3.0 ) |  | M | 77.4067 |  | 77.4067 | 98.0814 | 7592.1547 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 27.7778 | 2.016 | 3.5309 | 197.732
[22 empty] | Fuel | Material | LTR | 1.76 | 1.9841 | 0.88704 | 49.433 | 87.0021
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 5.6667 | 8.4706 | 17.3085 | 830.8067
[22 empty] | Fuel | Material | LTR | 1.76 | 0.56667 | 3.1059 | 173.0847 | 304.6291
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 1.9616 | 45.1174
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 5.8849 | 10.3574
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 27.7778 | 1.728 | 3.5309 | 169.4846
[22 empty] | Fuel | Material | LTR | 1.76 | 2.7778 | 0.6336 | 35.3093 | 62.1443
[22 empty] | Steel Shoring D>3.0 M | Material | M | 60 | 1 | 60 | 98.0814 | 5884.881
[9 empty] | 98.0814 | 98.0814 |  | 98.0814 | [9 empty] | Pipe Laying & Protection |  | M | 257.5833 |  | 257.5833 | 98.0814 | 25264.1211 | 0 | 0 | 0 | 0 | 0
[22 empty] | GRP Pipe 400 mm | Material | M | 144 | 1 | 144 | 98.0814 | 14123.7144
[22 empty] | GRP Fitting 400 mm | Material | M | 15 | 1 | 15 | 98.0814 | 1471.2203
[22 empty] | Workmanship GRP pipe 400 mm | SC | M | 50 | 1 | 50 | 98.0814 | 4904.0675
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 8.3333 | 30 | 11.7698 | 2942.4405
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 8.3333 | 18 | 11.7698 | 1765.4643
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.32694 | 57.2141
[9 empty] | 98.0814 | 98.0814 |  | 98.0814 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 98.0814 | 490.4068 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 98.0814 | 490.4068
STR11 |  | Pipes with an inner diameter of 400 mm at a depth of 3.0 - 3.5 m | m | 31.7139 | 831 | 26354.2509 | 342.7969 | 10871.4265 | 31.7139 | 31.7139 |  | 31.7139 | 100% | 831 | 26354.2509 | 342.7969 | 10871.4265 |  | 10871.4265 | [7 empty] | 342.7969 | 31.7139 | 10871.4265 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 31.7139 | 31.7139 |  | 31.7139 | [9 empty] | Excavation ( W= 1.20 & d= 3.5 ) |  | M | 80.2136 |  | 80.2136 | 31.7139 | 2543.8849 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 23.8095 | 2.352 | 1.332 | 74.5911
[22 empty] | Fuel | Material | LTR | 1.76 | 1.7007 | 1.0349 | 18.6478 | 32.8201
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 4.8571 | 9.8824 | 6.5293 | 313.408
[22 empty] | Fuel | Material | LTR | 1.76 | 0.48571 | 3.6235 | 65.2933 | 114.9162
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 0.63428 | 14.5884
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 1.9028 | 3.349
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 23.8095 | 2.016 | 1.332 | 63.9352
[22 empty] | Fuel | Material | LTR | 1.76 | 2.381 | 0.7392 | 13.3198 | 23.4429
[22 empty] | Steel Shoring D>3.0 M | Material | M | 60 | 1 | 60 | 31.7139 | 1902.834
[9 empty] | 31.7139 | 31.7139 |  | 31.7139 | [9 empty] | Pipe Laying & Protection |  | M | 257.5833 |  | 257.5833 | 31.7139 | 8168.9721 | 0 | 0 | 0 | 0 | 0
[22 empty] | GRP Pipe 400 mm | Material | M | 144 | 1 | 144 | 31.7139 | 4566.8016
[22 empty] | GRP Fitting 400 mm | Material | M | 15 | 1 | 15 | 31.7139 | 475.7085
[22 empty] | Workmanship GRP pipe 400 mm | SC | M | 50 | 1 | 50 | 31.7139 | 1585.695
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 8.3333 | 30 | 3.8057 | 951.417
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 8.3333 | 18 | 3.8057 | 570.8502
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.10571 | 18.4998
[9 empty] | 31.7139 | 31.7139 |  | 31.7139 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 31.7139 | 158.5695 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 31.7139 | 158.5695
STR11 |  | Pipes with an inner diameter of 400 mm at a depth of 3.5 - 4.0 m | m | 20.5905 | 856 | 17625.468 | 345.6037 | 7116.154 | 20.5905 | 20.5905 |  | 20.5905 | 100% | 856 | 17625.468 | 345.6037 | 7116.154 |  | 7116.154 | [7 empty] | 345.6037 | 20.5905 | 7116.154 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 20.5905 | 20.5905 |  | 20.5905 | [9 empty] | Excavation ( W= 1.20 & d= 4.0 ) |  | M | 83.0204 |  | 83.0204 | 20.5905 | 1709.4318 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 20.8333 | 2.688 | 0.98834 | 55.3473
[22 empty] | Fuel | Material | LTR | 1.76 | 1.4881 | 1.1827 | 13.8368 | 24.3528
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 4.25 | 11.2941 | 4.8448 | 232.5515
[22 empty] | Fuel | Material | LTR | 1.76 | 0.425 | 4.1412 | 48.4482 | 85.2689
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 0.41181 | 9.4716
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 1.2354 | 2.1744
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 20.8333 | 2.304 | 0.98834 | 47.4405
[22 empty] | Fuel | Material | LTR | 1.76 | 2.0833 | 0.8448 | 9.8834 | 17.3949
[22 empty] | Steel Shoring D>3.0 M | Material | M | 60 | 1 | 60 | 20.5905 | 1235.43
[9 empty] | 20.5905 | 20.5905 |  | 20.5905 | [9 empty] | Pipe Laying & Protection |  | M | 257.5833 |  | 257.5833 | 20.5905 | 5303.7696 | 0 | 0 | 0 | 0 | 0
[22 empty] | GRP Pipe 400 mm | Material | M | 144 | 1 | 144 | 20.5905 | 2965.032
[22 empty] | GRP Fitting 400 mm | Material | M | 15 | 1 | 15 | 20.5905 | 308.8575
[22 empty] | Workmanship GRP pipe 400 mm | SC | M | 50 | 1 | 50 | 20.5905 | 1029.525
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 8.3333 | 30 | 2.4709 | 617.715
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 8.3333 | 18 | 2.4709 | 370.629
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.068635 | 12.0111
[9 empty] | 20.5905 | 20.5905 |  | 20.5905 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 20.5905 | 102.9525 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 20.5905 | 102.9525
STR11 |  | Pipes with an inner diameter of 450 mm at a depth of 0 - 1.5 m | m |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Pipes with an inner diameter of 450 mm at a depth of 1.5 - 2.0 m | m | 38.1 | 558 | 21259.8 | 317.8441 | 12109.8621 | 38.1 | 38.1 |  | 38.1 | 100% | 558 | 21259.8 | 317.8441 | 12109.8621 |  | 12109.8621 | [7 empty] | 317.8441 | 38.1 | 12109.8621 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 38.1 | 38.1 |  | 38.1 | [9 empty] | Excavation ( W= 1.25 & d= 2.0 ) |  | M | 12.2608 |  | 12.2608 | 38.1 | 467.1371 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 40 | 1.4 | 0.9525 | 53.34
[22 empty] | Fuel | Material | LTR | 1.76 | 2.8571 | 0.616 | 13.335 | 23.4696
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 8.16 | 5.8824 | 4.6691 | 224.1176
[22 empty] | Fuel | Material | LTR | 1.76 | 0.816 | 2.1569 | 46.6912 | 82.1765
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 0.762 | 17.526
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 2.286 | 4.0234
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 40 | 1.2 | 0.9525 | 45.72
[22 empty] | Fuel | Material | LTR | 1.76 | 4 | 0.44 | 9.525 | 16.764
[9 empty] | 38.1 | 38.1 |  | 38.1 | [9 empty] | Pipe Laying & Protection |  | M | 300.5833 |  | 300.5833 | 38.1 | 11452.225 | 0 | 0 | 0 | 0 | 0
[22 empty] | GRP Pipe 450 mm | Material | M | 180 | 1 | 180 | 38.1 | 6858
[22 empty] | GRP Fitting 450 mm | Material | M | 18 | 1 | 18 | 38.1 | 685.8
[22 empty] | Workmanship GRP pipe 450 mm | SC | M | 52 | 1 | 52 | 38.1 | 1981.2
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 8 | 31.25 | 4.7625 | 1190.625
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 8 | 18.75 | 4.7625 | 714.375
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.127 | 22.225
[9 empty] | 38.1 | 38.1 |  | 38.1 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 38.1 | 190.5 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 38.1 | 190.5
STR11 |  | Pipes with an inner diameter of 450 mm at a depth of 2.0 - 2.5 m | m | 64.4101 | 572 | 36842.6058 | 355.768 | 22915.0672 | 64.4101 | 64.4101 |  | 64.4101 | 100% | 572 | 36842.6058 | 355.768 | 22915.0672 |  | 22915.0672 | [7 empty] | 355.768 | 64.4101 | 22915.0672 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 64.4101 | 64.4101 |  | 64.4101 | [9 empty] | Excavation ( W= 1.25 & d= 2.5 ) |  | M | 50.1846 |  | 50.1846 | 64.4101 | 3232.3989 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 32 | 1.75 | 2.0128 | 112.7178
[22 empty] | Fuel | Material | LTR | 1.76 | 2.2857 | 0.77 | 28.1794 | 49.5958
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 6.528 | 7.3529 | 9.8668 | 473.604
[22 empty] | Fuel | Material | LTR | 1.76 | 0.6528 | 2.6961 | 98.6675 | 173.6548
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 1.2882 | 29.6287
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 3.8646 | 6.8017
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 32 | 1.5 | 2.0128 | 96.6152
[22 empty] | Fuel | Material | LTR | 1.76 | 3.2 | 0.55 | 20.1282 | 35.4256
[22 empty] | Steel Shoring D=2.5 M | Material | M | 35 | 1 | 35 | 64.4101 | 2254.3552
[9 empty] | 64.4101 | 64.4101 |  | 64.4101 | [9 empty] | Pipe Laying & Protection |  | M | 300.5833 |  | 300.5833 | 64.4101 | 19360.6176 | 0 | 0 | 0 | 0 | 0
[22 empty] | GRP Pipe 450 mm | Material | M | 180 | 1 | 180 | 64.4101 | 11593.827
[22 empty] | GRP Fitting 450 mm | Material | M | 18 | 1 | 18 | 64.4101 | 1159.3827
[22 empty] | Workmanship GRP pipe 450 mm | SC | M | 52 | 1 | 52 | 64.4101 | 3349.3278
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 8 | 31.25 | 8.0513 | 2012.8172
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 8 | 18.75 | 8.0513 | 1207.6903
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.2147 | 37.5726
[9 empty] | 64.4101 | 64.4101 |  | 64.4101 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 64.4101 | 322.0507 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 64.4101 | 322.0507
STR11 |  | Pipes with an inner diameter of 450 mm at a depth of 2.5 - 3.0 m | m | 116.7132 | 702 | 81932.6313 | 383.6918 | 44781.8736 | 116.7132 | 116.7132 |  | 116.7132 | 100% | 702 | 81932.6313 | 383.6918 | 44781.8736 |  | 44781.8736 | [7 empty] | 383.6918 | 116.7132 | 44781.8736 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 116.7132 | 116.7132 |  | 116.7132 | [9 empty] | Excavation ( W= 1.25 & d= 3.0 ) |  | M | 78.1084 |  | 78.1084 | 116.7132 | 9116.2802 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 26.6667 | 2.1 | 4.3767 | 245.0976
[22 empty] | Fuel | Material | LTR | 1.76 | 1.9048 | 0.924 | 61.2744 | 107.843
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 5.44 | 8.8235 | 21.4546 | 1029.8219
[22 empty] | Fuel | Material | LTR | 1.76 | 0.544 | 3.2353 | 214.5462 | 377.6014
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 2.3343 | 53.688
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 7.0028 | 12.3249
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 26.6667 | 1.8 | 4.3767 | 210.0837
[22 empty] | Fuel | Material | LTR | 1.76 | 2.6667 | 0.66 | 43.7674 | 77.0307
[22 empty] | Steel Shoring D>3.0 M | Material | M | 60 | 1 | 60 | 116.7132 | 7002.789
[9 empty] | 116.7132 | 116.7132 |  | 116.7132 | [9 empty] | Pipe Laying & Protection |  | M | 300.5833 |  | 300.5833 | 116.7132 | 35082.0277 | 0 | 0 | 0 | 0 | 0
[22 empty] | GRP Pipe 450 mm | Material | M | 180 | 1 | 180 | 116.7132 | 21008.367
[22 empty] | GRP Fitting 450 mm | Material | M | 18 | 1 | 18 | 116.7132 | 2100.8367
[22 empty] | Workmanship GRP pipe 450 mm | SC | M | 52 | 1 | 52 | 116.7132 | 6069.0838
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 8 | 31.25 | 14.5891 | 3647.2859
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 8 | 18.75 | 14.5891 | 2188.3716
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.38904 | 68.0827
[9 empty] | 116.7132 | 116.7132 |  | 116.7132 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 116.7132 | 583.5658 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 116.7132 | 583.5658
STR11 |  | Pipes with an inner diameter of 450 mm at a depth of 3.0 - 3.5 m | m | 50.3122 | 919 | 46236.9118 | 386.6156 | 19451.4794 | 50.3122 | 50.3122 |  | 50.3122 | 100% | 919 | 46236.9118 | 386.6156 | 19451.4794 |  | 19451.4794 | [7 empty] | 386.6156 | 50.3122 | 19451.4794 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 50.3122 | 50.3122 |  | 50.3122 | [9 empty] | Excavation ( W= 1.25 & d= 3.5 ) |  | M | 81.0322 |  | 81.0322 | 50.3122 | 4076.9096 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 22.8571 | 2.45 | 2.2012 | 123.2649
[22 empty] | Fuel | Material | LTR | 1.76 | 1.6327 | 1.078 | 30.8162 | 54.2366
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 4.6629 | 10.2941 | 10.79 | 517.9197
[22 empty] | Fuel | Material | LTR | 1.76 | 0.46629 | 3.7745 | 107.8999 | 189.9039
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 1.0062 | 23.1436
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 3.0187 | 5.313
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 22.8571 | 2.1 | 2.2012 | 105.6556
[22 empty] | Fuel | Material | LTR | 1.76 | 2.2857 | 0.77 | 22.0116 | 38.7404
[22 empty] | Steel Shoring D>3.0 M | Material | M | 60 | 1 | 60 | 50.3122 | 3018.732
[9 empty] | 50.3122 | 50.3122 |  | 50.3122 | [9 empty] | Pipe Laying & Protection |  | M | 300.5833 |  | 300.5833 | 50.3122 | 15123.0088 | 0 | 0 | 0 | 0 | 0
[22 empty] | GRP Pipe 450 mm | Material | M | 180 | 1 | 180 | 50.3122 | 9056.196
[22 empty] | GRP Fitting 450 mm | Material | M | 18 | 1 | 18 | 50.3122 | 905.6196
[22 empty] | Workmanship GRP pipe 450 mm | SC | M | 52 | 1 | 52 | 50.3122 | 2616.2344
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 8 | 31.25 | 6.289 | 1572.2562
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 8 | 18.75 | 6.289 | 943.3537
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.16771 | 29.3488
[9 empty] | 50.3122 | 50.3122 |  | 50.3122 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 50.3122 | 251.561 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 50.3122 | 251.561
STR11 |  | Pipes with an inner diameter of 450 mm at a depth of 3.5 - 4.0 m | m |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Pipes with an inner diameter of 500 mm at a depth of 0 - 1.5 m | m | 89.062 | 610 | 54327.82 | 406.6746 | 36219.2557 | 89.062 | 89.062 |  | 89.062 | 100% | 610 | 54327.82 | 406.6746 | 36219.2557 |  | 36219.2557 | [7 empty] | 406.6746 | 89.062 | 36219.2557 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 89.062 | 89.062 |  | 89.062 | [9 empty] | Excavation ( W= 1.5 & d= 1.5 ) |  | M | 11.0913 |  | 11.0913 | 89.062 | 987.8128 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 44.4444 | 1.26 | 2.0039 | 112.2181
[22 empty] | Fuel | Material | LTR | 1.76 | 3.1746 | 0.5544 | 28.0545 | 49.376
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 9.0667 | 5.2941 | 9.823 | 471.5047
[22 empty] | Fuel | Material | LTR | 1.76 | 0.90667 | 1.9412 | 98.2301 | 172.8851
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 1.7812 | 40.9685
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 5.3437 | 9.4049
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 44.4444 | 1.08 | 2.0039 | 96.187
[22 empty] | Fuel | Material | LTR | 1.76 | 4.4444 | 0.396 | 20.0389 | 35.2686
[9 empty] | 89.062 | 89.062 |  | 89.062 | [9 empty] | Pipe Laying & Protection |  | M | 390.5833 |  | 390.5833 | 89.062 | 34786.1328 | 0 | 0 | 0 | 0 | 0
[22 empty] | GRP Pipe 500 mm | Material | M | 250 | 1 | 250 | 89.062 | 22265.5
[22 empty] | GRP Fitting 500 mm | Material | M | 25 | 1 | 25 | 89.062 | 2226.55
[22 empty] | Workmanship GRP pipe 500 mm | SC | M | 55 | 1 | 55 | 89.062 | 4898.41
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 6.6667 | 37.5 | 13.3593 | 3339.825
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 6.6667 | 22.5 | 13.3593 | 2003.895
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.29687 | 51.9528
[9 empty] | 89.062 | 89.062 |  | 89.062 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 89.062 | 445.31 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 89.062 | 445.31
STR11 |  | Pipes with an inner diameter of 500 mm at a depth of 1.5 - 2.0 m | m | 2.9261 | 629 | 1840.5483 | 410.1832 | 1200.2575 | 2.9261 | 2.9261 |  | 2.9261 | 100% | 629 | 1840.5483 | 410.1832 | 1200.2575 |  | 1200.2575 | [7 empty] | 410.1832 | 2.9261 | 1200.2575 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 2.9261 | 2.9261 |  | 2.9261 | [9 empty] | Excavation ( W= 1.5 & d= 2.0 ) |  | M | 14.5999 |  | 14.5999 | 2.9261 | 42.7214 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 33.3333 | 1.68 | 0.087784 | 4.9159
[22 empty] | Fuel | Material | LTR | 1.76 | 2.381 | 0.7392 | 1.229 | 2.163
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 6.8 | 7.0588 | 0.43032 | 20.6552
[22 empty] | Fuel | Material | LTR | 1.76 | 0.68 | 2.5882 | 4.3032 | 7.5736
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 0.058523 | 1.346
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 0.17557 | 0.309
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 33.3333 | 1.44 | 0.087784 | 4.2137
[22 empty] | Fuel | Material | LTR | 1.76 | 3.3333 | 0.528 | 0.87784 | 1.545
[9 empty] | 2.9261 | 2.9261 |  | 2.9261 | [9 empty] | Pipe Laying & Protection |  | M | 390.5833 |  | 390.5833 | 2.9261 | 1142.9054 | 0 | 0 | 0 | 0 | 0
[22 empty] | GRP Pipe 500 mm | Material | M | 250 | 1 | 250 | 2.9261 | 731.5375
[22 empty] | GRP Fitting 500 mm | Material | M | 25 | 1 | 25 | 2.9261 | 73.1538
[22 empty] | Workmanship GRP pipe 500 mm | SC | M | 55 | 1 | 55 | 2.9261 | 160.9382
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 6.6667 | 37.5 | 0.43892 | 109.7306
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 6.6667 | 22.5 | 0.43892 | 65.8384
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.0097538 | 1.7069
[9 empty] | 2.9261 | 2.9261 |  | 2.9261 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 2.9261 | 14.6307 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 2.9261 | 14.6307
STR11 |  | Pipes with an inner diameter of 500 mm at a depth of 2.0 - 2.5 m | m | 141.7987 | 694 | 98408.2631 | 448.6918 | 63623.8854 | 141.7987 | 141.7987 |  | 141.7987 | 100% | 694 | 98408.2631 | 448.6918 | 63623.8854 |  | 63623.8854 | [7 empty] | 448.6918 | 141.7987 | 63623.8854 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 141.7987 | 141.7987 |  | 141.7987 | [9 empty] | Excavation ( W= 1.5 & d= 2.5 ) |  | M | 53.1084 |  | 53.1084 | 141.7987 | 7530.7028 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 26.6667 | 2.1 | 5.3174 | 297.7772
[22 empty] | Fuel | Material | LTR | 1.76 | 1.9048 | 0.924 | 74.4443 | 131.022
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 5.44 | 8.8235 | 26.0659 | 1251.1646
[22 empty] | Fuel | Material | LTR | 1.76 | 0.544 | 3.2353 | 260.6593 | 458.7603
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 2.836 | 65.2274
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 8.5079 | 14.9739
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 26.6667 | 1.8 | 5.3174 | 255.2376
[22 empty] | Fuel | Material | LTR | 1.76 | 2.6667 | 0.66 | 53.1745 | 93.5871
[22 empty] | Steel Shoring D=2.5 M | Material | M | 35 | 1 | 35 | 141.7987 | 4962.9528
[9 empty] | 141.7987 | 141.7987 |  | 141.7987 | [9 empty] | Pipe Laying & Protection |  | M | 390.5833 |  | 390.5833 | 141.7987 | 55384.1894 | 0 | 0 | 0 | 0 | 0
[22 empty] | GRP Pipe 500 mm | Material | M | 250 | 1 | 250 | 141.7987 | 35449.6625
[22 empty] | GRP Fitting 500 mm | Material | M | 25 | 1 | 25 | 141.7987 | 3544.9663
[22 empty] | Workmanship GRP pipe 500 mm | SC | M | 55 | 1 | 55 | 141.7987 | 7798.9258
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 6.6667 | 37.5 | 21.2698 | 5317.4494
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 6.6667 | 22.5 | 21.2698 | 3190.4696
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.47266 | 82.7159
[9 empty] | 141.7987 | 141.7987 |  | 141.7987 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 141.7987 | 708.9933 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 141.7987 | 708.9933
STR11 |  | Pipes with an inner diameter of 500 mm at a depth of 2.5 - 3.0 m | m | 146.9924 | 778 | 114360.0872 | 477.2003 | 70144.8205 | 146.9924 | 146.9924 |  | 146.9924 | 100% | 778 | 114360.0872 | 477.2003 | 70144.8205 |  | 70144.8205 | [7 empty] | 477.2003 | 146.9924 | 70144.8205 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 146.9924 | 146.9924 |  | 146.9924 | [9 empty] | Excavation ( W= 1.5 & d= 3.0 ) |  | M | 81.617 |  | 81.617 | 146.9924 | 11997.077 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 22.2222 | 2.52 | 6.6147 | 370.4208
[22 empty] | Fuel | Material | LTR | 1.76 | 1.5873 | 1.1088 | 92.6052 | 162.9852
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 4.5333 | 10.5882 | 32.4248 | 1556.3901
[22 empty] | Fuel | Material | LTR | 1.76 | 0.45333 | 3.8824 | 324.2479 | 570.6764
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 2.9398 | 67.6165
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 8.8195 | 15.5224
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 22.2222 | 2.16 | 6.6147 | 317.5036
[22 empty] | Fuel | Material | LTR | 1.76 | 2.2222 | 0.792 | 66.1466 | 116.418
[22 empty] | Steel Shoring D>3.0 M | Material | M | 60 | 1 | 60 | 146.9924 | 8819.544
[9 empty] | 146.9924 | 146.9924 |  | 146.9924 | [9 empty] | Pipe Laying & Protection |  | M | 390.5833 |  | 390.5833 | 146.9924 | 57412.7816 | 0 | 0 | 0 | 0 | 0
[22 empty] | GRP Pipe 500 mm | Material | M | 250 | 1 | 250 | 146.9924 | 36748.1
[22 empty] | GRP Fitting 500 mm | Material | M | 25 | 1 | 25 | 146.9924 | 3674.81
[22 empty] | Workmanship GRP pipe 500 mm | SC | M | 55 | 1 | 55 | 146.9924 | 8084.582
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 6.6667 | 37.5 | 22.0489 | 5512.215
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 6.6667 | 22.5 | 22.0489 | 3307.329
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.48997 | 85.7456
[9 empty] | 146.9924 | 146.9924 |  | 146.9924 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 146.9924 | 734.962 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 146.9924 | 734.962
STR11 |  | Pipes with an inner diameter of 500 mm at a depth of 3.0 - 3.5 m | m | 28.8517 | 805 | 23225.6185 | 480.7089 | 13869.2686 | 28.8517 | 28.8517 |  | 28.8517 | 100% | 805 | 23225.6185 | 480.7089 | 13869.2686 |  | 13869.2686 | [7 empty] | 480.7089 | 28.8517 | 13869.2686 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 28.8517 | 28.8517 |  | 28.8517 | [9 empty] | Excavation ( W= 1.5 & d= 3.5 ) |  | M | 85.1256 |  | 85.1256 | 28.8517 | 2456.0169 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 19.0476 | 2.94 | 1.5147 | 84.824
[22 empty] | Fuel | Material | LTR | 1.76 | 1.3605 | 1.2936 | 21.206 | 37.3226
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 3.8857 | 12.3529 | 7.4251 | 356.4034
[22 empty] | Fuel | Material | LTR | 1.76 | 0.38857 | 4.5294 | 74.2507 | 130.6812
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 0.57703 | 13.2718
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 1.7311 | 3.0467
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 19.0476 | 2.52 | 1.5147 | 72.7063
[22 empty] | Fuel | Material | LTR | 1.76 | 1.9048 | 0.924 | 15.1471 | 26.659
[22 empty] | Steel Shoring D>3.0 M | Material | M | 60 | 1 | 60 | 28.8517 | 1731.102
[9 empty] | 28.8517 | 28.8517 |  | 28.8517 | [9 empty] | Pipe Laying & Protection |  | M | 390.5833 |  | 390.5833 | 28.8517 | 11268.9932 | 0 | 0 | 0 | 0 | 0
[22 empty] | GRP Pipe 500 mm | Material | M | 250 | 1 | 250 | 28.8517 | 7212.925
[22 empty] | GRP Fitting 500 mm | Material | M | 25 | 1 | 25 | 28.8517 | 721.2925
[22 empty] | Workmanship GRP pipe 500 mm | SC | M | 55 | 1 | 55 | 28.8517 | 1586.8435
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 6.6667 | 37.5 | 4.3278 | 1081.9387
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 6.6667 | 22.5 | 4.3278 | 649.1632
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.096172 | 16.8302
[9 empty] | 28.8517 | 28.8517 |  | 28.8517 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 28.8517 | 144.2585 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 28.8517 | 144.2585
STR11 |  | Pipes with an inner diameter of 500 mm at a depth of 3.5 - 4.0 m | m | 7.1 | 957 | 6794.7 | 484.2175 | 3437.9439 | 7.1 | 7.1 |  | 7.1 | 100% | 957 | 6794.7 | 484.2175 | 3437.9439 |  | 3437.9439 | [7 empty] | 484.2175 | 7.1 | 3437.9439 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 7.1 | 7.1 |  | 7.1 | [9 empty] | Excavation ( W= 1.5 & d= 4.0 ) |  | M | 88.6341 |  | 88.6341 | 7.1 | 629.3022 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 16.6667 | 3.36 | 0.426 | 23.856
[22 empty] | Fuel | Material | LTR | 1.76 | 1.1905 | 1.4784 | 5.964 | 10.4966
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 3.4 | 14.1176 | 2.0882 | 100.2353
[22 empty] | Fuel | Material | LTR | 1.76 | 0.34 | 5.1765 | 20.8824 | 36.7529
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 0.142 | 3.266
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 0.426 | 0.74976
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 16.6667 | 2.88 | 0.426 | 20.448
[22 empty] | Fuel | Material | LTR | 1.76 | 1.6667 | 1.056 | 4.26 | 7.4976
[22 empty] | Steel Shoring D>3.0 M | Material | M | 60 | 1 | 60 | 7.1 | 426
[9 empty] | 7.1 | 7.1 |  | 7.1 | [9 empty] | Pipe Laying & Protection |  | M | 390.5833 |  | 390.5833 | 7.1 | 2773.1417 | 0 | 0 | 0 | 0 | 0
[22 empty] | GRP Pipe 500 mm | Material | M | 250 | 1 | 250 | 7.1 | 1775
[22 empty] | GRP Fitting 500 mm | Material | M | 25 | 1 | 25 | 7.1 | 177.5
[22 empty] | Workmanship GRP pipe 500 mm | SC | M | 55 | 1 | 55 | 7.1 | 390.5
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 6.6667 | 37.5 | 1.065 | 266.25
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 6.6667 | 22.5 | 1.065 | 159.75
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.023667 | 4.1417
[9 empty] | 7.1 | 7.1 |  | 7.1 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 7.1 | 35.5 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 7.1 | 35.5
STR11 |  | Pipes with an inner diameter of 600 mm at a depth of 0 - 1.5 m | m |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Pipes with an inner diameter of 600 mm at a depth of 1.5 - 2.0 m | m | 12.2029 | 735 | 8969.1682 | 464.1188 | 5663.6186 | 12.2029 | 12.2029 |  | 12.2029 | 100% | 735 | 8969.1682 | 464.1188 | 5663.6186 |  | 5663.6186 | [7 empty] | 464.1188 | 12.2029 | 5663.6186 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 12.2029 | 12.2029 |  | 12.2029 | [9 empty] | Excavation ( W= 1.6 & d= 2.0 ) |  | M | 15.5355 |  | 15.5355 | 12.2029 | 189.5786 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 31.25 | 1.792 | 0.39049 | 21.8677
[22 empty] | Fuel | Material | LTR | 1.76 | 2.2321 | 0.78848 | 5.4669 | 9.6218
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 6.375 | 7.5294 | 1.9142 | 91.881
[22 empty] | Fuel | Material | LTR | 1.76 | 0.6375 | 2.7608 | 19.1419 | 33.6897
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 0.24406 | 5.6134
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 0.73218 | 1.2886
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 31.25 | 1.536 | 0.39049 | 18.7437
[22 empty] | Fuel | Material | LTR | 1.76 | 3.125 | 0.5632 | 3.9049 | 6.8727
[9 empty] | 12.2029 | 12.2029 |  | 12.2029 | [9 empty] | Pipe Laying & Protection |  | M | 443.5833 |  | 443.5833 | 12.2029 | 5413.0252 | 0 | 0 | 0 | 0 | 0
[22 empty] | GRP Pipe 600 mm | Material | M | 290 | 1 | 290 | 12.2029 | 3538.8555
[22 empty] | GRP Fitting 600 mm | Material | M | 29 | 1 | 29 | 12.2029 | 353.8855
[22 empty] | Workmanship GRP pipe 600 mm | SC | M | 60 | 1 | 60 | 12.2029 | 732.177
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 6.25 | 40 | 1.9525 | 488.118
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 6.25 | 24 | 1.9525 | 292.8708
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.040676 | 7.1184
[9 empty] | 12.2029 | 12.2029 |  | 12.2029 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 12.2029 | 61.0147 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 12.2029 | 61.0147
STR11 |  | Pipes with an inner diameter of 600 mm at a depth of 2.0 - 2.5 m | m | 142.2742 | 802 | 114103.8683 | 502.8613 | 71544.161 | 142.2742 | 142.2742 |  | 142.2742 | 100% | 802 | 114103.8683 | 502.8613 | 71544.161 |  | 71544.161 | [7 empty] | 502.8613 | 142.2742 | 71544.161 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 142.2742 | 142.2742 |  | 142.2742 | [9 empty] | Excavation ( W= 1.6 & d= 2.5 ) |  | M | 54.2779 |  | 54.2779 | 142.2742 | 7722.3485 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 25 | 2.24 | 5.691 | 318.6941
[22 empty] | Fuel | Material | LTR | 1.76 | 1.7857 | 0.9856 | 79.6735 | 140.2254
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 5.1 | 9.4118 | 27.8969 | 1339.0508
[22 empty] | Fuel | Material | LTR | 1.76 | 0.51 | 3.451 | 278.9689 | 490.9853
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 2.8455 | 65.4461
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 8.5364 | 15.0242
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 25 | 1.92 | 5.691 | 273.1664
[22 empty] | Fuel | Material | LTR | 1.76 | 2.5 | 0.704 | 56.9097 | 100.161
[22 empty] | Steel Shoring D=2.5 M | Material | M | 35 | 1 | 35 | 142.2742 | 4979.5953
[9 empty] | 142.2742 | 142.2742 |  | 142.2742 | [9 empty] | Pipe Laying & Protection |  | M | 443.5833 |  | 443.5833 | 142.2742 | 63110.4417 | 0 | 0 | 0 | 0 | 0
[22 empty] | GRP Pipe 600 mm | Material | M | 290 | 1 | 290 | 142.2742 | 41259.5035
[22 empty] | GRP Fitting 600 mm | Material | M | 29 | 1 | 29 | 142.2742 | 4125.9504
[22 empty] | Workmanship GRP pipe 600 mm | SC | M | 60 | 1 | 60 | 142.2742 | 8536.449
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 6.25 | 40 | 22.7639 | 5690.966
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 6.25 | 24 | 22.7639 | 3414.5796
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.47425 | 82.9933
[9 empty] | 142.2742 | 142.2742 |  | 142.2742 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 142.2742 | 711.3708 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 142.2742 | 711.3708
STR11 |  | Pipes with an inner diameter of 600 mm at a depth of 2.5 - 3.0 m | m | 113.8975 | 831 | 94648.8225 | 531.6037 | 60548.3378 | 113.8975 | 113.8975 |  | 113.8975 | 100% | 831 | 94648.8225 | 531.6037 | 60548.3378 |  | 60548.3378 | [7 empty] | 531.6037 | 113.8975 | 60548.3378 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 113.8975 | 113.8975 |  | 113.8975 | [9 empty] | Excavation ( W= 1.6 & d= 3.0 ) |  | M | 83.0204 |  | 83.0204 | 113.8975 | 9455.8176 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 20.8333 | 2.688 | 5.4671 | 306.1565
[22 empty] | Fuel | Material | LTR | 1.76 | 1.4881 | 1.1827 | 76.5391 | 134.7089
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 4.25 | 11.2941 | 26.7994 | 1286.3718
[22 empty] | Fuel | Material | LTR | 1.76 | 0.425 | 4.1412 | 267.9941 | 471.6696
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 2.278 | 52.3929
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 6.8339 | 12.0276
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 20.8333 | 2.304 | 5.4671 | 262.4198
[22 empty] | Fuel | Material | LTR | 1.76 | 2.0833 | 0.8448 | 54.6708 | 96.2206
[22 empty] | Steel Shoring D>3.0 M | Material | M | 60 | 1 | 60 | 113.8975 | 6833.85
[9 empty] | 113.8975 | 113.8975 |  | 113.8975 | [9 empty] | Pipe Laying & Protection |  | M | 443.5833 |  | 443.5833 | 113.8975 | 50523.0327 | 0 | 0 | 0 | 0 | 0
[22 empty] | GRP Pipe 600 mm | Material | M | 290 | 1 | 290 | 113.8975 | 33030.275
[22 empty] | GRP Fitting 600 mm | Material | M | 29 | 1 | 29 | 113.8975 | 3303.0275
[22 empty] | Workmanship GRP pipe 600 mm | SC | M | 60 | 1 | 60 | 113.8975 | 6833.85
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 6.25 | 40 | 18.2236 | 4555.9
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 6.25 | 24 | 18.2236 | 2733.54
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.37966 | 66.4402
[9 empty] | 113.8975 | 113.8975 |  | 113.8975 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 113.8975 | 569.4875 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 113.8975 | 569.4875
STR11 |  | Pipes with an inner diameter of 600 mm at a depth of 3.0 - 3.5 m | m | 49.5605 | 915 | 45347.9032 | 535.3462 | 26532.0529 | 49.5605 | 49.5605 |  | 49.5605 | 100% | 915 | 45347.9032 | 535.3462 | 26532.0529 |  | 26532.0529 | [7 empty] | 535.3462 | 49.5605 | 26532.0529 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 49.5605 | 49.5605 |  | 49.5605 | [9 empty] | Excavation ( W= 1.6 & d= 3.5 ) |  | M | 86.7629 |  | 86.7629 | 49.5605 | 4300.0162 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 17.8571 | 3.136 | 2.7754 | 155.4219
[22 empty] | Fuel | Material | LTR | 1.76 | 1.2755 | 1.3798 | 38.8555 | 68.3856
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 3.6429 | 13.1765 | 13.6049 | 653.0331
[22 empty] | Fuel | Material | LTR | 1.76 | 0.36429 | 4.8314 | 136.0486 | 239.4455
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 0.99121 | 22.7979
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 2.9736 | 5.2336
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 17.8571 | 2.688 | 2.7754 | 133.2188
[22 empty] | Fuel | Material | LTR | 1.76 | 1.7857 | 0.9856 | 27.7539 | 48.8469
[22 empty] | Steel Shoring D>3.0 M | Material | M | 60 | 1 | 60 | 49.5605 | 2973.633
[9 empty] | 49.5605 | 49.5605 |  | 49.5605 | [9 empty] | Pipe Laying & Protection |  | M | 443.5833 |  | 443.5833 | 49.5605 | 21984.234 | 0 | 0 | 0 | 0 | 0
[22 empty] | GRP Pipe 600 mm | Material | M | 290 | 1 | 290 | 49.5605 | 14372.5595
[22 empty] | GRP Fitting 600 mm | Material | M | 29 | 1 | 29 | 49.5605 | 1437.2559
[22 empty] | Workmanship GRP pipe 600 mm | SC | M | 60 | 1 | 60 | 49.5605 | 2973.633
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 6.25 | 40 | 7.9297 | 1982.422
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 6.25 | 24 | 7.9297 | 1189.4532
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.1652 | 28.9103
[9 empty] | 49.5605 | 49.5605 |  | 49.5605 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 49.5605 | 247.8027 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 49.5605 | 247.8027
STR11 |  | Pipes with an inner diameter of 600 mm at a depth of 3.5 - 4.0 m | m | 9.775 | 1070 | 10459.3035 | 539.0887 | 5269.6189 | 9.775 | 9.775 |  | 9.775 | 100% | 1070 | 10459.3035 | 539.0887 | 5269.6189 |  | 5269.6189 | [7 empty] | 539.0887 | 9.775 | 5269.6189 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 9.775 | 9.775 |  | 9.775 | [9 empty] | Excavation ( W= 1.6 & d= 4.0 ) |  | M | 90.5054 |  | 90.5054 | 9.775 | 884.6943 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 15.625 | 3.584 | 0.6256 | 35.0338
[22 empty] | Fuel | Material | LTR | 1.76 | 1.1161 | 1.577 | 8.7584 | 15.4149
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 3.1875 | 15.0588 | 3.0667 | 147.2008
[22 empty] | Fuel | Material | LTR | 1.76 | 0.31875 | 5.5216 | 30.6668 | 53.9736
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 0.1955 | 4.4965
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 0.5865 | 1.0322
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 15.625 | 3.072 | 0.6256 | 30.029
[22 empty] | Fuel | Material | LTR | 1.76 | 1.5625 | 1.1264 | 6.256 | 11.0106
[22 empty] | Steel Shoring D>3.0 M | Material | M | 60 | 1 | 60 | 9.775 | 586.503
[9 empty] | 9.775 | 9.775 |  | 9.775 | [9 empty] | Pipe Laying & Protection |  | M | 443.5833 |  | 443.5833 | 9.775 | 4336.0493 | 0 | 0 | 0 | 0 | 0
[22 empty] | GRP Pipe 600 mm | Material | M | 290 | 1 | 290 | 9.775 | 2834.7645
[22 empty] | GRP Fitting 600 mm | Material | M | 29 | 1 | 29 | 9.775 | 283.4764
[22 empty] | Workmanship GRP pipe 600 mm | SC | M | 60 | 1 | 60 | 9.775 | 586.503
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 6.25 | 40 | 1.564 | 391.002
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 6.25 | 24 | 1.564 | 234.6012
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.032583 | 5.7021
[9 empty] | 9.775 | 9.775 |  | 9.775 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 9.775 | 48.8752 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 9.775 | 48.8752
STR11 |  | Pipes with an inner diameter of 700 mm at a depth of 0 - 1.5 m | m |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Pipes with an inner diameter of 700 mm at a depth of 1.5 - 2.0 m | m | 33.19 | 893 | 29638.67 | 540.0544 | 17924.4064 | 33.19 | 33.19 |  | 33.19 | 100% | 893 | 29638.67 | 540.0544 | 17924.4064 |  | 17924.4064 | [7 empty] | 540.0544 | 33.19 | 17924.4064 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 33.19 | 33.19 |  | 33.19 | [9 empty] | Excavation ( W= 1.7 & d= 2.0 ) |  | M | 16.4711 |  | 16.4711 | 33.19 | 546.6756 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 29.4118 | 1.904 | 1.1285 | 63.1938
[22 empty] | Fuel | Material | LTR | 1.76 | 2.1008 | 0.83776 | 15.7984 | 27.8053
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 6 | 8 | 5.5317 | 265.52
[22 empty] | Fuel | Material | LTR | 1.76 | 0.6 | 2.9333 | 55.3167 | 97.3573
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 0.6638 | 15.2674
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 1.9914 | 3.5049
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 29.4118 | 1.632 | 1.1285 | 54.1661
[22 empty] | Fuel | Material | LTR | 1.76 | 2.9412 | 0.5984 | 11.2846 | 19.8609
[9 empty] | 33.19 | 33.19 |  | 33.19 | [9 empty] | Pipe Laying & Protection |  | M | 518.5833 |  | 518.5833 | 33.19 | 17211.7808 | 0 | 0 | 0 | 0 | 0
[22 empty] | GRP Pipe 700 mm | Material | M | 350 | 1 | 350 | 33.19 | 11616.5
[22 empty] | GRP Fitting 700 mm | Material | M | 35 | 1 | 35 | 33.19 | 1161.65
[22 empty] | Workmanship GRP pipe 700 mm | SC | M | 65 | 1 | 65 | 33.19 | 2157.35
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 5.8824 | 42.5 | 5.6423 | 1410.575
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 5.8824 | 25.5 | 5.6423 | 846.345
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.11063 | 19.3608
[9 empty] | 33.19 | 33.19 |  | 33.19 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 33.19 | 165.95 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 33.19 | 165.95
STR11 |  | Pipes with an inner diameter of 700 mm at a depth of 2.0 - 2.5 m | m | 109.6897 | 959 | 105192.3744 | 579.0308 | 63513.6858 | 109.6897 | 109.6897 |  | 109.6897 | 100% | 959 | 105192.3744 | 579.0308 | 63513.6858 |  | 63513.6858 | [7 empty] | 579.0308 | 109.6897 | 63513.6858 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 109.6897 | 109.6897 |  | 109.6897 | [9 empty] | Excavation ( W= 1.7 & d= 2.5 ) |  | M | 55.4475 |  | 55.4475 | 109.6897 | 6082.0132 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 23.5294 | 2.38 | 4.6618 | 261.0614
[22 empty] | Fuel | Material | LTR | 1.76 | 1.6807 | 1.0472 | 65.2653 | 114.867
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 4.8 | 10 | 22.852 | 1096.8965
[22 empty] | Fuel | Material | LTR | 1.76 | 0.48 | 3.6667 | 228.5201 | 402.1954
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 2.1938 | 50.4572
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 6.5814 | 11.5832
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 23.5294 | 2.04 | 4.6618 | 223.7669
[22 empty] | Fuel | Material | LTR | 1.76 | 2.3529 | 0.748 | 46.6181 | 82.0479
[22 empty] | Steel Shoring D=2.5 M | Material | M | 35 | 1 | 35 | 109.6897 | 3839.1378
[9 empty] | 109.6897 | 109.6897 |  | 109.6897 | [9 empty] | Pipe Laying & Protection |  | M | 518.5833 |  | 518.5833 | 109.6897 | 56883.2243 | 0 | 0 | 0 | 0 | 0
[22 empty] | GRP Pipe 700 mm | Material | M | 350 | 1 | 350 | 109.6897 | 38391.3775
[22 empty] | GRP Fitting 700 mm | Material | M | 35 | 1 | 35 | 109.6897 | 3839.1378
[22 empty] | Workmanship GRP pipe 700 mm | SC | M | 65 | 1 | 65 | 109.6897 | 7129.8273
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 5.8824 | 42.5 | 18.6472 | 4661.8101
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 5.8824 | 25.5 | 18.6472 | 2797.0861
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.36563 | 63.9856
[9 empty] | 109.6897 | 109.6897 |  | 109.6897 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 109.6897 | 548.4483 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 109.6897 | 548.4483
STR11 |  | Pipes with an inner diameter of 700 mm at a depth of 2.5 - 3.0 m | m | 96.0397 | 1048 | 100649.6056 | 608.0072 | 58392.8265 | 96.0397 | 96.0397 |  | 96.0397 | 100% | 1048 | 100649.6056 | 608.0072 | 58392.8265 |  | 58392.8265 | [7 empty] | 608.0072 | 96.0397 | 58392.8265 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 96.0397 | 96.0397 |  | 96.0397 | [9 empty] | Excavation ( W= 1.7 & d= 3.0 ) |  | M | 84.4238 |  | 84.4238 | 96.0397 | 8108.0403 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 19.6078 | 2.856 | 4.898 | 274.2894
[22 empty] | Fuel | Material | LTR | 1.76 | 1.4006 | 1.2566 | 68.5723 | 120.6873
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 4 | 12 | 24.0099 | 1152.4764
[22 empty] | Fuel | Material | LTR | 1.76 | 0.4 | 4.4 | 240.0992 | 422.5747
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 1.9208 | 44.1783
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 5.7624 | 10.1418
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 19.6078 | 2.448 | 4.898 | 235.1052
[22 empty] | Fuel | Material | LTR | 1.76 | 1.9608 | 0.8976 | 48.9802 | 86.2052
[22 empty] | Steel Shoring D>3.0 M | Material | M | 60 | 1 | 60 | 96.0397 | 5762.382
[9 empty] | 96.0397 | 96.0397 |  | 96.0397 | [9 empty] | Pipe Laying & Protection |  | M | 518.5833 |  | 518.5833 | 96.0397 | 49804.5878 | 0 | 0 | 0 | 0 | 0
[22 empty] | GRP Pipe 700 mm | Material | M | 350 | 1 | 350 | 96.0397 | 33613.895
[22 empty] | GRP Fitting 700 mm | Material | M | 35 | 1 | 35 | 96.0397 | 3361.3895
[22 empty] | Workmanship GRP pipe 700 mm | SC | M | 65 | 1 | 65 | 96.0397 | 6242.5805
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 5.8824 | 42.5 | 16.3267 | 4081.6872
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 5.8824 | 25.5 | 16.3267 | 2449.0123
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.32013 | 56.0232
[9 empty] | 96.0397 | 96.0397 |  | 96.0397 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 96.0397 | 480.1985 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 96.0397 | 480.1985
STR11 |  | Pipes with an inner diameter of 700 mm at a depth of 3.0 - 3.5 m | m | 14.765 | 1077 | 15901.905 | 611.9835 | 9035.9371 | 14.765 | 14.765 |  | 14.765 | 100% | 1077 | 15901.905 | 611.9835 | 9035.9371 |  | 9035.9371 | [7 empty] | 611.9835 | 14.765 | 9035.9371 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 14.765 | 14.765 |  | 14.765 | [9 empty] | Excavation ( W= 1.7 & d= 3.5 ) |  | M | 88.4002 |  | 88.4002 | 14.765 | 1305.2291 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 16.8067 | 3.332 | 0.87852 | 49.197
[22 empty] | Fuel | Material | LTR | 1.76 | 1.2005 | 1.4661 | 12.2992 | 21.6467
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 3.4286 | 14 | 4.3065 | 206.71
[22 empty] | Fuel | Material | LTR | 1.76 | 0.34286 | 5.1333 | 43.0646 | 75.7937
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 0.2953 | 6.7919
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 0.8859 | 1.5592
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 16.8067 | 2.856 | 0.87852 | 42.1688
[22 empty] | Fuel | Material | LTR | 1.76 | 1.6807 | 1.0472 | 8.7852 | 15.4619
[22 empty] | Steel Shoring D>3.0 M | Material | M | 60 | 1 | 60 | 14.765 | 885.9
[9 empty] | 14.765 | 14.765 |  | 14.765 | [9 empty] | Pipe Laying & Protection |  | M | 518.5833 |  | 518.5833 | 14.765 | 7656.8829 | 0 | 0 | 0 | 0 | 0
[22 empty] | GRP Pipe 700 mm | Material | M | 350 | 1 | 350 | 14.765 | 5167.75
[22 empty] | GRP Fitting 700 mm | Material | M | 35 | 1 | 35 | 14.765 | 516.775
[22 empty] | Workmanship GRP pipe 700 mm | SC | M | 65 | 1 | 65 | 14.765 | 959.725
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 5.8824 | 42.5 | 2.51 | 627.5125
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 5.8824 | 25.5 | 2.51 | 376.5075
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.049217 | 8.6129
[9 empty] | 14.765 | 14.765 |  | 14.765 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 14.765 | 73.825 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 14.765 | 73.825
STR11 |  | Pipes with an inner diameter of 700 mm at a depth of 3.5 - 4.0 m | m |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Pipes with an inner diameter of 800 mm at a depth of 0 - 1.5 m | m |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Pipes with an inner diameter of 800 mm at a depth of 1.5 - 2.0 m | m |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Pipes with an inner diameter of 800 mm at a depth of 2.0 - 2.5 m | m |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Pipes with an inner diameter of 800 mm at a depth of 2.5 - 3.0 m | m | 79.0211 | 1177 | 93007.8935 | 708.4106 | 55979.4202 | 79.0211 | 79.0211 |  | 79.0211 | 100% | 1177 | 93007.8935 | 708.4106 | 55979.4202 |  | 55979.4202 | [7 empty] | 708.4106 | 79.0211 | 55979.4202 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 79.0211 | 79.0211 |  | 79.0211 | [9 empty] | Excavation ( W= 1.8 & d= 3.0 ) |  | M | 85.8273 |  | 85.8273 | 79.0211 | 6782.1693 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 18.5185 | 3.024 | 4.2671 | 238.96
[22 empty] | Fuel | Material | LTR | 1.76 | 1.3228 | 1.3306 | 59.74 | 105.1424
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 3.7778 | 12.7059 | 20.9174 | 1004.0334
[22 empty] | Fuel | Material | LTR | 1.76 | 0.37778 | 4.6588 | 209.1736 | 368.1456
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 1.5804 | 36.3497
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 4.7413 | 8.3446
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 18.5185 | 2.592 | 4.2671 | 204.8228
[22 empty] | Fuel | Material | LTR | 1.76 | 1.8519 | 0.9504 | 42.6714 | 75.1017
[22 empty] | Steel Shoring D>3.0 M | Material | M | 60 | 1 | 60 | 79.0211 | 4741.269
[9 empty] | 79.0211 | 79.0211 |  | 79.0211 | [9 empty] | Pipe Laying & Protection |  | M | 617.5833 |  | 617.5833 | 79.0211 | 48802.1452 | 0 | 0 | 0 | 0 | 0
[22 empty] | GRP Pipe 800 mm | Material | M | 430 | 1 | 430 | 79.0211 | 33979.0945
[22 empty] | GRP Fitting 800 mm | Material | M | 43 | 1 | 43 | 79.0211 | 3397.9094
[22 empty] | Workmanship GRP pipe 800 mm | SC | M | 72 | 1 | 72 | 79.0211 | 5689.5228
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 5.5556 | 45 | 14.2238 | 3555.9517
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 5.5556 | 27 | 14.2238 | 2133.571
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.2634 | 46.0957
[9 empty] | 79.0211 | 79.0211 |  | 79.0211 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 79.0211 | 395.1057 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 79.0211 | 395.1057
STR11 |  | Pipes with an inner diameter of 800 mm at a depth of 3.0 - 3.5 m | m | 13.079 | 1209 | 15812.5714 | 712.6209 | 9320.4041 | 13.079 | 13.079 |  | 13.079 | 100% | 1209 | 15812.5714 | 712.6209 | 9320.4041 |  | 9320.4041 | [7 empty] | 712.6209 | 13.079 | 9320.4041 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 13.079 | 13.079 |  | 13.079 | [9 empty] | Excavation ( W= 1.8 & d= 3.5 ) |  | M | 90.0375 |  | 90.0375 | 13.079 | 1177.6055 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 15.873 | 3.528 | 0.82398 | 46.1429
[22 empty] | Fuel | Material | LTR | 1.76 | 1.1338 | 1.5523 | 11.5357 | 20.3029
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 3.2381 | 14.8235 | 4.0391 | 193.8777
[22 empty] | Fuel | Material | LTR | 1.76 | 0.32381 | 5.4353 | 40.3912 | 71.0885
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 0.26158 | 6.0164
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 0.78474 | 1.3811
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 15.873 | 3.024 | 0.82398 | 39.551
[22 empty] | Fuel | Material | LTR | 1.76 | 1.5873 | 1.1088 | 8.2398 | 14.5021
[22 empty] | Steel Shoring D>3.0 M | Material | M | 60 | 1 | 60 | 13.079 | 784.743
[9 empty] | 13.079 | 13.079 |  | 13.079 | [9 empty] | Pipe Laying & Protection |  | M | 617.5833 |  | 617.5833 | 13.079 | 8077.4033 | 0 | 0 | 0 | 0 | 0
[22 empty] | GRP Pipe 800 mm | Material | M | 430 | 1 | 430 | 13.079 | 5623.9915
[22 empty] | GRP Fitting 800 mm | Material | M | 43 | 1 | 43 | 13.079 | 562.3991
[22 empty] | Workmanship GRP pipe 800 mm | SC | M | 72 | 1 | 72 | 13.079 | 941.6916
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 5.5556 | 45 | 2.3542 | 588.5572
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 5.5556 | 27 | 2.3542 | 353.1343
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.043597 | 7.6294
[9 empty] | 13.079 | 13.079 |  | 13.079 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 13.079 | 65.3952 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 13.079 | 65.3952
Supply and installation of uPVC pipes in trenches, including excavation, backfilling, compaction, waste removal, facility protection, reinforcement work, warning tapes, testing, and commissioning upon completion in accordance with plans, specifications, and requirements of the concerned authority (backfill work under and around the pipe is measured individually)
STR11 |  | Pipes with a diameter of 150 mm at a depth of 0 - 1.5 m, for connection with collection basins. | m | 7192.0875 | 48 | 345220.2005 | 70.8242 | 509373.5904 | 7192.0875 | 7192.0875 |  | 7192.0875 | 100% | 48 | 345220.2005 | 70.8242 | 509373.5904 |  | 509373.5904 | [7 empty] | 70.8242 | 7192.0875 | 509373.5904 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 7192.0875 | 7192.0875 |  | 7192.0875 | [9 empty] | Excavation ( W= 0.6 & d= 1.5 ) |  | M | 4.0742 |  | 4.0742 | 7192.0875 | 29301.7491 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 133.3333 | 0.42 | 53.9407 | 3020.6768
[22 empty] | Fuel | Material | LTR | 1.76 | 9.5238 | 0.1848 | 755.1692 | 1329.0978
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 27.2 | 1.7647 | 264.415 | 12691.9191
[22 empty] | Fuel | Material | LTR | 1.76 | 2.72 | 0.64706 | 2644.1498 | 4653.7037
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 143.8418 | 3308.3603
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 431.5253 | 759.4844
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 133.3333 | 0.36 | 53.9407 | 2589.1515
[22 empty] | Fuel | Material | LTR | 1.76 | 13.3333 | 0.132 | 539.4066 | 949.3556
[9 empty] | 7192.0875 | 7192.0875 |  | 7192.0875 | [9 empty] | Pipe Laying & Protection |  | M | 61.75 |  | 61.75 | 7192.0875 | 444111.4037 | 0 | 0 | 0 | 0 | 0
[22 empty] | UPVC Pipe 150 mm | Material | M | 33.5 | 1 | 33.5 | 7192.0875 | 240934.9316
[22 empty] | UPVC Fitting 150 mm | Material | M | 2 | 1 | 2 | 7192.0875 | 14384.175
[22 empty] | Skilled Labor | Manpower | HR | 17 | 18 | 0.94444 | 399.5604 | 6792.5271
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 18 | 0.72222 | 399.5604 | 5194.2854
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 16.6667 | 15 | 431.5253 | 107881.3127
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 16.6667 | 9 | 431.5253 | 64728.7876
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 23.9736 | 4195.3844
[9 empty] | 7192.0875 | 7192.0875 |  | 7192.0875 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 7192.0875 | 35960.4376 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 7192.0875 | 35960.4376
STR11 |  | Precast Concrete Box Trays (Box Pipes)
STR11 |  | Supply and installation of box-shaped concrete drainage pipes made of precast concrete in trenches. This includes vertical walls, excavation, backfilling, compaction, waste removal, facility protection, support works, partitions, diversions, warning tape, testing and delivery upon complete completion of the work in accordance with plans, specifications and manufacturers’ recommendations (backfilling work under and around the pipe is measured individually)
STR11 |  | Box pipes measuring (internal) 500 x 500 mm in trenches |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Depth 0.0 - 1.5 m | m | 169.0988 | 2318 | 391970.972 | 1261.0447 | 213241.1237 | 169.0988 | 169.0988 |  | 169.0988 | 100% | 2318 | 391970.972 | 1261.0447 | 213241.1237 |  | 213241.1237 | [7 empty] | 1261.0447 | 169.0988 | 213241.1237 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 169.0988 | 169.0988 |  | 169.0988 | [9 empty] | Excavation ( W= 1.7 & d= 1.5 ) |  | M | 12.4947 |  | 12.4947 | 169.0988 | 2112.8419 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 39.2157 | 1.428 | 4.312 | 241.4731
[22 empty] | Fuel | Material | LTR | 1.76 | 2.8011 | 0.62832 | 60.3683 | 106.2481
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 8 | 6 | 21.1373 | 1014.5927
[22 empty] | Fuel | Material | LTR | 1.76 | 0.8 | 2.2 | 211.3735 | 372.0173
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 3.382 | 77.7854
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 10.1459 | 17.8568
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 39.2157 | 1.224 | 4.312 | 206.9769
[22 empty] | Fuel | Material | LTR | 1.76 | 3.9216 | 0.4488 | 43.1202 | 75.8915
[9 empty] | 169.0988 | 169.0988 |  | 169.0988 | [9 empty] | Precast Box Conduit (500x500 mm) |  | M | 1248.55 |  | 1248.55 | 169.0988 | 211128.2818 | 0 | 0 | 0 | 0 | 0
[22 empty] | Precast Box Conduit Supply | Material | M³ | 2200 | 1.7857 | 1232 | 94.6953 | 208329.697
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 8 | 10 | 21.1373 | 1690.9878
[22 empty] | Fuel | Material | LTR | 1.76 | 0.53333 | 3.3 | 317.0602 | 558.026
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 4 | 3.25 | 42.2747 | 549.571
STR11 |  | Depth 1.5 - 2.0 m | m | 36.9045 | 2397 | 88460.0026 | 1265.0211 | 46684.9267 | 36.9045 | 36.9045 |  | 36.9045 | 100% | 2397 | 88460.0026 | 1265.0211 | 46684.9267 |  | 46684.9267 | [7 empty] | 1265.0211 | 36.9045 | 46684.9267 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 36.9045 | 36.9045 |  | 36.9045 | [9 empty] | Excavation ( W= 1.7 & d= 2.0 ) |  | M | 16.4711 |  | 16.4711 | 36.9045 | 607.8569 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 29.4118 | 1.904 | 1.2548 | 70.2661
[22 empty] | Fuel | Material | LTR | 1.76 | 2.1008 | 0.83776 | 17.5665 | 30.9171
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 6 | 8 | 6.1507 | 295.2357
[22 empty] | Fuel | Material | LTR | 1.76 | 0.6 | 2.9333 | 61.5074 | 108.2531
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 0.73809 | 16.9761
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 2.2143 | 3.8971
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 29.4118 | 1.632 | 1.2548 | 60.2281
[22 empty] | Fuel | Material | LTR | 1.76 | 2.9412 | 0.5984 | 12.5475 | 22.0836
[9 empty] | 36.9045 | 36.9045 |  | 36.9045 | [9 empty] | Precast Box Conduit (500x500 mm) |  | M | 1248.55 |  | 1248.55 | 36.9045 | 46077.0698 | 0 | 0 | 0 | 0 | 0
[22 empty] | Precast Box Conduit Supply | Material | M³ | 2200 | 1.7857 | 1232 | 20.6665 | 45466.3009
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 8 | 10 | 4.6131 | 369.0446
[22 empty] | Fuel | Material | LTR | 1.76 | 0.53333 | 3.3 | 69.1959 | 121.7847
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 4 | 3.25 | 9.2261 | 119.9395
STR11 |  | Depth 2.0 - 2.5 m | m | 28.8383 | 2482 | 71576.7102 | 1303.9975 | 37605.0962 | 28.8383 | 28.8383 |  | 28.8383 | 100% | 2482 | 71576.7102 | 1303.9975 | 37605.0962 |  | 37605.0962 | [7 empty] | 1303.9975 | 28.8383 | 37605.0962 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 28.8383 | 28.8383 |  | 28.8383 | [9 empty] | Excavation ( W= 1.7 & d= 2.5 ) |  | M | 55.4475 |  | 55.4475 | 28.8383 | 1599.0118 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 23.5294 | 2.38 | 1.2256 | 68.6352
[22 empty] | Fuel | Material | LTR | 1.76 | 1.6807 | 1.0472 | 17.1588 | 30.1995
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 4.8 | 10 | 6.008 | 288.3832
[22 empty] | Fuel | Material | LTR | 1.76 | 0.48 | 3.6667 | 60.0798 | 105.7405
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 0.57677 | 13.2656
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 1.7303 | 3.0453
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 23.5294 | 2.04 | 1.2256 | 58.8302
[22 empty] | Fuel | Material | LTR | 1.76 | 2.3529 | 0.748 | 12.2563 | 21.5711
[22 empty] | Steel Shoring D=2.5 M | Material | M | 35 | 1 | 35 | 28.8383 | 1009.3412
[9 empty] | 28.8383 | 28.8383 |  | 28.8383 | [9 empty] | Precast Box Conduit (500x500 mm) |  | M | 1248.55 |  | 1248.55 | 28.8383 | 36006.0844 | 0 | 0 | 0 | 0 | 0
[22 empty] | Precast Box Conduit Supply | Material | M³ | 2200 | 1.7857 | 1232 | 16.1495 | 35528.8102
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 8 | 10 | 3.6048 | 288.3832
[22 empty] | Fuel | Material | LTR | 1.76 | 0.53333 | 3.3 | 54.0719 | 95.1665
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 4 | 3.25 | 7.2096 | 93.7245
STR11 |  | Depth 2.5 - 3.0 m | m |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Box pipes (internal) size 1000x500mm in trenches |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Depth 0.0 - 1.5 m | m | 12.2895 | 3045 | 37421.5427 | 2805.9567 | 34483.819 | 12.2895 | 12.2895 |  | 12.2895 | 100% | 3045 | 37421.5427 | 2805.9567 | 34483.819 |  | 34483.819 | [7 empty] | 2805.9567 | 12.2895 | 34483.819 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 12.2895 | 12.2895 |  | 12.2895 | [9 empty] | Excavation ( W= 2.4 & d= 1.5 ) |  | M | 17.4067 |  | 17.4067 | 12.2895 | 213.9199 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 27.7778 | 2.016 | 0.44242 | 24.7756
[22 empty] | Fuel | Material | LTR | 1.76 | 1.9841 | 0.88704 | 6.1939 | 10.9013
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 5.6667 | 8.4706 | 2.1687 | 104.0993
[22 empty] | Fuel | Material | LTR | 1.76 | 0.56667 | 3.1059 | 21.6874 | 38.1698
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 0.24579 | 5.6532
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 0.73737 | 1.2978
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 27.7778 | 1.728 | 0.44242 | 21.2363
[22 empty] | Fuel | Material | LTR | 1.76 | 2.7778 | 0.6336 | 4.4242 | 7.7866
[9 empty] | 12.2895 | 12.2895 |  | 12.2895 | [9 empty] | Precast Box Conduit (1000x500 mm) |  | M | 2788.55 |  | 2788.55 | 12.2895 | 34269.8992 | 0 | 0 | 0 | 0 | 0
[22 empty] | Precast Box Conduit Supply | Material | M³ | 2200 | 0.79365 | 2772 | 15.4848 | 34066.5079
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 8 | 10 | 1.5362 | 122.895
[22 empty] | Fuel | Material | LTR | 1.76 | 0.53333 | 3.3 | 23.0428 | 40.5554
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 4 | 3.25 | 3.0724 | 39.9409
STR11 |  | Depth 1.5 - 2.0 m | m | 69.8399 | 3147 | 219786.008 | 2811.5704 | 196359.656 | 69.8399 | 69.8399 |  | 69.8399 | 100% | 3147 | 219786.008 | 2811.5704 | 196359.656 |  | 196359.656 | [7 empty] | 2811.5704 | 69.8399 | 196359.656 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 69.8399 | 69.8399 |  | 69.8399 | [9 empty] | Excavation ( W= 2.4 & d= 2.0 ) |  | M | 23.0204 |  | 23.0204 | 69.8399 | 1607.7423 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 20.8333 | 2.688 | 3.3523 | 187.7295
[22 empty] | Fuel | Material | LTR | 1.76 | 1.4881 | 1.1827 | 46.9324 | 82.601
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 4.25 | 11.2941 | 16.4329 | 788.7795
[22 empty] | Fuel | Material | LTR | 1.76 | 0.425 | 4.1412 | 164.3291 | 289.2191
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 1.3968 | 32.1263
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 4.1904 | 7.3751
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 20.8333 | 2.304 | 3.3523 | 160.911
[22 empty] | Fuel | Material | LTR | 1.76 | 2.0833 | 0.8448 | 33.5231 | 59.0007
[9 empty] | 69.8399 | 69.8399 |  | 69.8399 | [9 empty] | Precast Box Conduit (1000x500 mm) |  | M | 2788.55 |  | 2788.55 | 69.8399 | 194751.9137 | 0 | 0 | 0 | 0 | 0
[22 empty] | Precast Box Conduit Supply | Material | M³ | 2200 | 0.79365 | 2772 | 87.9982 | 193596.0642
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 8 | 10 | 8.73 | 698.3985
[22 empty] | Fuel | Material | LTR | 1.76 | 0.53333 | 3.3 | 130.9497 | 230.4715
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 4 | 3.25 | 17.46 | 226.9795
STR11 |  | Depth 2.0 - 2.5 m | m | 167.1248 | 3261 | 544994.0706 | 2852.1841 | 476670.7858 | 167.1248 | 167.1248 |  | 167.1248 | 100% | 3261 | 544994.0706 | 2852.1841 | 476670.7858 |  | 476670.7858 | [7 empty] | 2852.1841 | 167.1248 | 476670.7858 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 167.1248 | 167.1248 |  | 167.1248 | [9 empty] | Excavation ( W= 2.4 & d= 2.5 ) |  | M | 63.6341 |  | 63.6341 | 167.1248 | 10634.8411 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 16.6667 | 3.36 | 10.0275 | 561.5394
[22 empty] | Fuel | Material | LTR | 1.76 | 1.1905 | 1.4784 | 140.3849 | 247.0773
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 3.4 | 14.1176 | 49.1544 | 2359.4094
[22 empty] | Fuel | Material | LTR | 1.76 | 0.34 | 5.1765 | 491.5436 | 865.1168
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 3.3425 | 76.8774
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 10.0275 | 17.6484
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 16.6667 | 2.88 | 10.0275 | 481.3195
[22 empty] | Fuel | Material | LTR | 1.76 | 1.6667 | 1.056 | 100.2749 | 176.4838
[22 empty] | Steel Shoring D=2.5 M | Material | M | 35 | 1 | 35 | 167.1248 | 5849.369
[9 empty] | 167.1248 | 167.1248 |  | 167.1248 | [9 empty] | Precast Box Conduit (1000x500 mm) |  | M | 2788.55 |  | 2788.55 | 167.1248 | 466035.9447 | 0 | 0 | 0 | 0 | 0
[22 empty] | Precast Box Conduit Supply | Material | M³ | 2200 | 0.79365 | 2772 | 210.5773 | 463270.0288
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 8 | 10 | 20.8906 | 1671.2483
[22 empty] | Fuel | Material | LTR | 1.76 | 0.53333 | 3.3 | 313.3591 | 551.5119
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 4 | 3.25 | 41.7812 | 543.1557
STR11 |  | Depth 2.5 - 3.0 m | m | 15.7495 | 3386 | 53327.7223 | 2882.7978 | 45402.5522 | 15.7495 | 15.7495 |  | 15.7495 | 100% | 3386 | 53327.7223 | 2882.7978 | 45402.5522 |  | 45402.5522 | [7 empty] | 2882.7978 | 15.7495 | 45402.5522 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 15.7495 | 15.7495 |  | 15.7495 | [9 empty] | Excavation ( W= 2.4 & d= 3.0 ) |  | M | 94.2478 |  | 94.2478 | 15.7495 | 1484.3537 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 13.8889 | 4.032 | 1.134 | 63.5019
[22 empty] | Fuel | Material | LTR | 1.76 | 0.99206 | 1.7741 | 15.8755 | 27.9408
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 2.8333 | 16.9412 | 5.5586 | 266.8146
[22 empty] | Fuel | Material | LTR | 1.76 | 0.28333 | 6.2118 | 55.5864 | 97.832
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 0.31499 | 7.2448
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 0.94497 | 1.6631
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 13.8889 | 3.456 | 1.134 | 54.4302
[22 empty] | Fuel | Material | LTR | 1.76 | 1.3889 | 1.2672 | 11.3396 | 19.9577
[22 empty] | Steel Shoring D>3.0 M | Material | M | 60 | 1 | 60 | 15.7495 | 944.9685
[9 empty] | 15.7495 | 15.7495 |  | 15.7495 | [9 empty] | Precast Box Conduit (1000x500 mm) |  | M | 2788.55 |  | 2788.55 | 15.7495 | 43918.1985 | 0 | 0 | 0 | 0 | 0
[22 empty] | Precast Box Conduit Supply | Material | M³ | 2200 | 0.79365 | 2772 | 19.8443 | 43657.5447
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 8 | 10 | 1.9687 | 157.4947
[22 empty] | Fuel | Material | LTR | 1.76 | 0.53333 | 3.3 | 29.5303 | 51.9733
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 4 | 3.25 | 3.9374 | 51.1858
STR11 |  | Depth 3.0 - 3.5 m | m | 10.74 | 3524 | 37847.76 | 2888.4115 | 31021.5398 | 10.74 | 10.74 |  | 10.74 | 100% | 3524 | 37847.76 | 2888.4115 | 31021.5398 |  | 31021.5398 | [7 empty] | 2888.4115 | 10.74 | 31021.5398 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 10.74 | 10.74 |  | 10.74 | [9 empty] | Excavation ( W= 2.4 & d= 3.5 ) |  | M | 99.8615 |  | 99.8615 | 10.74 | 1072.5128 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 11.9048 | 4.704 | 0.90216 | 50.521
[22 empty] | Fuel | Material | LTR | 1.76 | 0.85034 | 2.0698 | 12.6302 | 22.2292
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 2.4286 | 19.7647 | 4.4224 | 212.2729
[22 empty] | Fuel | Material | LTR | 1.76 | 0.24286 | 7.2471 | 44.2235 | 77.8334
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 0.2148 | 4.9404
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 0.6444 | 1.1341
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 11.9048 | 4.032 | 0.90216 | 43.3037
[22 empty] | Fuel | Material | LTR | 1.76 | 1.1905 | 1.4784 | 9.0216 | 15.878
[22 empty] | Steel Shoring D>3.0 M | Material | M | 60 | 1 | 60 | 10.74 | 644.4
[9 empty] | 10.74 | 10.74 |  | 10.74 | [9 empty] | Precast Box Conduit (1000x500 mm) |  | M | 2788.55 |  | 2788.55 | 10.74 | 29949.027 | 0 | 0 | 0 | 0 | 0
[22 empty] | Precast Box Conduit Supply | Material | M³ | 2200 | 0.79365 | 2772 | 13.5324 | 29771.28
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 8 | 10 | 1.3425 | 107.4
[22 empty] | Fuel | Material | LTR | 1.76 | 0.53333 | 3.3 | 20.1375 | 35.442
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 4 | 3.25 | 2.685 | 34.905
STR11 |  | Depth 3.5 - 4.0 m | m |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Depth 4.0 - 4.5 m | m |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Box pipes (internal) size 1000x700 mm in trenches |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Depth 0.0 - 1.5 m | m |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Depth 1.5 - 2.0 m | m | 31.682 | 3448 | 109239.536 | 3075.5704 | 97440.2219 | 31.682 | 31.682 |  | 31.682 | 100% | 3448 | 109239.536 | 3075.5704 | 97440.2219 |  | 97440.2219 | [7 empty] | 3075.5704 | 31.682 | 97440.2219 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 31.682 | 31.682 |  | 31.682 | [9 empty] | Excavation ( W= 2.4 & d= 2.0 ) |  | M | 23.0204 |  | 23.0204 | 31.682 | 729.3328 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 20.8333 | 2.688 | 1.5207 | 85.1612
[22 empty] | Fuel | Material | LTR | 1.76 | 1.4881 | 1.1827 | 21.2903 | 37.4709
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 4.25 | 11.2941 | 7.4546 | 357.8202
[22 empty] | Fuel | Material | LTR | 1.76 | 0.425 | 4.1412 | 74.5459 | 131.2008
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 0.63364 | 14.5737
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 1.9009 | 3.3456
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 20.8333 | 2.304 | 1.5207 | 72.9953
[22 empty] | Fuel | Material | LTR | 1.76 | 2.0833 | 0.8448 | 15.2074 | 26.765
[9 empty] | 31.682 | 31.682 |  | 31.682 | [9 empty] | Precast Box Conduit (1000x700 mm) |  | M | 3052.55 |  | 3052.55 | 31.682 | 96710.8891 | 0 | 0 | 0 | 0 | 0
[22 empty] | Precast Box Conduit Supply | Material | M³ | 2200 | 0.72464 | 3036 | 43.7212 | 96186.552
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 8 | 10 | 3.9603 | 316.82
[22 empty] | Fuel | Material | LTR | 1.76 | 0.53333 | 3.3 | 59.4038 | 104.5506
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 4 | 3.25 | 7.9205 | 102.9665
STR11 |  | Depth 2.0 - 2.5 m | m | 100.3231 | 3571 | 358253.6116 | 3116.1841 | 312625.095 | 100.3231 | 100.3231 |  | 100.3231 | 100% | 3571 | 358253.6116 | 3116.1841 | 312625.095 |  | 312625.095 | [7 empty] | 3116.1841 | 100.3231 | 312625.095 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 100.3231 | 100.3231 |  | 100.3231 | [9 empty] | Excavation ( W= 2.4 & d= 2.5 ) |  | M | 63.6341 |  | 63.6341 | 100.3231 | 6383.9688 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 16.6667 | 3.36 | 6.0194 | 337.0854
[22 empty] | Fuel | Material | LTR | 1.76 | 1.1905 | 1.4784 | 84.2714 | 148.3176
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 3.4 | 14.1176 | 29.5068 | 1416.3254
[22 empty] | Fuel | Material | LTR | 1.76 | 0.34 | 5.1765 | 295.0678 | 519.3193
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 2.0065 | 46.1486
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 6.0194 | 10.5941
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 16.6667 | 2.88 | 6.0194 | 288.9304
[22 empty] | Fuel | Material | LTR | 1.76 | 1.6667 | 1.056 | 60.1938 | 105.9411
[22 empty] | Steel Shoring D=2.5 M | Material | M | 35 | 1 | 35 | 100.3231 | 3511.3068
[9 empty] | 100.3231 | 100.3231 |  | 100.3231 | [9 empty] | Precast Box Conduit (1000x700 mm) |  | M | 3052.55 |  | 3052.55 | 100.3231 | 306241.1263 | 0 | 0 | 0 | 0 | 0
[22 empty] | Precast Box Conduit Supply | Material | M³ | 2200 | 0.72464 | 3036 | 138.4458 | 304580.7798
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 8 | 10 | 12.5404 | 1003.2305
[22 empty] | Fuel | Material | LTR | 1.76 | 0.53333 | 3.3 | 188.1057 | 331.0661
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 4 | 3.25 | 25.0808 | 326.0499
STR11 |  | Depth 2.5 - 3.0 m | m | 58.3939 | 3707 | 216466.2244 | 3146.7978 | 183753.8288 | 58.3939 | 58.3939 |  | 58.3939 | 100% | 3707 | 216466.2244 | 3146.7978 | 183753.8288 |  | 183753.8288 | [7 empty] | 3146.7978 | 58.3939 | 183753.8288 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 58.3939 | 58.3939 |  | 58.3939 | [9 empty] | Excavation ( W= 2.4 & d= 3.0 ) |  | M | 94.2478 |  | 94.2478 | 58.3939 | 5503.4988 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 13.8889 | 4.032 | 4.2044 | 235.4442
[22 empty] | Fuel | Material | LTR | 1.76 | 0.99206 | 1.7741 | 58.8611 | 103.5955
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 2.8333 | 16.9412 | 20.6096 | 989.2615
[22 empty] | Fuel | Material | LTR | 1.76 | 0.28333 | 6.2118 | 206.0962 | 362.7292
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 1.1679 | 26.8612
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 3.5036 | 6.1664
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 13.8889 | 3.456 | 4.2044 | 201.8094
[22 empty] | Fuel | Material | LTR | 1.76 | 1.3889 | 1.2672 | 42.0436 | 73.9968
[22 empty] | Steel Shoring D>3.0 M | Material | M | 60 | 1 | 60 | 58.3939 | 3503.6346
[9 empty] | 58.3939 | 58.3939 |  | 58.3939 | [9 empty] | Precast Box Conduit (1000x700 mm) |  | M | 3052.55 |  | 3052.55 | 58.3939 | 178250.33 | 0 | 0 | 0 | 0 | 0
[22 empty] | Precast Box Conduit Supply | Material | M³ | 2200 | 0.72464 | 3036 | 80.5836 | 177283.9108
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 8 | 10 | 7.2992 | 583.9391
[22 empty] | Fuel | Material | LTR | 1.76 | 0.53333 | 3.3 | 109.4886 | 192.6999
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 4 | 3.25 | 14.5985 | 189.7802
STR11 |  | Depth 3.0 - 3.5 m | m | 28.4442 | 3858 | 109737.7815 | 3152.4115 | 89667.8712 | 28.4442 | 28.4442 |  | 28.4442 | 100% | 3858 | 109737.7815 | 3152.4115 | 89667.8712 |  | 89667.8712 | [7 empty] | 3152.4115 | 28.4442 | 89667.8712 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 28.4442 | 28.4442 |  | 28.4442 | [9 empty] | Excavation ( W= 2.4 & d= 3.5 ) |  | M | 99.8615 |  | 99.8615 | 28.4442 | 2840.4827 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 11.9048 | 4.704 | 2.3893 | 133.8016
[22 empty] | Fuel | Material | LTR | 1.76 | 0.85034 | 2.0698 | 33.4504 | 58.8727
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 2.4286 | 19.7647 | 11.7123 | 562.1915
[22 empty] | Fuel | Material | LTR | 1.76 | 0.24286 | 7.2471 | 117.1232 | 206.1369
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 0.56888 | 13.0843
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 1.7067 | 3.0037
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 11.9048 | 4.032 | 2.3893 | 114.6871
[22 empty] | Fuel | Material | LTR | 1.76 | 1.1905 | 1.4784 | 23.8931 | 42.0519
[22 empty] | Steel Shoring D>3.0 M | Material | M | 60 | 1 | 60 | 28.4442 | 1706.6529
[9 empty] | 28.4442 | 28.4442 |  | 28.4442 | [9 empty] | Precast Box Conduit (1000x700 mm) |  | M | 3052.55 |  | 3052.55 | 28.4442 | 86827.3885 | 0 | 0 | 0 | 0 | 0
[22 empty] | Precast Box Conduit Supply | Material | M³ | 2200 | 0.72464 | 3036 | 39.253 | 86356.6367
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 8 | 10 | 3.5555 | 284.4421
[22 empty] | Fuel | Material | LTR | 1.76 | 0.53333 | 3.3 | 53.3329 | 93.8659
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 4 | 3.25 | 7.1111 | 92.4437
STR11 |  | Depth 3.5 - 4.0 m | m | 22.111 | 4023 | 88952.7541 | 3158.0252 | 69827.2537 | 22.111 | 22.111 |  | 22.111 | 100% | 4023 | 88952.7541 | 3158.0252 | 69827.2537 |  | 69827.2537 | [7 empty] | 3158.0252 | 22.111 | 69827.2537 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 22.111 | 22.111 |  | 22.111 | [9 empty] | Excavation ( W= 2.4 & d= 4.0 ) |  | M | 105.4752 |  | 105.4752 | 22.111 | 2332.168 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 10.4167 | 5.376 | 2.1227 | 118.869
[22 empty] | Fuel | Material | LTR | 1.76 | 0.74405 | 2.3654 | 29.7173 | 52.3024
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 2.125 | 22.5882 | 10.4052 | 499.4496
[22 empty] | Fuel | Material | LTR | 1.76 | 0.2125 | 8.2824 | 104.052 | 183.1315
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 0.44222 | 10.1711
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 1.3267 | 2.3349
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 10.4167 | 4.608 | 2.1227 | 101.8877
[22 empty] | Fuel | Material | LTR | 1.76 | 1.0417 | 1.6896 | 21.2266 | 37.3588
[22 empty] | Steel Shoring D>3.0 M | Material | M | 60 | 1 | 60 | 22.111 | 1326.663
[9 empty] | 22.111 | 22.111 |  | 22.111 | [9 empty] | Precast Box Conduit (1000x700 mm) |  | M | 3052.55 |  | 3052.55 | 22.111 | 67495.0857 | 0 | 0 | 0 | 0 | 0
[22 empty] | Precast Box Conduit Supply | Material | M³ | 2200 | 0.72464 | 3036 | 30.5132 | 67129.1478
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 8 | 10 | 2.7639 | 221.1105
[22 empty] | Fuel | Material | LTR | 1.76 | 0.53333 | 3.3 | 41.4582 | 72.9665
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 4 | 3.25 | 5.5278 | 71.8609
STR11 |  | Box pipes (internal) size 1500x500mm in trenches |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Depth 0.0 - 1.5 m | m | 33.8446 | 3771 | 127628.1374 | 3469.4653 | 117422.8032 | 33.8446 | 33.8446 |  | 33.8446 | 100% | 3771 | 127628.1374 | 3469.4653 | 117422.8032 |  | 117422.8032 | [7 empty] | 3469.4653 | 33.8446 | 117422.8032 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 33.8446 | 33.8446 |  | 33.8446 | [9 empty] | Excavation ( W= 2.9 & d= 1.5 ) |  | M | 20.9153 |  | 20.9153 | 33.8446 | 707.87 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 22.9885 | 2.436 | 1.4722 | 82.4455
[22 empty] | Fuel | Material | LTR | 1.76 | 1.642 | 1.0718 | 20.6114 | 36.276
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 4.6897 | 10.2353 | 7.2169 | 346.4098
[22 empty] | Fuel | Material | LTR | 1.76 | 0.46897 | 3.7529 | 72.1687 | 127.0169
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 0.67689 | 15.5685
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 2.0307 | 3.574
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 22.9885 | 2.088 | 1.4722 | 70.6676
[22 empty] | Fuel | Material | LTR | 1.76 | 2.2989 | 0.7656 | 14.7224 | 25.9115
[9 empty] | 33.8446 | 33.8446 |  | 33.8446 | [9 empty] | Precast Box Conduit (1500x500 mm) |  | M | 3448.55 |  | 3448.55 | 33.8446 | 116714.9333 | 0 | 0 | 0 | 0 | 0
[22 empty] | Precast Box Conduit Supply | Material | M³ | 2200 | 0.64103 | 3432 | 52.7976 | 116154.8045
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 8 | 10 | 4.2306 | 338.4464
[22 empty] | Fuel | Material | LTR | 1.76 | 0.53333 | 3.3 | 63.4587 | 111.6873
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 4 | 3.25 | 8.4612 | 109.9951
STR11 |  | Depth 1.5 - 2.0 m | m | 36.9854 | 3899 | 144206.0551 | 3476.2485 | 128570.4239 | 36.9854 | 36.9854 |  | 36.9854 | 100% | 3899 | 144206.0551 | 3476.2485 | 128570.4239 |  | 128570.4239 | [7 empty] | 3476.2485 | 36.9854 | 128570.4239 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 36.9854 | 36.9854 |  | 36.9854 | [9 empty] | Excavation ( W= 2.9 & d= 2.0 ) |  | M | 27.6985 |  | 27.6985 | 36.9854 | 1024.44 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 17.2414 | 3.248 | 2.1452 | 120.1286
[22 empty] | Fuel | Material | LTR | 1.76 | 1.2315 | 1.4291 | 30.0321 | 52.8566
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 3.5172 | 13.6471 | 10.5155 | 504.7419
[22 empty] | Fuel | Material | LTR | 1.76 | 0.35172 | 5.0039 | 105.1546 | 185.072
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 0.73971 | 17.0133
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 2.2191 | 3.9057
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 17.2414 | 2.784 | 2.1452 | 102.9673
[22 empty] | Fuel | Material | LTR | 1.76 | 1.7241 | 1.0208 | 21.4515 | 37.7547
[9 empty] | 36.9854 | 36.9854 |  | 36.9854 | [9 empty] | Precast Box Conduit (1500x500 mm) |  | M | 3448.55 |  | 3448.55 | 36.9854 | 127545.9839 | 0 | 0 | 0 | 0 | 0
[22 empty] | Precast Box Conduit Supply | Material | M³ | 2200 | 0.64103 | 3432 | 57.6972 | 126933.8756
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 8 | 10 | 4.6232 | 369.854
[22 empty] | Fuel | Material | LTR | 1.76 | 0.53333 | 3.3 | 69.3476 | 122.0518
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 4 | 3.25 | 9.2463 | 120.2025
STR11 |  | Depth 2.0 - 2.5 m | m | 16.6391 | 4039 | 67205.1431 | 3518.0317 | 58536.7234 | 16.6391 | 16.6391 |  | 16.6391 | 100% | 4039 | 67205.1431 | 3518.0317 | 58536.7234 |  | 58536.7234 | [7 empty] | 3518.0317 | 16.6391 | 58536.7234 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 16.6391 | 16.6391 |  | 16.6391 | [9 empty] | Excavation ( W= 2.9 & d= 2.5 ) |  | M | 69.4817 |  | 69.4817 | 16.6391 | 1156.1103 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 13.7931 | 4.06 | 1.2063 | 67.5546
[22 empty] | Fuel | Material | LTR | 1.76 | 0.98522 | 1.7864 | 16.8886 | 29.724
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 2.8138 | 17.0588 | 5.9134 | 283.8427
[22 empty] | Fuel | Material | LTR | 1.76 | 0.28138 | 6.2549 | 59.1339 | 104.0757
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 0.33278 | 7.654
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 0.99834 | 1.7571
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 13.7931 | 3.48 | 1.2063 | 57.9039
[22 empty] | Fuel | Material | LTR | 1.76 | 1.3793 | 1.276 | 12.0633 | 21.2314
[22 empty] | Steel Shoring D=2.5 M | Material | M | 35 | 1 | 35 | 16.6391 | 582.3669
[9 empty] | 16.6391 | 16.6391 |  | 16.6391 | [9 empty] | Precast Box Conduit (1500x500 mm) |  | M | 3448.55 |  | 3448.55 | 16.6391 | 57380.6131 | 0 | 0 | 0 | 0 | 0
[22 empty] | Precast Box Conduit Supply | Material | M³ | 2200 | 0.64103 | 3432 | 25.9569 | 57105.2368
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 8 | 10 | 2.0799 | 166.3905
[22 empty] | Fuel | Material | LTR | 1.76 | 0.53333 | 3.3 | 31.1982 | 54.9089
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 4 | 3.25 | 4.1598 | 54.0769
STR11 |  | Depth 2.5 - 3.0 m | m |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Depth 3.0 - 3.5 m | m |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Depth 3.5 - 4.0 m | m |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Box pipes measuring (internal) 1500x700 mm in trenches |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Depth 0.0 - 1.5 m | m | 1.6987 | 4060 | 6896.519 | 3733.4653 | 6341.8508 | 1.6987 | 1.6987 |  | 1.6987 | 100% | 4060 | 6896.519 | 3733.4653 | 6341.8508 |  | 6341.8508 | [7 empty] | 3733.4653 | 1.6987 | 6341.8508 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 1.6987 | 1.6987 |  | 1.6987 | [9 empty] | Excavation ( W= 2.9 & d= 1.5 ) |  | M | 20.9153 |  | 20.9153 | 1.6987 | 35.5277 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 22.9885 | 2.436 | 0.073891 | 4.1379
[22 empty] | Fuel | Material | LTR | 1.76 | 1.642 | 1.0718 | 1.0345 | 1.8207
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 4.6897 | 10.2353 | 0.36221 | 17.3862
[22 empty] | Fuel | Material | LTR | 1.76 | 0.46897 | 3.7529 | 3.6221 | 6.3749
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 0.033973 | 0.78138
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 0.10192 | 0.17938
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 22.9885 | 2.088 | 0.073891 | 3.5468
[22 empty] | Fuel | Material | LTR | 1.76 | 2.2989 | 0.7656 | 0.73891 | 1.3005
[9 empty] | 1.6987 | 1.6987 |  | 1.6987 | [9 empty] | Precast Box Conduit (1500x700 mm) |  | M | 3712.55 |  | 3712.55 | 1.6987 | 6306.3231 | 0 | 0 | 0 | 0 | 0
[22 empty] | Precast Box Conduit Supply | Material | M³ | 2200 | 0.59524 | 3696 | 2.8537 | 6278.2104
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 8 | 10 | 0.21233 | 16.9865
[22 empty] | Fuel | Material | LTR | 1.76 | 0.53333 | 3.3 | 3.185 | 5.6055
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 4 | 3.25 | 0.42466 | 5.5206
STR11 |  | Depth 1.5 - 2.0 m | m | 33.3259 | 4197 | 139869.0121 | 3740.2485 | 124647.3345 | 33.3259 | 33.3259 |  | 33.3259 | 100% | 4197 | 139869.0121 | 3740.2485 | 124647.3345 |  | 124647.3345 | [7 empty] | 3740.2485 | 33.3259 | 124647.3345 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 33.3259 | 33.3259 |  | 33.3259 | [9 empty] | Excavation ( W= 2.9 & d= 2.0 ) |  | M | 27.6985 |  | 27.6985 | 33.3259 | 923.0788 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 17.2414 | 3.248 | 1.9329 | 108.2427
[22 empty] | Fuel | Material | LTR | 1.76 | 1.2315 | 1.4291 | 27.0607 | 47.6268
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 3.5172 | 13.6471 | 9.475 | 454.8012
[22 empty] | Fuel | Material | LTR | 1.76 | 0.35172 | 5.0039 | 94.7502 | 166.7604
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 0.66652 | 15.3299
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 1.9996 | 3.5192
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 17.2414 | 2.784 | 1.9329 | 92.7794
[22 empty] | Fuel | Material | LTR | 1.76 | 1.7241 | 1.0208 | 19.3291 | 34.0191
[9 empty] | 33.3259 | 33.3259 |  | 33.3259 | [9 empty] | Precast Box Conduit (1500x700 mm) |  | M | 3712.55 |  | 3712.55 | 33.3259 | 123724.2557 | 0 | 0 | 0 | 0 | 0
[22 empty] | Precast Box Conduit Supply | Material | M³ | 2200 | 0.59524 | 3696 | 55.9876 | 123172.7112
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 8 | 10 | 4.1657 | 333.2595
[22 empty] | Fuel | Material | LTR | 1.76 | 0.53333 | 3.3 | 62.4862 | 109.9756
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 4 | 3.25 | 8.3315 | 108.3093
STR11 |  | Depth 2.0 - 2.5 m | m | 51.4996 | 4348 | 223920.2391 | 3782.0317 | 194773.1021 | 51.4996 | 51.4996 |  | 51.4996 | 100% | 4348 | 223920.2391 | 3782.0317 | 194773.1021 |  | 194773.1021 | [7 empty] | 3782.0317 | 51.4996 | 194773.1021 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 51.4996 | 51.4996 |  | 51.4996 | [9 empty] | Excavation ( W= 2.9 & d= 2.5 ) |  | M | 69.4817 |  | 69.4817 | 51.4996 | 3578.2807 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 13.7931 | 4.06 | 3.7337 | 209.0884
[22 empty] | Fuel | Material | LTR | 1.76 | 0.98522 | 1.7864 | 52.2721 | 91.9989
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 2.8138 | 17.0588 | 18.3026 | 878.5225
[22 empty] | Fuel | Material | LTR | 1.76 | 0.28138 | 6.2549 | 183.0255 | 322.1249
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 1.03 | 23.6898
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 3.09 | 5.4384
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 13.7931 | 3.48 | 3.7337 | 179.2186
[22 empty] | Fuel | Material | LTR | 1.76 | 1.3793 | 1.276 | 37.3372 | 65.7135
[22 empty] | Steel Shoring D=2.5 M | Material | M | 35 | 1 | 35 | 51.4996 | 1802.4858
[9 empty] | 51.4996 | 51.4996 |  | 51.4996 | [9 empty] | Precast Box Conduit (1500x700 mm) |  | M | 3712.55 |  | 3712.55 | 51.4996 | 191194.8214 | 0 | 0 | 0 | 0 | 0
[22 empty] | Precast Box Conduit Supply | Material | M³ | 2200 | 0.59524 | 3696 | 86.5193 | 190342.5031
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 8 | 10 | 6.4374 | 514.9959
[22 empty] | Fuel | Material | LTR | 1.76 | 0.53333 | 3.3 | 96.5617 | 169.9487
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 4 | 3.25 | 12.8749 | 167.3737
STR11 |  | Depth 2.5 - 3.0 m | m | 24.2284 | 4514 | 109367.2233 | 3813.815 | 92402.8248 | 24.2284 | 24.2284 |  | 24.2284 | 100% | 4514 | 109367.2233 | 3813.815 | 92402.8248 |  | 92402.8248 | [7 empty] | 3813.815 | 24.2284 | 92402.8248 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 24.2284 | 24.2284 |  | 24.2284 | [9 empty] | Excavation ( W= 2.9 & d= 3.0 ) |  | M | 101.265 |  | 101.265 | 24.2284 | 2453.4928 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 11.4943 | 4.872 | 2.1079 | 118.041
[22 empty] | Fuel | Material | LTR | 1.76 | 0.82102 | 2.1437 | 29.5103 | 51.938
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 2.3448 | 20.4706 | 10.3327 | 495.9706
[22 empty] | Fuel | Material | LTR | 1.76 | 0.23448 | 7.5059 | 103.3272 | 181.8559
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 0.48457 | 11.1451
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 1.4537 | 2.5585
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 11.4943 | 4.176 | 2.1079 | 101.178
[22 empty] | Fuel | Material | LTR | 1.76 | 1.1494 | 1.5312 | 21.0788 | 37.0986
[22 empty] | Steel Shoring D>3.0 M | Material | M | 60 | 1 | 60 | 24.2284 | 1453.707
[9 empty] | 24.2284 | 24.2284 |  | 24.2284 | [9 empty] | Precast Box Conduit (1500x700 mm) |  | M | 3712.55 |  | 3712.55 | 24.2284 | 89949.332 | 0 | 0 | 0 | 0 | 0
[22 empty] | Precast Box Conduit Supply | Material | M³ | 2200 | 0.59524 | 3696 | 40.7038 | 89548.3512
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 8 | 10 | 3.0286 | 242.2845
[22 empty] | Fuel | Material | LTR | 1.76 | 0.53333 | 3.3 | 45.4283 | 79.9539
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 4 | 3.25 | 6.0571 | 78.7425
STR11 |  | Depth 3.0 - 3.5 m | m |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Depth 3.5 - 4.0 m | m |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Depth 4.0 - 4.5 m | m |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Box pipes measuring (internal) 1500x750 mm in trenches |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Depth 0.0 - 1.5 m | m |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Depth 1.5 - 2.0 m | m |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Depth 2.0 - 2.5 m | m | 13.4654 | 4426 | 59597.9932 | 3848.0317 | 51815.4018 | 13.4654 | 13.4654 |  | 13.4654 | 100% | 4426 | 59597.9932 | 3848.0317 | 51815.4018 |  | 51815.4018 | [7 empty] | 3848.0317 | 13.4654 | 51815.4018 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 13.4654 | 13.4654 |  | 13.4654 | [9 empty] | Excavation ( W= 2.9 & d= 2.5 ) |  | M | 69.4817 |  | 69.4817 | 13.4654 | 935.6013 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 13.7931 | 4.06 | 0.97624 | 54.6696
[22 empty] | Fuel | Material | LTR | 1.76 | 0.98522 | 1.7864 | 13.6674 | 24.0546
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 2.8138 | 17.0588 | 4.7855 | 229.7044
[22 empty] | Fuel | Material | LTR | 1.76 | 0.28138 | 6.2549 | 47.8551 | 84.2249
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 0.26931 | 6.1941
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 0.80793 | 1.4219
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 13.7931 | 3.48 | 0.97624 | 46.8597
[22 empty] | Fuel | Material | LTR | 1.76 | 1.3793 | 1.276 | 9.7624 | 17.1819
[22 empty] | Steel Shoring D=2.5 M | Material | M | 35 | 1 | 35 | 13.4654 | 471.2901
[9 empty] | 13.4654 | 13.4654 |  | 13.4654 | [9 empty] | Precast Box Conduit (1500x750 mm) |  | M | 3778.55 |  | 3778.55 | 13.4654 | 50879.8005 | 0 | 0 | 0 | 0 | 0
[22 empty] | Precast Box Conduit Supply | Material | M³ | 2200 | 0.5848 | 3762 | 23.0259 | 50656.9477
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 8 | 10 | 1.6832 | 134.6543
[22 empty] | Fuel | Material | LTR | 1.76 | 0.53333 | 3.3 | 25.2477 | 44.4359
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 4 | 3.25 | 3.3664 | 43.7626
STR11 |  | Depth 2.5 - 3.0 m | m |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Depth 3.0 - 3.5 m | m |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Depth 3.5 - 4.0 m | m |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Box pipes measuring (internal) 1600x700 mm in trenches |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Depth 0.0 - 1.5 m | m |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Depth 1.5 - 2.0 m | m | 44.9557 | 4347 | 195422.3627 | 3873.1841 | 174121.6451 | 44.9557 | 44.9557 |  | 44.9557 | 100% | 4347 | 195422.3627 | 3873.1841 | 174121.6451 |  | 174121.6451 | [7 empty] | 3873.1841 | 44.9557 | 174121.6451 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 44.9557 | 44.9557 |  | 44.9557 | [9 empty] | Excavation ( W= 3.0 & d= 2.0 ) |  | M | 28.6341 |  | 28.6341 | 44.9557 | 1287.2664 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 16.6667 | 3.36 | 2.6973 | 151.0511
[22 empty] | Fuel | Material | LTR | 1.76 | 1.1905 | 1.4784 | 37.7628 | 66.4625
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 3.4 | 14.1176 | 13.2223 | 634.6685
[22 empty] | Fuel | Material | LTR | 1.76 | 0.34 | 5.1765 | 132.2226 | 232.7118
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 0.89911 | 20.6796
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 2.6973 | 4.7473
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 16.6667 | 2.88 | 2.6973 | 129.4724
[22 empty] | Fuel | Material | LTR | 1.76 | 1.6667 | 1.056 | 26.9734 | 47.4732
[9 empty] | 44.9557 | 44.9557 |  | 44.9557 | [9 empty] | Precast Box Conduit (1600x700 mm) |  | M | 3844.55 |  | 3844.55 | 44.9557 | 172834.3788 | 0 | 0 | 0 | 0 | 0
[22 empty] | Precast Box Conduit Supply | Material | M³ | 2200 | 0.57471 | 3828 | 78.2229 | 172090.3622
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 8 | 10 | 5.6195 | 449.5568
[22 empty] | Fuel | Material | LTR | 1.76 | 0.53333 | 3.3 | 84.2919 | 148.3538
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 4 | 3.25 | 11.2389 | 146.106
STR11 |  | Depth 2.0 - 2.5 m | m | 323.7623 | 3784 | 1225116.3729 | 3915.2012 | 1267594.3845 | 323.7623 | 323.7623 |  | 323.7623 | 100% | 3784 | 1225116.3729 | 3915.2012 | 1267594.3845 |  | 1267594.3845 | [7 empty] | 3915.2012 | 323.7623 | 1267594.3845 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 323.7623 | 323.7623 |  | 323.7623 | [9 empty] | Excavation ( W= 3.0 & d= 2.5 ) |  | M | 70.6512 |  | 70.6512 | 323.7623 | 22874.2071 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 13.3333 | 4.2 | 24.2822 | 1359.8015
[22 empty] | Fuel | Material | LTR | 1.76 | 0.95238 | 1.848 | 339.9504 | 598.3126
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 2.72 | 17.6471 | 119.0302 | 5713.4516
[22 empty] | Fuel | Material | LTR | 1.76 | 0.272 | 6.4706 | 1190.3024 | 2094.9322
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 6.4752 | 148.9306
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 19.4257 | 34.1893
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 13.3333 | 3.6 | 24.2822 | 1165.5441
[22 empty] | Fuel | Material | LTR | 1.76 | 1.3333 | 1.32 | 242.8217 | 427.3662
[22 empty] | Steel Shoring D=2.5 M | Material | M | 35 | 1 | 35 | 323.7623 | 11331.6789
[9 empty] | 323.7623 | 323.7623 |  | 323.7623 | [9 empty] | Precast Box Conduit (1600x700 mm) |  | M | 3844.55 |  | 3844.55 | 323.7623 | 1244720.1775 | 0 | 0 | 0 | 0 | 0
[22 empty] | Precast Box Conduit Supply | Material | M³ | 2200 | 0.57471 | 3828 | 563.3463 | 1239361.9121
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 8 | 10 | 40.4703 | 3237.6226
[22 empty] | Fuel | Material | LTR | 1.76 | 0.53333 | 3.3 | 607.0542 | 1068.4154
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 4 | 3.25 | 80.9406 | 1052.2273
STR11 |  | Depth 2.5 - 3.0 m | m | 323.0001 | 3956 | 1277788.5341 | 3947.2184 | 1274952.0685 | 323.0001 | 323.0001 |  | 323.0001 | 100% | 3956 | 1277788.5341 | 3947.2184 | 1274952.0685 |  | 1274952.0685 | [7 empty] | 3947.2184 | 323.0001 | 1274952.0685 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 323.0001 | 323.0001 |  | 323.0001 | [9 empty] | Excavation ( W= 3.0 & d= 3.0 ) |  | M | 102.6684 |  | 102.6684 | 323.0001 | 33161.8995 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 11.1111 | 5.04 | 29.07 | 1627.9207
[22 empty] | Fuel | Material | LTR | 1.76 | 0.79365 | 2.2176 | 406.9802 | 716.2851
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 2.2667 | 21.1765 | 142.5001 | 6840.0029
[22 empty] | Fuel | Material | LTR | 1.76 | 0.22667 | 7.7647 | 1425.0006 | 2508.001
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 6.46 | 148.5801
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 19.38 | 34.1088
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 11.1111 | 4.32 | 29.07 | 1395.3606
[22 empty] | Fuel | Material | LTR | 1.76 | 1.1111 | 1.584 | 290.7001 | 511.6322
[22 empty] | Steel Shoring D>3.0 M | Material | M | 60 | 1 | 60 | 323.0001 | 19380.0081
[9 empty] | 323.0001 | 323.0001 |  | 323.0001 | [9 empty] | Precast Box Conduit (1600x700 mm) |  | M | 3844.55 |  | 3844.55 | 323.0001 | 1241790.169 | 0 | 0 | 0 | 0 | 0
[22 empty] | Precast Box Conduit Supply | Material | M³ | 2200 | 0.57471 | 3828 | 562.0202 | 1236444.5168
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 8 | 10 | 40.375 | 3230.0013
[22 empty] | Fuel | Material | LTR | 1.76 | 0.53333 | 3.3 | 605.6253 | 1065.9004
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 4 | 3.25 | 80.75 | 1049.7504
STR11 |  | Depth 3.0 - 3.5 m | m | 75.5861 | 4145 | 313304.1773 | 3954.2355 | 298885.0427 | 75.5861 | 75.5861 |  | 75.5861 | 100% | 4145 | 313304.1773 | 3954.2355 | 298885.0427 |  | 298885.0427 | [7 empty] | 3954.2355 | 75.5861 | 298885.0427 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 75.5861 | 75.5861 |  | 75.5861 | [9 empty] | Excavation ( W= 3.0 & d= 3.5 ) |  | M | 109.6855 |  | 109.6855 | 75.5861 | 8290.6941 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 9.5238 | 5.88 | 7.9365 | 444.446
[22 empty] | Fuel | Material | LTR | 1.76 | 0.68027 | 2.5872 | 111.1115 | 195.5562
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 1.9429 | 24.7059 | 38.9046 | 1867.4201
[22 empty] | Fuel | Material | LTR | 1.76 | 0.19429 | 9.0588 | 389.0458 | 684.7207
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 1.5117 | 34.7696
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 4.5352 | 7.9819
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 9.5238 | 5.04 | 7.9365 | 380.9537
[22 empty] | Fuel | Material | LTR | 1.76 | 0.95238 | 1.848 | 79.3654 | 139.683
[22 empty] | Steel Shoring D>3.0 M | Material | M | 60 | 1 | 60 | 75.5861 | 4535.163
[9 empty] | 75.5861 | 75.5861 |  | 75.5861 | [9 empty] | Precast Box Conduit (1600x700 mm) |  | M | 3844.55 |  | 3844.55 | 75.5861 | 290594.3485 | 0 | 0 | 0 | 0 | 0
[22 empty] | Precast Box Conduit Supply | Material | M³ | 2200 | 0.57471 | 3828 | 131.5197 | 289343.3994
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 8 | 10 | 9.4483 | 755.8605
[22 empty] | Fuel | Material | LTR | 1.76 | 0.53333 | 3.3 | 141.7238 | 249.434
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 4 | 3.25 | 18.8965 | 245.6547
STR11 |  | Depth 3.5 - 4.0 m | m | 42.8208 | 4354 | 186441.9809 | 3961.2526 | 169624.2049 | 42.8208 | 42.8208 |  | 42.8208 | 100% | 4354 | 186441.9809 | 3961.2526 | 169624.2049 |  | 169624.2049 | [7 empty] | 3961.2526 | 42.8208 | 169624.2049 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 42.8208 | 42.8208 |  | 42.8208 | [9 empty] | Excavation ( W= 3.0 & d= 4.0 ) |  | M | 116.7026 |  | 116.7026 | 42.8208 | 4997.306 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 8.3333 | 6.72 | 5.1385 | 287.7561
[22 empty] | Fuel | Material | LTR | 1.76 | 0.59524 | 2.9568 | 71.939 | 126.6127
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 1.7 | 28.2353 | 25.1887 | 1209.0593
[22 empty] | Fuel | Material | LTR | 1.76 | 0.17 | 10.3529 | 251.8874 | 443.3217
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 0.85642 | 19.6976
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 2.5693 | 4.5219
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 8.3333 | 5.76 | 5.1385 | 246.6481
[22 empty] | Fuel | Material | LTR | 1.76 | 0.83333 | 2.112 | 51.385 | 90.4376
[22 empty] | Steel Shoring D>3.0 M | Material | M | 60 | 1 | 60 | 42.8208 | 2569.251
[9 empty] | 42.8208 | 42.8208 |  | 42.8208 | [9 empty] | Precast Box Conduit (1600x700 mm) |  | M | 3844.55 |  | 3844.55 | 42.8208 | 164626.8989 | 0 | 0 | 0 | 0 | 0
[22 empty] | Precast Box Conduit Supply | Material | M³ | 2200 | 0.57471 | 3828 | 74.5083 | 163918.2138
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 8 | 10 | 5.3526 | 428.2085
[22 empty] | Fuel | Material | LTR | 1.76 | 0.53333 | 3.3 | 80.2891 | 141.3088
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 4 | 3.25 | 10.7052 | 139.1678
STR11 |  | Box pipes measuring (internal) 2000x500 mm in trenches |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Depth 0.0 - 1.5 m | m |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Depth 1.5 - 2.0 m | m | 8.2355 | 4647 | 38270.5079 | 4140.9266 | 34102.7251 | 8.2355 | 8.2355 |  | 8.2355 | 100% | 4647 | 38270.5079 | 4140.9266 | 34102.7251 |  | 34102.7251 | [7 empty] | 4140.9266 | 8.2355 | 34102.7251 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 8.2355 | 8.2355 |  | 8.2355 | [9 empty] | Excavation ( W= 3.4 & d= 2.0 ) |  | M | 32.3766 |  | 32.3766 | 8.2355 | 266.6384 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 14.7059 | 3.808 | 0.56002 | 31.3609
[22 empty] | Fuel | Material | LTR | 1.76 | 1.0504 | 1.6755 | 7.8402 | 13.7988
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 3 | 16 | 2.7452 | 131.7685
[22 empty] | Fuel | Material | LTR | 1.76 | 0.3 | 5.8667 | 27.4518 | 48.3151
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 0.16471 | 3.7883
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 0.49413 | 0.86967
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 14.7059 | 3.264 | 0.56002 | 26.8808
[22 empty] | Fuel | Material | LTR | 1.76 | 1.4706 | 1.1968 | 5.6002 | 9.8563
[9 empty] | 8.2355 | 8.2355 |  | 8.2355 | [9 empty] | Precast Box Conduit (2000x500 mm) |  | M | 4108.55 |  | 4108.55 | 8.2355 | 33836.0868 | 0 | 0 | 0 | 0 | 0
[22 empty] | Precast Box Conduit Supply | Material | M³ | 2200 | 0.53763 | 4092 | 15.3181 | 33699.7888
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 8 | 10 | 1.0294 | 82.3553
[22 empty] | Fuel | Material | LTR | 1.76 | 0.53333 | 3.3 | 15.4416 | 27.1772
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 4 | 3.25 | 2.0589 | 26.7655
STR11 |  | Depth 2.0 - 2.5 m | m | 24.0313 | 4814 | 115686.5338 | 4183.8793 | 100543.9339 | 24.0313 | 24.0313 |  | 24.0313 | 100% | 4814 | 115686.5338 | 4183.8793 | 100543.9339 |  | 100543.9339 | [7 empty] | 4183.8793 | 24.0313 | 100543.9339 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 24.0313 | 24.0313 |  | 24.0313 | [9 empty] | Excavation ( W= 3.4 & d= 2.5 ) |  | M | 75.3293 |  | 75.3293 | 24.0313 | 1810.2595 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 11.7647 | 4.76 | 2.0427 | 114.3888
[22 empty] | Fuel | Material | LTR | 1.76 | 0.84034 | 2.0944 | 28.5972 | 50.3311
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 2.4 | 20 | 10.013 | 480.6254
[22 empty] | Fuel | Material | LTR | 1.76 | 0.24 | 7.3333 | 100.1303 | 176.2293
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 0.48063 | 11.0544
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 1.4419 | 2.5377
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 11.7647 | 4.08 | 2.0427 | 98.0476
[22 empty] | Fuel | Material | LTR | 1.76 | 1.1765 | 1.496 | 20.4266 | 35.9508
[22 empty] | Steel Shoring D=2.5 M | Material | M | 35 | 1 | 35 | 24.0313 | 841.0944
[9 empty] | 24.0313 | 24.0313 |  | 24.0313 | [9 empty] | Precast Box Conduit (2000x500 mm) |  | M | 4108.55 |  | 4108.55 | 24.0313 | 98733.6744 | 0 | 0 | 0 | 0 | 0
[22 empty] | Precast Box Conduit Supply | Material | M³ | 2200 | 0.53763 | 4092 | 44.6982 | 98335.9568
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 8 | 10 | 3.0039 | 240.3127
[22 empty] | Fuel | Material | LTR | 1.76 | 0.53333 | 3.3 | 45.0586 | 79.3032
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 4 | 3.25 | 6.0078 | 78.1016
STR11 |  | Depth 2.5 - 3.0 m | m | 1.4868 | 4999 | 7432.3882 | 4216.8321 | 6269.4805 | 1.4868 | 1.4868 |  | 1.4868 | 100% | 4999 | 7432.3882 | 4216.8321 | 6269.4805 |  | 6269.4805 | [7 empty] | 4216.8321 | 1.4868 | 6269.4805 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 1.4868 | 1.4868 |  | 1.4868 | [9 empty] | Excavation ( W= 3.4 & d= 3.0 ) |  | M | 108.2821 |  | 108.2821 | 1.4868 | 160.9911 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 9.8039 | 5.712 | 0.15165 | 8.4925
[22 empty] | Fuel | Material | LTR | 1.76 | 0.70028 | 2.5133 | 2.1231 | 3.7367
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 2 | 24 | 0.74339 | 35.6826
[22 empty] | Fuel | Material | LTR | 1.76 | 0.2 | 8.8 | 7.4339 | 13.0836
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 0.029735 | 0.68392
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 0.089206 | 0.157
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 9.8039 | 4.896 | 0.15165 | 7.2793
[22 empty] | Fuel | Material | LTR | 1.76 | 0.98039 | 1.7952 | 1.5165 | 2.6691
[22 empty] | Steel Shoring D>3.0 M | Material | M | 60 | 1 | 60 | 1.4868 | 89.2065
[9 empty] | 1.4868 | 1.4868 |  | 1.4868 | [9 empty] | Precast Box Conduit (2000x500 mm) |  | M | 4108.55 |  | 4108.55 | 1.4868 | 6108.4894 | 0 | 0 | 0 | 0 | 0
[22 empty] | Precast Box Conduit Supply | Material | M³ | 2200 | 0.53763 | 4092 | 2.7654 | 6083.8833
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 8 | 10 | 0.18585 | 14.8677
[22 empty] | Fuel | Material | LTR | 1.76 | 0.53333 | 3.3 | 2.7877 | 4.9064
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 4 | 3.25 | 0.37169 | 4.832
STR11 |  | Depth 3.0 - 3.5 m | m |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Depth 3.5 - 4.0 m | m |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Box pipes (internal size) 2000x700 mm in trenches |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Depth 0.0 - 1.5 m |  | 4.8594 | 4784 | 23247.3696 | 4396.9738 | 21366.6547 | 4.8594 | 4.8594 |  | 4.8594 | 100% | 4784 | 23247.3696 | 4396.9738 | 21366.6547 |  | 21366.6547 | [7 empty] | 4396.9738 | 4.8594 | 21366.6547 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 4.8594 | 4.8594 |  | 4.8594 | [9 empty] | Excavation ( W= 3.4 & d= 1.5 ) |  | M | 24.4238 |  | 24.4238 | 4.8594 | 118.6852 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 19.6078 | 2.856 | 0.24783 | 13.8784
[22 empty] | Fuel | Material | LTR | 1.76 | 1.4006 | 1.2566 | 3.4696 | 6.1065
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 4 | 12 | 1.2149 | 58.3128
[22 empty] | Fuel | Material | LTR | 1.76 | 0.4 | 4.4 | 12.1485 | 21.3814
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 0.097188 | 2.2353
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 0.29156 | 0.51315
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 19.6078 | 2.448 | 0.24783 | 11.8958
[22 empty] | Fuel | Material | LTR | 1.76 | 1.9608 | 0.8976 | 2.4783 | 4.3618
[9 empty] | 4.8594 | 4.8594 |  | 4.8594 | [9 empty] | Precast Box Conduit (2000x700 mm) |  | M | 4372.55 |  | 4372.55 | 4.8594 | 21247.9695 | 0 | 0 | 0 | 0 | 0
[22 empty] | Precast Box Conduit Supply | Material | M³ | 2200 | 0.50505 | 4356 | 9.6216 | 21167.5464
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 8 | 10 | 0.60743 | 48.594
[22 empty] | Fuel | Material | LTR | 1.76 | 0.53333 | 3.3 | 9.1114 | 16.036
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 4 | 3.25 | 1.2149 | 15.7931
STR11 |  | Depth 1.5 - 2.0 m | m |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Depth 2.0 - 2.5 m | m | 42.3735 | 5125 | 217163.9569 | 4447.8793 | 188472.0148 | 42.3735 | 42.3735 |  | 42.3735 | 100% | 5125 | 217163.9569 | 4447.8793 | 188472.0148 |  | 188472.0148 | [7 empty] | 4447.8793 | 42.3735 | 188472.0148 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 42.3735 | 42.3735 |  | 42.3735 | [9 empty] | Excavation ( W= 3.4 & d= 2.5 ) |  | M | 75.3293 |  | 75.3293 | 42.3735 | 3191.9641 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 11.7647 | 4.76 | 3.6017 | 201.6976
[22 empty] | Fuel | Material | LTR | 1.76 | 0.84034 | 2.0944 | 50.4244 | 88.747
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 2.4 | 20 | 17.6556 | 847.4691
[22 empty] | Fuel | Material | LTR | 1.76 | 0.24 | 7.3333 | 176.5561 | 310.7387
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 0.84747 | 19.4918
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 2.5424 | 4.4746
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 11.7647 | 4.08 | 3.6017 | 172.8837
[22 empty] | Fuel | Material | LTR | 1.76 | 1.1765 | 1.496 | 36.0174 | 63.3907
[22 empty] | Steel Shoring D=2.5 M | Material | M | 35 | 1 | 35 | 42.3735 | 1483.0709
[9 empty] | 42.3735 | 42.3735 |  | 42.3735 | [9 empty] | Precast Box Conduit (2000x700 mm) |  | M | 4372.55 |  | 4372.55 | 42.3735 | 185280.0507 | 0 | 0 | 0 | 0 | 0
[22 empty] | Precast Box Conduit Supply | Material | M³ | 2200 | 0.50505 | 4356 | 83.8994 | 184578.77
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 8 | 10 | 5.2967 | 423.7345
[22 empty] | Fuel | Material | LTR | 1.76 | 0.53333 | 3.3 | 79.4502 | 139.8324
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 4 | 3.25 | 10.5934 | 137.7137
STR11 |  | Depth 2.5 - 3.0 m | m | 37.109 | 5320 | 197420.131 | 4480.8321 | 166279.409 | 37.109 | 37.109 |  | 37.109 | 100% | 5320 | 197420.131 | 4480.8321 | 166279.409 |  | 166279.409 | [7 empty] | 4480.8321 | 37.109 | 166279.409 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 37.109 | 37.109 |  | 37.109 | [9 empty] | Excavation ( W= 3.4 & d= 3.0 ) |  | M | 108.2821 |  | 108.2821 | 37.109 | 4018.2448 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 9.8039 | 5.712 | 3.7851 | 211.9669
[22 empty] | Fuel | Material | LTR | 1.76 | 0.70028 | 2.5133 | 52.9917 | 93.2654
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 2 | 24 | 18.5545 | 890.6171
[22 empty] | Fuel | Material | LTR | 1.76 | 0.2 | 8.8 | 185.5452 | 326.5596
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 0.74218 | 17.0702
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 2.2265 | 3.9187
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 9.8039 | 4.896 | 3.7851 | 181.6859
[22 empty] | Fuel | Material | LTR | 1.76 | 0.98039 | 1.7952 | 37.8512 | 66.6182
[22 empty] | Steel Shoring D>3.0 M | Material | M | 60 | 1 | 60 | 37.109 | 2226.5428
[9 empty] | 37.109 | 37.109 |  | 37.109 | [9 empty] | Precast Box Conduit (2000x700 mm) |  | M | 4372.55 |  | 4372.55 | 37.109 | 162261.1642 | 0 | 0 | 0 | 0 | 0
[22 empty] | Precast Box Conduit Supply | Material | M³ | 2200 | 0.50505 | 4356 | 73.4759 | 161647.0095
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 8 | 10 | 4.6386 | 371.0905
[22 empty] | Fuel | Material | LTR | 1.76 | 0.53333 | 3.3 | 69.5795 | 122.4599
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 4 | 3.25 | 9.2773 | 120.6044
STR11 |  | Depth 3.0 - 3.5 m | m | 56.3553 | 5536 | 311982.8301 | 4488.7848 | 252966.7258 | 56.3553 | 56.3553 |  | 56.3553 | 100% | 5536 | 311982.8301 | 4488.7848 | 252966.7258 |  | 252966.7258 | [7 empty] | 4488.7848 | 56.3553 | 252966.7258 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 56.3553 | 56.3553 |  | 56.3553 | [9 empty] | Excavation ( W= 3.4 & d= 3.5 ) |  | M | 116.2348 |  | 116.2348 | 56.3553 | 6550.4462 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 8.4034 | 6.664 | 6.7063 | 375.5516
[22 empty] | Fuel | Material | LTR | 1.76 | 0.60024 | 2.9322 | 93.8879 | 165.2427
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 1.7143 | 28 | 32.8739 | 1577.9478
[22 empty] | Fuel | Material | LTR | 1.76 | 0.17143 | 10.2667 | 328.7391 | 578.5809
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 1.1271 | 25.9234
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 3.3813 | 5.9511
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 8.4034 | 5.712 | 6.7063 | 321.9014
[22 empty] | Fuel | Material | LTR | 1.76 | 0.84034 | 2.0944 | 67.0628 | 118.0305
[22 empty] | Steel Shoring D>3.0 M | Material | M | 60 | 1 | 60 | 56.3553 | 3381.3168
[9 empty] | 56.3553 | 56.3553 |  | 56.3553 | [9 empty] | Precast Box Conduit (2000x700 mm) |  | M | 4372.55 |  | 4372.55 | 56.3553 | 246416.2796 | 0 | 0 | 0 | 0 | 0
[22 empty] | Precast Box Conduit Supply | Material | M³ | 2200 | 0.50505 | 4356 | 111.5835 | 245483.5997
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 8 | 10 | 7.0444 | 563.5528
[22 empty] | Fuel | Material | LTR | 1.76 | 0.53333 | 3.3 | 105.6662 | 185.9724
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 4 | 3.25 | 14.0888 | 183.1547
STR11 |  | Depth 3.5 - 4.0 m | m | 11.5629 | 5773 | 66752.6217 | 4496.7376 | 51995.3269 | 11.5629 | 11.5629 |  | 11.5629 | 100% | 5773 | 66752.6217 | 4496.7376 | 51995.3269 |  | 51995.3269 | [7 empty] | 4496.7376 | 11.5629 | 51995.3269 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 11.5629 | 11.5629 |  | 11.5629 | [9 empty] | Excavation ( W= 3.4 & d= 4.0 ) |  | M | 124.1876 |  | 124.1876 | 11.5629 | 1435.9685 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 7.3529 | 7.616 | 1.5726 | 88.063
[22 empty] | Fuel | Material | LTR | 1.76 | 0.52521 | 3.351 | 22.0158 | 38.7477
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 1.5 | 32 | 7.7086 | 370.0128
[22 empty] | Fuel | Material | LTR | 1.76 | 0.15 | 11.7333 | 77.086 | 135.6714
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 0.23126 | 5.3189
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 0.69377 | 1.221
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 7.3529 | 6.528 | 1.5726 | 75.4826
[22 empty] | Fuel | Material | LTR | 1.76 | 0.73529 | 2.3936 | 15.7255 | 27.677
[22 empty] | Steel Shoring D>3.0 M | Material | M | 60 | 1 | 60 | 11.5629 | 693.774
[9 empty] | 11.5629 | 11.5629 |  | 11.5629 | [9 empty] | Precast Box Conduit (2000x700 mm) |  | M | 4372.55 |  | 4372.55 | 11.5629 | 50559.3584 | 0 | 0 | 0 | 0 | 0
[22 empty] | Precast Box Conduit Supply | Material | M³ | 2200 | 0.50505 | 4356 | 22.8945 | 50367.9924
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 8 | 10 | 1.4454 | 115.629
[22 empty] | Fuel | Material | LTR | 1.76 | 0.53333 | 3.3 | 21.6804 | 38.1576
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 4 | 3.25 | 2.8907 | 37.5794
STR11 |  | Box pipes measuring (internal) 1600x800 mm in trenches |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Depth 0.0 - 1.5 m | m |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Depth 1.5 - 2.0 m | m |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Depth 2.0 - 2.5 m | m |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Depth 2.5 - 3.0 m | m |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Depth 3.0 - 3.5 m | m | 6.318 | 5033 | 31798.494 | 4086.2355 | 25816.8359 | 6.318 | 6.318 |  | 6.318 | 100% | 5033 | 31798.494 | 4086.2355 | 25816.8359 |  | 25816.8359 | [7 empty] | 4086.2355 | 6.318 | 25816.8359 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 6.318 | 6.318 |  | 6.318 | [9 empty] | Excavation ( W= 3.0 & d= 3.5 ) |  | M | 109.6855 |  | 109.6855 | 6.318 | 692.993 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 9.5238 | 5.88 | 0.66339 | 37.1498
[22 empty] | Fuel | Material | LTR | 1.76 | 0.68027 | 2.5872 | 9.2875 | 16.3459
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 1.9429 | 24.7059 | 3.2519 | 156.0918
[22 empty] | Fuel | Material | LTR | 1.76 | 0.19429 | 9.0588 | 32.5191 | 57.2336
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 0.12636 | 2.9063
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 0.37908 | 0.66718
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 9.5238 | 5.04 | 0.66339 | 31.8427
[22 empty] | Fuel | Material | LTR | 1.76 | 0.95238 | 1.848 | 6.6339 | 11.6757
[22 empty] | Steel Shoring D>3.0 M | Material | M | 60 | 1 | 60 | 6.318 | 379.08
[9 empty] | 6.318 | 6.318 |  | 6.318 | [9 empty] | Precast Box Conduit (1600x800 mm) |  | M | 3976.55 |  | 3976.55 | 6.318 | 25123.8429 | 0 | 0 | 0 | 0 | 0
[22 empty] | Precast Box Conduit Supply | Material | M³ | 2200 | 0.55556 | 3960 | 11.3724 | 25019.28
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 8 | 10 | 0.78975 | 63.18
[22 empty] | Fuel | Material | LTR | 1.76 | 0.53333 | 3.3 | 11.8463 | 20.8494
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 4 | 3.25 | 1.5795 | 20.5335
STR11 |  | Depth 3.5 - 4.0 m | m |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Box pipes (internal) 2000x800 mm in trenches |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Depth 0.0 - 1.5 m | m | 9.8585 | 4931 | 48612.2635 | 4528.9738 | 44648.8886 | 9.8585 | 9.8585 |  | 9.8585 | 100% | 4931 | 48612.2635 | 4528.9738 | 44648.8886 |  | 44648.8886 | [7 empty] | 4528.9738 | 9.8585 | 44648.8886 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 9.8585 | 9.8585 |  | 9.8585 | [9 empty] | Excavation ( W= 3.4 & d= 1.5 ) |  | M | 24.4238 |  | 24.4238 | 9.8585 | 240.7824 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 19.6078 | 2.856 | 0.50278 | 28.1559
[22 empty] | Fuel | Material | LTR | 1.76 | 1.4006 | 1.2566 | 7.039 | 12.3886
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 4 | 12 | 2.4646 | 118.302
[22 empty] | Fuel | Material | LTR | 1.76 | 0.4 | 4.4 | 24.6462 | 43.3774
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 0.19717 | 4.5349
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 0.59151 | 1.0411
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 19.6078 | 2.448 | 0.50278 | 24.1336
[22 empty] | Fuel | Material | LTR | 1.76 | 1.9608 | 0.8976 | 5.0278 | 8.849
[9 empty] | 9.8585 | 9.8585 |  | 9.8585 | [9 empty] | Precast Box Conduit (2000x800 mm) |  | M | 4504.55 |  | 4504.55 | 9.8585 | 44408.1062 | 0 | 0 | 0 | 0 | 0
[22 empty] | Precast Box Conduit Supply | Material | M³ | 2200 | 0.4902 | 4488 | 20.1113 | 44244.948
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 8 | 10 | 1.2323 | 98.585
[22 empty] | Fuel | Material | LTR | 1.76 | 0.53333 | 3.3 | 18.4847 | 32.533
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 4 | 3.25 | 2.4646 | 32.0401
STR11 |  | Depth 1.5 - 2.0 m | m | 10.8369 | 5097 | 55235.6793 | 4536.9266 | 49166.2197 | 10.8369 | 10.8369 |  | 10.8369 | 100% | 5097 | 55235.6793 | 4536.9266 | 49166.2197 |  | 49166.2197 | [7 empty] | 4536.9266 | 10.8369 | 49166.2197 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 10.8369 | 10.8369 |  | 10.8369 | [9 empty] | Excavation ( W= 3.4 & d= 2.0 ) |  | M | 32.3766 |  | 32.3766 | 10.8369 | 350.8618 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 14.7059 | 3.808 | 0.73691 | 41.2669
[22 empty] | Fuel | Material | LTR | 1.76 | 1.0504 | 1.6755 | 10.3167 | 18.1574
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 3 | 16 | 3.6123 | 173.3904
[22 empty] | Fuel | Material | LTR | 1.76 | 0.3 | 5.8667 | 36.123 | 63.5765
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 0.21674 | 4.985
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 0.65021 | 1.1444
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 14.7059 | 3.264 | 0.73691 | 35.3716
[22 empty] | Fuel | Material | LTR | 1.76 | 1.4706 | 1.1968 | 7.3691 | 12.9696
[9 empty] | 10.8369 | 10.8369 |  | 10.8369 | [9 empty] | Precast Box Conduit (2000x800 mm) |  | M | 4504.55 |  | 4504.55 | 10.8369 | 48815.3579 | 0 | 0 | 0 | 0 | 0
[22 empty] | Precast Box Conduit Supply | Material | M³ | 2200 | 0.4902 | 4488 | 22.1073 | 48636.0072
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 8 | 10 | 1.3546 | 108.369
[22 empty] | Fuel | Material | LTR | 1.76 | 0.53333 | 3.3 | 20.3192 | 35.7618
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 4 | 3.25 | 2.7092 | 35.2199
STR11 |  | Depth 2.0 - 2.5 m | m | 19.9955 | 5280 | 105576.24 | 4579.8793 | 91576.9772 | 19.9955 | 19.9955 |  | 19.9955 | 100% | 5280 | 105576.24 | 4579.8793 | 91576.9772 |  | 91576.9772 | [7 empty] | 4579.8793 | 19.9955 | 91576.9772 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 19.9955 | 19.9955 |  | 19.9955 | [9 empty] | Excavation ( W= 3.4 & d= 2.5 ) |  | M | 75.3293 |  | 75.3293 | 19.9955 | 1506.2477 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 11.7647 | 4.76 | 1.6996 | 95.1786
[22 empty] | Fuel | Material | LTR | 1.76 | 0.84034 | 2.0944 | 23.7946 | 41.8786
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 2.4 | 20 | 8.3315 | 399.91
[22 empty] | Fuel | Material | LTR | 1.76 | 0.24 | 7.3333 | 83.3146 | 146.6337
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 0.39991 | 9.1979
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 1.1997 | 2.1115
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 11.7647 | 4.08 | 1.6996 | 81.5816
[22 empty] | Fuel | Material | LTR | 1.76 | 1.1765 | 1.496 | 16.9962 | 29.9133
[22 empty] | Steel Shoring D=2.5 M | Material | M | 35 | 1 | 35 | 19.9955 | 699.8425
[9 empty] | 19.9955 | 19.9955 |  | 19.9955 | [9 empty] | Precast Box Conduit (2000x800 mm) |  | M | 4504.55 |  | 4504.55 | 19.9955 | 90070.7295 | 0 | 0 | 0 | 0 | 0
[22 empty] | Precast Box Conduit Supply | Material | M³ | 2200 | 0.4902 | 4488 | 40.7908 | 89739.804
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 8 | 10 | 2.4994 | 199.955
[22 empty] | Fuel | Material | LTR | 1.76 | 0.53333 | 3.3 | 37.4916 | 65.9851
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 4 | 3.25 | 4.9989 | 64.9854
STR11 |  | Depth 2.5 - 3.0 m | m | 43.7439 | 5482 | 239804.3339 | 4612.8321 | 201783.4959 | 43.7439 | 43.7439 |  | 43.7439 | 100% | 5482 | 239804.3339 | 4612.8321 | 201783.4959 |  | 201783.4959 | [7 empty] | 4612.8321 | 43.7439 | 201783.4959 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 43.7439 | 43.7439 |  | 43.7439 | [9 empty] | Excavation ( W= 3.4 & d= 3.0 ) |  | M | 108.2821 |  | 108.2821 | 43.7439 | 4736.6859 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 9.8039 | 5.712 | 4.4619 | 249.8654
[22 empty] | Fuel | Material | LTR | 1.76 | 0.70028 | 2.5133 | 62.4664 | 109.9408
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 2 | 24 | 21.872 | 1049.8548
[22 empty] | Fuel | Material | LTR | 1.76 | 0.2 | 8.8 | 218.7197 | 384.9468
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 0.87488 | 20.1222
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 2.6246 | 4.6194
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 9.8039 | 4.896 | 4.4619 | 214.1704
[22 empty] | Fuel | Material | LTR | 1.76 | 0.98039 | 1.7952 | 44.6188 | 78.5291
[22 empty] | Steel Shoring D>3.0 M | Material | M | 60 | 1 | 60 | 43.7439 | 2624.637
[9 empty] | 43.7439 | 43.7439 |  | 43.7439 | [9 empty] | Precast Box Conduit (2000x800 mm) |  | M | 4504.55 |  | 4504.55 | 43.7439 | 197046.81 | 0 | 0 | 0 | 0 | 0
[22 empty] | Precast Box Conduit Supply | Material | M³ | 2200 | 0.4902 | 4488 | 89.2377 | 196322.8476
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 8 | 10 | 5.468 | 437.4395
[22 empty] | Fuel | Material | LTR | 1.76 | 0.53333 | 3.3 | 82.0199 | 144.355
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 4 | 3.25 | 10.936 | 142.1678
STR11 |  | Depth 3.0 - 3.5 m | m | 37.273 | 5705 | 212642.2368 | 4620.7848 | 172230.328 | 37.273 | 37.273 |  | 37.273 | 100% | 5705 | 212642.2368 | 4620.7848 | 172230.328 |  | 172230.328 | [7 empty] | 4620.7848 | 37.273 | 172230.328 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 37.273 | 37.273 |  | 37.273 | [9 empty] | Excavation ( W= 3.4 & d= 3.5 ) |  | M | 116.2348 |  | 116.2348 | 37.273 | 4332.416 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 8.4034 | 6.664 | 4.4355 | 248.387
[22 empty] | Fuel | Material | LTR | 1.76 | 0.60024 | 2.9322 | 62.0968 | 109.2903
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 1.7143 | 28 | 21.7426 | 1043.6429
[22 empty] | Fuel | Material | LTR | 1.76 | 0.17143 | 10.2667 | 217.4256 | 382.6691
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 0.74546 | 17.1456
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 2.2364 | 3.936
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 8.4034 | 5.712 | 4.4355 | 212.9031
[22 empty] | Fuel | Material | LTR | 1.76 | 0.84034 | 2.0944 | 44.3548 | 78.0645
[22 empty] | Steel Shoring D>3.0 M | Material | M | 60 | 1 | 60 | 37.273 | 2236.3776
[9 empty] | 37.273 | 37.273 |  | 37.273 | [9 empty] | Precast Box Conduit (2000x800 mm) |  | M | 4504.55 |  | 4504.55 | 37.273 | 167897.912 | 0 | 0 | 0 | 0 | 0
[22 empty] | Precast Box Conduit Supply | Material | M³ | 2200 | 0.4902 | 4488 | 76.0368 | 167281.0445
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 8 | 10 | 4.6591 | 372.7296
[22 empty] | Fuel | Material | LTR | 1.76 | 0.53333 | 3.3 | 69.8868 | 123.0008
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 4 | 3.25 | 9.3182 | 121.1371
STR11 |  | Depth 3.5 - 4.0 m | m | 6.9797 | 5949 | 41522.2056 | 4628.7376 | 32307.1765 | 6.9797 | 6.9797 |  | 6.9797 | 100% | 5949 | 41522.2056 | 4628.7376 | 32307.1765 |  | 32307.1765 | [7 empty] | 4628.7376 | 6.9797 | 32307.1765 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 6.9797 | 6.9797 |  | 6.9797 | [9 empty] | Excavation ( W= 3.4 & d= 4.0 ) |  | M | 124.1876 |  | 124.1876 | 6.9797 | 866.7914 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 7.3529 | 7.616 | 0.94924 | 53.1574
[22 empty] | Fuel | Material | LTR | 1.76 | 0.52521 | 3.351 | 13.2893 | 23.3892
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 1.5 | 32 | 4.6531 | 223.3502
[22 empty] | Fuel | Material | LTR | 1.76 | 0.15 | 11.7333 | 46.5313 | 81.8951
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 0.13959 | 3.2107
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 0.41878 | 0.73706
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 7.3529 | 6.528 | 0.94924 | 45.5634
[22 empty] | Fuel | Material | LTR | 1.76 | 0.73529 | 2.3936 | 9.4924 | 16.7066
[22 empty] | Steel Shoring D>3.0 M | Material | M | 60 | 1 | 60 | 6.9797 | 418.7817
[9 empty] | 6.9797 | 6.9797 |  | 6.9797 | [9 empty] | Precast Box Conduit (2000x800 mm) |  | M | 4504.55 |  | 4504.55 | 6.9797 | 31440.3851 | 0 | 0 | 0 | 0 | 0
[22 empty] | Precast Box Conduit Supply | Material | M³ | 2200 | 0.4902 | 4488 | 14.2386 | 31324.8712
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 8 | 10 | 0.87246 | 69.7969
[22 empty] | Fuel | Material | LTR | 1.76 | 0.53333 | 3.3 | 13.0869 | 23.033
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 4 | 3.25 | 1.7449 | 22.684
STR11 |  | Box pipes measuring (internal) 2500x700 mm in trenches |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Depth 0.0 - 1.5 m | m |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Depth 1.5 - 2.0 m | m |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Depth 2.0 - 2.5 m | m |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Depth 2.5 - 3.0 m | m | 10.7289 | 6543 | 70199.1927 | 5147.8492 | 55230.7594 | 10.7289 | 10.7289 |  | 10.7289 | 100% | 6543 | 70199.1927 | 5147.8492 | 55230.7594 |  | 55230.7594 | [7 empty] | 5147.8492 | 10.7289 | 55230.7594 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 10.7289 | 10.7289 |  | 10.7289 | [9 empty] | Excavation ( W= 3.9 & d= 3.0 ) |  | M | 115.2992 |  | 115.2992 | 10.7289 | 1237.0337 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 8.547 | 6.552 | 1.2553 | 70.2958
[22 empty] | Fuel | Material | LTR | 1.76 | 0.6105 | 2.8829 | 17.5739 | 30.9301
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 1.7436 | 27.5294 | 6.1533 | 295.3603
[22 empty] | Fuel | Material | LTR | 1.76 | 0.17436 | 10.0941 | 61.5334 | 108.2988
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 0.21458 | 4.9353
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 0.64373 | 1.133
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 8.547 | 5.616 | 1.2553 | 60.2535
[22 empty] | Fuel | Material | LTR | 1.76 | 0.8547 | 2.0592 | 12.5528 | 22.093
[22 empty] | Steel Shoring D>3.0 M | Material | M | 60 | 1 | 60 | 10.7289 | 643.734
[9 empty] | 10.7289 | 10.7289 |  | 10.7289 | [9 empty] | Precast Box Conduit (2500x700 mm) |  | M | 5032.55 |  | 5032.55 | 10.7289 | 53993.7257 | 0 | 0 | 0 | 0 | 0
[22 empty] | Precast Box Conduit Supply | Material | M³ | 2200 | 0.4386 | 5016 | 24.4619 | 53816.1624
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 8 | 10 | 1.3411 | 107.289
[22 empty] | Fuel | Material | LTR | 1.76 | 0.53333 | 3.3 | 20.1167 | 35.4054
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 4 | 3.25 | 2.6822 | 34.8689
STR11 |  | Depth 3.0 - 3.5 m | m | 6.5639 | 6809 | 44693.7313 | 5156.9715 | 33849.9482 | 6.5639 | 6.5639 |  | 6.5639 | 100% | 6809 | 44693.7313 | 5156.9715 | 33849.9482 |  | 33849.9482 | [7 empty] | 5156.9715 | 6.5639 | 33849.9482 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 6.5639 | 6.5639 |  | 6.5639 | [9 empty] | Excavation ( W= 3.9 & d= 3.5 ) |  | M | 124.4215 |  | 124.4215 | 6.5639 | 816.6926 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 7.326 | 7.644 | 0.89598 | 50.1746
[22 empty] | Fuel | Material | LTR | 1.76 | 0.52329 | 3.3634 | 12.5437 | 22.0768
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 1.4945 | 32.1176 | 4.392 | 210.8177
[22 empty] | Fuel | Material | LTR | 1.76 | 0.14945 | 11.7765 | 43.9203 | 77.2998
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 0.13128 | 3.0194
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 0.39384 | 0.69315
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 7.326 | 6.552 | 0.89598 | 43.0068
[22 empty] | Fuel | Material | LTR | 1.76 | 0.7326 | 2.4024 | 8.9598 | 15.7692
[22 empty] | Steel Shoring D>3.0 M | Material | M | 60 | 1 | 60 | 6.5639 | 393.8352
[9 empty] | 6.5639 | 6.5639 |  | 6.5639 | [9 empty] | Precast Box Conduit (2500x700 mm) |  | M | 5032.55 |  | 5032.55 | 6.5639 | 33033.2556 | 0 | 0 | 0 | 0 | 0
[22 empty] | Precast Box Conduit Supply | Material | M³ | 2200 | 0.4386 | 5016 | 14.9657 | 32924.6227
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 8 | 10 | 0.82049 | 65.6392
[22 empty] | Fuel | Material | LTR | 1.76 | 0.53333 | 3.3 | 12.3073 | 21.6609
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 4 | 3.25 | 1.641 | 21.3327
STR11 |  | Depth 3.5 - 4.0 m |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Rainwater drainage network
STR11 |  | Box pipes measuring (internal) 2500x800 mm in trenches |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Depth 0.0 - 1.5 m | m |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Depth 1.5 - 2.0 m | m |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Depth 2.0 - 2.5 m | m |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Depth 2.5 - 3.0 m | m | 9.2249 | 6704 | 61843.3944 | 5279.8492 | 48705.817 | 9.2249 | 9.2249 |  | 9.2249 | 100% | 6704 | 61843.3944 | 5279.8492 | 48705.817 |  | 48705.817 | [7 empty] | 5279.8492 | 9.2249 | 48705.817 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 9.2249 | 9.2249 |  | 9.2249 | [9 empty] | Excavation ( W= 3.9 & d= 3.0 ) |  | M | 115.2992 |  | 115.2992 | 9.2249 | 1063.6179 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 8.547 | 6.552 | 1.0793 | 60.4412
[22 empty] | Fuel | Material | LTR | 1.76 | 0.6105 | 2.8829 | 15.1103 | 26.5941
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 1.7436 | 27.5294 | 5.2907 | 253.9547
[22 empty] | Fuel | Material | LTR | 1.76 | 0.17436 | 10.0941 | 52.9072 | 93.1167
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 0.1845 | 4.2434
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 0.55349 | 0.97414
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 8.547 | 5.616 | 1.0793 | 51.8068
[22 empty] | Fuel | Material | LTR | 1.76 | 0.8547 | 2.0592 | 10.7931 | 18.9958
[22 empty] | Steel Shoring D>3.0 M | Material | M | 60 | 1 | 60 | 9.2249 | 553.491
[9 empty] | 9.2249 | 9.2249 |  | 9.2249 | [9 empty] | Precast Box Conduit (2500x800 mm) |  | M | 5164.55 |  | 5164.55 | 9.2249 | 47642.1991 | 0 | 0 | 0 | 0 | 0
[22 empty] | Precast Box Conduit Supply | Material | M³ | 2200 | 0.42735 | 5148 | 21.5861 | 47489.5278
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 8 | 10 | 1.1531 | 92.2485
[22 empty] | Fuel | Material | LTR | 1.76 | 0.53333 | 3.3 | 17.2966 | 30.442
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 4 | 3.25 | 2.3062 | 29.9808
STR11 |  | Depth 3.0 - 3.5 m | m | 15.9613 | 6976 | 111345.8544 | 5288.9715 | 84418.7282 | 15.9613 | 15.9613 |  | 15.9613 | 100% | 6976 | 111345.8544 | 5288.9715 | 84418.7282 |  | 84418.7282 | [7 empty] | 5288.9715 | 15.9613 | 84418.7282 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 15.9613 | 15.9613 |  | 15.9613 | [9 empty] | Excavation ( W= 3.9 & d= 3.5 ) |  | M | 124.4215 |  | 124.4215 | 15.9613 | 1985.9254 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 7.326 | 7.644 | 2.1787 | 122.008
[22 empty] | Fuel | Material | LTR | 1.76 | 0.52329 | 3.3634 | 30.502 | 53.6835
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 1.4945 | 32.1176 | 10.68 | 512.6386
[22 empty] | Fuel | Material | LTR | 1.76 | 0.14945 | 11.7765 | 106.7997 | 187.9675
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 0.31923 | 7.3422
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 0.95768 | 1.6855
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 7.326 | 6.552 | 2.1787 | 104.5783
[22 empty] | Fuel | Material | LTR | 1.76 | 0.7326 | 2.4024 | 21.7871 | 38.3454
[22 empty] | Steel Shoring D>3.0 M | Material | M | 60 | 1 | 60 | 15.9613 | 957.6765
[9 empty] | 15.9613 | 15.9613 |  | 15.9613 | [9 empty] | Precast Box Conduit (2500x800 mm) |  | M | 5164.55 |  | 5164.55 | 15.9613 | 82432.8028 | 0 | 0 | 0 | 0 | 0
[22 empty] | Precast Box Conduit Supply | Material | M³ | 2200 | 0.42735 | 5148 | 37.3494 | 82168.6437
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 8 | 10 | 1.9952 | 159.6128
[22 empty] | Fuel | Material | LTR | 1.76 | 0.53333 | 3.3 | 29.9274 | 52.6722
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 4 | 3.25 | 3.9903 | 51.8741
STR11 |  | Depth 3.5 - 4.0 m | m |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Box pipes measuring (internal) 3000x500 mm in trenches |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Depth 0.0 - 1.5 m | m | 2.28 | 6815 | 15538.2 | 5459.991 | 12448.7794 | 2.28 | 2.28 |  | 2.28 | 100% | 6815 | 15538.2 | 5459.991 | 12448.7794 |  | 12448.7794 | [7 empty] | 5459.991 | 2.28 | 12448.7794 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 2.28 | 2.28 |  | 2.28 | [9 empty] | Excavation ( W= 4.4 & d= 1.5 ) |  | M | 31.441 |  | 31.441 | 2.28 | 71.6854 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 15.1515 | 3.696 | 0.15048 | 8.4269
[22 empty] | Fuel | Material | LTR | 1.76 | 1.0823 | 1.6262 | 2.1067 | 3.7078
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 3.0909 | 15.5294 | 0.73765 | 35.4071
[22 empty] | Fuel | Material | LTR | 1.76 | 0.30909 | 5.6941 | 7.3765 | 12.9826
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 0.0456 | 1.0488
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 0.1368 | 0.24077
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 15.1515 | 3.168 | 0.15048 | 7.223
[22 empty] | Fuel | Material | LTR | 1.76 | 1.5152 | 1.1616 | 1.5048 | 2.6484
[9 empty] | 2.28 | 2.28 |  | 2.28 | [9 empty] | Precast Box Conduit (3000x500 mm) |  | M | 5428.55 |  | 5428.55 | 2.28 | 12377.094 | 0 | 0 | 0 | 0 | 0
[22 empty] | Precast Box Conduit Supply | Material | M³ | 2200 | 0.4065 | 5412 | 5.6088 | 12339.36
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 8 | 10 | 0.285 | 22.8
[22 empty] | Fuel | Material | LTR | 1.76 | 0.53333 | 3.3 | 4.275 | 7.524
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 4 | 3.25 | 0.57 | 7.41
STR11 |  | Box pipes measuring (internal) 1800x500 mm in trenches |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Depth 0.0 - 1.5 m | m | 4.104 | 4206 | 17261.424 | 3867.5704 | 15872.509 | 4.104 | 4.104 |  | 4.104 | 100% | 4206 | 17261.424 | 3867.5704 | 15872.509 |  | 15872.509 | [7 empty] | 3867.5704 | 4.104 | 15872.509 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 4.104 | 4.104 |  | 4.104 | [9 empty] | Excavation ( W= 3.2 & d= 1.5 ) |  | M | 23.0204 |  | 23.0204 | 4.104 | 94.4758 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 20.8333 | 2.688 | 0.19699 | 11.0316
[22 empty] | Fuel | Material | LTR | 1.76 | 1.4881 | 1.1827 | 2.7579 | 4.8539
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 4.25 | 11.2941 | 0.96565 | 46.3511
[22 empty] | Fuel | Material | LTR | 1.76 | 0.425 | 4.1412 | 9.6565 | 16.9954
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 0.08208 | 1.8878
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 0.24624 | 0.43338
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 20.8333 | 2.304 | 0.19699 | 9.4556
[22 empty] | Fuel | Material | LTR | 1.76 | 2.0833 | 0.8448 | 1.9699 | 3.4671
[9 empty] | 4.104 | 4.104 |  | 4.104 | [9 empty] | Precast Box Conduit (1800x500 mm) |  | M | 3844.55 |  | 3844.55 | 4.104 | 15778.0332 | 0 | 0 | 0 | 0 | 0
[22 empty] | Precast Box Conduit Supply | Material | M³ | 2200 | 0.57471 | 3828 | 7.141 | 15710.112
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 8 | 10 | 0.513 | 41.04
[22 empty] | Fuel | Material | LTR | 1.76 | 0.53333 | 3.3 | 7.695 | 13.5432
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 4 | 3.25 | 1.026 | 13.338
STR11 |  | Box pipes measuring (internal) 2000x600 mm in trenches |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Depth 0.0 - 1.5 m |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Depth 1.5 - 2.0 m | m | 29.4273 | 4796 | 141133.3308 | 4272.9266 | 125740.6925 | 29.4273 | 29.4273 |  | 29.4273 | 100% | 4796 | 141133.3308 | 4272.9266 | 125740.6925 |  | 125740.6925 | [7 empty] | 4272.9266 | 29.4273 | 125740.6925 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 29.4273 | 29.4273 |  | 29.4273 | [9 empty] | Excavation ( W= 3.4 & d= 2.0 ) |  | M | 32.3766 |  | 32.3766 | 29.4273 | 952.7555 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 14.7059 | 3.808 | 2.0011 | 112.0592
[22 empty] | Fuel | Material | LTR | 1.76 | 1.0504 | 1.6755 | 28.0148 | 49.306
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 3 | 16 | 9.8091 | 470.8368
[22 empty] | Fuel | Material | LTR | 1.76 | 0.3 | 5.8667 | 98.091 | 172.6402
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 0.58855 | 13.5366
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 1.7656 | 3.1075
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 14.7059 | 3.264 | 2.0011 | 96.0507
[22 empty] | Fuel | Material | LTR | 1.76 | 1.4706 | 1.1968 | 20.0106 | 35.2186
[9 empty] | 29.4273 | 29.4273 |  | 29.4273 | [9 empty] | Precast Box Conduit (2000x600 mm) |  | M | 4240.55 |  | 4240.55 | 29.4273 | 124787.937 | 0 | 0 | 0 | 0 | 0
[22 empty] | Precast Box Conduit Supply | Material | M³ | 2200 | 0.52083 | 4224 | 56.5004 | 124300.9152
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 8 | 10 | 3.6784 | 294.273
[22 empty] | Fuel | Material | LTR | 1.76 | 0.53333 | 3.3 | 55.1762 | 97.1101
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 4 | 3.25 | 7.3568 | 95.6387
STR11 |  | Box pipes (internal size) 2000x750 mm in trenches |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Depth 1.5 - 2.0 m |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Depth 2.0 - 2.5 m | m | 4.5679 | 5204 | 23771.2215 | 4513.8793 | 20618.8366 | 4.5679 | 4.5679 |  | 4.5679 | 100% | 5204 | 23771.2215 | 4513.8793 | 20618.8366 |  | 20618.8366 | [7 empty] | 4513.8793 | 4.5679 | 20618.8366 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 4.5679 | 4.5679 |  | 4.5679 | [9 empty] | Excavation ( W= 3.4 & d= 2.5 ) |  | M | 75.3293 |  | 75.3293 | 4.5679 | 344.095 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 11.7647 | 4.76 | 0.38827 | 21.7431
[22 empty] | Fuel | Material | LTR | 1.76 | 0.84034 | 2.0944 | 5.4358 | 9.567
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 2.4 | 20 | 1.9033 | 91.3575
[22 empty] | Fuel | Material | LTR | 1.76 | 0.24 | 7.3333 | 19.0328 | 33.4978
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 0.091358 | 2.1012
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 0.27407 | 0.48237
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 11.7647 | 4.08 | 0.38827 | 18.6369
[22 empty] | Fuel | Material | LTR | 1.76 | 1.1765 | 1.496 | 3.8827 | 6.8335
[22 empty] | Steel Shoring D=2.5 M | Material | M | 35 | 1 | 35 | 4.5679 | 159.8756
[9 empty] | 4.5679 | 4.5679 |  | 4.5679 | [9 empty] | Precast Box Conduit (2000x750 mm) |  | M | 4438.55 |  | 4438.55 | 4.5679 | 20274.7416 | 0 | 0 | 0 | 0 | 0
[22 empty] | Precast Box Conduit Supply | Material | M³ | 2200 | 0.49751 | 4422 | 9.1814 | 20199.1433
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 8 | 10 | 0.57098 | 45.6788
[22 empty] | Fuel | Material | LTR | 1.76 | 0.53333 | 3.3 | 8.5648 | 15.074
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 4 | 3.25 | 1.142 | 14.8456
STR11 |  | Depth 2.5 - 3.0 m | m | 15.3029 | 5402 | 82666.1307 | 4546.8321 | 69579.603 | 15.3029 | 15.3029 |  | 15.3029 | 100% | 5402 | 82666.1307 | 4546.8321 | 69579.603 |  | 69579.603 | [7 empty] | 4546.8321 | 15.3029 | 69579.603 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 15.3029 | 15.3029 |  | 15.3029 | [9 empty] | Excavation ( W= 3.4 & d= 3.0 ) |  | M | 108.2821 |  | 108.2821 | 15.3029 | 1657.0271 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 9.8039 | 5.712 | 1.5609 | 87.41
[22 empty] | Fuel | Material | LTR | 1.76 | 0.70028 | 2.5133 | 21.8525 | 38.4604
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 2 | 24 | 7.6514 | 367.269
[22 empty] | Fuel | Material | LTR | 1.76 | 0.2 | 8.8 | 76.5144 | 134.6653
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 0.30606 | 7.0393
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 0.91817 | 1.616
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 9.8039 | 4.896 | 1.5609 | 74.9229
[22 empty] | Fuel | Material | LTR | 1.76 | 0.98039 | 1.7952 | 15.6089 | 27.4717
[22 empty] | Steel Shoring D>3.0 M | Material | M | 60 | 1 | 60 | 15.3029 | 918.1725
[9 empty] | 15.3029 | 15.3029 |  | 15.3029 | [9 empty] | Precast Box Conduit (2000x750 mm) |  | M | 4438.55 |  | 4438.55 | 15.3029 | 67922.5758 | 0 | 0 | 0 | 0 | 0
[22 empty] | Precast Box Conduit Supply | Material | M³ | 2200 | 0.49751 | 4422 | 30.7588 | 67669.3132
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 8 | 10 | 1.9129 | 153.0287
[22 empty] | Fuel | Material | LTR | 1.76 | 0.53333 | 3.3 | 28.6929 | 50.4995
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 4 | 3.25 | 3.8257 | 49.7343
STR11 |  | Box pipes (internal size) 2500 x 750 mm in trenches |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Depth 0.0 - 1.5 m |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Box pipes (internal size) 3000x800 mm in trenches |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Depth 2.5 - 3.0 m |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Box pipes (internal size) 3500x700 mm in trenches |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Depth 1.5 - 2.0 m |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Depth 2.5 - 3.0 m |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Box pipes (internal size) 3500 x 800 mm in trenches |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Depth 2.5 - 3.0 m |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Box pipes (internal size) 4000x700 mm in trenches |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Depth 2.0 - 2.5 m |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Additional excavation and backfilling works, drilling into rock | m³ |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Tube ferries at the road junction |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Construction of tubular culverts, including road cutting culverts, connection and transfer to drainage channels and box pipes, earthworks, dewatering, cleaning concrete, construction works, reinforcement, formwork, etc., as shown in the drawings and specifications and in accordance with the requirements of the manufacturers.
STR11 |  | Scheme No.: DAM3-01-001-CH2-TS8-1-STR-DRW -0356
STR11 |  | 2 pipes, 600 mm diameter GRP pipe | m | 395.1 | 1856 | 733305.6 | 2291.0392 | 905189.6065 | 395.1 | 395.1 |  | 395.1 | 100% | 1856 | 733305.6 | 2291.0392 | 905189.6065 |  | 905189.6065 | [7 empty] | 2291.0392 | 395.1 | 905189.6065 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 395.1 | 395.1 |  | 395.1 | [9 empty] | Excavate & Disposal (3.4*1.5) |  | M | 15.7272 |  | 15.7272 | 395.1 | 6213.8167 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 23.5294 | 2.38 | 16.7918 | 940.338
[22 empty] | Fuel | Material | LTR | 1.76 | 1.6807 | 1.0472 | 235.0845 | 413.7487
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 5.3333 | 9 | 74.0812 | 3555.9
[22 empty] | Fuel | Material | LTR | 1.76 | 0.53333 | 3.3 | 740.8125 | 1303.83
[9 empty] | 395.1 | 395.1 |  | 395.1 | [9 empty] | Pipe culvert Installation |  | M | 2219.99 |  | 2219.99 | 395.1 | 877118.049 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 5.3333 | 46.875 | 74.0813 | 18520.3125
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.432 | 810.18 | 914.5775 | 320102.118
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 6.1715 | 405.09 | 64.0204 | 160051.059
[22 empty] | Workmanship plain concrete | SC | M³ | 150 | 5.3333 | 28.125 | 74.0813 | 11112.1875
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 0.432 | 347.22 | 914.5775 | 137186.622
[22 empty] | GRP Pipe 600 mm | Material | M | 290 | 0.5 | 580 | 790.2 | 229158
[22 empty] | Skilled Labor | Manpower | HR | 17 | 12 | 1.4167 | 32.925 | 559.725
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 12 | 1.0833 | 32.925 | 428.025
[9 empty] | 395.1 | 395.1 |  | 395.1 | [9 empty] | Waterproofing Insulation |  | Ea | 48 |  | 48 | 395.1 | 18964.8 | 0 | 0 | 0 | 0 | 0
[22 empty] | 2 Layers Bituminous Application | SC | M² | 10 | 0.20833 | 48 | 1896.48 | 18964.8
[9 empty] | 395.1 | 395.1 |  | 395.1 | [9 empty] | Backfilling |  | Ea | 7.322 |  | 7.322 | 395.1 | 2892.9408 | 0 | 0 | 0 | 0 | 0
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 80 | 0.82 | 4.9388 | 323.982
[22 empty] | Fuel | Material | LTR | 1.76 | 8.8889 | 0.198 | 44.4488 | 78.2298
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 18.1333 | 2.6471 | 21.7886 | 1045.8529
[22 empty] | Fuel | Material | LTR | 1.76 | 1.8133 | 0.97059 | 217.886 | 383.4794
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 33.3333 | 1.08 | 11.853 | 426.708
[22 empty] | Fuel | Material | LTR | 1.76 | 3.7037 | 0.4752 | 106.677 | 187.7515
[22 empty] | Plate Compactor | Machinery | HR | 23 | 25 | 0.92 | 15.804 | 363.492
[22 empty] | Fuel | Material | LTR | 1.76 | 8.3333 | 0.2112 | 47.412 | 83.4451
STR11 |  | Construction of tubular culverts, including road cutting culverts, connection and transfer to drainage channels and box pipes, earthworks, dewatering, cleaning concrete, construction works, reinforcement, formwork, etc., as shown in the drawings and specifications and in accordance with the requirements of the manufacturers.
STR11 |  | Scheme No.: DAM3-01-001-CH2-TS8-1-STR-DRW -0355
STR11 |  | 1 pipe, 600 mm diameter GRP pipe | m |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | The box crossing at the intersection of the road |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Construction of single-chamber box culverts, including road cutting culverts, connection and transfer to drainage channels and box pipes, earthworks, dewatering, cleaning concrete, construction works, reinforcement, formwork, etc., complete as shown in the plans and specifications and in accordance with the requirements of the manufacturers.
STR11 |  | Scheme No.: DAM3-01-001-CH2-TS8-1-STR-DRW -0358
STR11 |  | Internal measurement: 700x1500mm | m |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Internal measurement: 2500 x 800mm | m | 7.644 | 7733 | 59111.052 | 5279.8492 | 40359.1674 | 7.644 | 7.644 |  | 7.644 | 100% | 7733 | 59111.052 | 5279.8492 | 40359.1674 |  | 40359.1674 | [7 empty] | 5279.8492 | 7.644 | 40359.1674 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 7.644 | 7.644 |  | 7.644 | [9 empty] | Excavation ( W= 3.9 & d= 3.0 ) |  | M | 115.2992 |  | 115.2992 | 7.644 | 881.3472 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 8.547 | 6.552 | 0.89435 | 50.0835
[22 empty] | Fuel | Material | LTR | 1.76 | 0.6105 | 2.8829 | 12.5209 | 22.0367
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 1.7436 | 27.5294 | 4.3841 | 210.4348
[22 empty] | Fuel | Material | LTR | 1.76 | 0.17436 | 10.0941 | 43.8406 | 77.1594
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 0.15288 | 3.5162
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 0.45864 | 0.80721
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 8.547 | 5.616 | 0.89435 | 42.9287
[22 empty] | Fuel | Material | LTR | 1.76 | 0.8547 | 2.0592 | 8.9435 | 15.7405
[22 empty] | Steel Shoring D>3.0 M | Material | M | 60 | 1 | 60 | 7.644 | 458.64
[9 empty] | 7.644 | 7.644 |  | 7.644 | [9 empty] | Precast Box Conduit (2500x800 mm) |  | M | 5164.55 |  | 5164.55 | 7.644 | 39477.8202 | 0 | 0 | 0 | 0 | 0
[22 empty] | Precast Box Conduit Supply | Material | M³ | 2200 | 0.42735 | 5148 | 17.887 | 39351.312
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 8 | 10 | 0.9555 | 76.44
[22 empty] | Fuel | Material | LTR | 1.76 | 0.53333 | 3.3 | 14.3325 | 25.2252
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 4 | 3.25 | 1.911 | 24.843
STR11 |  | Flush Inlet Manholes |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
STR11 |  | Creating GRP manholes for the entry of wastewater into all pipes of various diameters. This includes excavation, backfilling, compaction, waste removal, dewatering, cleaning concrete, concrete bases, surrounding soil, reinforcement, formwork, concrete room frames, slabs, brick and masonry work, cement bases, waterproofing, waterproofing, entrance covers and frames, safety rings, and dividers in accordance with the plans, specifications, and requirements of the concerned authority.
STR11 |  | Diagram No. DAM3-01-001-CH2-TS8-1-STR-DRW-0307 REV A01
STR11 |  | Diagram No. DAM3-01-001-CH2-TS8-1-STR-DRW-0311 REV A01
STR11 |  | Circular manhole measuring 1200 mm inner diameter
STR11 |  | Manhole depth 0-1.5m(GRP) | nr | 2 | 11392 | 22784 | 6056.6049 | 12113.2099 | 2 | 2 |  | 2 | 100% | 11392 | 22784 | 6056.6049 | 12113.2099 |  | 12113.2099 | [7 empty] | 6056.6049 | 2 | 12113.2099 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 2 | 2 |  | 2 | [9 empty] | Excavate & Disposal (2.5*2.5*2.0) |  | Ea | 50.2761 |  | 50.2761 | 2 | 100.5522 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 8 | 7 | 0.25 | 14
[22 empty] | Fuel | Material | LTR | 1.76 | 0.57143 | 3.08 | 3.5 | 6.16
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 1.632 | 29.4118 | 1.2255 | 58.8235
[22 empty] | Fuel | Material | LTR | 1.76 | 0.1632 | 10.7843 | 12.2549 | 21.5686
[9 empty] | 2 | 2 |  | 2 | [9 empty] | Concrete Base 30 cm |  | Ea | 1432.696 |  | 1432.696 | 2 | 2865.392 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 2.2676 | 110.25 | 0.882 | 220.5
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.83333 | 420 | 2.4 | 840
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 10.4167 | 240 | 0.192 | 480
[22 empty] | Workmanship plain concrete | SC | M³ | 150 | 2.2676 | 66.15 | 0.882 | 132.3
[22 empty] | Workmanship RC concrete | SC | M³ | 450 | 0.83333 | 540 | 2.4 | 1080
[22 empty] | 2 Layers Bituminous Application | SC | M² | 10 | 0.17763 | 56.296 | 11.2592 | 112.592
[9 empty] | 2 | 2 |  | 2 | [9 empty] | Manhole Installation |  | Ea | 4362.8 |  | 4362.8 | 2 | 8725.6 | 0 | 0 | 0 | 0 | 0
[22 empty] | GRP manhole Dia 1200 mm D=1.5 m W Cover | Material | Ea | 2590 | 1 | 2590 | 2 | 5180
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 0.5 | 160 | 4 | 320
[22 empty] | Fuel | Material | HR | 1.76 | 0.033333 | 52.8 | 60 | 105.6
[22 empty] | Brick & Masonery for Manhole Neck | SC | LS | 1500 | 1 | 1500 | 2 | 3000
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.5 | 34 | 4 | 68
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.5 | 26 | 4 | 52
[9 empty] | 2 | 2 |  | 2 | [9 empty] | Backfilling |  | Ea | 210.8329 |  | 210.8329 | 2 | 421.6657 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.097664 | 102.392 | 20.4784 | 204.784
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 9.7664 | 6.7169 | 0.20478 | 13.4338
[22 empty] | Fuel | Material | LTR | 1.76 | 1.0852 | 1.6219 | 1.8431 | 3.2438
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 1.9923 | 24.0922 | 1.0038 | 48.1845
[22 empty] | Fuel | Material | LTR | 1.76 | 0.19923 | 8.8338 | 10.0384 | 17.6676
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 4.8832 | 7.3722 | 0.40957 | 14.7444
[22 empty] | Fuel | Material | LTR | 1.76 | 0.54258 | 3.2438 | 3.6861 | 6.4876
[22 empty] | Plate Compactor | Machinery | HR | 23 | 0.5 | 46 | 4 | 92
[22 empty] | Fuel | Material | LTR | 1.76 | 0.16667 | 10.56 | 12 | 21.12
STR11 |  | Manhole 1.5-2.0m deep(GRP) | nr | 4.8 | 14728 | 70694.4 | 6631.8822 | 31833.0344 | 4.8 | 4.8 |  | 4.8 | 100% | 14728 | 70694.4 | 6631.8822 | 31833.0344 |  | 31833.0344 | [7 empty] | 6631.8822 | 4.8 | 31833.0344 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 4.8 | 4.8 |  | 4.8 | [9 empty] | Excavate & Disposal (2.5*2.5*2.5) |  | Ea | 62.8451 |  | 62.8451 | 4.8 | 301.6565 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 6.4 | 8.75 | 0.75 | 42
[22 empty] | Fuel | Material | LTR | 1.76 | 0.45714 | 3.85 | 10.5 | 18.48
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 1.3056 | 36.7647 | 3.6765 | 176.4706
[22 empty] | Fuel | Material | LTR | 1.76 | 0.13056 | 13.4804 | 36.7647 | 64.7059
[9 empty] | 4.8 | 4.8 |  | 4.8 | [9 empty] | Concrete Base 30 cm |  | Ea | 1432.696 |  | 1432.696 | 4.8 | 6876.9408 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 2.2676 | 110.25 | 2.1168 | 529.2
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.83333 | 420 | 5.76 | 2016
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 10.4167 | 240 | 0.4608 | 1152
[22 empty] | Workmanship plain concrete | SC | M³ | 150 | 2.2676 | 66.15 | 2.1168 | 317.52
[22 empty] | Workmanship RC concrete | SC | M³ | 450 | 0.83333 | 540 | 5.76 | 2592
[22 empty] | 2 Layers Bituminous Application | SC | M² | 10 | 0.17763 | 56.296 | 27.0221 | 270.2208
[9 empty] | 4.8 | 4.8 |  | 4.8 | [9 empty] | Manhole Installation |  | Ea | 4872.8 |  | 4872.8 | 4.8 | 23389.44 | 0 | 0 | 0 | 0 | 0
[22 empty] | GRP manhole Dia 1200 mm D=2.0 m W Cover | Material | Ea | 3100 | 1 | 3100 | 4.8 | 14880
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 0.5 | 160 | 9.6 | 768
[22 empty] | Fuel | Material | HR | 1.76 | 0.033333 | 52.8 | 144 | 253.44
[22 empty] | Brick & Masonery for Manhole Neck | SC | LS | 1500 | 1 | 1500 | 4.8 | 7200
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.5 | 34 | 9.6 | 163.2
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.5 | 26 | 9.6 | 124.8
[9 empty] | 4.8 | 4.8 |  | 4.8 | [9 empty] | Backfilling |  | Ea | 263.5411 |  | 263.5411 | 4.8 | 1264.9972 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.078131 | 127.99 | 61.4352 | 614.352
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 7.8131 | 8.3961 | 0.61435 | 40.3015
[22 empty] | Fuel | Material | LTR | 1.76 | 0.86812 | 2.0274 | 5.5292 | 9.7313
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 1.5939 | 30.1153 | 3.0115 | 144.5534
[22 empty] | Fuel | Material | LTR | 1.76 | 0.15939 | 11.0423 | 30.1153 | 53.0029
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 3.9066 | 9.2153 | 1.2287 | 44.2333
[22 empty] | Fuel | Material | LTR | 1.76 | 0.43406 | 4.0547 | 11.0583 | 19.4627
[22 empty] | Plate Compactor | Machinery | HR | 23 | 0.4 | 57.5 | 12 | 276
[22 empty] | Fuel | Material | LTR | 1.76 | 0.13333 | 13.2 | 36 | 63.36
STR11 |  | Manhole with depth 2.0-2.5m(GRP) | nr | 7.125 | 18316 | 130501.5 | 7197.1594 | 51279.7608 | 7.125 | 7.125 |  | 7.125 | 100% | 18316 | 130501.5 | 7197.1594 | 51279.7608 |  | 51279.7608 | [7 empty] | 7197.1594 | 7.125 | 51279.7608 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 7.125 | 7.125 |  | 7.125 | [9 empty] | Excavate & Disposal (2.5*2.5*3.0) |  | Ea | 75.4141 |  | 75.4141 | 7.125 | 537.3256 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 5.3333 | 10.5 | 1.3359 | 74.8125
[22 empty] | Fuel | Material | LTR | 1.76 | 0.38095 | 4.62 | 18.7031 | 32.9175
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 1.088 | 44.1176 | 6.5487 | 314.3382
[22 empty] | Fuel | Material | LTR | 1.76 | 0.1088 | 16.1765 | 65.4871 | 115.2574
[9 empty] | 7.125 | 7.125 |  | 7.125 | [9 empty] | Concrete Base 30 cm |  | Ea | 1432.696 |  | 1432.696 | 7.125 | 10207.959 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 2.2676 | 110.25 | 3.1421 | 785.5313
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.83333 | 420 | 8.55 | 2992.5
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 10.4167 | 240 | 0.684 | 1710
[22 empty] | Workmanship plain concrete | SC | M³ | 150 | 2.2676 | 66.15 | 3.1421 | 471.3188
[22 empty] | Workmanship RC concrete | SC | M³ | 450 | 0.83333 | 540 | 8.55 | 3847.5
[22 empty] | 2 Layers Bituminous Application | SC | M² | 10 | 0.17763 | 56.296 | 40.1109 | 401.109
[9 empty] | 7.125 | 7.125 |  | 7.125 | [9 empty] | Manhole Installation |  | Ea | 5372.8 |  | 5372.8 | 7.125 | 38281.2 | 0 | 0 | 0 | 0 | 0
[22 empty] | GRP manhole Dia 1200 mm D=2.5 m W Cover | Material | Ea | 3600 | 1 | 3600 | 7.125 | 25650
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 0.5 | 160 | 14.25 | 1140
[22 empty] | Fuel | Material | HR | 1.76 | 0.033333 | 52.8 | 213.75 | 376.2
[22 empty] | Brick & Masonery for Manhole Neck | SC | LS | 1500 | 1 | 1500 | 7.125 | 10687.5
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.5 | 34 | 14.25 | 242.25
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.5 | 26 | 14.25 | 185.25
[9 empty] | 7.125 | 7.125 |  | 7.125 | [9 empty] | Backfilling |  | Ea | 316.2493 |  | 316.2493 | 7.125 | 2253.2762 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.065109 | 153.588 | 109.4315 | 1094.3145
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 6.5109 | 10.0754 | 1.0943 | 71.787
[22 empty] | Fuel | Material | LTR | 1.76 | 0.72344 | 2.4328 | 9.8488 | 17.3339
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 1.3282 | 36.1384 | 5.3643 | 257.4858
[22 empty] | Fuel | Material | LTR | 1.76 | 0.13282 | 13.2507 | 53.6429 | 94.4114
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 3.2555 | 11.0583 | 2.1886 | 78.7906
[22 empty] | Fuel | Material | LTR | 1.76 | 0.36172 | 4.8657 | 19.6977 | 34.6679
[22 empty] | Plate Compactor | Machinery | HR | 23 | 0.33333 | 69 | 21.375 | 491.625
[22 empty] | Fuel | Material | LTR | 1.76 | 0.11111 | 15.84 | 64.125 | 112.86
STR11 |  | Manhole 2.5-3.0m deep(GRP) | nr | 1.5 | 22092 | 33138 | 8162.4366 | 12243.655 | 1.5 | 1.5 |  | 1.5 | 100% | 22092 | 33138 | 8162.4366 | 12243.655 |  | 12243.655 | [7 empty] | 8162.4366 | 1.5 | 12243.655 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 1.5 | 1.5 |  | 1.5 | [9 empty] | Excavate & Disposal (2.5*2.5*3.5) |  | Ea | 87.9831 |  | 87.9831 | 1.5 | 131.9747 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 4.5714 | 12.25 | 0.32812 | 18.375
[22 empty] | Fuel | Material | LTR | 1.76 | 0.32653 | 5.39 | 4.5937 | 8.085
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.93257 | 51.4706 | 1.6085 | 77.2059
[22 empty] | Fuel | Material | LTR | 1.76 | 0.093257 | 18.8725 | 16.0846 | 28.3088
[9 empty] | 1.5 | 1.5 |  | 1.5 | [9 empty] | Concrete Base 30 cm |  | Ea | 1432.696 |  | 1432.696 | 1.5 | 2149.044 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 2.2676 | 110.25 | 0.6615 | 165.375
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.83333 | 420 | 1.8 | 630
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 10.4167 | 240 | 0.144 | 360
[22 empty] | Workmanship plain concrete | SC | M³ | 150 | 2.2676 | 66.15 | 0.6615 | 99.225
[22 empty] | Workmanship RC concrete | SC | M³ | 450 | 0.83333 | 540 | 1.8 | 810
[22 empty] | 2 Layers Bituminous Application | SC | M² | 10 | 0.17763 | 56.296 | 8.4444 | 84.444
[9 empty] | 1.5 | 1.5 |  | 1.5 | [9 empty] | Manhole Installation |  | Ea | 6272.8 |  | 6272.8 | 1.5 | 9409.2 | 0 | 0 | 0 | 0 | 0
[22 empty] | GRP manhole Dia 1200 mm D=3.0 m W Cover | Material | Ea | 4500 | 1 | 4500 | 1.5 | 6750
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 0.5 | 160 | 3 | 240
[22 empty] | Fuel | Material | HR | 1.76 | 0.033333 | 52.8 | 45 | 79.2
[22 empty] | Brick & Masonery for Manhole Neck | SC | LS | 1500 | 1 | 1500 | 1.5 | 2250
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.5 | 34 | 3 | 51
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.5 | 26 | 3 | 39
[9 empty] | 1.5 | 1.5 |  | 1.5 | [9 empty] | Backfilling |  | Ea | 368.9575 |  | 368.9575 | 1.5 | 553.4363 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.055808 | 179.186 | 26.8779 | 268.779
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 5.5808 | 11.7546 | 0.26878 | 17.6319
[22 empty] | Fuel | Material | LTR | 1.76 | 0.62009 | 2.8383 | 2.419 | 4.2575
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 1.1385 | 42.1614 | 1.3175 | 63.2421
[22 empty] | Fuel | Material | LTR | 1.76 | 0.11385 | 15.4592 | 13.1754 | 23.1888
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 2.7904 | 12.9014 | 0.53756 | 19.3521
[22 empty] | Fuel | Material | LTR | 1.76 | 0.31004 | 5.6766 | 4.838 | 8.5149
[22 empty] | Plate Compactor | Machinery | HR | 23 | 0.28571 | 80.5 | 5.25 | 120.75
[22 empty] | Fuel | Material | LTR | 1.76 | 0.095238 | 18.48 | 15.75 | 27.72
STR11 |  | Manhole 3.0-3.5m deep(GRP) | nr | 0.275 | 25743 | 7079.325 | 9077.7139 | 2496.3713 | 0.275 | 0.275 |  | 0.275 | 100% | 25743 | 7079.325 | 9077.7139 | 2496.3713 |  | 2496.3713 | [7 empty] | 9077.7139 | 0.275 | 2496.3713 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 0.275 | 0.275 |  | 0.275 | [9 empty] | Excavate & Disposal (2.5*2.5*4.0) |  | Ea | 100.5522 |  | 100.5522 | 0.275 | 27.6518 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 4 | 14 | 0.06875 | 3.85
[22 empty] | Fuel | Material | LTR | 1.76 | 0.28571 | 6.16 | 0.9625 | 1.694
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.816 | 58.8235 | 0.33701 | 16.1765
[22 empty] | Fuel | Material | LTR | 1.76 | 0.0816 | 21.5686 | 3.3701 | 5.9314
[9 empty] | 0.275 | 0.275 |  | 0.275 | [9 empty] | Concrete Base 30 cm |  | Ea | 1432.696 |  | 1432.696 | 0.275 | 393.9914 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 2.2676 | 110.25 | 0.12127 | 30.3187
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.83333 | 420 | 0.33 | 115.5
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 10.4167 | 240 | 0.0264 | 66
[22 empty] | Workmanship plain concrete | SC | M³ | 150 | 2.2676 | 66.15 | 0.12127 | 18.1912
[22 empty] | Workmanship RC concrete | SC | M³ | 450 | 0.83333 | 540 | 0.33 | 148.5
[22 empty] | 2 Layers Bituminous Application | SC | M² | 10 | 0.17763 | 56.296 | 1.5481 | 15.4814
[9 empty] | 0.275 | 0.275 |  | 0.275 | [9 empty] | Manhole Installation |  | Ea | 7122.8 |  | 7122.8 | 0.275 | 1958.77 | 0 | 0 | 0 | 0 | 0
[22 empty] | GRP manhole Dia 1200 mm D=3.5 m W Cover | Material | Ea | 5350 | 1 | 5350 | 0.275 | 1471.25
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 0.5 | 160 | 0.55 | 44
[22 empty] | Fuel | Material | HR | 1.76 | 0.033333 | 52.8 | 8.25 | 14.52
[22 empty] | Brick & Masonery for Manhole Neck | SC | LS | 1500 | 1 | 1500 | 0.275 | 412.5
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.5 | 34 | 0.55 | 9.35
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.5 | 26 | 0.55 | 7.15
[9 empty] | 0.275 | 0.275 |  | 0.275 | [9 empty] | Backfilling |  | Ea | 421.6657 |  | 421.6657 | 0.275 | 115.9581 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.048832 | 204.784 | 5.6316 | 56.3156
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 4.8832 | 13.4338 | 0.056316 | 3.6943
[22 empty] | Fuel | Material | LTR | 1.76 | 0.54258 | 3.2438 | 0.50684 | 0.89204
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.99617 | 48.1845 | 0.27606 | 13.2507
[22 empty] | Fuel | Material | LTR | 1.76 | 0.099617 | 17.6676 | 2.7606 | 4.8586
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 2.4416 | 14.7444 | 0.11263 | 4.0547
[22 empty] | Fuel | Material | LTR | 1.76 | 0.27129 | 6.4876 | 1.0137 | 1.7841
[21 empty] | 4 | Plate Compactor | Machinery | HR | 23 | 0.25 | 92 | 1.1 | 25.3
[22 empty] | Fuel | Material | LTR | 1.76 | 0.083333 | 21.12 | 3.3 | 5.808
STR11 |  | Manhole 3.5-4.0m deep(GRP) | nr | 0.2 | 32099 | 6419.8 | 10092.9911 | 2018.5982 | 0.2 | 0.2 |  | 0.2 | 100% | 32099 | 6419.8 | 10092.9911 | 2018.5982 |  | 2018.5982 | [7 empty] | 10092.9911 | 0.2 | 2018.5982 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 0.2 | 0.2 |  | 0.2 | [9 empty] | Excavate & Disposal (2.5*2.5*4.5) |  | Ea | 113.1212 |  | 113.1212 | 0.2 | 22.6242 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 3.5556 | 15.75 | 0.05625 | 3.15
[22 empty] | Fuel | Material | LTR | 1.76 | 0.25397 | 6.93 | 0.7875 | 1.386
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.72533 | 66.1765 | 0.27574 | 13.2353
[22 empty] | Fuel | Material | LTR | 1.76 | 0.072533 | 24.2647 | 2.7574 | 4.8529
[9 empty] | 0.2 | 0.2 |  | 0.2 | [9 empty] | Concrete Base 30 cm |  | Ea | 1432.696 |  | 1432.696 | 0.2 | 286.5392 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 2.2676 | 110.25 | 0.0882 | 22.05
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.83333 | 420 | 0.24 | 84
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 10.4167 | 240 | 0.0192 | 48
[22 empty] | Workmanship plain concrete | SC | M³ | 150 | 2.2676 | 66.15 | 0.0882 | 13.23
[22 empty] | Workmanship RC concrete | SC | M³ | 450 | 0.83333 | 540 | 0.24 | 108
[22 empty] | 2 Layers Bituminous Application | SC | M² | 10 | 0.17763 | 56.296 | 1.1259 | 11.2592
[9 empty] | 0.2 | 0.2 |  | 0.2 | [9 empty] | Manhole Installation |  | Ea | 8072.8 |  | 8072.8 | 0.2 | 1614.56 | 0 | 0 | 0 | 0 | 0
[22 empty] | GRP manhole Dia 1200 mm D=4.0 m W Cover | Material | Ea | 6300 | 1 | 6300 | 0.2 | 1260
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 0.5 | 160 | 0.4 | 32
[22 empty] | Fuel | Material | HR | 1.76 | 0.033333 | 52.8 | 6 | 10.56
[22 empty] | Brick & Masonery for Manhole Neck | SC | LS | 1500 | 1 | 1500 | 0.2 | 300
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.5 | 34 | 0.4 | 6.8
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.5 | 26 | 0.4 | 5.2
[9 empty] | 0.2 | 0.2 |  | 0.2 | [9 empty] | Backfilling |  | Ea | 474.3739 |  | 474.3739 | 0.2 | 94.8748 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.043406 | 230.382 | 4.6076 | 46.0764
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 4.3406 | 15.1131 | 0.046076 | 3.0226
[22 empty] | Fuel | Material | LTR | 1.76 | 0.48229 | 3.6493 | 0.41469 | 0.72985
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.88549 | 54.2075 | 0.22586 | 10.8415
[22 empty] | Fuel | Material | LTR | 1.76 | 0.088549 | 19.8761 | 2.2586 | 3.9752
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 2.1703 | 16.5875 | 0.092153 | 3.3175
[22 empty] | Fuel | Material | LTR | 1.76 | 0.24115 | 7.2985 | 0.82938 | 1.4597
[21 empty] | 4.5 | Plate Compactor | Machinery | HR | 23 | 0.22222 | 103.5 | 0.9 | 20.7
[22 empty] | Fuel | Material | LTR | 1.76 | 0.074074 | 23.76 | 2.7 | 4.752
STR11 |  | Increasing the depth difference by 0.5 for a circular manhole measuring inner diameter of 1200 mm (GRP) | nr |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Increasing the depth difference by 1.00 for a circular manhole measuring 1200 mm inner diameter (GRP) | nr |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Increase depth difference of 1.50 for a circular manhole measuring 1200 mm inner diameter (GRP) | nr |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Increased 2.00 depth differential for circular manhole measuring 1200 mm inner diameter (GRP) | nr |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Increase depth difference of 2.50 for circular manhole measuring 1200mm inner diameter (GRP) | nr |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Increased 3.00 depth difference for a circular manhole measuring 1200 mm inner diameter (GRP) | nr |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Circular manhole measuring 1500 mm inner diameter
STR11 |  | Manhole depth 0-1.5m(GRP) | nr | 1.8 | 18448 | 33206.4 | 7473.5752 | 13452.4354 | 1.8 | 1.8 |  | 1.8 | 100% | 18448 | 33206.4 | 7473.5752 | 13452.4354 |  | 13452.4354 | [7 empty] | 7473.5752 | 1.8 | 13452.4354 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 1.8 | 1.8 |  | 1.8 | [9 empty] | Excavate & Disposal (3.0*3.0*2.0) |  | Ea | 72.3976 |  | 72.3976 | 1.8 | 130.3156 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 5.5556 | 10.08 | 0.324 | 18.144
[22 empty] | Fuel | Material | LTR | 1.76 | 0.39683 | 4.4352 | 4.536 | 7.9834
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 1.1333 | 42.3529 | 1.5882 | 76.2353
[22 empty] | Fuel | Material | LTR | 1.76 | 0.11333 | 15.5294 | 15.8824 | 27.9529
[9 empty] | 1.8 | 1.8 |  | 1.8 | [9 empty] | Concrete Base 30 cm |  | Ea | 1883.8375 |  | 1883.8375 | 1.8 | 3390.9075 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 1.7361 | 144 | 1.0368 | 259.2
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.63012 | 555.45 | 2.8566 | 999.81
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 7.8765 | 317.4 | 0.22853 | 571.32
[22 empty] | Workmanship plain concrete | SC | M³ | 150 | 1.7361 | 86.4 | 1.0368 | 155.52
[22 empty] | Workmanship RC concrete | SC | M³ | 450 | 0.63012 | 714.15 | 2.8566 | 1285.47
[22 empty] | 2 Layers Bituminous Application | SC | M² | 10 | 0.15052 | 66.4375 | 11.9588 | 119.5875
[9 empty] | 1.8 | 1.8 |  | 1.8 | [9 empty] | Manhole Installation |  | Ea | 5242.8 |  | 5242.8 | 1.8 | 9437.04 | 0 | 0 | 0 | 0 | 0
[22 empty] | GRP manhole Dia 1500 mm D=1.5 m W Cover | Material | Ea | 3470 | 1 | 3470 | 1.8 | 6246
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 0.5 | 160 | 3.6 | 288
[22 empty] | Fuel | Material | HR | 1.76 | 0.033333 | 52.8 | 54 | 95.04
[22 empty] | Brick & Masonery for Manhole Neck | SC | LS | 1500 | 1 | 1500 | 1.8 | 2700
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.5 | 34 | 3.6 | 61.2
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.5 | 26 | 3.6 | 46.8
[9 empty] | 1.8 | 1.8 |  | 1.8 | [9 empty] | Backfilling |  | Ea | 274.5402 |  | 274.5402 | 1.8 | 494.1723 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.06912 | 144.675 | 26.0415 | 260.415
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 6.912 | 9.4907 | 0.26042 | 17.0832
[22 empty] | Fuel | Material | LTR | 1.76 | 0.768 | 2.2917 | 2.3437 | 4.125
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 1.4101 | 34.0412 | 1.2765 | 61.2741
[22 empty] | Fuel | Material | LTR | 1.76 | 0.14101 | 12.4818 | 12.7654 | 22.4672
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 3.456 | 10.4166 | 0.52083 | 18.7499
[22 empty] | Fuel | Material | LTR | 1.76 | 0.384 | 4.5833 | 4.6875 | 8.2499
[22 empty] | Plate Compactor | Machinery | HR | 23 | 0.5 | 46 | 3.6 | 82.8
[22 empty] | Fuel | Material | LTR | 1.76 | 0.16667 | 10.56 | 10.8 | 19.008
STR11 |  | Manhole 1.5-2.0m deep(GRP) | nr | 9.405 | 24547 | 230864.535 | 8320.3097 | 78252.5124 | 9.405 | 9.405 |  | 9.405 | 100% | 24547 | 230864.535 | 8320.3097 | 78252.5124 |  | 78252.5124 | [7 empty] | 8320.3097 | 9.405 | 78252.5124 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 9.405 | 9.405 |  | 9.405 | [9 empty] | Excavate & Disposal (3.0*3.0*2.5) |  | Ea | 90.4969 |  | 90.4969 | 9.405 | 851.1237 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 4.4444 | 12.6 | 2.1161 | 118.503
[22 empty] | Fuel | Material | LTR | 1.76 | 0.31746 | 5.544 | 29.6258 | 52.1413
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.90667 | 52.9412 | 10.3732 | 497.9118
[22 empty] | Fuel | Material | LTR | 1.76 | 0.090667 | 19.4118 | 103.7316 | 182.5676
[9 empty] | 9.405 | 9.405 |  | 9.405 | [9 empty] | Concrete Base 30 cm |  | Ea | 1883.8375 |  | 1883.8375 | 9.405 | 17717.4917 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 1.7361 | 144 | 5.4173 | 1354.32
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.63012 | 555.45 | 14.9257 | 5224.0073
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 7.8765 | 317.4 | 1.1941 | 2985.147
[22 empty] | Workmanship plain concrete | SC | M³ | 150 | 1.7361 | 86.4 | 5.4173 | 812.592
[22 empty] | Workmanship RC concrete | SC | M³ | 450 | 0.63012 | 714.15 | 14.9257 | 6716.5808
[22 empty] | 2 Layers Bituminous Application | SC | M² | 10 | 0.15052 | 66.4375 | 62.4845 | 624.8447
[9 empty] | 9.405 | 9.405 |  | 9.405 | [9 empty] | Manhole Installation |  | Ea | 6002.8 |  | 6002.8 | 9.405 | 56456.334 | 0 | 0 | 0 | 0 | 0
[22 empty] | GRP manhole Dia 1500 mm D=2.0 m W Cover | Material | Ea | 4230 | 1 | 4230 | 9.405 | 39783.15
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 0.5 | 160 | 18.81 | 1504.8
[22 empty] | Fuel | Material | HR | 1.76 | 0.033333 | 52.8 | 282.15 | 496.584
[22 empty] | Brick & Masonery for Manhole Neck | SC | LS | 1500 | 1 | 1500 | 9.405 | 14107.5
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.5 | 34 | 18.81 | 319.77
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.5 | 26 | 18.81 | 244.53
[9 empty] | 9.405 | 9.405 |  | 9.405 | [9 empty] | Backfilling |  | Ea | 343.1752 |  | 343.1752 | 9.405 | 3227.563 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.055296 | 180.8438 | 170.0835 | 1700.8355
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 5.5296 | 11.8633 | 1.7008 | 111.5748
[22 empty] | Fuel | Material | LTR | 1.76 | 0.6144 | 2.8646 | 15.3075 | 26.9412
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 1.128 | 42.5515 | 8.3374 | 400.1966
[22 empty] | Fuel | Material | LTR | 1.76 | 0.1128 | 15.6022 | 83.3743 | 146.7387
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 2.7648 | 13.0207 | 3.4017 | 122.4602
[22 empty] | Fuel | Material | LTR | 1.76 | 0.3072 | 5.7291 | 30.615 | 53.8825
[22 empty] | Plate Compactor | Machinery | HR | 23 | 0.4 | 57.5 | 23.5125 | 540.7875
[22 empty] | Fuel | Material | LTR | 1.76 | 0.13333 | 13.2 | 70.5375 | 124.146
STR11 |  | Manhole with depth 2.0-2.5m(GRP) | nr | 15.875 | 30652 | 486600.5 | 8887.0441 | 141081.825 | 15.875 | 15.875 |  | 15.875 | 100% | 30652 | 486600.5 | 8887.0441 | 141081.825 |  | 141081.825 | [7 empty] | 8887.0441 | 15.875 | 141081.825 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 15.875 | 15.875 |  | 15.875 | [9 empty] | Excavate & Disposal (3.0*3.0*3.0) |  | Ea | 108.5963 |  | 108.5963 | 15.875 | 1723.9667 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 3.7037 | 15.12 | 4.2862 | 240.03
[22 empty] | Fuel | Material | LTR | 1.76 | 0.26455 | 6.6528 | 60.0075 | 105.6132
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.75556 | 63.5294 | 21.011 | 1008.5294
[22 empty] | Fuel | Material | LTR | 1.76 | 0.075556 | 23.2941 | 210.1103 | 369.7941
[9 empty] | 15.875 | 15.875 |  | 15.875 | [9 empty] | Concrete Base 30 cm |  | Ea | 1883.8375 |  | 1883.8375 | 15.875 | 29905.9203 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 1.7361 | 144 | 9.144 | 2286
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.63012 | 555.45 | 25.1936 | 8817.7687
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 7.8765 | 317.4 | 2.0155 | 5038.725
[22 empty] | Workmanship plain concrete | SC | M³ | 150 | 1.7361 | 86.4 | 9.144 | 1371.6
[22 empty] | Workmanship RC concrete | SC | M³ | 450 | 0.63012 | 714.15 | 25.1936 | 11337.1312
[22 empty] | 2 Layers Bituminous Application | SC | M² | 10 | 0.15052 | 66.4375 | 105.4695 | 1054.6953
[9 empty] | 15.875 | 15.875 |  | 15.875 | [9 empty] | Manhole Installation |  | Ea | 6482.8 |  | 6482.8 | 15.875 | 102914.45 | 0 | 0 | 0 | 0 | 0
[22 empty] | GRP manhole Dia 1500 mm D=2.5 m W Cover | Material | Ea | 4710 | 1 | 4710 | 15.875 | 74771.25
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 0.5 | 160 | 31.75 | 2540
[22 empty] | Fuel | Material | HR | 1.76 | 0.033333 | 52.8 | 476.25 | 838.2
[22 empty] | Brick & Masonery for Manhole Neck | SC | LS | 1500 | 1 | 1500 | 15.875 | 23812.5
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.5 | 34 | 31.75 | 539.75
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.5 | 26 | 31.75 | 412.75
[9 empty] | 15.875 | 15.875 |  | 15.875 | [9 empty] | Backfilling |  | Ea | 411.8103 |  | 411.8103 | 15.875 | 6537.488 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.04608 | 217.0125 | 344.5073 | 3445.0734
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 4.608 | 14.236 | 3.4451 | 225.9968
[22 empty] | Fuel | Material | LTR | 1.76 | 0.512 | 3.4375 | 31.0057 | 54.57
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.94004 | 51.0618 | 16.8876 | 810.6055
[22 empty] | Fuel | Material | LTR | 1.76 | 0.094004 | 18.7226 | 168.8761 | 297.222
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 2.304 | 15.6249 | 6.8901 | 248.0453
[22 empty] | Fuel | Material | LTR | 1.76 | 0.256 | 6.875 | 62.0113 | 109.1399
[22 empty] | Plate Compactor | Machinery | HR | 23 | 0.33333 | 69 | 47.625 | 1095.375
[22 empty] | Fuel | Material | LTR | 1.76 | 0.11111 | 15.84 | 142.875 | 251.46
STR11 |  | Manhole 2.5-3.0m deep(GRP) | nr | 12.265 | 36757 | 450824.605 | 9413.7785 | 115459.9936 | 12.265 | 12.265 |  | 12.265 | 100% | 36757 | 450824.605 | 9413.7785 | 115459.9936 |  | 115459.9936 | [7 empty] | 9413.7785 | 12.265 | 115459.9936 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 12.265 | 12.265 |  | 12.265 | [9 empty] | Excavate & Disposal (3.0*3.0*3.5) |  | Ea | 126.6957 |  | 126.6957 | 12.265 | 1553.923 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 3.1746 | 17.64 | 3.8635 | 216.3546
[22 empty] | Fuel | Material | LTR | 1.76 | 0.22676 | 7.7616 | 54.0886 | 95.196
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.64762 | 74.1176 | 18.9386 | 909.0529
[22 empty] | Fuel | Material | LTR | 1.76 | 0.064762 | 27.1765 | 189.386 | 333.3194
[9 empty] | 12.265 | 12.265 |  | 12.265 | [9 empty] | Concrete Base 30 cm |  | Ea | 1883.8375 |  | 1883.8375 | 12.265 | 23105.2669 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 1.7361 | 144 | 7.0646 | 1766.16
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.63012 | 555.45 | 19.4646 | 6812.5942
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 7.8765 | 317.4 | 1.5572 | 3892.911
[22 empty] | Workmanship plain concrete | SC | M³ | 150 | 1.7361 | 86.4 | 7.0646 | 1059.696
[22 empty] | Workmanship RC concrete | SC | M³ | 450 | 0.63012 | 714.15 | 19.4646 | 8759.0497
[22 empty] | 2 Layers Bituminous Application | SC | M² | 10 | 0.15052 | 66.4375 | 81.4856 | 814.8559
[9 empty] | 12.265 | 12.265 |  | 12.265 | [9 empty] | Manhole Installation |  | Ea | 6922.8 |  | 6922.8 | 12.265 | 84908.142 | 0 | 0 | 0 | 0 | 0
[22 empty] | GRP manhole Dia 1500 mm D=3.0 m W Cover | Material | Ea | 5150 | 1 | 5150 | 12.265 | 63164.75
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 0.5 | 160 | 24.53 | 1962.4
[22 empty] | Fuel | Material | HR | 1.76 | 0.033333 | 52.8 | 367.95 | 647.592
[22 empty] | Brick & Masonery for Manhole Neck | SC | LS | 1500 | 1 | 1500 | 12.265 | 18397.5
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.5 | 34 | 24.53 | 417.01
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.5 | 26 | 24.53 | 318.89
[9 empty] | 12.265 | 12.265 |  | 12.265 | [9 empty] | Backfilling |  | Ea | 480.4453 |  | 480.4453 | 12.265 | 5892.6617 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.039497 | 253.1812 | 310.5268 | 3105.268
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 3.9497 | 16.6087 | 3.1053 | 203.7056
[22 empty] | Fuel | Material | LTR | 1.76 | 0.43886 | 4.0104 | 27.9474 | 49.1874
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.80575 | 59.5721 | 15.2219 | 730.6513
[22 empty] | Fuel | Material | LTR | 1.76 | 0.080575 | 21.8431 | 152.219 | 267.9055
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 1.9749 | 18.2291 | 6.2105 | 223.5793
[22 empty] | Fuel | Material | LTR | 1.76 | 0.21943 | 8.0208 | 55.8948 | 98.3749
[22 empty] | Plate Compactor | Machinery | HR | 23 | 0.28571 | 80.5 | 42.9275 | 987.3325
[22 empty] | Fuel | Material | LTR | 1.76 | 0.095238 | 18.48 | 128.7825 | 226.6572
STR11 |  | Manhole 3.0-3.5m deep(GRP) | nr | 3.86 | 42863 | 165451.18 | 10150.513 | 39180.98 | 3.86 | 3.86 |  | 3.86 | 100% | 42863 | 165451.18 | 10150.513 | 39180.98 |  | 39180.98 | [7 empty] | 10150.513 | 3.86 | 39180.98 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 3.86 | 3.86 |  | 3.86 | [9 empty] | Excavate & Disposal (3.0*3.0*4.0) |  | Ea | 144.7951 |  | 144.7951 | 3.86 | 558.9091 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 2.7778 | 20.16 | 1.3896 | 77.8176
[22 empty] | Fuel | Material | LTR | 1.76 | 0.19841 | 8.8704 | 19.4544 | 34.2397
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.56667 | 84.7059 | 6.8118 | 326.9647
[22 empty] | Fuel | Material | LTR | 1.76 | 0.056667 | 31.0588 | 68.1176 | 119.8871
[9 empty] | 3.86 | 3.86 |  | 3.86 | [9 empty] | Concrete Base 30 cm |  | Ea | 1883.8375 |  | 1883.8375 | 3.86 | 7271.6128 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 1.7361 | 144 | 2.2234 | 555.84
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.63012 | 555.45 | 6.1258 | 2144.037
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 7.8765 | 317.4 | 0.49007 | 1225.164
[22 empty] | Workmanship plain concrete | SC | M³ | 150 | 1.7361 | 86.4 | 2.2234 | 333.504
[22 empty] | Workmanship RC concrete | SC | M³ | 450 | 0.63012 | 714.15 | 6.1258 | 2756.619
[22 empty] | 2 Layers Bituminous Application | SC | M² | 10 | 0.15052 | 66.4375 | 25.6449 | 256.4488
[9 empty] | 3.86 | 3.86 |  | 3.86 | [9 empty] | Manhole Installation |  | Ea | 7572.8 |  | 7572.8 | 3.86 | 29231.008 | 0 | 0 | 0 | 0 | 0
[22 empty] | GRP manhole Dia 1500 mm D=3.5 m W Cover | Material | Ea | 5800 | 1 | 5800 | 3.86 | 22388
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 0.5 | 160 | 7.72 | 617.6
[22 empty] | Fuel | Material | HR | 1.76 | 0.033333 | 52.8 | 115.8 | 203.808
[22 empty] | Brick & Masonery for Manhole Neck | SC | LS | 1500 | 1 | 1500 | 3.86 | 5790
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.5 | 34 | 7.72 | 131.24
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.5 | 26 | 7.72 | 100.36
[9 empty] | 3.86 | 3.86 |  | 3.86 | [9 empty] | Backfilling |  | Ea | 549.0804 |  | 549.0804 | 3.86 | 2119.4502 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.03456 | 289.35 | 111.6891 | 1116.891
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 3.456 | 18.9814 | 1.1169 | 73.268
[22 empty] | Fuel | Material | LTR | 1.76 | 0.384 | 4.5833 | 10.052 | 17.6916
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.70503 | 68.0824 | 5.475 | 262.7979
[22 empty] | Fuel | Material | LTR | 1.76 | 0.070503 | 24.9635 | 54.7496 | 96.3592
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 1.728 | 20.8332 | 2.2338 | 80.4162
[22 empty] | Fuel | Material | LTR | 1.76 | 0.192 | 9.1666 | 20.104 | 35.3831
[22 empty] | Plate Compactor | Machinery | HR | 23 | 0.25 | 92 | 15.44 | 355.12
[22 empty] | Fuel | Material | LTR | 1.76 | 0.083333 | 21.12 | 46.32 | 81.5232
STR11 |  | Manhole 3.5-4.0m deep(GRP) | nr | 1.29 | 49093 | 63329.97 | 10987.2474 | 14173.5491 | 1.29 | 1.29 |  | 1.29 | 100% | 49093 | 63329.97 | 10987.2474 | 14173.5491 |  | 14173.5491 | [7 empty] | 10987.2474 | 1.29 | 14173.5491 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 1.29 | 1.29 |  | 1.29 | [9 empty] | Excavate & Disposal (3.0*3.0*4.5) |  | Ea | 162.8945 |  | 162.8945 | 1.29 | 210.1339 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 2.4691 | 22.68 | 0.52245 | 29.2572
[22 empty] | Fuel | Material | LTR | 1.76 | 0.17637 | 9.9792 | 7.3143 | 12.8732
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.5037 | 95.2941 | 2.561 | 122.9294
[22 empty] | Fuel | Material | LTR | 1.76 | 0.05037 | 34.9412 | 25.6103 | 45.0741
[9 empty] | 1.29 | 1.29 |  | 1.29 | [9 empty] | Concrete Base 30 cm |  | Ea | 1883.8375 |  | 1883.8375 | 1.29 | 2430.1504 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 1.7361 | 144 | 0.74304 | 185.76
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.63012 | 555.45 | 2.0472 | 716.5305
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 7.8765 | 317.4 | 0.16378 | 409.446
[22 empty] | Workmanship plain concrete | SC | M³ | 150 | 1.7361 | 86.4 | 0.74304 | 111.456
[22 empty] | Workmanship RC concrete | SC | M³ | 450 | 0.63012 | 714.15 | 2.0472 | 921.2535
[22 empty] | 2 Layers Bituminous Application | SC | M² | 10 | 0.15052 | 66.4375 | 8.5704 | 85.7044
[9 empty] | 1.29 | 1.29 |  | 1.29 | [9 empty] | Manhole Installation |  | Ea | 8322.8 |  | 8322.8 | 1.29 | 10736.412 | 0 | 0 | 0 | 0 | 0
[22 empty] | GRP manhole Dia 1500 mm D=4.0 m W Cover | Material | Ea | 6550 | 1 | 6550 | 1.29 | 8449.5
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 0.5 | 160 | 2.58 | 206.4
[22 empty] | Fuel | Material | HR | 1.76 | 0.033333 | 52.8 | 38.7 | 68.112
[22 empty] | Brick & Masonery for Manhole Neck | SC | LS | 1500 | 1 | 1500 | 1.29 | 1935
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.5 | 34 | 2.58 | 43.86
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.5 | 26 | 2.58 | 33.54
[9 empty] | 1.29 | 1.29 |  | 1.29 | [9 empty] | Backfilling |  | Ea | 617.7154 |  | 617.7154 | 1.29 | 796.8529 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.03072 | 325.5188 | 41.9919 | 419.9192
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 3.072 | 21.354 | 0.41992 | 27.5467
[22 empty] | Fuel | Material | LTR | 1.76 | 0.34134 | 5.1562 | 3.7793 | 6.6515
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.62669 | 76.5926 | 2.0584 | 98.8045
[22 empty] | Fuel | Material | LTR | 1.76 | 0.062669 | 28.084 | 20.5843 | 36.2283
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 1.536 | 23.4374 | 0.83984 | 30.2342
[22 empty] | Fuel | Material | LTR | 1.76 | 0.17067 | 10.3124 | 7.5585 | 13.303
[22 empty] | Plate Compactor | Machinery | HR | 23 | 0.22222 | 103.5 | 5.805 | 133.515
[22 empty] | Fuel | Material | LTR | 1.76 | 0.074074 | 23.76 | 17.415 | 30.6504
STR11 |  | Increasing the depth difference by 0.5 for a circular manhole measuring 1500 mm inner diameter (GRP) | nr |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Increasing the depth difference by 1.00 for a circular manhole measuring 1500 mm inner diameter (GRP) | nr |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Increase depth difference of 1.50 for a circular manhole measuring 1500 mm inner diameter (GRP) | nr |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Increased 2.00 depth differential for a circular manhole measuring 1500 mm inner diameter (GRP) | nr |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Increase depth difference of 2.50 for circular manhole measuring 1500mm inner diameter (GRP) | nr |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Increased 3.00 depth difference for a circular manhole measuring 1500 mm inner diameter (GRP) | nr |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Circular manhole measuring 1800 mm inner diameter
STR11 |  | Manhole depth 0-1.5m(GRP) | nr |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Manhole 1.5-2.0m deep(GRP) | nr | 0.395 | 22860 | 9029.7 | 9813.863 | 3876.4759 | 0.395 | 0.395 |  | 0.395 | 100% | 22860 | 9029.7 | 9813.863 | 3876.4759 |  | 3876.4759 | [7 empty] | 9813.863 | 0.395 | 3876.4759 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 0.395 | 0.395 |  | 0.395 | [9 empty] | Excavate & Disposal (3.5*3.5*2.5) |  | Ea | 123.1764 |  | 123.1764 | 0.395 | 48.6547 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 3.2653 | 17.15 | 0.12097 | 6.7742
[22 empty] | Fuel | Material | LTR | 1.76 | 0.23324 | 7.546 | 1.6936 | 2.9807
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.66612 | 72.0588 | 0.59298 | 28.4632
[22 empty] | Fuel | Material | LTR | 1.76 | 0.066612 | 26.4216 | 5.9298 | 10.4365
[9 empty] | 0.395 | 0.395 |  | 0.395 | [9 empty] | Concrete Base 30 cm |  | Ea | 2396.566 |  | 2396.566 | 0.395 | 946.6436 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 1.3717 | 182.25 | 0.28795 | 71.9887
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.4931 | 709.8 | 0.80106 | 280.371
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 6.1637 | 405.6 | 0.064085 | 160.212
[22 empty] | Workmanship plain concrete | SC | M³ | 150 | 1.3717 | 109.35 | 0.28795 | 43.1932
[22 empty] | Workmanship RC concrete | SC | M³ | 450 | 0.4931 | 912.6 | 0.80106 | 360.477
[22 empty] | 2 Layers Bituminous Application | SC | M² | 10 | 0.12993 | 76.966 | 3.0402 | 30.4016
[9 empty] | 0.395 | 0.395 |  | 0.395 | [9 empty] | Manhole Installation |  | Ea | 6857.8 |  | 6857.8 | 0.395 | 2708.831 | 0 | 0 | 0 | 0 | 0
[22 empty] | GRP manhole Dia 1800 mm D=2.0 m W Cover | Material | Ea | 5085 | 1 | 5085 | 0.395 | 2008.575
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 0.5 | 160 | 0.79 | 63.2
[22 empty] | Fuel | Material | HR | 1.76 | 0.033333 | 52.8 | 11.85 | 20.856
[22 empty] | Brick & Masonery for Manhole Neck | SC | LS | 1500 | 1 | 1500 | 0.395 | 592.5
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.5 | 34 | 0.79 | 13.43
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.5 | 26 | 0.79 | 10.27
[9 empty] | 0.395 | 0.395 |  | 0.395 | [9 empty] | Backfilling |  | Ea | 436.3206 |  | 436.3206 | 0.395 | 172.3466 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.041209 | 242.665 | 9.5853 | 95.8527
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 4.1209 | 15.9188 | 0.095853 | 6.2879
[22 empty] | Fuel | Material | LTR | 1.76 | 0.45788 | 3.8438 | 0.86267 | 1.5183
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.84067 | 57.0976 | 0.46987 | 22.5536
[22 empty] | Fuel | Material | LTR | 1.76 | 0.084067 | 20.9358 | 4.6987 | 8.2696
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 2.0605 | 17.4719 | 0.19171 | 6.9014
[22 empty] | Fuel | Material | LTR | 1.76 | 0.22894 | 7.6876 | 1.7253 | 3.0366
[22 empty] | Plate Compactor | Machinery | HR | 23 | 0.4 | 57.5 | 0.9875 | 22.7125
[22 empty] | Fuel | Material | LTR | 1.76 | 0.13333 | 13.2 | 2.9625 | 5.214
STR11 |  | Manhole with depth 2.0-2.5m(GRP) | nr | 2.925 | 28575 | 83581.875 | 10735.7624 | 31402.105 | 2.925 | 2.925 |  | 2.925 | 100% | 28575 | 83581.875 | 10735.7624 | 31402.105 |  | 31402.105 | [7 empty] | 10735.7624 | 2.925 | 31402.105 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 2.925 | 2.925 |  | 2.925 | [9 empty] | Excavate & Disposal (3.5*3.5*3.0) |  | Ea | 147.8117 |  | 147.8117 | 2.925 | 432.3491 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 2.7211 | 20.58 | 1.0749 | 60.1965
[22 empty] | Fuel | Material | LTR | 1.76 | 0.19436 | 9.0552 | 15.0491 | 26.4865
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.5551 | 86.4706 | 5.2693 | 252.9265
[22 empty] | Fuel | Material | LTR | 1.76 | 0.05551 | 31.7059 | 52.693 | 92.7397
[9 empty] | 2.925 | 2.925 |  | 2.925 | [9 empty] | Concrete Base 30 cm |  | Ea | 2396.566 |  | 2396.566 | 2.925 | 7009.9555 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 1.3717 | 182.25 | 2.1323 | 533.0812
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.4931 | 709.8 | 5.9319 | 2076.165
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 6.1637 | 405.6 | 0.47455 | 1186.38
[22 empty] | Workmanship plain concrete | SC | M³ | 150 | 1.3717 | 109.35 | 2.1323 | 319.8487
[22 empty] | Workmanship RC concrete | SC | M³ | 450 | 0.4931 | 912.6 | 5.9319 | 2669.355
[22 empty] | 2 Layers Bituminous Application | SC | M² | 10 | 0.12993 | 76.966 | 22.5126 | 225.1255
[9 empty] | 2.925 | 2.925 |  | 2.925 | [9 empty] | Manhole Installation |  | Ea | 7667.8 |  | 7667.8 | 2.925 | 22428.315 | 0 | 0 | 0 | 0 | 0
[22 empty] | GRP manhole Dia 1800 mm D=2.5 m W Cover | Material | Ea | 5895 | 1 | 5895 | 2.925 | 17242.875
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 0.5 | 160 | 5.85 | 468
[22 empty] | Fuel | Material | HR | 1.76 | 0.033333 | 52.8 | 87.75 | 154.44
[22 empty] | Brick & Masonery for Manhole Neck | SC | LS | 1500 | 1 | 1500 | 2.925 | 4387.5
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.5 | 34 | 5.85 | 99.45
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.5 | 26 | 5.85 | 76.05
[9 empty] | 2.925 | 2.925 |  | 2.925 | [9 empty] | Backfilling |  | Ea | 523.5847 |  | 523.5847 | 2.925 | 1531.4853 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.034341 | 291.198 | 85.1754 | 851.7541
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 3.4341 | 19.1026 | 0.85175 | 55.8751
[22 empty] | Fuel | Material | LTR | 1.76 | 0.38157 | 4.6126 | 7.6658 | 13.4918
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.70055 | 68.5172 | 4.1753 | 200.4127
[22 empty] | Fuel | Material | LTR | 1.76 | 0.070055 | 25.123 | 41.7527 | 73.4847
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 1.717 | 20.9663 | 1.7035 | 61.3263
[22 empty] | Fuel | Material | LTR | 1.76 | 0.19078 | 9.2252 | 15.3316 | 26.9836
[22 empty] | Plate Compactor | Machinery | HR | 23 | 0.33333 | 69 | 8.775 | 201.825
[22 empty] | Fuel | Material | LTR | 1.76 | 0.11111 | 15.84 | 26.325 | 46.332
STR11 |  | Manhole 2.5-3.0m deep(GRP) | nr | 2.05 | 34366 | 70450.3 | 11657.6618 | 23898.2067 | 2.05 | 2.05 |  | 2.05 | 100% | 34366 | 70450.3 | 11657.6618 | 23898.2067 |  | 23898.2067 | [7 empty] | 11657.6618 | 2.05 | 23898.2067 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 2.05 | 2.05 |  | 2.05 | [9 empty] | Excavate & Disposal (3.5*3.5*3.5) |  | Ea | 172.4469 |  | 172.4469 | 2.05 | 353.5162 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 2.3324 | 24.01 | 0.87894 | 49.2205
[22 empty] | Fuel | Material | LTR | 1.76 | 0.1666 | 10.5644 | 12.3051 | 21.657
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.4758 | 100.8824 | 4.3085 | 206.8088
[22 empty] | Fuel | Material | LTR | 1.76 | 0.04758 | 36.9902 | 43.0852 | 75.8299
[9 empty] | 2.05 | 2.05 |  | 2.05 | [9 empty] | Concrete Base 30 cm |  | Ea | 2396.566 |  | 2396.566 | 2.05 | 4912.9603 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 1.3717 | 182.25 | 1.4944 | 373.6125
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.4931 | 709.8 | 4.1574 | 1455.09
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 6.1637 | 405.6 | 0.33259 | 831.48
[22 empty] | Workmanship plain concrete | SC | M³ | 150 | 1.3717 | 109.35 | 1.4944 | 224.1675
[22 empty] | Workmanship RC concrete | SC | M³ | 450 | 0.4931 | 912.6 | 4.1574 | 1870.83
[22 empty] | 2 Layers Bituminous Application | SC | M² | 10 | 0.12993 | 76.966 | 15.778 | 157.7803
[9 empty] | 2.05 | 2.05 |  | 2.05 | [9 empty] | Manhole Installation |  | Ea | 8477.8 |  | 8477.8 | 2.05 | 17379.49 | 0 | 0 | 0 | 0 | 0
[22 empty] | GRP manhole Dia 1800 mm D=3.0 m W Cover | Material | Ea | 6705 | 1 | 6705 | 2.05 | 13745.25
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 0.5 | 160 | 4.1 | 328
[22 empty] | Fuel | Material | HR | 1.76 | 0.033333 | 52.8 | 61.5 | 108.24
[22 empty] | Brick & Masonery for Manhole Neck | SC | LS | 1500 | 1 | 1500 | 2.05 | 3075
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.5 | 34 | 4.1 | 69.7
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.5 | 26 | 4.1 | 53.3
[9 empty] | 2.05 | 2.05 |  | 2.05 | [9 empty] | Backfilling |  | Ea | 610.8488 |  | 610.8488 | 2.05 | 1252.2401 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.029435 | 339.731 | 69.6449 | 696.4485
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 2.9435 | 22.2864 | 0.69645 | 45.687
[22 empty] | Fuel | Material | LTR | 1.76 | 0.32706 | 5.3813 | 6.268 | 11.0317
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.60048 | 79.9367 | 3.414 | 163.8702
[22 empty] | Fuel | Material | LTR | 1.76 | 0.060048 | 29.3101 | 34.1396 | 60.0858
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 1.4718 | 24.4606 | 1.3929 | 50.1443
[22 empty] | Fuel | Material | LTR | 1.76 | 0.16353 | 10.7627 | 12.5361 | 22.0635
[22 empty] | Plate Compactor | Machinery | HR | 23 | 0.28571 | 80.5 | 7.175 | 165.025
[22 empty] | Fuel | Material | LTR | 1.76 | 0.095238 | 18.48 | 21.525 | 37.884
STR11 |  | Manhole 3.0-3.5m deep(GRP) | nr | 0.29 | 35121 | 10185.09 | 12579.5612 | 3648.0727 | 0.29 | 0.29 |  | 0.29 | 100% | 35121 | 10185.09 | 12579.5612 | 3648.0727 |  | 3648.0727 | [7 empty] | 12579.5612 | 0.29 | 3648.0727 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 0.29 | 0.29 |  | 0.29 | [9 empty] | Excavate & Disposal (3.5*3.5*4.0) |  | Ea | 197.0822 |  | 197.0822 | 0.29 | 57.1538 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 2.0408 | 27.44 | 0.1421 | 7.9576
[22 empty] | Fuel | Material | LTR | 1.76 | 0.14577 | 12.0736 | 1.9894 | 3.5013
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.41633 | 115.2941 | 0.69657 | 33.4353
[22 empty] | Fuel | Material | LTR | 1.76 | 0.041633 | 42.2745 | 6.9657 | 12.2596
[9 empty] | 0.29 | 0.29 |  | 0.29 | [9 empty] | Concrete Base 30 cm |  | Ea | 2396.566 |  | 2396.566 | 0.29 | 695.0041 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 1.3717 | 182.25 | 0.21141 | 52.8525
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.4931 | 709.8 | 0.58812 | 205.842
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 6.1637 | 405.6 | 0.04705 | 117.624
[22 empty] | Workmanship plain concrete | SC | M³ | 150 | 1.3717 | 109.35 | 0.21141 | 31.7115
[22 empty] | Workmanship RC concrete | SC | M³ | 450 | 0.4931 | 912.6 | 0.58812 | 264.654
[22 empty] | 2 Layers Bituminous Application | SC | M² | 10 | 0.12993 | 76.966 | 2.232 | 22.3201
[9 empty] | 0.29 | 0.29 |  | 0.29 | [9 empty] | Manhole Installation |  | Ea | 9287.8 |  | 9287.8 | 0.29 | 2693.462 | 0 | 0 | 0 | 0 | 0
[22 empty] | GRP manhole Dia 1800 mm D=3.5 m W Cover | Material | Ea | 7515 | 1 | 7515 | 0.29 | 2179.35
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 0.5 | 160 | 0.58 | 46.4
[22 empty] | Fuel | Material | HR | 1.76 | 0.033333 | 52.8 | 8.7 | 15.312
[22 empty] | Brick & Masonery for Manhole Neck | SC | LS | 1500 | 1 | 1500 | 0.29 | 435
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.5 | 34 | 0.58 | 9.86
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.5 | 26 | 0.58 | 7.54
[9 empty] | 0.29 | 0.29 |  | 0.29 | [9 empty] | Backfilling |  | Ea | 698.113 |  | 698.113 | 0.29 | 202.4528 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.025756 | 388.264 | 11.2597 | 112.5966
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 2.5756 | 25.4701 | 0.1126 | 7.3863
[22 empty] | Fuel | Material | LTR | 1.76 | 0.28617 | 6.1501 | 1.0134 | 1.7835
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.52542 | 91.3562 | 0.55194 | 26.4933
[22 empty] | Fuel | Material | LTR | 1.76 | 0.052542 | 33.4973 | 5.5194 | 9.7142
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 1.2878 | 27.955 | 0.22519 | 8.107
[22 empty] | Fuel | Material | LTR | 1.76 | 0.14309 | 12.3002 | 2.0267 | 3.5671
[22 empty] | Plate Compactor | Machinery | HR | 23 | 0.25 | 92 | 1.16 | 26.68
[22 empty] | Fuel | Material | LTR | 1.76 | 0.083333 | 21.12 | 3.48 | 6.1248
STR11 |  | Manhole 3.5-4.0m deep(GRP) | nr |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Circular manhole measuring 3000 mm inner diameter
STR11 |  | Manhole with a depth of 0-1.5 m | nr |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Manhole depth 0-1.5m(GRP) | nr |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Manhole with a depth of 1.5-2.0 m | nr |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Manhole 1.5-2.0m deep(GRP) | nr |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Manhole with a depth of 2.0-2.5 m | nr |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Manhole with depth 2.0-2.5m(GRP) | nr |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Manhole with a depth of 2.5-3.0 m | nr |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Manhole 2.5-3.0m deep(GRP) | nr |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Manhole with a depth of 3.0-3.5 m | nr |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Manhole 3.0-3.5m deep(GRP) | nr |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Manhole with a depth of 3.5-4.0 m | nr |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Manhole 3.5-4.0m deep(GRP) | nr |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Flush Inlet Manholes (continued) |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Constructing concrete manholes for the entry of wastewater onto box drain pipes. This includes excavation, backfilling, compaction, waste removal, dewatering, sanitation concrete, concrete bases, walls, roof slabs, surrounding soil, reinforcement, formwork, concrete room frames, slabs, brickwork, masonry, cement bases, waterproofing, waterproofing, entrance covers and frames, safety rings, dividers and intersections according to the plans. Specifications and requirements of the concerned authority. |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
STR11 |  | Schemes no. DAM2-01-002-CH2-TS8--1-STR-DRW-0313 Rev A |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Manhole on box pipes 1000x1000mm wide
STR11 |  | Manhole with a depth of 0.0-1.5 m | nr | 57.07 | 5921 | 337911.47 | 3430.6319 | 195786.1605 | 57.07 | 57.07 |  | 57.07 | 100% | 5921 | 337911.47 | 3430.6319 | 195786.1605 |  | 195786.1605 | [7 empty] | 3430.6319 | 57.07 | 195786.1605 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 57.07 | 57.07 |  | 57.07 | [9 empty] | Excavate & Disposal (2.5*2.5*1.5) |  | Ea | 37.7071 |  | 37.7071 | 57.07 | 2151.9418 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 10.6667 | 5.25 | 5.3503 | 299.6175
[22 empty] | Fuel | Material | LTR | 1.76 | 0.7619 | 2.31 | 74.9044 | 131.8317
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 2.176 | 22.0588 | 26.227 | 1258.8971
[22 empty] | Fuel | Material | LTR | 1.76 | 0.2176 | 8.0882 | 262.2702 | 461.5956
[9 empty] | 57.07 | 57.07 |  | 57.07 | [9 empty] | Concrete Manhole Installation |  | Ea | 2847.2031 |  | 2847.2031 | 57.07 | 162489.8796 | 0 | 0 | 0 | 0 | 0
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.66667 | 525 | 85.605 | 29961.75
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 8.3333 | 300 | 6.8484 | 17121
[22 empty] | Trench RC Concrete workmanship | SC | M³ | 300 | 0.66667 | 450 | 85.605 | 25681.5
[22 empty] | Concrete manhole Cover, frames | Material | Ea | 1250 | 1 | 1250 | 57.07 | 71337.5
[22 empty] | Boom Truck 10T | Machinery | HR | 67.6923 | 4 | 16.9231 | 14.2675 | 965.8
[22 empty] | Fuel | Material | HR | 1.76 | 0.33333 | 5.28 | 171.21 | 301.3296
[22 empty] | Chamber Pipes Pieces | Material | LS | 150 | 1 | 150 | 57.07 | 8560.5
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.2 | 85 | 285.35 | 4850.95
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.2 | 65 | 285.35 | 3709.55
[9 empty] | 57.07 | 57.07 |  | 57.07 | [9 empty] | Internal and external Insulation |  | Ea | 420 |  | 420 | 57.07 | 23969.4 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply & apply external waterproofing | SC | M² | 40 | 0.16667 | 240 | 342.42 | 13696.8
[22 empty] | Supply & apply internal coating | SC | M² | 30 | 0.16667 | 180 | 342.42 | 10272.6
[9 empty] | 57.07 | 57.07 |  | 57.07 | [9 empty] | Backfilling |  | Ea | 125.7217 |  | 125.7217 | 57.07 | 7174.9391 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.12698 | 78.75 | 449.4262 | 4494.2625
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 12.6984 | 5.166 | 4.4943 | 294.8236
[22 empty] | Fuel | Material | LTR | 1.76 | 1.4109 | 1.2474 | 40.4484 | 71.1891
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 2.5905 | 18.5294 | 22.0307 | 1057.4735
[22 empty] | Fuel | Material | LTR | 1.76 | 0.25905 | 6.7941 | 220.307 | 387.7403
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 6.3492 | 5.67 | 8.9885 | 323.5869
[22 empty] | Fuel | Material | LTR | 1.76 | 0.70547 | 2.4948 | 80.8967 | 142.3782
[22 empty] | Plate Compactor | Machinery | HR | 23 | 4 | 5.75 | 14.2675 | 328.1525
[22 empty] | Fuel | Material | LTR | 1.76 | 1.3333 | 1.32 | 42.8025 | 75.3324
STR11 |  | Manhole with a depth of 1.5-2.0 m | nr | 55.39 | 7249 | 401522.11 | 3962.7515 | 219496.8034 | 55.39 | 55.39 |  | 55.39 | 100% | 7249 | 401522.11 | 3962.7515 | 219496.8034 |  | 219496.8034 | [7 empty] | 3962.7515 | 55.39 | 219496.8034 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 55.39 | 55.39 |  | 55.39 | [9 empty] | Excavate & Disposal (2.5*2.5*2.0) |  | Ea | 50.2761 |  | 50.2761 | 55.39 | 2784.792 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 8 | 7 | 6.9237 | 387.73
[22 empty] | Fuel | Material | LTR | 1.76 | 0.57143 | 3.08 | 96.9325 | 170.6012
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 1.632 | 29.4118 | 33.94 | 1629.1176
[22 empty] | Fuel | Material | LTR | 1.76 | 0.1632 | 10.7843 | 339.3995 | 597.3431
[9 empty] | 55.39 | 55.39 |  | 55.39 | [9 empty] | Concrete Manhole Installation |  | Ea | 3187.2031 |  | 3187.2031 | 55.39 | 176539.1784 | 0 | 0 | 0 | 0 | 0
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.52632 | 665 | 105.241 | 36834.35
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 6.5789 | 380 | 8.4193 | 21048.2
[22 empty] | Trench RC Concrete workmanship | SC | M³ | 300 | 0.52632 | 570 | 105.241 | 31572.3
[22 empty] | Concrete manhole Cover, frames | Material | Ea | 1250 | 1 | 1250 | 55.39 | 69237.5
[22 empty] | Boom Truck 10T | Machinery | HR | 67.6923 | 4 | 16.9231 | 13.8475 | 937.3692
[22 empty] | Fuel | Material | HR | 1.76 | 0.33333 | 5.28 | 166.17 | 292.4592
[22 empty] | Chamber Pipes Pieces | Material | LS | 150 | 1 | 150 | 55.39 | 8308.5
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.2 | 85 | 276.95 | 4708.15
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.2 | 65 | 276.95 | 3600.35
[9 empty] | 55.39 | 55.39 |  | 55.39 | [9 empty] | Internal and external Insulation |  | Ea | 560 |  | 560 | 55.39 | 31018.4 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply & apply external waterproofing | SC | M² | 40 | 0.125 | 320 | 443.12 | 17724.8
[22 empty] | Supply & apply internal coating | SC | M² | 30 | 0.125 | 240 | 443.12 | 13293.6
[9 empty] | 55.39 | 55.39 |  | 55.39 | [9 empty] | Backfilling |  | Ea | 165.2723 |  | 165.2723 | 55.39 | 9154.433 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.095238 | 105 | 581.595 | 5815.95
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 9.5238 | 6.888 | 5.8159 | 381.5263
[22 empty] | Fuel | Material | LTR | 1.76 | 1.0582 | 1.6632 | 52.3435 | 92.1246
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 1.9429 | 24.7059 | 28.5096 | 1368.4588
[22 empty] | Fuel | Material | LTR | 1.76 | 0.19429 | 9.0588 | 285.0956 | 501.7682
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 4.7619 | 7.56 | 11.6319 | 418.7484
[22 empty] | Fuel | Material | LTR | 1.76 | 0.5291 | 3.3264 | 104.6871 | 184.2493
[22 empty] | Plate Compactor | Machinery | HR | 23 | 4 | 5.75 | 13.8475 | 318.4925
[22 empty] | Fuel | Material | LTR | 1.76 | 1.3333 | 1.32 | 41.5425 | 73.1148
STR11 |  | Manhole with a depth of 2.0-2.5 m | nr | 65.74 | 8582 | 564180.68 | 4497.2277 | 295647.7506 | 65.74 | 65.74 |  | 65.74 | 100% | 8582 | 564180.68 | 4497.2277 | 295647.7506 |  | 295647.7506 | [7 empty] | 4497.2277 | 65.74 | 295647.7506 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 65.74 | 65.74 |  | 65.74 | [9 empty] | Excavate & Disposal (2.5*2.5*2.5) |  | Ea | 62.8451 |  | 62.8451 | 65.74 | 4131.4367 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 6.4 | 8.75 | 10.2719 | 575.225
[22 empty] | Fuel | Material | LTR | 1.76 | 0.45714 | 3.85 | 143.8062 | 253.099
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 1.3056 | 36.7647 | 50.3523 | 2416.9118
[22 empty] | Fuel | Material | LTR | 1.76 | 0.13056 | 13.4804 | 503.5233 | 886.201
[9 empty] | 65.74 | 65.74 |  | 65.74 | [9 empty] | Concrete Manhole Installation |  | Ea | 3527.2031 |  | 3527.2031 | 65.74 | 231878.3303 | 0 | 0 | 0 | 0 | 0
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.43478 | 805 | 151.202 | 52920.7
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 5.4348 | 460 | 12.0962 | 30240.4
[22 empty] | Trench RC Concrete workmanship | SC | M³ | 300 | 0.43478 | 690 | 151.202 | 45360.6
[22 empty] | Concrete manhole Cover, frames | Material | Ea | 1250 | 1 | 1250 | 65.74 | 82175
[22 empty] | Boom Truck 10T | Machinery | HR | 67.6923 | 4 | 16.9231 | 16.435 | 1112.5231
[22 empty] | Fuel | Material | HR | 1.76 | 0.33333 | 5.28 | 197.22 | 347.1072
[22 empty] | Chamber Pipes Pieces | Material | LS | 150 | 1 | 150 | 65.74 | 9861
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.2 | 85 | 328.7 | 5587.9
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.2 | 65 | 328.7 | 4273.1
[9 empty] | 65.74 | 65.74 |  | 65.74 | [9 empty] | Internal and external Insulation |  | Ea | 700 |  | 700 | 65.74 | 46018 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply & apply external waterproofing | SC | M² | 40 | 0.1 | 400 | 657.4 | 26296
[22 empty] | Supply & apply internal coating | SC | M² | 30 | 0.1 | 300 | 657.4 | 19722
[9 empty] | 65.74 | 65.74 |  | 65.74 | [9 empty] | Backfilling |  | Ea | 207.1795 |  | 207.1795 | 65.74 | 13619.9836 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.07619 | 131.25 | 862.8375 | 8628.375
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 7.619 | 8.61 | 8.6284 | 566.0214
[22 empty] | Fuel | Material | LTR | 1.76 | 0.84656 | 2.079 | 77.6554 | 136.6735
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 1.5543 | 30.8824 | 42.296 | 2030.2059
[22 empty] | Fuel | Material | LTR | 1.76 | 0.15543 | 11.3235 | 422.9596 | 744.4088
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 3.8095 | 9.45 | 17.2567 | 621.243
[22 empty] | Fuel | Material | LTR | 1.76 | 0.42328 | 4.158 | 155.3107 | 273.3469
[22 empty] | Plate Compactor | Machinery | HR | 23 | 3 | 7.6667 | 21.9133 | 504.0067
[22 empty] | Fuel | Material | LTR | 1.76 | 1 | 1.76 | 65.74 | 115.7024
STR11 |  | Manhole with a depth of 2.5-3.0 m | nr | 20.58 | 9915 | 204050.7 | 5029.3473 | 103503.9678 | 20.58 | 20.58 |  | 20.58 | 100% | 9915 | 204050.7 | 5029.3473 | 103503.9678 |  | 103503.9678 | [7 empty] | 5029.3473 | 20.58 | 103503.9678 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 20.58 | 20.58 |  | 20.58 | [9 empty] | Excavate & Disposal (2.5*2.5*3.0) |  | Ea | 75.4141 |  | 75.4141 | 20.58 | 1552.0225 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 5.3333 | 10.5 | 3.8587 | 216.09
[22 empty] | Fuel | Material | LTR | 1.76 | 0.38095 | 4.62 | 54.0225 | 95.0796
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 1.088 | 44.1176 | 18.9154 | 907.9412
[22 empty] | Fuel | Material | LTR | 1.76 | 0.1088 | 16.1765 | 189.1544 | 332.9118
[9 empty] | 20.58 | 20.58 |  | 20.58 | [9 empty] | Concrete Manhole Installation |  | Ea | 3867.2031 |  | 3867.2031 | 20.58 | 79587.0393 | 0 | 0 | 0 | 0 | 0
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.37037 | 945 | 55.566 | 19448.1
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 4.6296 | 540 | 4.4453 | 11113.2
[22 empty] | Trench RC Concrete workmanship | SC | M³ | 300 | 0.37037 | 810 | 55.566 | 16669.8
[22 empty] | Concrete manhole Cover, frames | Material | Ea | 1250 | 1 | 1250 | 20.58 | 25725
[22 empty] | Boom Truck 10T | Machinery | HR | 67.6923 | 4 | 16.9231 | 5.145 | 348.2769
[22 empty] | Fuel | Material | HR | 1.76 | 0.33333 | 5.28 | 61.74 | 108.6624
[22 empty] | Chamber Pipes Pieces | Material | LS | 150 | 1 | 150 | 20.58 | 3087
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.2 | 85 | 102.9 | 1749.3
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.2 | 65 | 102.9 | 1337.7
[9 empty] | 20.58 | 20.58 |  | 20.58 | [9 empty] | Internal and external Insulation |  | Ea | 840 |  | 840 | 20.58 | 17287.2 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply & apply external waterproofing | SC | M² | 40 | 0.083333 | 480 | 246.96 | 9878.4
[22 empty] | Supply & apply internal coating | SC | M² | 30 | 0.083333 | 360 | 246.96 | 7408.8
[9 empty] | 20.58 | 20.58 |  | 20.58 | [9 empty] | Backfilling |  | Ea | 246.7301 |  | 246.7301 | 20.58 | 5077.706 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.063492 | 157.5 | 324.135 | 3241.35
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 6.3492 | 10.332 | 3.2413 | 212.6326
[22 empty] | Fuel | Material | LTR | 1.76 | 0.70547 | 2.4948 | 29.1721 | 51.343
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 1.2952 | 37.0588 | 15.889 | 762.6706
[22 empty] | Fuel | Material | LTR | 1.76 | 0.12952 | 13.5882 | 158.8897 | 279.6459
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 3.1746 | 11.34 | 6.4827 | 233.3772
[22 empty] | Fuel | Material | LTR | 1.76 | 0.35273 | 4.9896 | 58.3443 | 102.686
[22 empty] | Plate Compactor | Machinery | HR | 23 | 3 | 7.6667 | 6.86 | 157.78
[22 empty] | Fuel | Material | LTR | 1.76 | 1 | 1.76 | 20.58 | 36.2208
STR11 |  | Manhole with a depth of 3.0-3.5 m | nr | 6.81 | 11249 | 76605.69 | 5566.1802 | 37905.6875 | 6.81 | 6.81 |  | 6.81 | 100% | 11249 | 76605.69 | 5566.1802 | 37905.6875 |  | 37905.6875 | [7 empty] | 5566.1802 | 6.81 | 37905.6875 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 6.81 | 6.81 |  | 6.81 | [9 empty] | Excavate & Disposal (2.5*2.5*3.5) |  | Ea | 87.9831 |  | 87.9831 | 6.81 | 599.1652 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 4.5714 | 12.25 | 1.4897 | 83.4225
[22 empty] | Fuel | Material | LTR | 1.76 | 0.32653 | 5.39 | 20.8556 | 36.7059
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.93257 | 51.4706 | 7.3024 | 350.5147
[22 empty] | Fuel | Material | LTR | 1.76 | 0.093257 | 18.8725 | 73.0239 | 128.5221
[9 empty] | 6.81 | 6.81 |  | 6.81 | [9 empty] | Concrete Manhole Installation |  | Ea | 4207.2031 |  | 4207.2031 | 6.81 | 28651.053 | 0 | 0 | 0 | 0 | 0
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.32258 | 1085 | 21.111 | 7388.85
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 4.0323 | 620 | 1.6889 | 4222.2
[22 empty] | Trench RC Concrete workmanship | SC | M³ | 300 | 0.32258 | 930 | 21.111 | 6333.3
[22 empty] | Concrete manhole Cover, frames | Material | Ea | 1250 | 1 | 1250 | 6.81 | 8512.5
[22 empty] | Boom Truck 10T | Machinery | HR | 67.6923 | 4 | 16.9231 | 1.7025 | 115.2462
[22 empty] | Fuel | Material | HR | 1.76 | 0.33333 | 5.28 | 20.43 | 35.9568
[22 empty] | Chamber Pipes Pieces | Material | LS | 150 | 1 | 150 | 6.81 | 1021.5
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.2 | 85 | 34.05 | 578.85
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.2 | 65 | 34.05 | 442.65
[9 empty] | 6.81 | 6.81 |  | 6.81 | [9 empty] | Internal and external Insulation |  | Ea | 980 |  | 980 | 6.81 | 6673.8 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply & apply external waterproofing | SC | M² | 40 | 0.071429 | 560 | 95.34 | 3813.6
[22 empty] | Supply & apply internal coating | SC | M² | 30 | 0.071429 | 420 | 95.34 | 2860.2
[9 empty] | 6.81 | 6.81 |  | 6.81 | [9 empty] | Backfilling |  | Ea | 290.994 |  | 290.994 | 6.81 | 1981.6694 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.054422 | 183.75 | 125.1337 | 1251.3375
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 5.4422 | 12.054 | 1.2513 | 82.0877
[22 empty] | Fuel | Material | LTR | 1.76 | 0.60469 | 2.9106 | 11.262 | 19.8212
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 1.1102 | 43.2353 | 6.134 | 294.4324
[22 empty] | Fuel | Material | LTR | 1.76 | 0.11102 | 15.8529 | 61.3401 | 107.9585
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 2.7211 | 13.23 | 2.5027 | 90.0963
[22 empty] | Fuel | Material | LTR | 1.76 | 0.30234 | 5.8212 | 22.5241 | 39.6424
[22 empty] | Plate Compactor | Machinery | HR | 23 | 2 | 11.5 | 3.405 | 78.315
[22 empty] | Fuel | Material | LTR | 1.76 | 0.66667 | 2.64 | 10.215 | 17.9784
STR11 |  | Manhole with a depth of 3.5-4.0 m | nr | 1.86 | 12583 | 23404.38 | 6112.4398 | 11369.1381 | 1.86 | 1.86 |  | 1.86 | 100% | 12583 | 23404.38 | 6112.4398 | 11369.1381 |  | 11369.1381 | [7 empty] | 6112.4398 | 1.86 | 11369.1381 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 1.86 | 1.86 |  | 1.86 | [9 empty] | Excavate & Disposal (2.5*2.5*4) |  | Ea | 100.5522 |  | 100.5522 | 1.86 | 187.027 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 4 | 14 | 0.465 | 26.04
[22 empty] | Fuel | Material | LTR | 1.76 | 0.28571 | 6.16 | 6.51 | 11.4576
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.816 | 58.8235 | 2.2794 | 109.4118
[22 empty] | Fuel | Material | LTR | 1.76 | 0.0816 | 21.5686 | 22.7941 | 40.1176
[9 empty] | 1.86 | 1.86 |  | 1.86 | [9 empty] | Concrete Manhole Installation |  | Ea | 4547.2031 |  | 4547.2031 | 1.86 | 8457.7977 | 0 | 0 | 0 | 0 | 0
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.28571 | 1225 | 6.51 | 2278.5
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 3.5714 | 700 | 0.5208 | 1302
[22 empty] | Trench RC Concrete workmanship | SC | M³ | 300 | 0.28571 | 1050 | 6.51 | 1953
[22 empty] | Concrete manhole Cover, frames | Material | Ea | 1250 | 1 | 1250 | 1.86 | 2325
[22 empty] | Boom Truck 10T | Machinery | HR | 67.6923 | 4 | 16.9231 | 0.465 | 31.4769
[22 empty] | Fuel | Material | HR | 1.76 | 0.33333 | 5.28 | 5.58 | 9.8208
[22 empty] | Chamber Pipes Pieces | Material | LS | 150 | 1 | 150 | 1.86 | 279
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.2 | 85 | 9.3 | 158.1
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.2 | 65 | 9.3 | 120.9
[9 empty] | 1.86 | 1.86 |  | 1.86 | [9 empty] | Internal and external Insulation |  | Ea | 1120 |  | 1120 | 1.86 | 2083.2 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply & apply external waterproofing | SC | M² | 40 | 0.0625 | 640 | 29.76 | 1190.4
[22 empty] | Supply & apply internal coating | SC | M² | 30 | 0.0625 | 480 | 29.76 | 892.8
[9 empty] | 1.86 | 1.86 |  | 1.86 | [9 empty] | Backfilling |  | Ea | 344.6846 |  | 344.6846 | 1.86 | 641.1134 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.047619 | 210 | 39.06 | 390.6
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 4.7619 | 13.776 | 0.3906 | 25.6234
[22 empty] | Fuel | Material | LTR | 1.76 | 0.5291 | 3.3264 | 3.5154 | 6.1871
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.97143 | 49.4118 | 1.9147 | 91.9059
[22 empty] | Fuel | Material | LTR | 1.76 | 0.097143 | 18.1176 | 19.1471 | 33.6988
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 2.381 | 15.12 | 0.7812 | 28.1232
[22 empty] | Fuel | Material | LTR | 1.76 | 0.26455 | 6.6528 | 7.0308 | 12.3742
[22 empty] | Plate Compactor | Machinery | HR | 23 | 1 | 23 | 1.86 | 42.78
[22 empty] | Fuel | Material | LTR | 1.76 | 0.33333 | 5.28 | 5.58 | 9.8208
STR11 |  | Manhole with a depth of more than -4.0 m | nr | 0.29 | 17921 | 5197.09 | 7204.959 | 2089.4381 | 0.29 | 0.29 |  | 0.29 | 100% | 17921 | 5197.09 | 7204.959 | 2089.4381 |  | 2089.4381 | [7 empty] | 7204.959 | 0.29 | 2089.4381 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 0.29 | 0.29 |  | 0.29 | [9 empty] | Excavate & Disposal (2.5*2.5*5) |  | Ea | 125.6902 |  | 125.6902 | 0.29 | 36.4502 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 3.2 | 17.5 | 0.090625 | 5.075
[22 empty] | Fuel | Material | LTR | 1.76 | 0.22857 | 7.7 | 1.2688 | 2.233
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.6528 | 73.5294 | 0.44424 | 21.3235
[22 empty] | Fuel | Material | LTR | 1.76 | 0.06528 | 26.9608 | 4.4424 | 7.8186
[9 empty] | 0.29 | 0.29 |  | 0.29 | [9 empty] | Concrete Manhole Installation |  | Ea | 5227.2031 |  | 5227.2031 | 0.29 | 1515.8889 | 0 | 0 | 0 | 0 | 0
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.23256 | 1505 | 1.247 | 436.45
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 2.907 | 860 | 0.09976 | 249.4
[22 empty] | Trench RC Concrete workmanship | SC | M³ | 300 | 0.23256 | 1290 | 1.247 | 374.1
[22 empty] | Concrete manhole Cover, frames | Material | Ea | 1250 | 1 | 1250 | 0.29 | 362.5
[22 empty] | Boom Truck 10T | Machinery | HR | 67.6923 | 4 | 16.9231 | 0.0725 | 4.9077
[22 empty] | Fuel | Material | HR | 1.76 | 0.33333 | 5.28 | 0.87 | 1.5312
[22 empty] | Chamber Pipes Pieces | Material | LS | 150 | 1 | 150 | 0.29 | 43.5
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.2 | 85 | 1.45 | 24.65
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.2 | 65 | 1.45 | 18.85
[9 empty] | 0.29 | 0.29 |  | 0.29 | [9 empty] | Internal and external Insulation |  | Ea | 1400 |  | 1400 | 0.29 | 406 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply & apply external waterproofing | SC | M² | 40 | 0.05 | 800 | 5.8 | 232
[22 empty] | Supply & apply internal coating | SC | M² | 30 | 0.05 | 600 | 5.8 | 174
[9 empty] | 0.29 | 0.29 |  | 0.29 | [9 empty] | Backfilling |  | Ea | 452.0658 |  | 452.0658 | 0.29 | 131.0991 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.038095 | 262.5 | 7.6125 | 76.125
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 3.8095 | 17.22 | 0.076125 | 4.9938
[22 empty] | Fuel | Material | LTR | 1.76 | 0.42328 | 4.158 | 0.68513 | 1.2058
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.77714 | 61.7647 | 0.37316 | 17.9118
[22 empty] | Fuel | Material | LTR | 1.76 | 0.077714 | 22.6471 | 3.7316 | 6.5676
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 1.9048 | 18.9 | 0.15225 | 5.481
[22 empty] | Fuel | Material | LTR | 1.76 | 0.21164 | 8.316 | 1.3703 | 2.4116
[22 empty] | Plate Compactor | Machinery | HR | 23 | 0.5 | 46 | 0.58 | 13.34
[22 empty] | Fuel | Material | LTR | 1.76 | 0.16667 | 10.56 | 1.74 | 3.0624
STR11 |  | Manhole on box pipes 1500x1500mm wide
STR11 |  | Manhole with a depth of 0.0-1.5 m | nr | 14.18 | 8854 | 125549.72 | 4519.8735 | 64091.8057 | 14.18 | 14.18 |  | 14.18 | 100% | 8854 | 125549.72 | 4519.8735 | 64091.8057 |  | 64091.8057 | [7 empty] | 4519.8735 | 14.18 | 64091.8057 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 14.18 | 14.18 |  | 14.18 | [9 empty] | Excavate & Disposal (3.0*3.0*1.5) |  | Ea | 54.2982 |  | 54.2982 | 14.18 | 769.948 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 7.4074 | 7.56 | 1.9143 | 107.2008
[22 empty] | Fuel | Material | LTR | 1.76 | 0.5291 | 3.3264 | 26.8002 | 47.1684
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 1.5111 | 31.7647 | 9.3838 | 450.4235
[22 empty] | Fuel | Material | LTR | 1.76 | 0.15111 | 11.6471 | 93.8382 | 165.1553
[9 empty] | 14.18 | 14.18 |  | 14.18 | [9 empty] | Concrete Manhole Installation |  | Ea | 3675.9531 |  | 3675.9531 | 14.18 | 52125.0146 | 0 | 0 | 0 | 0 | 0
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.40404 | 866.25 | 35.0955 | 12283.425
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 5.0505 | 495 | 2.8076 | 7019.1
[22 empty] | Trench RC Concrete workmanship | SC | M³ | 300 | 0.40404 | 742.5 | 35.0955 | 10528.65
[22 empty] | Concrete manhole Cover, frames | Material | Ea | 1250 | 1 | 1250 | 14.18 | 17725
[22 empty] | Boom Truck 10T | Machinery | HR | 67.6923 | 4 | 16.9231 | 3.545 | 239.9692
[22 empty] | Fuel | Material | HR | 1.76 | 0.33333 | 5.28 | 42.54 | 74.8704
[22 empty] | Chamber Pipes Pieces | Material | LS | 150 | 1 | 150 | 14.18 | 2127
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.2 | 85 | 70.9 | 1205.3
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.2 | 65 | 70.9 | 921.7
[9 empty] | 14.18 | 14.18 |  | 14.18 | [9 empty] | Internal and external Insulation |  | Ea | 630 |  | 630 | 14.18 | 8933.4 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply & apply external waterproofing | SC | M² | 40 | 0.11111 | 360 | 127.62 | 5104.8
[22 empty] | Supply & apply internal coating | SC | M² | 30 | 0.11111 | 270 | 127.62 | 3828.6
[9 empty] | 14.18 | 14.18 |  | 14.18 | [9 empty] | Backfilling |  | Ea | 159.6222 |  | 159.6222 | 14.18 | 2263.4431 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.098765 | 101.25 | 143.5725 | 1435.725
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 9.8765 | 6.642 | 1.4357 | 94.1836
[22 empty] | Fuel | Material | LTR | 1.76 | 1.0974 | 1.6038 | 12.9215 | 22.7419
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 2.0148 | 23.8235 | 7.0379 | 337.8176
[22 empty] | Fuel | Material | LTR | 1.76 | 0.20148 | 8.7353 | 70.3787 | 123.8665
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 4.9383 | 7.29 | 2.8714 | 103.3722
[22 empty] | Fuel | Material | LTR | 1.76 | 0.5487 | 3.2076 | 25.843 | 45.4838
[22 empty] | Plate Compactor | Machinery | HR | 23 | 4 | 5.75 | 3.545 | 81.535
[22 empty] | Fuel | Material | LTR | 1.76 | 1.3333 | 1.32 | 10.635 | 18.7176
STR11 |  | Manhole with a depth of 1.5-2.0 m | nr | 51.29 | 10722 | 549931.38 | 5308.8236 | 272289.5622 | 51.29 | 51.29 |  | 51.29 | 100% | 10722 | 549931.38 | 5308.8236 | 272289.5622 |  | 272289.5622 | [7 empty] | 5308.8236 | 51.29 | 272289.5622 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 51.29 | 51.29 |  | 51.29 | [9 empty] | Excavate & Disposal (3.0*3.0*2.0) |  | Ea | 72.3976 |  | 72.3976 | 51.29 | 3713.2705 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 5.5556 | 10.08 | 9.2322 | 517.0032
[22 empty] | Fuel | Material | LTR | 1.76 | 0.39683 | 4.4352 | 129.2508 | 227.4814
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 1.1333 | 42.3529 | 45.2559 | 2172.2824
[22 empty] | Fuel | Material | LTR | 1.76 | 0.11333 | 15.5294 | 452.5588 | 796.5035
[9 empty] | 51.29 | 51.29 |  | 51.29 | [9 empty] | Concrete Manhole Installation |  | Ea | 4185.9531 |  | 4185.9531 | 51.29 | 214697.5333 | 0 | 0 | 0 | 0 | 0
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.3252 | 1076.25 | 157.7168 | 55200.8625
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 4.065 | 615 | 12.6173 | 31543.35
[22 empty] | Trench RC Concrete workmanship | SC | M³ | 300 | 0.3252 | 922.5 | 157.7168 | 47315.025
[22 empty] | Concrete manhole Cover, frames | Material | Ea | 1250 | 1 | 1250 | 51.29 | 64112.5
[22 empty] | Boom Truck 10T | Machinery | HR | 67.6923 | 4 | 16.9231 | 12.8225 | 867.9846
[22 empty] | Fuel | Material | HR | 1.76 | 0.33333 | 5.28 | 153.87 | 270.8112
[22 empty] | Chamber Pipes Pieces | Material | LS | 150 | 1 | 150 | 51.29 | 7693.5
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.2 | 85 | 256.45 | 4359.65
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.2 | 65 | 256.45 | 3333.85
[9 empty] | 51.29 | 51.29 |  | 51.29 | [9 empty] | Internal and external Insulation |  | Ea | 840 |  | 840 | 51.29 | 43083.6 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply & apply external waterproofing | SC | M² | 40 | 0.083333 | 480 | 615.48 | 24619.2
[22 empty] | Supply & apply internal coating | SC | M² | 30 | 0.083333 | 360 | 615.48 | 18464.4
[9 empty] | 51.29 | 51.29 |  | 51.29 | [9 empty] | Backfilling |  | Ea | 210.473 |  | 210.473 | 51.29 | 10795.1584 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.074074 | 135 | 692.415 | 6924.15
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 7.4074 | 8.856 | 6.9242 | 454.2242
[22 empty] | Fuel | Material | LTR | 1.76 | 0.82305 | 2.1384 | 62.3174 | 109.6785
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 1.5111 | 31.7647 | 33.9419 | 1629.2118
[22 empty] | Fuel | Material | LTR | 1.76 | 0.15111 | 11.6471 | 339.4191 | 597.3776
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 3.7037 | 9.72 | 13.8483 | 498.5388
[22 empty] | Fuel | Material | LTR | 1.76 | 0.41152 | 4.2768 | 124.6347 | 219.3571
[22 empty] | Plate Compactor | Machinery | HR | 23 | 4 | 5.75 | 12.8225 | 294.9175
[22 empty] | Fuel | Material | LTR | 1.76 | 1.3333 | 1.32 | 38.4675 | 67.7028
STR11 |  | Manhole with a depth of 2.0-2.5 m | nr | 72.88 | 12611 | 919089.68 | 6100.1304 | 444577.5029 | 72.88 | 72.88 |  | 72.88 | 100% | 12611 | 919089.68 | 6100.1304 | 444577.5029 |  | 444577.5029 | [7 empty] | 6100.1304 | 72.88 | 444577.5029 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 72.88 | 72.88 |  | 72.88 | [9 empty] | Excavate & Disposal (3.0*3.0*2.5) |  | Ea | 90.4969 |  | 90.4969 | 72.88 | 6595.4171 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 4.4444 | 12.6 | 16.398 | 918.288
[22 empty] | Fuel | Material | LTR | 1.76 | 0.31746 | 5.544 | 229.572 | 404.0467
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.90667 | 52.9412 | 80.3824 | 3858.3529
[22 empty] | Fuel | Material | LTR | 1.76 | 0.090667 | 19.4118 | 803.8235 | 1414.7294
[9 empty] | 72.88 | 72.88 |  | 72.88 | [9 empty] | Concrete Manhole Installation |  | Ea | 4695.9531 |  | 4695.9531 | 72.88 | 342241.0602 | 0 | 0 | 0 | 0 | 0
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.27211 | 1286.25 | 267.834 | 93741.9
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 3.4014 | 735 | 21.4267 | 53566.8
[22 empty] | Trench RC Concrete workmanship | SC | M³ | 300 | 0.27211 | 1102.5 | 267.834 | 80350.2
[22 empty] | Concrete manhole Cover, frames | Material | Ea | 1250 | 1 | 1250 | 72.88 | 91100
[22 empty] | Boom Truck 10T | Machinery | HR | 67.6923 | 4 | 16.9231 | 18.22 | 1233.3538
[22 empty] | Fuel | Material | HR | 1.76 | 0.33333 | 5.28 | 218.64 | 384.8064
[22 empty] | Chamber Pipes Pieces | Material | LS | 150 | 1 | 150 | 72.88 | 10932
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.2 | 85 | 364.4 | 6194.8
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.2 | 65 | 364.4 | 4737.2
[9 empty] | 72.88 | 72.88 |  | 72.88 | [9 empty] | Internal and external Insulation |  | Ea | 1050 |  | 1050 | 72.88 | 76524 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply & apply external waterproofing | SC | M² | 40 | 0.066667 | 600 | 1093.2 | 43728
[22 empty] | Supply & apply internal coating | SC | M² | 30 | 0.066667 | 450 | 1093.2 | 32796
[9 empty] | 72.88 | 72.88 |  | 72.88 | [9 empty] | Backfilling |  | Ea | 263.6804 |  | 263.6804 | 72.88 | 19217.0256 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.059259 | 168.75 | 1229.85 | 12298.5
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 5.9259 | 11.07 | 12.2985 | 806.7816
[22 empty] | Fuel | Material | LTR | 1.76 | 0.65844 | 2.673 | 110.6865 | 194.8082
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 1.2089 | 39.7059 | 60.2868 | 2893.7647
[22 empty] | Fuel | Material | LTR | 1.76 | 0.12089 | 14.5588 | 602.8676 | 1061.0471
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 2.963 | 12.15 | 24.597 | 885.492
[22 empty] | Fuel | Material | LTR | 1.76 | 0.32922 | 5.346 | 221.373 | 389.6165
[22 empty] | Plate Compactor | Machinery | HR | 23 | 3 | 7.6667 | 24.2933 | 558.7467
[22 empty] | Fuel | Material | LTR | 1.76 | 1 | 1.76 | 72.88 | 128.2688
STR11 |  | Manhole with a depth of 2.5-3.0 m | nr | 60.61 | 14502 | 878966.22 | 6889.0805 | 417547.1703 | 60.61 | 60.61 |  | 60.61 | 100% | 14502 | 878966.22 | 6889.0805 | 417547.1703 |  | 417547.1703 | [7 empty] | 6889.0805 | 60.61 | 417547.1703 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 60.61 | 60.61 |  | 60.61 | [9 empty] | Excavate & Disposal (3.0*3.0*3.0) |  | Ea | 108.5963 |  | 108.5963 | 60.61 | 6582.0235 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 3.7037 | 15.12 | 16.3647 | 916.4232
[22 empty] | Fuel | Material | LTR | 1.76 | 0.26455 | 6.6528 | 229.1058 | 403.2262
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.75556 | 63.5294 | 80.2191 | 3850.5176
[22 empty] | Fuel | Material | LTR | 1.76 | 0.075556 | 23.2941 | 802.1912 | 1411.8565
[9 empty] | 60.61 | 60.61 |  | 60.61 | [9 empty] | Concrete Manhole Installation |  | Ea | 5205.9531 |  | 5205.9531 | 60.61 | 315532.816 | 0 | 0 | 0 | 0 | 0
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.23392 | 1496.25 | 259.1078 | 90687.7125
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 2.924 | 855 | 20.7286 | 51821.55
[22 empty] | Trench RC Concrete workmanship | SC | M³ | 300 | 0.23392 | 1282.5 | 259.1078 | 77732.325
[22 empty] | Concrete manhole Cover, frames | Material | Ea | 1250 | 1 | 1250 | 60.61 | 75762.5
[22 empty] | Boom Truck 10T | Machinery | HR | 67.6923 | 4 | 16.9231 | 15.1525 | 1025.7077
[22 empty] | Fuel | Material | HR | 1.76 | 0.33333 | 5.28 | 181.83 | 320.0208
[22 empty] | Chamber Pipes Pieces | Material | LS | 150 | 1 | 150 | 60.61 | 9091.5
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.2 | 85 | 303.05 | 5151.85
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.2 | 65 | 303.05 | 3939.65
[9 empty] | 60.61 | 60.61 |  | 60.61 | [9 empty] | Internal and external Insulation |  | Ea | 1260 |  | 1260 | 60.61 | 76368.6 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply & apply external waterproofing | SC | M² | 40 | 0.055556 | 720 | 1090.98 | 43639.2
[22 empty] | Supply & apply internal coating | SC | M² | 30 | 0.055556 | 540 | 1090.98 | 32729.4
[9 empty] | 60.61 | 60.61 |  | 60.61 | [9 empty] | Backfilling |  | Ea | 314.5311 |  | 314.5311 | 60.61 | 19063.7308 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.049383 | 202.5 | 1227.3525 | 12273.525
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 4.9383 | 13.284 | 12.2735 | 805.1432
[22 empty] | Fuel | Material | LTR | 1.76 | 0.5487 | 3.2076 | 110.4617 | 194.4126
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 1.0074 | 47.6471 | 60.1643 | 2887.8882
[22 empty] | Fuel | Material | LTR | 1.76 | 0.10074 | 17.4706 | 601.6434 | 1058.8924
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 2.4691 | 14.58 | 24.5471 | 883.6938
[22 empty] | Fuel | Material | LTR | 1.76 | 0.27435 | 6.4152 | 220.9235 | 388.8253
[22 empty] | Plate Compactor | Machinery | HR | 23 | 3 | 7.6667 | 20.2033 | 464.6767
[22 empty] | Fuel | Material | LTR | 1.76 | 1 | 1.76 | 60.61 | 106.6736
STR11 |  | Manhole with a depth of 3.0-3.5 m | nr | 20.8 | 16391 | 340932.8 | 7682.744 | 159801.0748 | 20.8 | 20.8 |  | 20.8 | 100% | 16391 | 340932.8 | 7682.744 | 159801.0748 |  | 159801.0748 | [7 empty] | 7682.744 | 20.8 | 159801.0748 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 20.8 | 20.8 |  | 20.8 | [9 empty] | Excavate & Disposal (3.0*3.0*3.5) |  | Ea | 126.6957 |  | 126.6957 | 20.8 | 2635.2709 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 3.1746 | 17.64 | 6.552 | 366.912
[22 empty] | Fuel | Material | LTR | 1.76 | 0.22676 | 7.7616 | 91.728 | 161.4413
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.64762 | 74.1176 | 32.1176 | 1541.6471
[22 empty] | Fuel | Material | LTR | 1.76 | 0.064762 | 27.1765 | 321.1765 | 565.2706
[9 empty] | 20.8 | 20.8 |  | 20.8 | [9 empty] | Concrete Manhole Installation |  | Ea | 5715.9531 |  | 5715.9531 | 20.8 | 118891.824 | 0 | 0 | 0 | 0 | 0
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.20513 | 1706.25 | 101.4 | 35490
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 2.5641 | 975 | 8.112 | 20280
[22 empty] | Trench RC Concrete workmanship | SC | M³ | 300 | 0.20513 | 1462.5 | 101.4 | 30420
[22 empty] | Concrete manhole Cover, frames | Material | Ea | 1250 | 1 | 1250 | 20.8 | 26000
[22 empty] | Boom Truck 10T | Machinery | HR | 67.6923 | 4 | 16.9231 | 5.2 | 352
[22 empty] | Fuel | Material | HR | 1.76 | 0.33333 | 5.28 | 62.4 | 109.824
[22 empty] | Chamber Pipes Pieces | Material | LS | 150 | 1 | 150 | 20.8 | 3120
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.2 | 85 | 104 | 1768
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.2 | 65 | 104 | 1352
[9 empty] | 20.8 | 20.8 |  | 20.8 | [9 empty] | Internal and external Insulation |  | Ea | 1470 |  | 1470 | 20.8 | 30576 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply & apply external waterproofing | SC | M² | 40 | 0.047619 | 840 | 436.8 | 17472
[22 empty] | Supply & apply internal coating | SC | M² | 30 | 0.047619 | 630 | 436.8 | 13104
[9 empty] | 20.8 | 20.8 |  | 20.8 | [9 empty] | Backfilling |  | Ea | 370.0952 |  | 370.0952 | 20.8 | 7697.9799 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.042328 | 236.25 | 491.4 | 4914
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 4.2328 | 15.498 | 4.914 | 322.3584
[22 empty] | Fuel | Material | LTR | 1.76 | 0.47031 | 3.7422 | 44.226 | 77.8378
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.86349 | 55.5882 | 24.0882 | 1156.2353
[22 empty] | Fuel | Material | LTR | 1.76 | 0.086349 | 20.3824 | 240.8824 | 423.9529
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 2.1164 | 17.01 | 9.828 | 353.808
[22 empty] | Fuel | Material | LTR | 1.76 | 0.23516 | 7.4844 | 88.452 | 155.6755
[22 empty] | Plate Compactor | Machinery | HR | 23 | 2 | 11.5 | 10.4 | 239.2
[22 empty] | Fuel | Material | LTR | 1.76 | 0.66667 | 2.64 | 31.2 | 54.912
STR11 |  | Manhole with a depth of 3.5-4.0 m | nr | 4.95 | 18282 | 90495.9 | 8485.8341 | 42004.8789 | 4.95 | 4.95 |  | 4.95 | 100% | 18282 | 90495.9 | 8485.8341 | 42004.8789 |  | 42004.8789 | [7 empty] | 8485.8341 | 4.95 | 42004.8789 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 4.95 | 4.95 |  | 4.95 | [9 empty] | Excavate & Disposal (3.0*3.0*4.0) |  | Ea | 144.7951 |  | 144.7951 | 4.95 | 716.7358 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 2.7778 | 20.16 | 1.782 | 99.792
[22 empty] | Fuel | Material | LTR | 1.76 | 0.19841 | 8.8704 | 24.948 | 43.9085
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.56667 | 84.7059 | 8.7353 | 419.2941
[22 empty] | Fuel | Material | LTR | 1.76 | 0.056667 | 31.0588 | 87.3529 | 153.7412
[9 empty] | 4.95 | 4.95 |  | 4.95 | [9 empty] | Concrete Manhole Installation |  | Ea | 6225.9531 |  | 6225.9531 | 4.95 | 30818.4677 | 0 | 0 | 0 | 0 | 0
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.18265 | 1916.25 | 27.1012 | 9485.4375
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 2.2831 | 1095 | 2.1681 | 5420.25
[22 empty] | Trench RC Concrete workmanship | SC | M³ | 300 | 0.18265 | 1642.5 | 27.1012 | 8130.375
[22 empty] | Concrete manhole Cover, frames | Material | Ea | 1250 | 1 | 1250 | 4.95 | 6187.5
[22 empty] | Boom Truck 10T | Machinery | HR | 67.6923 | 4 | 16.9231 | 1.2375 | 83.7692
[22 empty] | Fuel | Material | HR | 1.76 | 0.33333 | 5.28 | 14.85 | 26.136
[22 empty] | Chamber Pipes Pieces | Material | LS | 150 | 1 | 150 | 4.95 | 742.5
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.2 | 85 | 24.75 | 420.75
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.2 | 65 | 24.75 | 321.75
[9 empty] | 4.95 | 4.95 |  | 4.95 | [9 empty] | Internal and external Insulation |  | Ea | 1680 |  | 1680 | 4.95 | 8316 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply & apply external waterproofing | SC | M² | 40 | 0.041667 | 960 | 118.8 | 4752
[22 empty] | Supply & apply internal coating | SC | M² | 30 | 0.041667 | 720 | 118.8 | 3564
[9 empty] | 4.95 | 4.95 |  | 4.95 | [9 empty] | Backfilling |  | Ea | 435.0859 |  | 435.0859 | 4.95 | 2153.6754 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.037037 | 270 | 133.65 | 1336.5
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 3.7037 | 17.712 | 1.3365 | 87.6744
[22 empty] | Fuel | Material | LTR | 1.76 | 0.41152 | 4.2768 | 12.0285 | 21.1702
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.75556 | 63.5294 | 6.5515 | 314.4706
[22 empty] | Fuel | Material | LTR | 1.76 | 0.075556 | 23.2941 | 65.5147 | 115.3059
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 1.8519 | 19.44 | 2.673 | 96.228
[22 empty] | Fuel | Material | LTR | 1.76 | 0.20576 | 8.5536 | 24.057 | 42.3403
[22 empty] | Plate Compactor | Machinery | HR | 23 | 1 | 23 | 4.95 | 113.85
[22 empty] | Fuel | Material | LTR | 1.76 | 0.33333 | 5.28 | 14.85 | 26.136
STR11 |  | Manhole with a depth of more than -4.0 m | nr |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Concrete rooms
STR11 |  | Creating concrete chambers on all pipes of various diameters, including excavation, backfilling, compaction, waste removal, dewatering, cleaning concrete, reinforced concrete bases, walls, reinforcement, slabs, formwork, construction work, waterproofing, entrance covers and frames, safety rings, and dividers, in accordance with the requirements of the concerned authority, plans, and specifications.
STR11 |  | (Gully outfalls) Water drainage outfalls from collection basins | nr | 245.375 | 5980 | 1467342.6497 | 3962.7515 | 972360.239 | 245.375 | 245.375 |  | 245.375 | 100% | 5980 | 1467342.6497 | 3962.7515 | 972360.239 |  | 972360.239 | [7 empty] | 3962.7515 | 245.375 | 972360.239 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 245.375 | 245.375 |  | 245.375 | [9 empty] | Excavate & Disposal (2.5*2.5*2.0) |  | Ea | 50.2761 |  | 50.2761 | 245.375 | 12336.494 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 8 | 7 | 30.6719 | 1717.6252
[22 empty] | Fuel | Material | LTR | 1.76 | 0.57143 | 3.08 | 429.4063 | 755.7551
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 1.632 | 29.4118 | 150.3523 | 7216.9125
[22 empty] | Fuel | Material | LTR | 1.76 | 0.1632 | 10.7843 | 1503.5234 | 2646.2013
[9 empty] | 245.375 | 245.375 |  | 245.375 | [9 empty] | Chamber Installation |  | Ea | 3187.2031 |  | 3187.2031 | 245.375 | 782060.0348 | 0 | 0 | 0 | 0 | 0
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.52632 | 665 | 466.2125 | 163174.3917
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 6.5789 | 380 | 37.297 | 93242.5095
[22 empty] | Trench RC Concrete workmanship | SC | M³ | 300 | 0.52632 | 570 | 466.2125 | 139863.7643
[22 empty] | Concrete manhole Cover, frames | Material | Ea | 1250 | 1 | 1250 | 245.375 | 306718.7813
[22 empty] | Boom Truck 10T | Machinery | HR | 67.6923 | 4 | 16.9231 | 61.3438 | 4152.5004
[22 empty] | Fuel | Material | HR | 1.76 | 0.33333 | 5.28 | 736.1251 | 1295.5801
[22 empty] | Chamber Pipes Pieces | Material | LS | 150 | 1 | 150 | 245.375 | 36806.2538
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.2 | 85 | 1226.8751 | 20856.8771
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.2 | 65 | 1226.8751 | 15949.3766
[9 empty] | 245.375 | 245.375 |  | 245.375 | [9 empty] | Internal and external Insulation |  | Ea | 560 |  | 560 | 245.375 | 137410.014 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply & apply external waterproofing | SC | M² | 40 | 0.125 | 320 | 1963.0002 | 78520.008
[22 empty] | Supply & apply internal coating | SC | M² | 30 | 0.125 | 240 | 1963.0002 | 58890.006
[9 empty] | 245.375 | 245.375 |  | 245.375 | [9 empty] | Backfilling |  | Ea | 165.2723 |  | 165.2723 | 245.375 | 40553.6962 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.095238 | 105 | 2576.4378 | 25764.3776
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 9.5238 | 6.888 | 25.7644 | 1690.1432
[22 empty] | Fuel | Material | LTR | 1.76 | 1.0582 | 1.6632 | 231.8794 | 408.1077
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 1.9429 | 24.7059 | 126.296 | 6062.2065
[22 empty] | Fuel | Material | LTR | 1.76 | 0.19429 | 9.0588 | 1262.9597 | 2222.8091
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 4.7619 | 7.56 | 51.5288 | 1855.0352
[22 empty] | Fuel | Material | LTR | 1.76 | 0.5291 | 3.3264 | 463.7588 | 816.2155
[22 empty] | Plate Compactor | Machinery | HR | 23 | 4 | 5.75 | 61.3438 | 1410.9064
[22 empty] | Fuel | Material | LTR | 1.76 | 1.3333 | 1.32 | 184.0313 | 323.895
STR11 |  | Catch Basins | nr | 104.23 | 20504 | 2137131.92 | 12376.1937 | 1289970.6672 | 104.23 | 104.23 |  | 104.23 | 100% | 20504 | 2137131.92 | 12376.1937 | 1289970.6672 |  | 1289970.6672 | [7 empty] | 12376.1937 | 104.23 | 1289970.6672 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 104.23 | 104.23 |  | 104.23 | [9 empty] | Excavate & Disposal (4.5*3.4*2.0) |  | Ea | 123.0758 |  | 123.0758 | 104.23 | 12828.1948 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 3.268 | 17.136 | 31.8944 | 1786.0853
[22 empty] | Fuel | Material | LTR | 1.76 | 0.23343 | 7.5398 | 446.5213 | 785.8775
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.66667 | 72 | 156.345 | 7504.56
[22 empty] | Fuel | Material | LTR | 1.76 | 0.066667 | 26.4 | 1563.45 | 2751.672
[9 empty] | 104.23 | 104.23 |  | 104.23 | [9 empty] | Chamber Installation (3.3*2.2) |  | Ea | 10442.5623 |  | 10442.5623 | 104.23 | 1088428.2693 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 1.1905 | 210 | 87.5532 | 21888.3
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.13671 | 2560.25 | 762.4425 | 266854.8575
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 1.7088 | 1463 | 60.9954 | 152488.49
[22 empty] | Workmanship plain concrete | SC | M³ | 150 | 1.1905 | 126 | 87.5532 | 13132.98
[22 empty] | Trench RC Concrete workmanship | SC | M³ | 300 | 0.13671 | 2194.5 | 762.4425 | 228732.735
[22 empty] | Supply & apply Chamber Cover, frames | Material | Ea | 3500 | 1 | 3500 | 104.23 | 364805
[22 empty] | Boom Truck 10T | Machinery | HR | 67.6923 | 1 | 67.6923 | 104.23 | 7055.5692
[22 empty] | Fuel | Material | HR | 1.76 | 0.083333 | 21.12 | 1250.76 | 2201.3376
[22 empty] | Chamber Pipes Pieces | Material | LS | 150 | 1 | 150 | 104.23 | 15634.5
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.2 | 85 | 521.15 | 8859.55
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.2 | 65 | 521.15 | 6774.95
[9 empty] | 104.23 | 104.23 |  | 104.23 | [9 empty] | Internal and external Insulation |  | Ea | 1540 |  | 1540 | 104.23 | 160514.2 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply & apply external waterproofing | SC | M² | 40 | 0.045455 | 880 | 2293.06 | 91722.4
[22 empty] | Supply & apply internal coating | SC | M² | 30 | 0.045455 | 660 | 2293.06 | 68791.8
[9 empty] | 104.23 | 104.23 |  | 104.23 | [9 empty] | Backfilling |  | Ea | 270.5555 |  | 270.5555 | 104.23 | 28200.003 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.062189 | 160.8 | 1676.0184 | 16760.184
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 6.2189 | 10.5485 | 16.7602 | 1099.4681
[22 empty] | Fuel | Material | LTR | 1.76 | 0.69099 | 2.5471 | 150.8417 | 265.4813
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 1.2687 | 37.8353 | 82.1578 | 3943.5727
[22 empty] | Fuel | Material | LTR | 1.76 | 0.12687 | 13.8729 | 821.5776 | 1445.9767
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 3.1095 | 11.5776 | 33.5204 | 1206.7332
[22 empty] | Fuel | Material | LTR | 1.76 | 0.34549 | 5.0941 | 301.6833 | 530.9626
[22 empty] | Plate Compactor | Machinery | HR | 23 | 1 | 23 | 104.23 | 2397.29
[22 empty] | Fuel | Material | LTR | 1.76 | 0.33333 | 5.28 | 312.69 | 550.3344
STR11 |  | (Gully outfalls) Water drainage outfalls from collection basins |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
STR11 |  | Construction of outfalls to drain rainwater from collection basins, including protection, stone cladding (Riprap), all other bases, and edge and edge finishes in accordance with the advice of the landscaping engineer. It also includes slopes, earthworks, concrete works, construction works, connections, etc. According to the requirements of the concerned authority, plans and specifications |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
STR11 |  | (Gully outfalls to swales) Drainage outfalls to surface channels | nr | 307.05 | 4721 | 1449583.05 | 3017.016 | 926374.7777 | 307.05 | 307.05 |  | 307.05 | 100% | 4721 | 1449583.05 | 3017.016 | 926374.7777 |  | 926374.7777 | [7 empty] | 3017.016 | 307.05 | 926374.7777 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 307.05 | 307.05 |  | 307.05 | [9 empty] | Excavate & Disposal (2.2*2.2*1.0) |  | Ea | 19.4669 |  | 19.4669 | 307.05 | 5977.3109 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 20.6612 | 2.7104 | 14.8612 | 832.2283
[22 empty] | Fuel | Material | LTR | 1.76 | 1.4758 | 1.1926 | 208.0571 | 366.1805
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 4.2149 | 11.3882 | 72.8491 | 3496.7576
[22 empty] | Fuel | Material | LTR | 1.76 | 0.42149 | 4.1757 | 728.4912 | 1282.1445
[9 empty] | 307.05 | 307.05 |  | 307.05 | [9 empty] | Chamber Installation (1.0*1.0) |  | Ea | 2631.4123 |  | 2631.4123 | 307.05 | 807975.1491 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 6.9444 | 36 | 44.2152 | 11053.8
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.90909 | 385 | 337.755 | 118214.25
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 11.3636 | 220 | 27.0204 | 67551
[22 empty] | Workmanship plain concrete | SC | M³ | 150 | 6.9444 | 21.6 | 44.2152 | 6632.28
[22 empty] | Trench RC Concrete workmanship | SC | M³ | 300 | 0.90909 | 330 | 337.755 | 101326.5
[22 empty] | Concrete manhole Cover, frames | Material | Ea | 1250 | 1 | 1250 | 307.05 | 383812.5
[22 empty] | Boom Truck 10T | Machinery | HR | 67.6923 | 1 | 67.6923 | 307.05 | 20784.9231
[22 empty] | Fuel | Material | HR | 1.76 | 0.083333 | 21.12 | 3684.6 | 6484.896
[22 empty] | Chamber Pipes Pieces | Material | LS | 150 | 1 | 150 | 307.05 | 46057.5
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.2 | 85 | 1535.25 | 26099.25
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.2 | 65 | 1535.25 | 19958.25
[9 empty] | 307.05 | 307.05 |  | 307.05 | [9 empty] | Internal and external Insulation |  | Ea | 280 |  | 280 | 307.05 | 85974 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply & apply external waterproofing | SC | M² | 40 | 0.25 | 160 | 1228.2 | 49128
[22 empty] | Supply & apply internal coating | SC | M² | 30 | 0.25 | 120 | 1228.2 | 36846
[9 empty] | 307.05 | 307.05 |  | 307.05 | [9 empty] | Backfilling |  | Ea | 86.1368 |  | 86.1368 | 307.05 | 26448.3177 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.26042 | 38.4 | 1179.072 | 11790.72
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 26.0417 | 2.519 | 11.7907 | 773.4712
[22 empty] | Fuel | Material | LTR | 1.76 | 2.8935 | 0.60826 | 106.1165 | 186.765
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 5.3125 | 9.0353 | 57.7976 | 2774.2871
[22 empty] | Fuel | Material | LTR | 1.76 | 0.53125 | 3.3129 | 577.9765 | 1017.2386
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 13.0208 | 2.7648 | 23.5814 | 848.9318
[22 empty] | Fuel | Material | LTR | 1.76 | 1.4468 | 1.2165 | 212.233 | 373.53
[22 empty] | Plate Compactor | Machinery | HR | 23 | 1 | 23 | 307.05 | 7062.15
[22 empty] | Fuel | Material | LTR | 1.76 | 0.33333 | 5.28 | 921.15 | 1621.224
STR11 |  | Ref.Drg. DAM3-01-001-CH2-TS8-1-STR-DRW 0300-Rev A01 (Curbs measured seperately) |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
STR11 |  | Outfalls from low brooders to drainage chambers/surface canals. (Bardware is measured in a separate item) | nr |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
STR11 |  | Precast chambers for absorption pits equipped with a cast-in-place base, including earthworks, protection works, cover, frame, connections, and connection pipe, completely complete in all respects, as shown in plan No. (DAM3-01-001-CH2-TS8-1-STR-DRW-0301) | nr | 70.8 | 19456 | 1377484.8 | 13368.3086 | 946476.2455 | 70.8 | 70.8 |  | 70.8 | 100% | 19456 | 1377484.8 | 13368.3086 | 946476.2455 |  | 946476.2455 | [7 empty] | 13368.3086 | 70.8 | 946476.2455 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 70.8 | 70.8 |  | 70.8 | [9 empty] | Excavate & Disposal (3.5*3.5*3.0) |  | Ea | 147.8117 |  | 147.8117 | 70.8 | 10465.0663 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 2.7211 | 20.58 | 26.019 | 1457.064
[22 empty] | Fuel | Material | LTR | 1.76 | 0.19436 | 9.0552 | 364.266 | 641.1082
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.5551 | 86.4706 | 127.5441 | 6122.1176
[22 empty] | Fuel | Material | LTR | 1.76 | 0.05551 | 31.7059 | 1275.4412 | 2244.7765
[9 empty] | 70.8 | 70.8 |  | 70.8 | [9 empty] | Chamber Installation (2.2*2.2*3) |  | Ea | 10981 |  | 10981 | 70.8 | 777454.8 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 1.7361 | 144 | 40.7808 | 10195.2
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.12419 | 2818.2 | 570.0816 | 199528.56
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 1.5524 | 1610.4 | 45.6065 | 114016.32
[22 empty] | Workmanship plain concrete | SC | M³ | 150 | 1.7361 | 86.4 | 40.7808 | 6117.12
[22 empty] | Trench RC Concrete workmanship | SC | M³ | 300 | 0.12419 | 2415.6 | 570.0816 | 171024.48
[22 empty] | Supply & apply Chamber Cover, frames | Material | Ea | 3500 | 1 | 3500 | 70.8 | 247800
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 1 | 80 | 70.8 | 5664
[22 empty] | Fuel | Material | HR | 1.76 | 0.066667 | 26.4 | 1062 | 1869.12
[22 empty] | Chamber Pipes Pieces | Material | LS | 150 | 1 | 150 | 70.8 | 10620
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.2 | 85 | 354 | 6018
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.2 | 65 | 354 | 4602
[9 empty] | 70.8 | 70.8 |  | 70.8 | [9 empty] | Internal and external Insulation |  | Ea | 1848 |  | 1848 | 70.8 | 130838.4 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply & apply external waterproofing | SC | M² | 40 | 0.037879 | 1056 | 1869.12 | 74764.8
[22 empty] | Supply & apply internal coating | SC | M² | 30 | 0.037879 | 792 | 1869.12 | 56073.6
[9 empty] | 70.8 | 70.8 |  | 70.8 | [9 empty] | Backfilling |  | Ea | 391.4969 |  | 391.4969 | 70.8 | 27717.9792 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.044984 | 222.3 | 1573.884 | 15738.84
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 4.4984 | 14.5829 | 15.7388 | 1032.4679
[22 empty] | Fuel | Material | LTR | 1.76 | 0.49983 | 3.5212 | 141.6496 | 249.3032
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.91768 | 52.3059 | 77.1512 | 3703.2565
[22 empty] | Fuel | Material | LTR | 1.76 | 0.091768 | 19.1788 | 771.5118 | 1357.8607
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 2.2492 | 16.0056 | 31.4777 | 1133.1965
[22 empty] | Fuel | Material | LTR | 1.76 | 0.24991 | 7.0425 | 283.2991 | 498.6065
[22 empty] | Plate Compactor | Machinery | HR | 23 | 0.5 | 46 | 141.6 | 3256.8
[22 empty] | Fuel | Material | LTR | 1.76 | 0.16667 | 10.56 | 424.8 | 747.648
STR11 |  | Backfill materials under and around pipes - Type (A) |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
STR11 |  | Granular bedding material or powdered gravel is well compacted under and around the pipe and at different depths in accordance with the plans, specifications and requirements of the concerned authority. |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
STR11 |  | Pipes with a diameter not exceeding 200 mm | m |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Pipes diameter from 201-300 mm | m | 5810.001 | 116 | 673960.116 | 63.5902 | 369459.0491 | 5810.001 | 5810.001 |  | 5810.001 | 100% | 116 | 673960.116 | 63.5902 | 369459.0491 |  | 369459.0491 | [7 empty] | 63.5902 | 5810.001 | 369459.0491 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 5810.001 | 5810.001 |  | 5810.001 | [9 empty] | Granular Material (W=1.0) |  | M | 63.5902 |  | 63.5902 | 5810.001 | 369459.0491 | 0 | 0 | 0 | 0 | 0
[22 empty] | Granular bedding backfilling material | Material | M³ | 70 | 1.2058 | 58.0545 | 4818.5243 | 337296.7031
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 120.5764 | 0.54405 | 48.1852 | 3160.952
[22 empty] | Fuel | Material | LTR | 1.76 | 13.3974 | 0.13137 | 433.6672 | 763.2543
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 16.3984 | 2.9271 | 354.3033 | 17006.5565
[22 empty] | Fuel | Material | LTR | 1.76 | 1.6398 | 1.0733 | 3543.0326 | 6235.7374
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 60.2882 | 0.59713 | 96.3705 | 3469.3375
[22 empty] | Fuel | Material | LTR | 1.76 | 6.6987 | 0.26274 | 867.3344 | 1526.5085
STR11 |  | Pipes diameter from 301-400 mm | m | 65.346 | 156 | 10193.976 | 82.3793 | 5383.1597 | 65.346 | 65.346 |  | 65.346 | 100% | 156 | 10193.976 | 82.3793 | 5383.1597 |  | 5383.1597 | [7 empty] | 82.3793 | 65.346 | 5383.1597 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 65.346 | 65.346 |  | 65.346 | [9 empty] | Granular Material (W=1.2) |  | M | 82.3793 |  | 82.3793 | 65.346 | 5383.1597 | 0 | 0 | 0 | 0 | 0
[22 empty] | Granular bedding backfilling material | Material | M³ | 70 | 0.93075 | 75.208 | 70.2077 | 4914.542
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 93.0752 | 0.70481 | 0.70208 | 46.0563
[22 empty] | Fuel | Material | LTR | 1.76 | 10.3417 | 0.17018 | 6.3187 | 11.1209
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 12.6582 | 3.792 | 5.1623 | 247.792
[22 empty] | Fuel | Material | LTR | 1.76 | 1.2658 | 1.3904 | 51.6233 | 90.8571
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 46.5376 | 0.77357 | 1.4042 | 50.5496
[22 empty] | Fuel | Material | LTR | 1.76 | 5.1708 | 0.34037 | 12.6374 | 22.2418
STR11 |  | Pipes diameter from 301-400 mm |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Pipes diameter from 401-500 mm | m | 86.001 | 187 | 16082.187 | 111.4659 | 9586.1778 | 86.001 | 86.001 |  | 86.001 | 100% | 187 | 16082.187 | 111.4659 | 9586.1778 |  | 9586.1778 | [7 empty] | 111.4659 | 86.001 | 9586.1778 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 86.001 | 86.001 |  | 86.001 | [9 empty] | Granular Material (W=1.5) |  | M | 111.4659 |  | 111.4659 | 86.001 | 9586.1778 | 0 | 0 | 0 | 0 | 0
[22 empty] | Granular bedding backfilling material | Material | M³ | 70 | 0.68788 | 101.7625 | 125.024 | 8751.6768
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 68.7876 | 0.95366 | 1.2502 | 82.0157
[22 empty] | Fuel | Material | LTR | 1.76 | 7.6431 | 0.23027 | 11.2522 | 19.8038
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 9.3551 | 5.1309 | 9.1929 | 441.261
[22 empty] | Fuel | Material | LTR | 1.76 | 0.93551 | 1.8813 | 91.9294 | 161.7957
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 34.3938 | 1.0467 | 2.5005 | 90.0172
[22 empty] | Fuel | Material | LTR | 1.76 | 3.8215 | 0.46055 | 22.5043 | 39.6076
STR11 |  | Pipes diameter from 501-600 mm | m |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Pipes diameter from 601-700 mm | m | 30.5 | 248 | 7564 | 139.9582 | 4268.7256 | 30.5 | 30.5 |  | 30.5 | 100% | 248 | 7564 | 139.9582 | 4268.7256 |  | 4268.7256 | [7 empty] | 139.9582 | 30.5 | 4268.7256 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 30.5 | 30.5 |  | 30.5 | [9 empty] | Granular Material (W=1.7) |  | M | 139.9582 |  | 139.9582 | 30.5 | 4268.7256 | 0 | 0 | 0 | 0 | 0
[22 empty] | Granular bedding backfilling material | Material | M³ | 70 | 0.54784 | 127.7745 | 55.6732 | 3897.1222
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 54.784 | 1.1974 | 0.55673 | 36.5216
[22 empty] | Fuel | Material | LTR | 1.76 | 6.0871 | 0.28914 | 5.0106 | 8.8186
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 7.4506 | 6.4424 | 4.0936 | 196.4936
[22 empty] | Fuel | Material | LTR | 1.76 | 0.74506 | 2.3622 | 40.9362 | 72.0476
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 27.392 | 1.3143 | 1.1135 | 40.0847
[22 empty] | Fuel | Material | LTR | 1.76 | 3.0436 | 0.57827 | 10.0212 | 17.6373
STR11 |  | Pipes diameter from 701-800 mm | m |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Backfill materials under and around pipes - Type (B) |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Concrete blocks under and around pipes in accordance with the procedures of the competent authorities, specifications and plans |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Pipes diameter from 201-300 mm | m |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Pipes diameter from 301-400 mm | m |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Pipes diameter from 401-500 mm | m |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Pipes diameter from 501-600 mm | m |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Pipes diameter from 601-700 mm | m |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Pipes diameter from 701-800 mm | m |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Extra work |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Additional excavation and backfilling works, drilling into rock | m³ |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Firewall gateways |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Excavations from materials other than topsoil, rock, or artificial solids |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Maximum depth 1 meter |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Maximum depth from 1 - 2 meters | m³ |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Maximum depth from 2 - 5 meters | m³ |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | The maximum depth is 5 - 10 metres | m³ |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Drilling accessories Preparing the surfaces of the base layer to be excavated to begin permanent works |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Excavations from materials other than topsoil, rock, or artificial solids | m³ |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Transporting surplus excavations to an approved location | m³ |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Backfills |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Backfilling using materials selected from the excavation product other than topsoil or rock. | m³ |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Backfilling with materials supplied from outside the city | m³ |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Concrete works on site Concrete supply Scheme No. (DAM3-01-001-CH2-TS8-1-STR-DRW-0358 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Concrete type (C15), OP cement, in hygiene concrete | m³ |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Concrete type (C20), OP cement, in construction | m³ |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Pouring concrete block |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | So that the thickness of the blinding concrete does not exceed 100 mm | m³ |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Armament The base slab is 300 - 500 mm thick | m³ |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Base slab with thickness exceeding 500 mm | m³ |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Floor slab (at ground level) 150 - 300 mm thick | m³ |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Floor slab (at ground level) 500mm thick | m³ |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Suspended slab with a thickness of 150 - 300 mm | m³ |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Wall below the ground floor with a thickness of 150 - 300 mm | m³ |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | A wall below the ground floor with a thickness of 300 - 500 mm | m³ |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | A wall below the ground floor with a thickness exceeding 500 mm | m³ |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Parapet wall / wing wall with a thickness of 300 - 500 mm | m³ |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Concrete accessories Rough brickwork finishes |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | The vertical level is 0.2 - 0.4 m wide | m² |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | The vertical level is 0.4 - 1.22 m wide | m² |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Vertical level with a width exceeding 1.22 metres | m² |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Horizontal plane with a width exceeding 1.22 metres | m² |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | The incline level is 0.4 - 1.22 meters wide | m² |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Finishes of the upper surface layers |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Power floating finishes | m² |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Reinforced and adjustable steel bars BS EN 10080 BS4449 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | 8 mm in diameter | t |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | 10 mm in diameter | t |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | 12 mm in diameter | t |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | 16 mm in diameter | t |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | 20 mm in diameter | t |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | 25 mm in diameter | t |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Waterproof insulation |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Lining of tanks (sinks). | m² |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Inlet Shaft |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Excavations from materials other than surface soil, rock, or artificial solid materials |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Concrete type (C40), OP cement, in construction | m³ |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Scheme No.:DAM3-01-001-CH2-TS8-1-STR-DRW-0358 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | He poured his kharsa nih |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Commodification |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Plates are hung with a thickness of 150-300 mm | m³ |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | The wall below the ground floor is 150-300 mm thick | m³ |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Concrete accessories |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Rough brickwork finishes |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | The vertical plane is 0.2-0.4 m wide | m² |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | The vertical plane is 0.4-1.22 meters wide | m² |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | The vertical plane is more than 1.22 meters wide | m² |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Horizontal plane with a width exceeding 1.22 metres | m² |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Finishes of the upper surface layers |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Power floating finishes | m² |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Commas |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Construction breaks | m² |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Armament |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Steel bars for reinforcement and adjustment BS EN 10080 BS 4449 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | 12mm cow | طن |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Waterproof insulation |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Lining of tanks (sinks). |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Peripheral lining from all sides, including the slat, the insulating layer of insulation, the screed, and so on, according to the plans. | m² |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Balata Al-Qaeda approach |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Excavations from materials other than average soil, rock, or artificial solid materials |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Maximum depth 1 meter | m³ |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | The maximum depth is 1-2 metres | m³ |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Drilling accessories |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Prepare the brightest base layer to be excavated to begin the hard work |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Excavations from materials other than topsoil, rock, or artificial solids | m³ |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Transporting surplus excavations to an approved location | m³ |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Backfills |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Backfilling using materials selected from the excavation results other than surface soil or rock | m³ |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Backfilling with materials supplied from outside the city | m³ |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Concrete works on site Concrete supply Scheme No. (DAM3-01-001-CH2-TS8-1-STR-DRW-0358 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Concrete type (C15), OP cement, in hygiene concrete | m³ |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Concrete type (C40), OP cement, in construction | m³ |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Pouring the concrete block |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | So that the thickness of the blinding concrete does not exceed 100 mm | m³ |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Commodification |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Suspended slab with thickness of 150-300 mm | m³ |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Concrete accessories |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Rough brickwork finishes |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | The vertical level is 0.2 - 0.4 m wide | m² |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Commas |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Construction breaks | m² |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | 16mm Dowels |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Scheme No. DAM3-01-001-CH2-TS8-1-STR-DRW--0358 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Finishes of the upper surface layers |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Waterproof insulation |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Lining tanks | m² |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Mesh barrier to trap floating litter (MS) according to plan and details | nr |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Rock works |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Artificial swimming pool - geo-textile - under stone cladding | m² |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | Stone cladding works with a thickness of (0.3 m) around the facility supported by a filter layer with a thickness of (0.15 m) | m² |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | 250mm diameter uPVC open drainage pipes laid and backfilled with gravel/in gravel backfilled trenches (trenches measured separately). | m |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
STR11 |  | 160mm diameter uPVC open drainage pipes laid and backfilled with gravel/in gravel backfilled trenches (trenches measured separately). | m | 25047.1716 | 156 | 3907358.7727 | 70.5 | 1765825.5992 | 25047.1716 | 25047.1716 |  | 25047.1716 | 100% | 156 | 3907358.7727 | 70.5 | 1765825.5992 |  | 1765825.5992 | [7 empty] | 70.5 | 25047.1716 | 1765825.5992 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 25047.1716 | 25047.1716 |  | 25047.1716 | [9 empty] | Pipe Laying |  | M | 70.5 |  | 70.5 | 25047.1716 | 1765825.5992 | 0 | 0 | 0 | 0 | 0
[22 empty] | UPVC Pipe 160 mm | Material | M | 33.5 | 1 | 33.5 | 25047.1716 | 839080.2493
[22 empty] | UPVC Fitting 160 mm | Material | M | 2 | 1 | 2 | 25047.1716 | 50094.3432
[22 empty] | Skilled Labor | Manpower | HR | 17 | 1 | 17 | 25047.1716 | 425801.9175
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 1 | 13 | 25047.1716 | 325613.2311
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 25047.1716 | 125235.8581
STR11 |  | 200mm diameter uPVC open drainage pipes laid and backfilled with gravel/in gravel backfilled trenches (trenches measured separately). | m | 31927.8155 | 249 | 7950026.0595 | 79 | 2522297.4245 | 31927.8155 | 31927.8155 |  | 31927.8155 | 100% | 249 | 7950026.0595 | 79 | 2522297.4245 |  | 2522297.4245 | [7 empty] | 79 | 31927.8155 | 2522297.4245 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 31927.8155 | 31927.8155 |  | 31927.8155 | [9 empty] | Pipe Laying |  | M | 79 |  | 79 | 31927.8155 | 2522297.4245 | 0 | 0 | 0 | 0 | 0
[22 empty] | UPVC Pipe 200 mm | Material | M | 40 | 1 | 40 | 31927.8155 | 1277112.62
[22 empty] | UPVC Fitting 200 mm | Material | M | 4 | 1 | 4 | 31927.8155 | 127711.262
[22 empty] | Skilled Labor | Manpower | HR | 17 | 1 | 17 | 31927.8155 | 542772.8635
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 1 | 13 | 31927.8155 | 415061.6015
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 31927.8155 | 159639.0775
STR11 |  | Gravel/backfill using gravel | m | 56974.9871 | 73 | 4159174.0598 | 55.9227 | 3186195.904 | 56974.9871 | 56974.9871 |  | 56974.9871 | 100% | 73 | 4159174.0598 | 55.9227 | 3186195.904 |  | 3186195.904 | [7 empty] | 55.9227 | 56974.9871 | 3186195.904 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 56974.9871 | 56974.9871 |  | 56974.9871 | [9 empty] | Granular Material (W=1.0) |  | M | 55.9227 |  | 55.9227 | 56974.9871 | 3186195.904 | 0 | 0 | 0 | 0 | 0
[22 empty] | Granular bedding backfilling material | Material | M³ | 70 | 1.3711 | 51.0545 | 41554.7069 | 2908829.4799
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 137.1084 | 0.47845 | 415.5471 | 27259.8877
[22 empty] | Fuel | Material | LTR | 1.76 | 15.2343 | 0.11553 | 3739.9236 | 6582.2656
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 18.6467 | 2.5742 | 3055.4932 | 146663.6713
[22 empty] | Fuel | Material | LTR | 1.76 | 1.8647 | 0.94386 | 30554.9315 | 53776.6795
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 68.5542 | 0.52513 | 831.0941 | 29919.3889
[22 empty] | Fuel | Material | LTR | 1.76 | 7.6171 | 0.23106 | 7479.8472 | 13164.5311
STR11 |  | Filter filter fabric as required. Packing with gravel/backfill using gravel within the filter fabric | m | 56974.9871 | 37 | 2108074.5234 | 16 | 911599.7939 | 56974.9871 | 56974.9871 |  | 56974.9871 | 100% | 37 | 2108074.5234 | 16 | 911599.7939 |  | 911599.7939 | [7 empty] | 16 | 56974.9871 | 911599.7939 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 56974.9871 | 56974.9871 |  | 56974.9871 | [9 empty] | Filter fabric |  | M | 16 |  | 16 | 56974.9871 | 911599.7939 | 0 | 0 | 0 | 0 | 0
[22 empty] | Filter fabric sheets arround the Gravel | Material | M² | 8 | 0.5 | 16 | 113949.9742 | 911599.7939
STR11 |  | A deep basin to collect underground water through sewage at a depth of 2.5 - 3.0 m | nr | 332.85 | 25274 | 8412450.9 | 15334.79 | 5104184.8465 | 332.85 | 332.85 |  | 332.85 | 100% | 25274 | 8412450.9 | 15334.79 | 5104184.8465 |  | 5104184.8465 | [7 empty] | 15334.79 | 332.85 | 5104184.8465 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 332.85 | 332.85 |  | 332.85 | [9 empty] | Excavate & Disposal (3.7*3.7*3.0) |  | Ea | 165.1871 |  | 165.1871 | 332.85 | 54982.5207 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 2.4349 | 22.9992 | 136.7015 | 7655.2837
[22 empty] | Fuel | Material | LTR | 1.76 | 0.17392 | 10.1196 | 1913.8209 | 3368.3248
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.49671 | 96.6353 | 670.1054 | 32165.0576
[22 empty] | Fuel | Material | LTR | 1.76 | 0.049671 | 35.4329 | 6701.0537 | 11793.8545
[9 empty] | 332.85 | 332.85 |  | 332.85 | [9 empty] | Chamber Installation (2.5*2.5*3) |  | Ea | 12676.75 |  | 12676.75 | 332.85 | 4219456.2375 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 1.3717 | 182.25 | 242.6477 | 60661.9125
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.10025 | 3491.25 | 3320.1788 | 1162062.5625
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 1.2531 | 1995 | 265.6143 | 664035.75
[22 empty] | Workmanship plain concrete | SC | M³ | 150 | 1.3717 | 109.35 | 242.6477 | 36397.1475
[22 empty] | Trench RC Concrete workmanship | SC | M³ | 300 | 0.10025 | 2992.5 | 3320.1788 | 996053.625
[22 empty] | Supply & apply Chamber Cover, frames | Material | Ea | 3500 | 1 | 3500 | 332.85 | 1164975
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 1 | 80 | 332.85 | 26628
[22 empty] | Fuel | Material | HR | 1.76 | 0.066667 | 26.4 | 4992.75 | 8787.24
[22 empty] | Chamber Pipes Pieces | Material | LS | 150 | 1 | 150 | 332.85 | 49927.5
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.2 | 85 | 1664.25 | 28292.25
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 0.2 | 65 | 1664.25 | 21635.25
[9 empty] | 332.85 | 332.85 |  | 332.85 | [9 empty] | Internal and external Insulation |  | Ea | 2100 |  | 2100 | 332.85 | 698985 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply & apply external waterproofing | SC | M² | 40 | 0.033333 | 1200 | 9985.5 | 399420
[22 empty] | Supply & apply internal coating | SC | M² | 30 | 0.033333 | 900 | 9985.5 | 299565
[9 empty] | 332.85 | 332.85 |  | 332.85 | [9 empty] | Backfilling |  | Ea | 392.8529 |  | 392.8529 | 332.85 | 130761.0883 | 0 | 0 | 0 | 0 | 0
[22 empty] | Backfilling Material | Material | M³ | 10 | 0.044803 | 223.2 | 7429.212 | 74292.12
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 4.4803 | 14.6419 | 74.2921 | 4873.5631
[22 empty] | Fuel | Material | LTR | 1.76 | 0.49781 | 3.5355 | 668.6291 | 1176.7872
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.91398 | 52.5176 | 364.1771 | 17480.4988
[22 empty] | Fuel | Material | LTR | 1.76 | 0.091398 | 19.2565 | 3641.7706 | 6409.5162
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 2.2401 | 16.0704 | 148.5842 | 5349.0326
[22 empty] | Fuel | Material | LTR | 1.76 | 0.2489 | 7.071 | 1337.2582 | 2353.5744
[22 empty] | Plate Compactor | Machinery | HR | 23 | 0.5 | 46 | 665.7 | 15311.1
[22 empty] | Fuel | Material | LTR | 1.76 | 0.16667 | 10.56 | 1997.1 | 3514.896
|  | General preparation of the site land |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
Ponds 12 |  | General preparation of the site land | m² | 625585 | 3 | 1876755 | 0.55655 | 348169.2091 | 625585 | 625585 |  | 625585 | 100% | 3 | 1876755 | 0.55655 | 348169.2091 |  | 348169.2091 | [7 empty] | 0.55655 | 625585 | 348169.2091 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 625585 | 625585 |  | 625585 | [7 empty] | 0 | 01 | Clearing |  | M² | 0.55655 |  | 0.55655 | 625585 | 348169.2091 | 0 | 0 | 0 | 0 | 0
[21 empty] | 01 | Grader | Machinery | Hr | 90.4 | 600 | 0.15067 | 1042.6417 | 94254.8067
[21 empty] | 01 | Fuel | Material | Litre | 1.76 | 28.5714 | 0.0616 | 21895.475 | 38536.036
[21 empty] | 01 | Wheel Loader | Machinery | Hr | 65.6 | 1000 | 0.0656 | 625.585 | 41038.376
[21 empty] | 01 | Fuel | Material | Litre | 1.76 | 111.1111 | 0.01584 | 5630.265 | 9909.2664
[21 empty] | 01 | Dump Truck 16 m³ | Machinery | Hr | 48 | 272 | 0.17647 | 2299.9449 | 110397.3529
[21 empty] | 01 | Fuel | Material | Litre | 1.76 | 27.2 | 0.064706 | 22999.4485 | 40479.0294
[21 empty] | 01 | Unskilled Labour | Manpower | Hr | 13 | 600 | 0.021667 | 1042.6417 | 13554.3417
Ponds 12 |  | Drilling for the purpose of cutting and leveling at all depths for materials other than surface or rock | m³ | 2317705 | 15 | 34765575 | 3.7637 | 8723223.5653 | 2317705 | 2317705 |  | 2317705 | 100% | 15 | 34765575 | 3.7637 | 8723223.5653 |  | 8723223.5653 | [7 empty] | 3.7637 | 2317705 | 8723223.5653 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 2317705 | 2317705 |  | 2317705 | [7 empty] | 0 | 01 | Cutting & Leveling |  | M³ | 3.7637 |  | 3.7637 | 2317705 | 8723223.5653 | 0 | 0 | 0 | 0 | 0
[21 empty] | 01 | Bulldozer CAT D8 | Machinery | Hr | 111.568 | 120 | 0.92973 | 19314.2083 | 2154847.5953
[21 empty] | 01 | Fuel | Material | Litre | 1.76 | 2.4742 | 0.71133 | 936739.1042 | 1648660.8233
[21 empty] | 01 | Grader | Machinery | Hr | 90.4 | 60 | 1.5067 | 38628.4167 | 3492008.8667
[21 empty] | 01 | Fuel | Material | Litre | 1.76 | 2.8571 | 0.616 | 811196.75 | 1427706.28
Ponds 12 |  | Dispose of excess excavated material from an approved site in accordance with the engineer’s directions | m³ | 2252295 | 13 | 29279835 | 5.7777 | 13013159.898 | 2252295 | 2252295 |  | 2252295 | 100% | 13 | 29279835 | 5.7777 | 13013159.898 |  | 13013159.898 | [7 empty] | 5.7777 | 2252295 | 13013159.898 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 2252295 | 2252295 |  | 2252295 | [7 empty] | 0 | 0102 | Soil Disposal |  | M³ | 5.7777 |  | 5.7777 | 2252295 | 13013159.898 | 0 | 0 | 0 | 0 | 0
[21 empty] | 0102 | Wheel Loader | Machinery | Hr | 65.6 | 100 | 0.656 | 22522.95 | 1477505.52
[21 empty] | 0102 | Fuel | Material | Litre | 1.76 | 11.1111 | 0.1584 | 202706.55 | 356763.528
[21 empty] | 0102 | Trailer Dump Truck 24 m³ | Machinery | Hr | 56 | 16.32 | 3.4314 | 138008.2721 | 7728463.2353
[21 empty] | 0102 | Fuel | Material | Litre | 1.76 | 1.2554 | 1.402 | 1794107.5368 | 3157629.2647
[21 empty] | 0102 | Unskilled Labour | Manpower | Hr | 13 | 100 | 0.13 | 22522.95 | 292798.35
Ponds 12 |  | Backfilling using materials selected from the excavation product other than topsoil or rock | m³ | 1 | 32 | 32 | 7.5223 | 7.5223 | 1 | 1 |  | 1 | 100% | 32 | 32 | 7.5223 | 7.5223 |  | 7.5223 | [7 empty] | 7.5223 | 1 | 7.5223 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 1 | 1 |  | 1 | [7 empty] | 0 | 01 | Stockpile Operation |  | M³ | 0.79937 |  | 0.79937 | 1 | 0.79937 | 0 | 0 | 0 | 0 | 0
[21 empty] | 01 | Bulldozer CAT D9 | Machinery | Hr | 132.304 | 500 | 0.26461 | 0.002 | 0.26461
[21 empty] | 01 | Fuel | Material | Litre | 1.76 | 10.3093 | 0.17072 | 0.097 | 0.17072
[21 empty] | 01 | Water Tank Trailer 32,000 Litre | Machinery | Hr | 52 | 500 | 0.104 | 0.002 | 0.104
[21 empty] | 01 | Fuel | Material | Litre | 1.76 | 62.5 | 0.02816 | 0.016 | 0.02816
[21 empty] | 01 | Compaction Water | Material | M³ | 2.8 | 50 | 0.056 | 0.02 | 0.056
[21 empty] | 01 | Wheel Loader | Machinery | Hr | 65.6 | 500 | 0.1312 | 0.002 | 0.1312
[21 empty] | 01 | Fuel | Material | Litre | 1.76 | 55.5556 | 0.03168 | 0.018 | 0.03168
[21 empty] | 01 | Unskilled Labour | Manpower | Hr | 13 | 1000 | 0.013 | 0.001 | 0.013
[9 empty] | 1 | 1 |  | 1 | [7 empty] | 0 | 02 | Material Hauling |  | M³ | 4.1629 |  | 4.1629 | 1 | 4.1629 | 0 | 0 | 0 | 0 | 0
[21 empty] | 02 | Excavator with Bucket 50T | Machinery | Hr | 131.2 | 122.4 | 1.0719 | 0.0081699 | 1.0719
[21 empty] | 02 | Fuel | Material | Litre | 1.76 | 3.825 | 0.46013 | 0.26144 | 0.46013
[21 empty] | 02 | Trailer Dump Truck 24 m³ | Machinery | Hr | 56 | 30.6 | 1.8301 | 0.03268 | 1.8301
[21 empty] | 02 | Fuel | Material | Litre | 1.76 | 2.3538 | 0.74771 | 0.42484 | 0.74771
[21 empty] | 02 | Unskilled Labour | Manpower | Hr | 13 | 244.8 | 0.053105 | 0.004085 | 0.053105
[9 empty] | 1 | 1 |  | 1 | [7 empty] | 0 | 03 | Spreading & leveling |  | M³ | 0.70756 |  | 0.70756 | 1 | 0.70756 | 0 | 0 | 0 | 0 | 0
[21 empty] | 03 | Grader | Machinery | Hr | 90.4 | 180 | 0.50222 | 0.0055556 | 0.50222
[21 empty] | 03 | Fuel | Material | Litre | 1.76 | 8.5714 | 0.20533 | 0.11667 | 0.20533
[9 empty] | 1 | 1 |  | 1 | [7 empty] | 0 | 04 | Compaction |  | M³ | 1.8525 |  | 1.8525 | 1 | 1.8525 | 0 | 0 | 0 | 0 | 0
[21 empty] | 04 | Roller Compactor 10 Ton | Machinery | Hr | 40 | 80 | 0.5 | 0.0125 | 0.5
[21 empty] | 04 | Fuel | Material | Litre | 1.76 | 5.7143 | 0.308 | 0.175 | 0.308
[21 empty] | 04 | Water Tank Trailer 32,000 Litre | Machinery | Hr | 52 | 80 | 0.65 | 0.0125 | 0.65
[21 empty] | 04 | Fuel | Material | Litre | 1.76 | 10 | 0.176 | 0.1 | 0.176
[21 empty] | 04 | Compaction Water | Material | M³ | 2.8 | 50 | 0.056 | 0.02 | 0.056
[21 empty] | 04 | Unskilled Labour | Manpower | Hr | 13 | 80 | 0.1625 | 0.0125 | 0.1625
Ponds 12 |  | Backfilling using imported materials other than topsoil or rock | m³ | 1 | 38 | 38 | 16.723 | 16.723 | 1 | 1 |  | 1 | 100% | 38 | 38 | 16.723 | 16.723 |  | 16.723 | [7 empty] | 16.723 | 1 | 16.723 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 1 | 1 |  | 1 | [7 empty] | 0 | 01 | Imported backfilling material |  | M³ | 10 |  | 10 | 1 | 10 | 0 | 0 | 0 | 0 | 0
[21 empty] | 01 | Backfilling Material | Material | M³ | 10 | 1 | 10 | 1 | 10
[9 empty] | 1 | 1 |  | 1 | [7 empty] | 0 | 02 | Material Hauling |  | M³ | 4.1629 |  | 4.1629 | 1 | 4.1629 | 0 | 0 | 0 | 0 | 0
[21 empty] | 02 | Excavator with Bucket 50T | Machinery | Hr | 131.2 | 122.4 | 1.0719 | 0.0081699 | 1.0719
[21 empty] | 02 | Fuel | Material | Litre | 1.76 | 3.825 | 0.46013 | 0.26144 | 0.46013
[21 empty] | 02 | Trailer Dump Truck 24 m³ | Machinery | Hr | 56 | 30.6 | 1.8301 | 0.03268 | 1.8301
[21 empty] | 02 | Fuel | Material | Litre | 1.76 | 2.3538 | 0.74771 | 0.42484 | 0.74771
[21 empty] | 02 | Unskilled Labour | Manpower | Hr | 13 | 244.8 | 0.053105 | 0.004085 | 0.053105
[9 empty] | 1 | 1 |  | 1 | [7 empty] | 0 | 03 | Spreading & leveling |  | M³ | 0.70756 |  | 0.70756 | 1 | 0.70756 | 0 | 0 | 0 | 0 | 0
[21 empty] | 03 | Grader | Machinery | Hr | 90.4 | 180 | 0.50222 | 0.0055556 | 0.50222
[21 empty] | 03 | Fuel | Material | Litre | 1.76 | 8.5714 | 0.20533 | 0.11667 | 0.20533
[9 empty] | 1 | 1 |  | 1 | [7 empty] | 0 | 04 | Compaction |  | M³ | 1.8525 |  | 1.8525 | 1 | 1.8525 | 0 | 0 | 0 | 0 | 0
[21 empty] | 04 | Roller Compactor 10 Ton | Machinery | Hr | 40 | 80 | 0.5 | 0.0125 | 0.5
[21 empty] | 04 | Fuel | Material | Litre | 1.76 | 5.7143 | 0.308 | 0.175 | 0.308
[21 empty] | 04 | Water Tank Trailer 32,000 Litre | Machinery | Hr | 52 | 80 | 0.65 | 0.0125 | 0.65
[21 empty] | 04 | Fuel | Material | Litre | 1.76 | 10 | 0.176 | 0.1 | 0.176
[21 empty] | 04 | Compaction Water | Material | M³ | 2.8 | 50 | 0.056 | 0.02 | 0.056
[21 empty] | 04 | Unskilled Labour | Manpower | Hr | 13 | 80 | 0.1625 | 0.0125 | 0.1625
Ponds 12 |  | Diagrams No. DAM3-01-001CH2-TS8-STR-DRW-0332 | m³ | 24 | 172 | 4128 | 120 | 2880 | 24 | 24 |  | 24 | 100% | 172 | 4128 | 120 | 2880 |  | 2880 | [7 empty] | 120 | 24 | 2880 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 24 | 24 |  | 24 | [7 empty] | 0 | 01 | Earth Work |  | M³ | 120 |  | 120 | 24 | 2880 | 0 | 0 | 0 | 0 | 0
[21 empty] | 01 | Earth Work | SC | M³ | 120 | 1 | 120 | 24 | 2880
Ponds 12 |  | Diagrams No. DAM3-01-001CH2-TS8-STR-DRW-0332 | m³ | 9380.3 | 174 | 1632172.2 | 120 | 1125636 | 9380.3 | 9380.3 |  | 9380.3 | 100% | 174 | 1632172.2 | 120 | 1125636 |  | 1125636 | [7 empty] | 120 | 9380.3 | 1125636 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 9380.3 | 9380.3 |  | 9380.3 | [7 empty] | 0 | 01 | Earth Work |  | M³ | 120 |  | 120 | 9380.3 | 1125636 | 0 | 0 | 0 | 0 | 0
[21 empty] | 01 | Earth Work | SC | M³ | 120 | 1 | 120 | 9380.3 | 1125636
Ponds 12 |  | Lining with HDPE geotextile for insulation at the bottom and including a 500 mm thick coarse sand mattress. | m² | 57843.087 | 48 | 2776468.176 | 24.0554 | 1391437.631 | 57843.087 | 57843.087 |  | 57843.087 | 100% | 48 | 2776468.176 | 24.0554 | 1391437.631 |  | 1391437.631 | [7 empty] | 24.0554 | 57843.087 | 1391437.631 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 57843.087 | 57843.087 |  | 57843.087 | [7 empty] | 0 | 01 | Sand BeddingHDPE Geotextile |  | M² | 5 |  | 5 | 57843.087 | 289215.435 | 0 | 0 | 0 | 0 | 0
[21 empty] | 01 | Supply & apply HDPE geotextile | SC | M² | 5 | 1 | 5 | 57843.087 | 289215.435
[9 empty] | 57843.087 | 57843.087 |  | 57843.087 | [7 empty] | 0 | 02 | Sand Bedding (500 mm Thick) |  | M² | 17.8889 |  | 17.8889 | 57843.087 | 1034747.2709 | 0 | 0 | 0 | 0 | 0
[21 empty] | 02 | Sand Supply | Material | M³ | 30 | 2 | 15 | 28921.5435 | 867646.305
[21 empty] | 02 | Wheel Loader | Machinery | Hr | 65.6 | 200 | 0.328 | 289.2154 | 18972.5325
[21 empty] | 02 | Fuel | Material | Litre | 1.76 | 22.2222 | 0.0792 | 2602.9389 | 4581.1725
[21 empty] | 02 | Trailer Dump Truck 24 m³ | Machinery | Hr | 56 | 32.64 | 1.7157 | 1772.1534 | 99240.5904
[21 empty] | 02 | Fuel | Material | Litre | 1.76 | 2.5108 | 0.70098 | 23037.9942 | 40546.8698
[21 empty] | 02 | Unskilled Labour | Manpower | Hr | 13 | 200 | 0.065 | 289.2154 | 3759.8007
[9 empty] | 57843.087 | 57843.087 |  | 57843.087 | [7 empty] | 0 | 03 | Spreading & leveling |  | M² | 0.21227 |  | 0.21227 | 57843.087 | 12278.1593 | 0 | 0 | 0 | 0 | 0
[21 empty] | 03 | Grader | Machinery | Hr | 90.4 | 600 | 0.15067 | 96.4051 | 8715.0251
[21 empty] | 03 | Fuel | Material | Litre | 1.76 | 28.5714 | 0.0616 | 2024.508 | 3563.1342
[9 empty] | 57843.087 | 57843.087 |  | 57843.087 | [7 empty] | 0 | 04 | Compaction |  | M² | 0.95425 |  | 0.95425 | 57843.087 | 55196.7658 | 0 | 0 | 0 | 0 | 0
[21 empty] | 04 | Roller Compactor 10 Ton | Machinery | Hr | 40 | 160 | 0.25 | 361.5193 | 14460.7717
[21 empty] | 04 | Fuel | Material | Litre | 1.76 | 11.4286 | 0.154 | 5061.2701 | 8907.8354
[21 empty] | 04 | Water Tank Trailer 32,000 Litre | Machinery | Hr | 52 | 160 | 0.325 | 361.5193 | 18799.0033
[21 empty] | 04 | Fuel | Material | Litre | 1.76 | 20 | 0.088 | 2892.1543 | 5090.1917
[21 empty] | 04 | Compaction Water | Material | M³ | 2.8 | 50 | 0.056 | 1156.8617 | 3239.2129
[21 empty] | 04 | Unskilled Labour | Manpower | Hr | 13 | 160 | 0.08125 | 361.5193 | 4699.7508
Ponds 12 |  | Siphon tubes with DI 90 bends Low levels for a sedimentation and deoiling facility, including side wall, low level area, compacted granular bed, coarse gravel compaction, earthworks, brickwork, reinforced concrete, waterproofing, finishing works, etc. | item | 12 | 22071 | 264852 | 37733.2682 | 452799.2185 | 12 | 12 |  | 12 | 100% | 22071 | 264852 | 37733.2682 | 452799.2185 |  | 452799.2185 | [7 empty] | 37733.2682 | 12 | 452799.2185 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 12 | 12 |  | 12 | [9 empty] | Excavate & Disposal |  | Ea | 2413.2518 |  | 2413.2518 | 12 | 28959.0212 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 0.16667 | 336 | 72 | 4032
[22 empty] | Fuel | Material | LTR | 1.76 | 0.011905 | 147.84 | 1008 | 1774.08
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.034 | 1411.7647 | 352.9412 | 16941.1765
[22 empty] | Fuel | Material | LTR | 1.76 | 0.0034 | 517.6471 | 3529.4118 | 6211.7647
[9 empty] | 12 | 12 |  | 12 | [7 empty] | 0 | 0403 | Siphon tubes with DI 90 bends |  | Ea | 8420 |  | 8420 | 12 | 101040 | 0 | 0 | 0 | 0 | 0
[21 empty] | 0403 | Supply Siphon Tubes | Material | M | 275 | 0.033333 | 8250 | 360 | 99000
[21 empty] | 0403 | Skilled labor | Manpower | Hr | 17 | 0.1 | 170 | 120 | 2040
[9 empty] | 12 | 12 |  | 12 | [9 empty] | RC Wall |  | Ea | 22200 |  | 22200 | 12 | 266400 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 0.33333 | 750 | 36 | 9000
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 0.05 | 7000 | 240 | 84000
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 0.5 | 5000 | 24 | 60000
[22 empty] | Workmanship plain concrete | SC | M³ | 150 | 0.33333 | 450 | 36 | 5400
[22 empty] | Workmanship RC concrete | SC | M³ | 450 | 0.05 | 9000 | 240 | 108000
[9 empty] | 12 | 12 |  | 12 | [7 empty] | 0 | 03 | Insulation & Riprap Works |  | Ea | 4600 |  | 4600 | 12 | 55200 | 0 | 0 | 0 | 0 | 0
[21 empty] | 03 | Supply & apply HDPE geotextile | SC | M² | 5 | 0.0083333 | 600 | 1440 | 7200
[21 empty] | 03 | Supply & apply grouted riprap 30 cm | SC | M² | 80 | 0.02 | 4000 | 600 | 48000
[9 empty] | 12 | 12 |  | 12 | [7 empty] | 0 | 0302 | Filling |  | Ea | 57.5324 |  | 57.5324 | 12 | 690.3893 | 0 | 0 | 0 | 0 | 0
[21 empty] | 0302 | Wheel Loader | Machinery | Hr | 65.6 | 5 | 13.12 | 2.4 | 157.44
[21 empty] | 0302 | Fuel | Material | Litre | 1.76 | 0.55556 | 3.168 | 21.6 | 38.016
[21 empty] | 0302 | Trailer Dump Truck 24 m³ | Machinery | Hr | 56 | 1.9125 | 29.281 | 6.2745 | 351.3725
[21 empty] | 0302 | Fuel | Material | Litre | 1.76 | 0.14712 | 11.9634 | 81.5686 | 143.5608
[9 empty] | 12 | 12 |  | 12 | [7 empty] | 0 | 0304 | Compaction |  | Ea | 42.484 |  | 42.484 | 12 | 509.808 | 0 | 0 | 0 | 0 | 0
[21 empty] | 0304 | Roller Compactor 10 Ton | Machinery | Hr | 40 | 3.0769 | 13 | 3.9 | 156
[21 empty] | 0304 | Fuel | Material | Litre | 1.76 | 0.21978 | 8.008 | 54.6 | 96.096
[21 empty] | 0304 | Water Tank Trailer 32,000 Litre | Machinery | Hr | 52 | 3.0769 | 16.9 | 3.9 | 202.8
[21 empty] | 0304 | Fuel | Material | Litre | 1.76 | 0.38462 | 4.576 | 31.2 | 54.912
Ponds 12 |  | Energy dissipation facilities, including 600mm stone walls (Gabion Baffles), stone cladding works (Riprap), ground bed compaction, paving works with coarse gravel, earthworks, brickwork, reinforced concrete, waterproofing works, finishing works, etc. | item | 12 | 33648 | 403776 | 31062.781 | 372753.3715 | 12 | 12 |  | 12 | 100% | 33648 | 403776 | 31062.781 | 372753.3715 |  | 372753.3715 | [7 empty] | 31062.781 | 12 | 372753.3715 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 12 | 12 |  | 12 | [9 empty] | Excavate & Disposal |  | Ea | 4826.5035 |  | 4826.5035 | 12 | 57918.0424 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 0.083333 | 672 | 144 | 8064
[22 empty] | Fuel | Material | LTR | 1.76 | 0.0059524 | 295.68 | 2016 | 3548.16
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 0.017 | 2823.5294 | 705.8824 | 33882.3529
[22 empty] | Fuel | Material | LTR | 1.76 | 0.0017 | 1035.2941 | 7058.8235 | 12423.5294
[9 empty] | 12 | 12 |  | 12 | [7 empty] | 0 | 0304 | Ground bed Compaction |  | Ea | 287.584 |  | 287.584 | 12 | 3451.008 | 0 | 0 | 0 | 0 | 0
[21 empty] | 0304 | Roller Compactor 10 Ton | Machinery | Hr | 40 | 0.45455 | 88 | 26.4 | 1056
[21 empty] | 0304 | Fuel | Material | Litre | 1.76 | 0.032468 | 54.208 | 369.6 | 650.496
[21 empty] | 0304 | Water Tank Trailer 32,000 Litre | Machinery | Hr | 52 | 0.45455 | 114.4 | 26.4 | 1372.8
[21 empty] | 0304 | Fuel | Material | Litre | 1.76 | 0.056818 | 30.976 | 211.2 | 371.712
[9 empty] | 12 | 12 |  | 12 | [7 empty] | 0 | 030403 | Siphon tubes with DI 90 bends |  | Ea | 8420 |  | 8420 | 12 | 101040 | 0 | 0 | 0 | 0 | 0
[21 empty] | 030403 | Supply Siphon Tubes | Material | M | 275 | 0.033333 | 8250 | 360 | 99000
[21 empty] | 030403 | Skilled labor | Manpower | Hr | 17 | 0.1 | 170 | 120 | 2040
[9 empty] | 12 | 12 |  | 12 | [9 empty] | Backfilling Filter Material (150 mm Thick) |  | Ea | 525.1628 |  | 525.1628 | 12 | 6301.9531 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Filter backfilling material | Material | M³ | 15 | 0.033333 | 450 | 360 | 5400
[22 empty] | Wheel Loader | Machinery | Hr | 65.6 | 3.3333 | 19.68 | 3.6 | 236.16
[22 empty] | Fuel | Material | Litre | 1.76 | 33.3333 | 0.0528 | 0.36 | 0.6336
[22 empty] | Trailer Dump Truck 24 m³ | Machinery | Hr | 56 | 1.02 | 54.902 | 11.7647 | 658.8235
[22 empty] | Fuel | Material | Litre | 1.76 | 3.3333 | 0.528 | 3.6 | 6.336
[9 empty] | 12 | 12 |  | 12 | [7 empty] | 0 | 03 | Insulation & Riprap Works |  | Ea | 15000 |  | 15000 | 12 | 180000 | 0 | 0 | 0 | 0 | 0
[21 empty] | 03 | Supply & apply HDPE geotextile | SC | M² | 5 | 0.005 | 1000 | 2400 | 12000
[21 empty] | 03 | Supply & apply grouted riprap 25 cm | SC | M² | 70 | 0.005 | 14000 | 2400 | 168000
[9 empty] | 12 | 12 |  | 12 | [7 empty] | 0 | 0302 | Backfilling Sand Material (300 mm Thick) |  | Ea | 2003.5307 |  | 2003.5307 | 12 | 24042.368 | 0 | 0 | 0 | 0 | 0
[22 empty] | Sand Supply | Material | M³ | 30 | 0.016667 | 1800 | 720 | 21600
[21 empty] | 0302 | Wheel Loader | Machinery | Hr | 65.6 | 1.6667 | 39.36 | 7.2 | 472.32
[21 empty] | 0302 | Fuel | Material | Litre | 1.76 | 0.18519 | 9.504 | 64.8 | 114.048
[21 empty] | 0302 | Trailer Dump Truck 24 m³ | Machinery | Hr | 56 | 0.51 | 109.8039 | 23.5294 | 1317.6471
[21 empty] | 0302 | Fuel | Material | Litre | 1.76 | 0.039231 | 44.8627 | 305.8824 | 538.3529
Ponds 12 |  | Scheme No.: DAM3-01-002-CH2-TS8-1-STR-DRW-0333 | m² | 2576.14 | 176 | 453400.64 | 120 | 309136.8 | 2576.14 | 2576.14 |  | 2576.14 | 100% | 176 | 453400.64 | 120 | 309136.8 |  | 309136.8 | [7 empty] | 120 | 2576.14 | 309136.8 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 2576.14 | 2576.14 |  | 2576.14 | [7 empty] | 0 | 01 | Earth Work |  | M³ | 120 |  | 120 | 2576.14 | 309136.8 | 0 | 0 | 0 | 0 | 0
[21 empty] | 01 | Earth Work | SC | M³ | 120 | 1 | 120 | 2576.14 | 309136.8
Ponds 12 |  | Excavations from materials other than topsoil, rock, or artificial solids | m³ | 1565.08 | 101 | 158073.08 | 30.658 | 47982.2104 | 1565.08 | 1565.08 |  | 1565.08 | 100% | 101 | 158073.08 | 30.658 | 47982.2104 |  | 47982.2104 | [7 empty] | 30.658 | 1565.08 | 47982.2104 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 1565.08 | 1565.08 |  | 1565.08 | [9 empty] | Rock Excavation & Disposal |  | M³ | 22.3553 |  | 22.3553 | 1565.08 | 34987.7746 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Hydraulic Hammer 50T | Machinery | HR | 150.4 | 15 | 10.0267 | 104.3387 | 15692.5355
[22 empty] | Fuel | Material | LTR | 1.76 | 0.46875 | 3.7547 | 3338.8373 | 5876.3537
[22 empty] | Excavator with Bucket 50T | Machinery | HR | 131.2 | 50 | 2.624 | 31.3016 | 4106.7699
[22 empty] | Fuel | Material | LTR | 1.76 | 1.5625 | 1.1264 | 1001.6512 | 1762.9061
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 13.6 | 3.5294 | 115.0794 | 5523.8118
[22 empty] | Fuel | Material | LTR | 1.76 | 1.36 | 1.2941 | 1150.7941 | 2025.3976
[9 empty] | 1565.08 | 1565.08 |  | 1565.08 | [9 empty] | Backfilling & Compaction |  | M³ | 8.3027 |  | 8.3027 | 1565.08 | 12994.4357 | 0 | 0 | 0 | 0 | 0
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 100 | 0.656 | 15.6508 | 1026.6925
[22 empty] | Fuel | Material | LTR | 1.76 | 11.1111 | 0.1584 | 140.8572 | 247.9087
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 13.6 | 3.5294 | 115.0794 | 5523.8118
[22 empty] | Fuel | Material | LTR | 1.76 | 1.36 | 1.2941 | 1150.7941 | 2025.3976
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 50 | 0.72 | 31.3016 | 1126.8576
[22 empty] | Fuel | Material | LTR | 1.76 | 5.5556 | 0.3168 | 281.7144 | 495.8173
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 80 | 0.6 | 19.5635 | 939.048
[22 empty] | Fuel | Material | LTR | 1.76 | 8 | 0.22 | 195.635 | 344.3176
[22 empty] | Roller Compactor 10 Ton | Machinery | HR | 40 | 80 | 0.5 | 19.5635 | 782.54
[22 empty] | Fuel | Material | LTR | 1.76 | 5.7143 | 0.308 | 273.889 | 482.0446
Ponds 12 |  | Maximum depth from 1 - 2 meters | m³ | 819.08 | 101 | 82727.08 | 30.658 | 25111.3482 | 819.08 | 819.08 |  | 819.08 | 100% | 101 | 82727.08 | 30.658 | 25111.3482 |  | 25111.3482 | [7 empty] | 30.658 | 819.08 | 25111.3482 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 819.08 | 819.08 |  | 819.08 | [9 empty] | Rock Excavation & Disposal |  | M³ | 22.3553 |  | 22.3553 | 819.08 | 18310.7486 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Hydraulic Hammer 50T | Machinery | HR | 150.4 | 15 | 10.0267 | 54.6053 | 8212.6421
[22 empty] | Fuel | Material | LTR | 1.76 | 0.46875 | 3.7547 | 1747.3707 | 3075.3724
[22 empty] | Excavator with Bucket 50T | Machinery | HR | 131.2 | 50 | 2.624 | 16.3816 | 2149.2659
[22 empty] | Fuel | Material | LTR | 1.76 | 1.5625 | 1.1264 | 524.2112 | 922.6117
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 13.6 | 3.5294 | 60.2265 | 2890.8706
[22 empty] | Fuel | Material | LTR | 1.76 | 1.36 | 1.2941 | 602.2647 | 1059.9859
[9 empty] | 819.08 | 819.08 |  | 819.08 | [9 empty] | Backfilling & Compaction |  | M³ | 8.3027 |  | 8.3027 | 819.08 | 6800.5996 | 0 | 0 | 0 | 0 | 0
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 100 | 0.656 | 8.1908 | 537.3165
[22 empty] | Fuel | Material | LTR | 1.76 | 11.1111 | 0.1584 | 73.7172 | 129.7423
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 13.6 | 3.5294 | 60.2265 | 2890.8706
[22 empty] | Fuel | Material | LTR | 1.76 | 1.36 | 1.2941 | 602.2647 | 1059.9859
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 50 | 0.72 | 16.3816 | 589.7376
[22 empty] | Fuel | Material | LTR | 1.76 | 5.5556 | 0.3168 | 147.4344 | 259.4845
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 80 | 0.6 | 10.2385 | 491.448
[22 empty] | Fuel | Material | LTR | 1.76 | 8 | 0.22 | 102.385 | 180.1976
[22 empty] | Roller Compactor 10 Ton | Machinery | HR | 40 | 80 | 0.5 | 10.2385 | 409.54
[22 empty] | Fuel | Material | LTR | 1.76 | 5.7143 | 0.308 | 143.339 | 252.2766
Ponds 12 |  | Maximum depth from 2 - 5 meters | m³ | 428.89 | 164 | 70337.96 | 30.658 | 13148.9063 | 428.89 | 428.89 |  | 428.89 | 100% | 164 | 70337.96 | 30.658 | 13148.9063 |  | 13148.9063 | [7 empty] | 30.658 | 428.89 | 13148.9063 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 428.89 | 428.89 |  | 428.89 | [9 empty] | Rock Excavation & Disposal |  | M³ | 22.3553 |  | 22.3553 | 428.89 | 9587.9486 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Hydraulic Hammer 50T | Machinery | HR | 150.4 | 15 | 10.0267 | 28.5927 | 4300.3371
[22 empty] | Fuel | Material | LTR | 1.76 | 0.46875 | 3.7547 | 914.9653 | 1610.339
[22 empty] | Excavator with Bucket 50T | Machinery | HR | 131.2 | 50 | 2.624 | 8.5778 | 1125.4074
[22 empty] | Fuel | Material | LTR | 1.76 | 1.5625 | 1.1264 | 274.4896 | 483.1017
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 13.6 | 3.5294 | 31.536 | 1513.7294
[22 empty] | Fuel | Material | LTR | 1.76 | 1.36 | 1.2941 | 315.3603 | 555.0341
[9 empty] | 428.89 | 428.89 |  | 428.89 | [9 empty] | Backfilling & Compaction |  | M³ | 8.3027 |  | 8.3027 | 428.89 | 3560.9576 | 0 | 0 | 0 | 0 | 0
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 100 | 0.656 | 4.2889 | 281.3518
[22 empty] | Fuel | Material | LTR | 1.76 | 11.1111 | 0.1584 | 38.6001 | 67.9362
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 13.6 | 3.5294 | 31.536 | 1513.7294
[22 empty] | Fuel | Material | LTR | 1.76 | 1.36 | 1.2941 | 315.3603 | 555.0341
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 50 | 0.72 | 8.5778 | 308.8008
[22 empty] | Fuel | Material | LTR | 1.76 | 5.5556 | 0.3168 | 77.2002 | 135.8724
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 80 | 0.6 | 5.3611 | 257.334
[22 empty] | Fuel | Material | LTR | 1.76 | 8 | 0.22 | 53.6112 | 94.3558
[22 empty] | Roller Compactor 10 Ton | Machinery | HR | 40 | 80 | 0.5 | 5.3611 | 214.445
[22 empty] | Fuel | Material | LTR | 1.76 | 5.7143 | 0.308 | 75.0557 | 132.0981
Ponds 12 |  | Excavations from materials other than topsoil, rock, or artificial solids | m³ | 1 | 101 | 101 | 30.658 | 30.658 | 1 | 1 |  | 1 | 100% | 101 | 101 | 30.658 | 30.658 |  | 30.658 | [7 empty] | 30.658 | 1 | 30.658 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 1 | 1 |  | 1 | [9 empty] | Rock Excavation & Disposal |  | M³ | 22.3553 |  | 22.3553 | 1 | 22.3553 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Hydraulic Hammer 50T | Machinery | HR | 150.4 | 15 | 10.0267 | 0.066667 | 10.0267
[22 empty] | Fuel | Material | LTR | 1.76 | 0.46875 | 3.7547 | 2.1333 | 3.7547
[22 empty] | Excavator with Bucket 50T | Machinery | HR | 131.2 | 50 | 2.624 | 0.02 | 2.624
[22 empty] | Fuel | Material | LTR | 1.76 | 1.5625 | 1.1264 | 0.64 | 1.1264
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 13.6 | 3.5294 | 0.073529 | 3.5294
[22 empty] | Fuel | Material | LTR | 1.76 | 1.36 | 1.2941 | 0.73529 | 1.2941
[9 empty] | 1 | 1 |  | 1 | [9 empty] | Backfilling & Compaction |  | M³ | 8.3027 |  | 8.3027 | 1 | 8.3027 | 0 | 0 | 0 | 0 | 0
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 100 | 0.656 | 0.01 | 0.656
[22 empty] | Fuel | Material | LTR | 1.76 | 11.1111 | 0.1584 | 0.09 | 0.1584
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 13.6 | 3.5294 | 0.073529 | 3.5294
[22 empty] | Fuel | Material | LTR | 1.76 | 1.36 | 1.2941 | 0.73529 | 1.2941
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 50 | 0.72 | 0.02 | 0.72
[22 empty] | Fuel | Material | LTR | 1.76 | 5.5556 | 0.3168 | 0.18 | 0.3168
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 80 | 0.6 | 0.0125 | 0.6
[22 empty] | Fuel | Material | LTR | 1.76 | 8 | 0.22 | 0.125 | 0.22
[22 empty] | Roller Compactor 10 Ton | Machinery | HR | 40 | 80 | 0.5 | 0.0125 | 0.5
[22 empty] | Fuel | Material | LTR | 1.76 | 5.7143 | 0.308 | 0.175 | 0.308
Ponds 12 |  | Transporting surplus excavations to an approved location | m³ | 1 | 19 | 19 | 13.8333 | 13.8333 | 1 | 1 |  | 1 | 100% | 19 | 19 | 13.8333 | 13.8333 |  | 13.8333 | [7 empty] | 13.8333 | 1 | 13.8333 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 1 | 1 |  | 1 | [7 empty] | 0 | 02 | Soil Disposal |  | M³ | 13.8333 |  | 13.8333 | 1 | 13.8333 | 0 | 0 | 0 | 0 | 0
[21 empty] | 02 | Wheel Loader | Machinery | Hr | 65.6 | 100 | 0.656 | 0.01 | 0.656
[21 empty] | 02 | Fuel | Material | Litre | 1.76 | 11.1111 | 0.1584 | 0.09 | 0.1584
[21 empty] | 02 | Trailer Dump Truck 24 m³ | Machinery | Hr | 56 | 6.12 | 9.1503 | 0.1634 | 9.1503
[21 empty] | 02 | Fuel | Material | Litre | 1.76 | 0.47077 | 3.7386 | 2.1242 | 3.7386
[21 empty] | 02 | Unskilled Labour | Manpower | Hr | 13 | 100 | 0.13 | 0.01 | 0.13
Ponds 12 |  | Backfilling using materials selected from the excavation product other than topsoil or rock. | m³ | 1 | 23 | 23 | 7.5223 | 7.5223 | 1 | 1 |  | 1 | 100% | 23 | 23 | 7.5223 | 7.5223 |  | 7.5223 | [7 empty] | 7.5223 | 1 | 7.5223 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 1 | 1 |  | 1 | [7 empty] | 0 | 01 | Stockpile Operation |  | M³ | 0.79937 |  | 0.79937 | 1 | 0.79937 | 0 | 0 | 0 | 0 | 0
[21 empty] | 01 | Bulldozer CAT D9 | Machinery | Hr | 132.304 | 500 | 0.26461 | 0.002 | 0.26461
[21 empty] | 01 | Fuel | Material | Litre | 1.76 | 10.3093 | 0.17072 | 0.097 | 0.17072
[21 empty] | 01 | Water Tank Trailer 32,000 Litre | Machinery | Hr | 52 | 500 | 0.104 | 0.002 | 0.104
[21 empty] | 01 | Fuel | Material | Litre | 1.76 | 62.5 | 0.02816 | 0.016 | 0.02816
[21 empty] | 01 | Compaction Water | Material | M³ | 2.8 | 50 | 0.056 | 0.02 | 0.056
[21 empty] | 01 | Wheel Loader | Machinery | Hr | 65.6 | 500 | 0.1312 | 0.002 | 0.1312
[21 empty] | 01 | Fuel | Material | Litre | 1.76 | 55.5556 | 0.03168 | 0.018 | 0.03168
[21 empty] | 01 | Unskilled Labour | Manpower | Hr | 13 | 1000 | 0.013 | 0.001 | 0.013
[9 empty] | 1 | 1 |  | 1 | [7 empty] | 0 | 02 | Material Hauling |  | M³ | 4.1629 |  | 4.1629 | 1 | 4.1629 | 0 | 0 | 0 | 0 | 0
[21 empty] | 02 | Excavator with Bucket 50T | Machinery | Hr | 131.2 | 122.4 | 1.0719 | 0.0081699 | 1.0719
[21 empty] | 02 | Fuel | Material | Litre | 1.76 | 3.825 | 0.46013 | 0.26144 | 0.46013
[21 empty] | 02 | Trailer Dump Truck 24 m³ | Machinery | Hr | 56 | 30.6 | 1.8301 | 0.03268 | 1.8301
[21 empty] | 02 | Fuel | Material | Litre | 1.76 | 2.3538 | 0.74771 | 0.42484 | 0.74771
[21 empty] | 02 | Unskilled Labour | Manpower | Hr | 13 | 244.8 | 0.053105 | 0.004085 | 0.053105
[9 empty] | 1 | 1 |  | 1 | [7 empty] | 0 | 03 | Spreading & leveling |  | M³ | 0.70756 |  | 0.70756 | 1 | 0.70756 | 0 | 0 | 0 | 0 | 0
[21 empty] | 03 | Grader | Machinery | Hr | 90.4 | 180 | 0.50222 | 0.0055556 | 0.50222
[21 empty] | 03 | Fuel | Material | Litre | 1.76 | 8.5714 | 0.20533 | 0.11667 | 0.20533
[9 empty] | 1 | 1 |  | 1 | [7 empty] | 0 | 04 | Compaction |  | M³ | 1.8525 |  | 1.8525 | 1 | 1.8525 | 0 | 0 | 0 | 0 | 0
[21 empty] | 04 | Roller Compactor 10 Ton | Machinery | Hr | 40 | 80 | 0.5 | 0.0125 | 0.5
[21 empty] | 04 | Fuel | Material | Litre | 1.76 | 5.7143 | 0.308 | 0.175 | 0.308
[21 empty] | 04 | Water Tank Trailer 32,000 Litre | Machinery | Hr | 52 | 80 | 0.65 | 0.0125 | 0.65
[21 empty] | 04 | Fuel | Material | Litre | 1.76 | 10 | 0.176 | 0.1 | 0.176
[21 empty] | 04 | Compaction Water | Material | M³ | 2.8 | 50 | 0.056 | 0.02 | 0.056
[21 empty] | 04 | Unskilled Labour | Manpower | Hr | 13 | 80 | 0.1625 | 0.0125 | 0.1625
Ponds 12 |  | Backfilling with materials supplied from outside the city | m³ | 1 | 38 | 38 | 16.723 | 16.723 | 1 | 1 |  | 1 | 100% | 38 | 38 | 16.723 | 16.723 |  | 16.723 | [7 empty] | 16.723 | 1 | 16.723 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 1 | 1 |  | 1 | [7 empty] | 0 | 01 | Imported backfilling material |  | M³ | 10 |  | 10 | 1 | 10 | 0 | 0 | 0 | 0 | 0
[21 empty] | 01 | Backfilling Material | Material | M³ | 10 | 1 | 10 | 1 | 10
[9 empty] | 1 | 1 |  | 1 | [7 empty] | 0 | 02 | Material Hauling |  | M³ | 4.1629 |  | 4.1629 | 1 | 4.1629 | 0 | 0 | 0 | 0 | 0
[21 empty] | 02 | Excavator with Bucket 50T | Machinery | Hr | 131.2 | 122.4 | 1.0719 | 0.0081699 | 1.0719
[21 empty] | 02 | Fuel | Material | Litre | 1.76 | 3.825 | 0.46013 | 0.26144 | 0.46013
[21 empty] | 02 | Trailer Dump Truck 24 m³ | Machinery | Hr | 56 | 30.6 | 1.8301 | 0.03268 | 1.8301
[21 empty] | 02 | Fuel | Material | Litre | 1.76 | 2.3538 | 0.74771 | 0.42484 | 0.74771
[21 empty] | 02 | Unskilled Labour | Manpower | Hr | 13 | 244.8 | 0.053105 | 0.004085 | 0.053105
[9 empty] | 1 | 1 |  | 1 | [7 empty] | 0 | 03 | Spreading & leveling |  | M³ | 0.70756 |  | 0.70756 | 1 | 0.70756 | 0 | 0 | 0 | 0 | 0
[21 empty] | 03 | Grader | Machinery | Hr | 90.4 | 180 | 0.50222 | 0.0055556 | 0.50222
[21 empty] | 03 | Fuel | Material | Litre | 1.76 | 8.5714 | 0.20533 | 0.11667 | 0.20533
[9 empty] | 1 | 1 |  | 1 | [7 empty] | 0 | 04 | Compaction |  | M³ | 1.8525 |  | 1.8525 | 1 | 1.8525 | 0 | 0 | 0 | 0 | 0
[21 empty] | 04 | Roller Compactor 10 Ton | Machinery | Hr | 40 | 80 | 0.5 | 0.0125 | 0.5
[21 empty] | 04 | Fuel | Material | Litre | 1.76 | 5.7143 | 0.308 | 0.175 | 0.308
[21 empty] | 04 | Water Tank Trailer 32,000 Litre | Machinery | Hr | 52 | 80 | 0.65 | 0.0125 | 0.65
[21 empty] | 04 | Fuel | Material | Litre | 1.76 | 10 | 0.176 | 0.1 | 0.176
[21 empty] | 04 | Compaction Water | Material | M³ | 2.8 | 50 | 0.056 | 0.02 | 0.056
[21 empty] | 04 | Unskilled Labour | Manpower | Hr | 13 | 80 | 0.1625 | 0.0125 | 0.1625
Ponds 12 |  | Concrete type (C15), OP cement, in hygiene concrete | m³ | 60.15 | 730 | 43909.5 | 390 | 23458.5 | 60.15 | 60.15 |  | 60.15 | 100% | 730 | 43909.5 | 390 | 23458.5 |  | 23458.5 | [7 empty] | 390 | 60.15 | 23458.5 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 60.15 | 60.15 |  | 60.15 | [9 empty] | Concrete |  | M³ | 390 |  | 390 | 60.15 | 23458.5 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C15 | Material | M³ | 240 | 1 | 240 | 60.15 | 14436
[22 empty] | Workmanship plain concrete | SC | M³ | 150 | 1 | 150 | 60.15 | 9022.5
Ponds 12 |  | Concrete type (C20), OP cement, in construction | m³ | 381.95 | 881 | 336497.95 | 400 | 152780 | 381.95 | 381.95 |  | 381.95 | 100% | 881 | 336497.95 | 400 | 152780 |  | 152780 | [7 empty] | 400 | 381.95 | 152780 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 381.95 | 381.95 |  | 381.95 | [9 empty] | Concrete |  | M³ | 400 |  | 400 | 381.95 | 152780 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 1 | 250 | 381.95 | 95487.5
[22 empty] | Workmanship plain concrete | SC | M³ | 150 | 1 | 150 | 381.95 | 57292.5
Ponds 12 |  | So that the thickness of the blinding concrete does not exceed 100 mm | m³ | 60.15 | 1007 | 60571.05 | 400 | 24060 | 60.15 | 60.15 |  | 60.15 | 100% | 1007 | 60571.05 | 400 | 24060 |  | 24060 | [7 empty] | 400 | 60.15 | 24060 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 60.15 | 60.15 |  | 60.15 | [9 empty] | Concrete |  | M³ | 400 |  | 400 | 60.15 | 24060 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 1 | 250 | 60.15 | 15037.5
[22 empty] | Workmanship plain concrete | SC | M³ | 150 | 1 | 150 | 60.15 | 9022.5
Ponds 12 |  | The base slab is 300 - 500 mm thick | m³ | 233.76 | 1007 | 235396.32 | 400 | 93504 | 233.76 | 233.76 |  | 233.76 | 100% | 1007 | 235396.32 | 400 | 93504 |  | 93504 | [7 empty] | 400 | 233.76 | 93504 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 233.76 | 233.76 |  | 233.76 | [9 empty] | Concrete |  | M³ | 400 |  | 400 | 233.76 | 93504 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 1 | 250 | 233.76 | 58440
[22 empty] | Workmanship plain concrete | SC | M³ | 150 | 1 | 150 | 233.76 | 35064
Ponds 12 |  | Wall below the ground floor with a thickness of 150 - 300 mm | m³ | 148.19 | 1070 | 158563.3 | 800 | 118552 | 148.19 | 148.19 |  | 148.19 | 100% | 1070 | 158563.3 | 800 | 118552 |  | 118552 | [7 empty] | 800 | 148.19 | 118552 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 148.19 | 148.19 |  | 148.19 | [9 empty] | Concrete |  | M³ | 800 |  | 800 | 148.19 | 118552 | 0 | 0 | 0 | 0 | 0
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 1 | 350 | 148.19 | 51866.5
[22 empty] | Workmanship RC concrete | SC | M³ | 450 | 1 | 450 | 148.19 | 66685.5
Ponds 12 |  | The vertical level is 0.2 - 0.4 m wide | m³ | 203.59 | 1102 | 224356.18 | 800 | 162872 | 203.59 | 203.59 |  | 203.59 | 100% | 1102 | 224356.18 | 800 | 162872 |  | 162872 | [7 empty] | 800 | 203.59 | 162872 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 203.59 | 203.59 |  | 203.59 | [9 empty] | Concrete |  | M³ | 800 |  | 800 | 203.59 | 162872 | 0 | 0 | 0 | 0 | 0
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 1 | 350 | 203.59 | 71256.5
[22 empty] | Workmanship RC concrete | SC | M³ | 450 | 1 | 450 | 203.59 | 91615.5
Ponds 12 |  | The vertical level is 0.4 - 1.22 m wide | m³ | 1306.55 | 1102 | 1439818.1 | 800 | 1045240 | 1306.55 | 1306.55 |  | 1306.55 | 100% | 1102 | 1439818.1 | 800 | 1045240 |  | 1045240 | [7 empty] | 800 | 1306.55 | 1045240 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 1306.55 | 1306.55 |  | 1306.55 | [9 empty] | Concrete |  | M³ | 800 |  | 800 | 1306.55 | 1045240 | 0 | 0 | 0 | 0 | 0
[22 empty] | Concrete Ready-mix C35 SRC | Material | M³ | 350 | 1 | 350 | 1306.55 | 457292.5
[22 empty] | Workmanship RC concrete | SC | M³ | 450 | 1 | 450 | 1306.55 | 587947.5
Ponds 12 |  | Power floating finishes | m² | 325.83 | 44 | 14336.52 | 20 | 6516.6 | 325.83 | 325.83 |  | 325.83 | 100% | 44 | 14336.52 | 20 | 6516.6 |  | 6516.6 | [7 empty] | 20 | 325.83 | 6516.6 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 325.83 | 325.83 |  | 325.83 | [9 empty] | Power floating finishes |  | M² | 20 |  | 20 | 325.83 | 6516.6 | 0 | 0 | 0 | 0 | 0
[22 empty] | Screed mortar | Material | M³ | 200 | 20 | 10 | 16.2915 | 3258.3
[22 empty] | Screed workmanship | SC | M³ | 200 | 20 | 10 | 16.2915 | 3258.3
Ponds 12 |  | 12 mm in diameter | t | 55.53 | 5791 | 321574.23 | 2500 | 138825 | 55.53 | 55.53 |  | 55.53 | 100% | 5791 | 321574.23 | 2500 | 138825 |  | 138825 | [7 empty] | 2500 | 55.53 | 138825 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 55.53 | 55.53 |  | 55.53 | [9 empty] | Steel RFT |  | Ton | 2500 |  | 2500 | 55.53 | 138825 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply of steel rebar | Material | Ton | 2500 | 1 | 2500 | 55.53 | 138825
Ponds 12 |  | Peripheral lining from all sides, including the filament, the insulating bitumen layer, screed leveling, etc. according to the plans. | m² | 1129.11 | 57 | 64359.27 | 60 | 67746.6 | 1129.11 | 1129.11 |  | 1129.11 | 100% | 57 | 64359.27 | 60 | 67746.6 |  | 67746.6 | [7 empty] | 60 | 1129.11 | 67746.6 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 1129.11 | 1129.11 |  | 1129.11 | [9 empty] | Waterproofing works |  | M² | 40 |  | 40 | 1129.11 | 45164.4 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply & apply external waterproofing | SC | M² | 40 | 1 | 40 | 1129.11 | 45164.4
[9 empty] | 1129.11 | 1129.11 |  | 1129.11 | [9 empty] | Screed works |  | M² | 20 |  | 20 | 1129.11 | 22582.2 | 0 | 0 | 0 | 0 | 0
[22 empty] | Screed mortar | Material | M³ | 200 | 20 | 10 | 56.4555 | 11291.1
[22 empty] | Screed workmanship | SC | M³ | 200 | 20 | 10 | 56.4555 | 11291.1
Ponds 12 |  | Entry road 5 m wide | m² | 9402.63 | 57 | 535949.91 | 92.7095 | 871713.126 | 9402.63 | 9402.63 |  | 9402.63 | 100% | 57 | 535949.91 | 92.7095 | 871713.126 |  | 871713.126 | [7 empty] | 92.7095 | 9402.63 | 871713.126 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 9402.63 | 9402.63 |  | 9402.63 | [9 empty] | Supply & Apply basecourse (20 cm) |  | M² | 13.8 |  | 13.8 | 9402.63 | 129756.294 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Basecourse Type 1&2 | Material | M³ | 25 | 5 | 5 | 1880.526 | 47013.15
[22 empty] | Subbase Transportation 0-60 KM | Material | M³ | 17 | 5 | 3.4 | 1880.526 | 31968.942
[22 empty] | Apply Basecourse 16-20 cm (1 Layer) | SC | M² | 5.4 | 1 | 5.4 | 9402.63 | 50774.202
[9 empty] | 9402.63 | 9402.63 |  | 9402.63 | [9 empty] | MC1 |  | M² | 3.45 |  | 3.45 | 9402.63 | 32439.0735 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply MC1 | Material | Ton | 2450 | 1000 | 2.45 | 9.4026 | 23036.4435
[22 empty] | Spray MC1 | SC | M² | 1 | 1 | 1 | 9402.63 | 9402.63
[9 empty] | 9402.63 | 9402.63 |  | 9402.63 | [9 empty] | Binder course depth (7 cm) |  | M² | 40.992 |  | 40.992 | 9402.63 | 385432.609 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Asphalt Binder Course | Material | Ton | 200 | 5.9524 | 33.6 | 1579.6418 | 315928.368
[22 empty] | Asphalt Transportation 0-60 KM | Material | Ton | 19 | 5.9524 | 3.192 | 1579.6418 | 30013.195
[22 empty] | Apply Asphalt Binder Course 7 CM | SC | M² | 4.2 | 1 | 4.2 | 9402.63 | 39491.046
[9 empty] | 9402.63 | 9402.63 |  | 9402.63 | [9 empty] | RC |  | M² | 4.1875 |  | 4.1875 | 9402.63 | 39373.5131 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply RC2 | Material | Ton | 2550 | 800 | 3.1875 | 11.7533 | 29970.8831
[22 empty] | Spray RC2 | SC | M² | 1 | 1 | 1 | 9402.63 | 9402.63
[9 empty] | 9402.63 | 9402.63 |  | 9402.63 | [9 empty] | Wearing course depth (5 cm) |  | M² | 30.28 |  | 30.28 | 9402.63 | 284711.6364 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Asphalt Binder Course | Material | Ton | 200 | 8.3333 | 24 | 1128.3156 | 225663.12
[22 empty] | Asphalt Transportation 0-60 KM | Material | Ton | 19 | 8.3333 | 2.28 | 1128.3156 | 21437.9964
[22 empty] | Apply Asphalt Wearing Course 3-5 CM | SC | M² | 4 | 1 | 4 | 9402.63 | 37610.52
Ponds 12 |  | Entry corridor 3 m wide | m² | 29792.11 | 57 | 1698150.27 | 92.7095 | 2762011.622 | 29792.11 | 29792.11 |  | 29792.11 | 100% | 57 | 1698150.27 | 92.7095 | 2762011.622 |  | 2762011.622 | [7 empty] | 92.7095 | 29792.11 | 2762011.622 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 29792.11 | 29792.11 |  | 29792.11 | [9 empty] | Supply & Apply basecourse (20 cm) |  | M² | 13.8 |  | 13.8 | 29792.11 | 411131.118 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Basecourse Type 1&2 | Material | M³ | 25 | 5 | 5 | 5958.422 | 148960.55
[22 empty] | Subbase Transportation 0-60 KM | Material | M³ | 17 | 5 | 3.4 | 5958.422 | 101293.174
[22 empty] | Apply Basecourse 16-20 cm (1 Layer) | SC | M² | 5.4 | 1 | 5.4 | 29792.11 | 160877.394
[9 empty] | 29792.11 | 29792.11 |  | 29792.11 | [9 empty] | MC1 |  | M² | 3.45 |  | 3.45 | 29792.11 | 102782.7795 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply MC1 | Material | Ton | 2450 | 1000 | 2.45 | 29.7921 | 72990.6695
[22 empty] | Spray MC1 | SC | M² | 1 | 1 | 1 | 29792.11 | 29792.11
[9 empty] | 29792.11 | 29792.11 |  | 29792.11 | [9 empty] | Binder course depth (7 cm) |  | M² | 40.992 |  | 40.992 | 29792.11 | 1221238.1731 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Asphalt Binder Course | Material | Ton | 200 | 5.9524 | 33.6 | 5005.0745 | 1001014.896
[22 empty] | Asphalt Transportation 0-60 KM | Material | Ton | 19 | 5.9524 | 3.192 | 5005.0745 | 95096.4151
[22 empty] | Apply Asphalt Binder Course 7 CM | SC | M² | 4.2 | 1 | 4.2 | 29792.11 | 125126.862
[9 empty] | 29792.11 | 29792.11 |  | 29792.11 | [9 empty] | RC |  | M² | 4.1875 |  | 4.1875 | 29792.11 | 124754.4606 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply RC2 | Material | Ton | 2550 | 800 | 3.1875 | 37.2401 | 94962.3506
[22 empty] | Spray RC2 | SC | M² | 1 | 1 | 1 | 29792.11 | 29792.11
[9 empty] | 29792.11 | 29792.11 |  | 29792.11 | [9 empty] | Wearing course depth (5 cm) |  | M² | 30.28 |  | 30.28 | 29792.11 | 902105.0908 | 0 | 0 | 0 | 0 | 0
[22 empty] | Supply Asphalt Binder Course | Material | Ton | 200 | 8.3333 | 24 | 3575.0532 | 715010.64
[22 empty] | Asphalt Transportation 0-60 KM | Material | Ton | 19 | 8.3333 | 2.28 | 3575.0532 | 67926.0108
[22 empty] | Apply Asphalt Wearing Course 3-5 CM | SC | M² | 4 | 1 | 4 | 29792.11 | 119168.44
Ponds 12 |  | Culvert 3000 x 700 mm | nr | 1 | 296 | 296 | 5821 | 5821 | 1 | 1 |  | 1 | 100% | 296 | 296 | 5821 | 5821 |  | 5821 | [7 empty] | 5821 | 1 | 5821 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 1 | 1 |  | 1 | [9 empty] | Culverts |  | Ea | 5821 |  | 5821 | 1 | 5821 | 0 | 0 | 0 | 0 | 0
[22 empty] | Precast Box Conduit Supply | Material | M³ | 2200 | 0.38462 | 5720 | 2.6 | 5720
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 5 | 16 | 0.2 | 16
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.2 | 85 | 5 | 85
Ponds 12 |  | Culvert 2500 x 600 mm | nr | 1 | 212 | 212 | 4721 | 4721 | 1 | 1 |  | 1 | 100% | 212 | 212 | 4721 | 4721 |  | 4721 | [7 empty] | 4721 | 1 | 4721 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 1 | 1 |  | 1 | [9 empty] | Culverts |  | Ea | 4721 |  | 4721 | 1 | 4721 | 0 | 0 | 0 | 0 | 0
[22 empty] | Precast Box Conduit Supply | Material | M³ | 2200 | 0.47619 | 4620 | 2.1 | 4620
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 5 | 16 | 0.2 | 16
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.2 | 85 | 5 | 85
Ponds 12 |  | Culvert 3500 x 800 mm | nr | 1 | 395 | 395 | 6701 | 6701 | 1 | 1 |  | 1 | 100% | 395 | 395 | 6701 | 6701 |  | 6701 | [7 empty] | 6701 | 1 | 6701 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 1 | 1 |  | 1 | [9 empty] | Culverts |  | Ea | 6701 |  | 6701 | 1 | 6701 | 0 | 0 | 0 | 0 | 0
[22 empty] | Precast Box Conduit Supply | Material | M³ | 2200 | 0.33333 | 6600 | 3 | 6600
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 5 | 16 | 0.2 | 16
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.2 | 85 | 5 | 85
Ponds 12 |  | Culvert 2000 x 600 mm | nr | 1 | 168 | 168 | 4061 | 4061 | 1 | 1 |  | 1 | 100% | 168 | 168 | 4061 | 4061 |  | 4061 | [7 empty] | 4061 | 1 | 4061 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 1 | 1 |  | 1 | [9 empty] | Culverts |  | Ea | 4061 |  | 4061 | 1 | 4061 | 0 | 0 | 0 | 0 | 0
[22 empty] | Precast Box Conduit Supply | Material | M³ | 2200 | 0.55556 | 3960 | 1.8 | 3960
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 5 | 16 | 0.2 | 16
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.2 | 85 | 5 | 85
Ponds 12 |  | Culvert 2500 x 700 mm | nr | 1 | 247 | 247 | 5381 | 5381 | 1 | 1 |  | 1 | 100% | 247 | 247 | 5381 | 5381 |  | 5381 | [7 empty] | 5381 | 1 | 5381 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 1 | 1 |  | 1 | [9 empty] | Culverts |  | Ea | 5381 |  | 5381 | 1 | 5381 | 0 | 0 | 0 | 0 | 0
[22 empty] | Precast Box Conduit Supply | Material | M³ | 2200 | 0.41667 | 5280 | 2.4 | 5280
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 5 | 16 | 0.2 | 16
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.2 | 85 | 5 | 85
Ponds 12 |  | Culvert 3000 x 750 mm | nr | 1 | 317 | 317 | 6481 | 6481 | 1 | 1 |  | 1 | 100% | 317 | 317 | 6481 | 6481 |  | 6481 | [7 empty] | 6481 | 1 | 6481 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 1 | 1 |  | 1 | [9 empty] | Culverts |  | Ea | 6481 |  | 6481 | 1 | 6481 | 0 | 0 | 0 | 0 | 0
[22 empty] | Precast Box Conduit Supply | Material | M³ | 2200 | 0.34483 | 6380 | 2.9 | 6380
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 5 | 16 | 0.2 | 16
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.2 | 85 | 5 | 85
Ponds 12 |  | Culvert 3000 x 800 mm | nr | 1 | 338 | 338 | 6261 | 6261 | 1 | 1 |  | 1 | 100% | 338 | 338 | 6261 | 6261 |  | 6261 | [7 empty] | 6261 | 1 | 6261 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 1 | 1 |  | 1 | [9 empty] | Culverts |  | Ea | 6261 |  | 6261 | 1 | 6261 | 0 | 0 | 0 | 0 | 0
[22 empty] | Precast Box Conduit Supply | Material | M³ | 2200 | 0.35714 | 6160 | 2.8 | 6160
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 5 | 16 | 0.2 | 16
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.2 | 85 | 5 | 85
Ponds 12 |  | Culvert 2500 x 800 mm | nr | 1 | 282 | 282 | 5821 | 5821 | 1 | 1 |  | 1 | 100% | 282 | 282 | 5821 | 5821 |  | 5821 | [7 empty] | 5821 | 1 | 5821 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 1 | 1 |  | 1 | [9 empty] | Culverts |  | Ea | 5821 |  | 5821 | 1 | 5821 | 0 | 0 | 0 | 0 | 0
[22 empty] | Precast Box Conduit Supply | Material | M³ | 2200 | 0.38462 | 5720 | 2.6 | 5720
[22 empty] | Mobile Crane 50 ton | Machinery | HR | 80 | 5 | 16 | 0.2 | 16
[22 empty] | Skilled Labor | Manpower | HR | 17 | 0.2 | 85 | 5 | 85
Ponds 12 |  | Additional excavation and backfilling works, drilling into rock to various depths, including disposal of waste to approved locations, warning tapes, and dewatering. | m³ | 1 | 101 | 101 | 30.658 | 30.658 | 1 | 1 |  | 1 | 100% | 101 | 101 | 30.658 | 30.658 |  | 30.658 | [7 empty] | 30.658 | 1 | 30.658 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 1 | 1 |  | 1 | [9 empty] | Rock Excavation & Disposal |  | M³ | 22.3553 |  | 22.3553 | 1 | 22.3553 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Hydraulic Hammer 50T | Machinery | HR | 150.4 | 15 | 10.0267 | 0.066667 | 10.0267
[22 empty] | Fuel | Material | LTR | 1.76 | 0.46875 | 3.7547 | 2.1333 | 3.7547
[22 empty] | Excavator with Bucket 50T | Machinery | HR | 131.2 | 50 | 2.624 | 0.02 | 2.624
[22 empty] | Fuel | Material | LTR | 1.76 | 1.5625 | 1.1264 | 0.64 | 1.1264
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 13.6 | 3.5294 | 0.073529 | 3.5294
[22 empty] | Fuel | Material | LTR | 1.76 | 1.36 | 1.2941 | 0.73529 | 1.2941
[9 empty] | 1 | 1 |  | 1 | [9 empty] | Backfilling & Compaction |  | M³ | 8.3027 |  | 8.3027 | 1 | 8.3027 | 0 | 0 | 0 | 0 | 0
[22 empty] | Wheel Loader | Machinery | HR | 65.6 | 100 | 0.656 | 0.01 | 0.656
[22 empty] | Fuel | Material | LTR | 1.76 | 11.1111 | 0.1584 | 0.09 | 0.1584
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 13.6 | 3.5294 | 0.073529 | 3.5294
[22 empty] | Fuel | Material | LTR | 1.76 | 1.36 | 1.2941 | 0.73529 | 1.2941
[22 empty] | Skid steer Loader with bucket | Machinery | HR | 36 | 50 | 0.72 | 0.02 | 0.72
[22 empty] | Fuel | Material | LTR | 1.76 | 5.5556 | 0.3168 | 0.18 | 0.3168
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 80 | 0.6 | 0.0125 | 0.6
[22 empty] | Fuel | Material | LTR | 1.76 | 8 | 0.22 | 0.125 | 0.22
[22 empty] | Roller Compactor 10 Ton | Machinery | HR | 40 | 80 | 0.5 | 0.0125 | 0.5
[22 empty] | Fuel | Material | LTR | 1.76 | 5.7143 | 0.308 | 0.175 | 0.308
D.S 14 |  | Road crossings for sewage pipes with a diameter of 300 mm | m |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
D.S 14 |  | Road crossings for sewage pipes with a diameter of 500 mm | m |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
D.S 14 |  | Road crossings for wastewater pipes with a diameter of 800 mm | m |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
D.S 14 |  | Road crossings for drinking water pipes with a diameter of 250 mm | m |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
D.S 14 |  | Road crossings for drinking water pipes, diameter 500 mm | m |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
D.S 14 |  | Road crossings for drinking water pipes, diameter 800 mm | m |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
D.S 14 |  | Road crossings for irrigation water pipes with a diameter of 250 mm | m |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
D.S 14 |  | Road crossings for irrigation water pipes with a diameter of 500 mm | m |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
D.S 14 |  | Road crossings for irrigation water pipes with a diameter of 800 mm | m |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
D.S 14 |  | Packaging of cross-section pipes: |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
D.S 14 |  | Supply and installation of drinking water, irrigation and sewage pipes crossing the roads, with installation with surrounding supports and closing them on both sides according to the plans, specifications and requirements of the concerned authority. |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
D.S 14 |  | uPVC pipes 300mm diameter | m | 1281.4 | 427 | 547157.8 | 156.1661 | 200111.1928 | 1281.4 | 1281.4 |  | 1281.4 | 100% | 427 | 547157.8 | 156.1661 | 200111.1928 |  | 200111.1928 | [7 empty] | 156.1661 | 1281.4 | 200111.1928 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 1281.4 | 1281.4 |  | 1281.4 | [9 empty] | Excavation ( W= 1.0 & d= 1.5 ) |  | M | 7.5827 |  | 7.5827 | 1281.4 | 9716.5095 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 66.6667 | 0.84 | 19.221 | 1076.376
[22 empty] | Fuel | Material | LTR | 1.76 | 4.7619 | 0.3696 | 269.094 | 473.6054
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 13.6 | 3.5294 | 94.2206 | 4522.5882
[22 empty] | Fuel | Material | LTR | 1.76 | 1.36 | 1.2941 | 942.2059 | 1658.2824
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 25.628 | 589.444
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 76.884 | 135.3158
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 66.6667 | 0.72 | 19.221 | 922.608
[22 empty] | Fuel | Material | LTR | 1.76 | 6.6667 | 0.264 | 192.21 | 338.2896
[9 empty] | 1281.4 | 1281.4 |  | 1281.4 | [9 empty] | Pipe Laying & Protection |  | M | 143.5833 |  | 143.5833 | 1281.4 | 183987.6833 | 0 | 0 | 0 | 0 | 0
[22 empty] | UPVC Pipe 300 mm | Material | M | 80 | 1 | 80 | 1281.4 | 102512
[22 empty] | UPVC Fitting 300 mm | Material | M | 8 | 1 | 8 | 1281.4 | 10251.2
[22 empty] | Skilled Labor | Manpower | HR | 17 | 2 | 8.5 | 640.7 | 10891.9
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 2 | 6.5 | 640.7 | 8329.1
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 10 | 25 | 128.14 | 32035
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 10 | 15 | 128.14 | 19221
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 4.2713 | 747.4833
[9 empty] | 1281.4 | 1281.4 |  | 1281.4 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 1281.4 | 6407 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 1281.4 | 6407
D.S 14 |  | uPVC pipes 315mm diameter | m | 2300.8 | 454 | 1044563.2 | 173.1661 | 398420.4772 | 2300.8 | 2300.8 |  | 2300.8 | 100% | 454 | 1044563.2 | 173.1661 | 398420.4772 |  | 398420.4772 | [7 empty] | 173.1661 | 2300.8 | 398420.4772 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 2300.8 | 2300.8 |  | 2300.8 | [9 empty] | Excavation ( W= 1.0 & d= 1.5 ) |  | M | 7.5827 |  | 7.5827 | 2300.8 | 17446.3438 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 66.6667 | 0.84 | 34.512 | 1932.672
[22 empty] | Fuel | Material | LTR | 1.76 | 4.7619 | 0.3696 | 483.168 | 850.3757
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 13.6 | 3.5294 | 169.1765 | 8120.4706
[22 empty] | Fuel | Material | LTR | 1.76 | 1.36 | 1.2941 | 1691.7647 | 2977.5059
[22 empty] | Plate Compactor | Machinery | HR | 23 | 50 | 0.46 | 46.016 | 1058.368
[22 empty] | Fuel | Material | LTR | 1.76 | 16.6667 | 0.1056 | 138.048 | 242.9645
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 66.6667 | 0.72 | 34.512 | 1656.576
[22 empty] | Fuel | Material | LTR | 1.76 | 6.6667 | 0.264 | 345.12 | 607.4112
[9 empty] | 2300.8 | 2300.8 |  | 2300.8 | [9 empty] | Pipe Laying & Protection |  | M | 160.5833 |  | 160.5833 | 2300.8 | 369470.1333 | 0 | 0 | 0 | 0 | 0
[22 empty] | UPVC Pipe 315 mm | Material | M | 95 | 1 | 95 | 2300.8 | 218576
[22 empty] | UPVC Fitting 315 mm | Material | M | 10 | 1 | 10 | 2300.8 | 23008
[22 empty] | Skilled Labor | Manpower | HR | 17 | 2 | 8.5 | 1150.4 | 19556.8
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 2 | 6.5 | 1150.4 | 14955.2
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 10 | 25 | 230.08 | 57520
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 10 | 15 | 230.08 | 34512
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 7.6693 | 1342.1333
[9 empty] | 2300.8 | 2300.8 |  | 2300.8 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 2300.8 | 11504 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 2300.8 | 11504
D.S 14 |  | uPVC pipes 400mm diameter | m | 3801.8 | 584 | 2220251.2 | 227.1351 | 863522.1799 | 3801.8 | 3801.8 |  | 3801.8 | 100% | 584 | 2220251.2 | 227.1351 | 863522.1799 |  | 863522.1799 | [7 empty] | 227.1351 | 3801.8 | 863522.1799 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 3801.8 | 3801.8 |  | 3801.8 | [9 empty] | Excavation ( W= 1.2 & d= 1.5 ) |  | M | 9.5518 |  | 9.5518 | 3801.8 | 36313.8633 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 55.5556 | 1.008 | 68.4324 | 3832.2144
[22 empty] | Fuel | Material | LTR | 1.76 | 3.9683 | 0.44352 | 958.0536 | 1686.1743
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 11.3333 | 4.2353 | 335.4529 | 16101.7412
[22 empty] | Fuel | Material | LTR | 1.76 | 1.1333 | 1.5529 | 3354.5294 | 5903.9718
[22 empty] | Plate Compactor | Machinery | HR | 23 | 25 | 0.92 | 152.072 | 3497.656
[22 empty] | Fuel | Material | LTR | 1.76 | 8.3333 | 0.2112 | 456.216 | 802.9402
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 55.5556 | 0.864 | 68.4324 | 3284.7552
[22 empty] | Fuel | Material | LTR | 1.76 | 5.5556 | 0.3168 | 684.324 | 1204.4102
[9 empty] | 3801.8 | 3801.8 |  | 3801.8 | [9 empty] | Pipe Laying & Protection |  | M | 212.5833 |  | 212.5833 | 3801.8 | 808199.3167 | 0 | 0 | 0 | 0 | 0
[22 empty] | UPVC Pipe 400 mm | Material | M | 135 | 1 | 135 | 3801.8 | 513243
[22 empty] | UPVC Fitting 400 mm | Material | M | 14 | 1 | 14 | 3801.8 | 53225.2
[22 empty] | Skilled Labor | Manpower | HR | 17 | 2 | 8.5 | 1900.9 | 32315.3
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 2 | 6.5 | 1900.9 | 24711.7
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 8.3333 | 30 | 456.216 | 114054
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 8.3333 | 18 | 456.216 | 68432.4
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 12.6727 | 2217.7167
[9 empty] | 3801.8 | 3801.8 |  | 3801.8 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 3801.8 | 19009 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 3801.8 | 19009
D.S 14 |  | uPVC pipes 600mm diameter | m | 830 | 1345 | 1116350 | 399.9419 | 331951.8105 | 830 | 830 |  | 830 | 100% | 1345 | 1116350 | 399.9419 | 331951.8105 |  | 331951.8105 | [7 empty] | 399.9419 | 830 | 331951.8105 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 830 | 830 |  | 830 | [9 empty] | Excavation ( W= 1.6 & d= 1.5 ) |  | M | 12.3586 |  | 12.3586 | 830 | 10257.6439 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 41.6667 | 1.344 | 19.92 | 1115.52
[22 empty] | Fuel | Material | LTR | 1.76 | 2.9762 | 0.59136 | 278.88 | 490.8288
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 8.5 | 5.6471 | 97.6471 | 4687.0588
[22 empty] | Fuel | Material | LTR | 1.76 | 0.85 | 2.0706 | 976.4706 | 1718.5882
[22 empty] | Plate Compactor | Machinery | HR | 23 | 25 | 0.92 | 33.2 | 763.6
[22 empty] | Fuel | Material | LTR | 1.76 | 8.3333 | 0.2112 | 99.6 | 175.296
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 41.6667 | 1.152 | 19.92 | 956.16
[22 empty] | Fuel | Material | LTR | 1.76 | 4.1667 | 0.4224 | 199.2 | 350.592
[9 empty] | 830 | 830 |  | 830 | [9 empty] | Pipe Laying & Protection |  | M | 382.5833 |  | 382.5833 | 830 | 317544.1667 | 0 | 0 | 0 | 0 | 0
[22 empty] | UPVC Pipe 600 mm | Material | M | 275 | 1 | 275 | 830 | 228250
[22 empty] | UPVC Fitting 600 mm | Material | M | 28 | 1 | 28 | 830 | 23240
[22 empty] | Skilled Labor | Manpower | HR | 17 | 2 | 8.5 | 415 | 7055
[22 empty] | Unskilled Labour | Manpower | HR | 13 | 2 | 6.5 | 415 | 5395
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 6.25 | 40 | 132.8 | 33200
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 6.25 | 24 | 132.8 | 19920
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 2.7667 | 484.1667
[9 empty] | 830 | 830 |  | 830 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 830 | 4150 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 830 | 4150
D.S 14 |  | GRP pipes 600mm diameter | m |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
D.S 14 |  | GRP pipes 800mm diameter | m | 1925 | 859 | 1653575 | 640.5556 | 1233069.6145 | 1925 | 1925 |  | 1925 | 100% | 859 | 1653575 | 640.5556 | 1233069.6145 |  | 1233069.6145 | [7 empty] | 640.5556 | 1925 | 1233069.6145 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 1925 | 1925 |  | 1925 | [9 empty] | Excavation ( W= 1.8 & d= 2.0 ) |  | M | 17.9723 |  | 17.9723 | 1925 | 34596.6979 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 27.7778 | 2.016 | 69.3 | 3880.8
[22 empty] | Fuel | Material | LTR | 1.76 | 1.9841 | 0.88704 | 970.2 | 1707.552
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 5.6667 | 8.4706 | 339.7059 | 16305.8824
[22 empty] | Fuel | Material | LTR | 1.76 | 0.56667 | 3.1059 | 3397.0588 | 5978.8235
[22 empty] | Plate Compactor | Machinery | HR | 23 | 25 | 0.92 | 77 | 1771
[22 empty] | Fuel | Material | LTR | 1.76 | 8.3333 | 0.2112 | 231 | 406.56
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 27.7778 | 1.728 | 69.3 | 3326.4
[22 empty] | Fuel | Material | LTR | 1.76 | 2.7778 | 0.6336 | 693 | 1219.68
[9 empty] | 1925 | 1925 |  | 1925 | [9 empty] | Pipe Laying & Protection |  | M | 617.5833 |  | 617.5833 | 1925 | 1188847.9167 | 0 | 0 | 0 | 0 | 0
[22 empty] | GRP Pipe 800 mm | Material | M | 430 | 1 | 430 | 1925 | 827750
[22 empty] | GRP Fitting 800 mm | Material | M | 43 | 1 | 43 | 1925 | 82775
[22 empty] | Workmanship GRP pipe 800 mm | SC | M | 72 | 1 | 72 | 1925 | 138600
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 5.5556 | 45 | 346.5 | 86625
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 5.5556 | 27 | 346.5 | 51975
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 6.4167 | 1122.9167
[9 empty] | 1925 | 1925 |  | 1925 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 1925 | 9625 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 1925 | 9625
D.S 14 |  | GRP pipes 1000mm diameter | m | 177 | 1147 | 203019 | 802.4269 | 142029.5575 | 177 | 177 |  | 177 | 100% | 1147 | 203019 | 802.4269 | 142029.5575 |  | 142029.5575 | [7 empty] | 802.4269 | 177 | 142029.5575 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 177 | 177 |  | 177 | [9 empty] | Excavation ( W= 2.0 & d= 2.0 ) |  | M | 19.8435 |  | 19.8435 | 177 | 3512.3075 | 0 | 0 | 0 | 0 | 0
[22 empty] | Excavator with Bucket 20T | Machinery | HR | 56 | 25 | 2.24 | 7.08 | 396.48
[22 empty] | Fuel | Material | LTR | 1.76 | 1.7857 | 0.9856 | 99.12 | 174.4512
[22 empty] | Dump Truck 16 m³ | Machinery | HR | 48 | 5.1 | 9.4118 | 34.7059 | 1665.8824
[22 empty] | Fuel | Material | LTR | 1.76 | 0.51 | 3.451 | 347.0588 | 610.8235
[22 empty] | Plate Compactor | Machinery | HR | 23 | 25 | 0.92 | 7.08 | 162.84
[22 empty] | Fuel | Material | LTR | 1.76 | 8.3333 | 0.2112 | 21.24 | 37.3824
[22 empty] | Water Tanker 18,000 Litre (6x6) | Machinery | HR | 48 | 25 | 1.92 | 7.08 | 339.84
[22 empty] | Fuel | Material | LTR | 1.76 | 2.5 | 0.704 | 70.8 | 124.608
[9 empty] | 177 | 177 |  | 177 | [9 empty] | Pipe Laying & Protection |  | M | 777.5833 |  | 777.5833 | 177 | 137632.25 | 0 | 0 | 0 | 0 | 0
[22 empty] | GRP Pipe 1000 mm | Material | M | 557 | 1 | 557 | 177 | 98589
[22 empty] | GRP Fitting 1000 mm | Material | M | 60 | 1 | 60 | 177 | 10620
[22 empty] | Workmanship GRP pipe 1000 mm | SC | M | 80 | 1 | 80 | 177 | 14160
[22 empty] | Supply Plain Concrete C25 | Material | M³ | 250 | 5 | 50 | 35.4 | 8850
[22 empty] | Trench Concrete workmanship | SC | M³ | 150 | 5 | 30 | 35.4 | 5310
[22 empty] | Warning Tape 250 mic 305 m roll | Material | Roll | 175 | 300 | 0.58333 | 0.59 | 103.25
[9 empty] | 177 | 177 |  | 177 | [9 empty] | Testing & Commissioning |  | M | 5 |  | 5 | 177 | 885 | 0 | 0 | 0 | 0 | 0
[22 empty] | Pipe Testing and Commissioning | SC | M | 5 | 1 | 5 | 177 | 885
LS 15 |  | Supply the following plants and trees Ref.Dwg No.DAM3-01-001-CH2-TS7-1-LSP-TEN-0221 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
LS 15 |  | Phoenix Dactylifera(PD) (300-350 cm height) | nr | 258 | 4784 | 1234272 | 1850 | 477300 | 258 | 258 |  | 258 | 100% | 4784 | 1234272 | 1850 | 477300 |  | 477300 | [7 empty] | 1850 | 258 | 477300 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 258 | 258 |  | 258 | [7 empty] | 0 | 01 | Phoenix Dactylifera(PD) (300-350 cm height) |  | Ea | 1850 |  | 1850 | 258 | 477300 | 0 | 0 | 0 | 0 | 0
[21 empty] | 01 | Phoenix Dactylifera(PD) (300-350 cm height) | SC | Ea | 1850 | 1 | 1850 | 258 | 477300
LS 15 |  | Shrubs and Vines, (2Lt pot, 30-40cm height) |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
LS 15 |  | Atriplex canescens 2Lt pot, 30-40cm height | nr | 200 | 227 | 45400 | 120 | 24000 | 200 | 200 |  | 200 | 100% | 227 | 45400 | 120 | 24000 |  | 24000 |  |  | Atriplex canescens 2Lt pot, 30-40cm height |  |  |  |  | 120 | 200 | 24000 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 200 | 200 |  | 200 | [7 empty] | 0 | 01 | Atriplex canescens 2Lt pot, 30-40cm height |  | Ea | 120 |  | 120 | 200 | 24000 | 0 | 0 | 0 | 0 | 0
[21 empty] | 01 |  | SC | Ea | 120 | 1 | 120 | 200 | 24000
LS 15 |  | Ref.Drg No.DAM3-01-001-AAD-TS8-1-LSP-DRW-0001 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
LS 15 |  | Peltophorum Inerme |  | 45.75 | 3524 | 161223 | 750 | 34312.5 | 45.75 | 45.75 |  | 45.75 | 100% | 3524 | 161223 | 750 | 34312.5 |  | 34312.5 |  |  | Peltophorum Inerme |  |  |  |  | 750 | 45.75 | 34312.5 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 45.75 | 45.75 |  | 45.75 | [7 empty] | 0 | 01 | Peltophorum Inerme |  | Ea | 750 |  | 750 | 45.75 | 34312.5 | 0 | 0 | 0 | 0 | 0
[21 empty] | 01 |  | SC | Ea | 750 | 1 | 750 | 45.75 | 34312.5
LS 15 |  | Palm trees (in meters) |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
LS 15 |  | Phoenix Dactylifera(PD) | nr | 258 | 4280 | 1104240 | 1850 | 477300 | 258 | 258 |  | 258 | 100% | 4280 | 1104240 | 1850 | 477300 |  | 477300 |  |  | Phoenix Dactylifera(PD) |  |  |  |  | 1850 | 258 | 477300 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 258 | 258 |  | 258 | [7 empty] | 0 | 01 | Phoenix Dactylifera(PD) |  | Ea | 1850 |  | 1850 | 258 | 477300 | 0 | 0 | 0 | 0 | 0
[21 empty] | 01 |  | SC | Ea | 1850 | 1 | 1850 | 258 | 477300
LS 15 |  | Shrubs and Vines |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
LS 15 |  | Atriplex canescens | nr | 200 | 227 | 45400 | 100 | 20000 | 200 | 200 |  | 200 | 100% | 227 | 45400 | 100 | 20000 |  | 20000 |  |  | Atriplex canescens |  |  |  |  | 100 | 200 | 20000 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 200 | 200 |  | 200 | [7 empty] | 0 | 01 | Atriplex canescens |  | Ea | 100 |  | 100 | 200 | 20000 | 0 | 0 | 0 | 0 | 0
[21 empty] | 01 |  | SC | Ea | 100 | 1 | 100 | 200 | 20000
LS 15 |  | Ref Doc. No. CS/DMm3-P2/AAD-615 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
LS 15 |  | Peltophorum Inerme | nr | 162 | 3524 | 570888 | 750 | 121500 | 162 | 162 |  | 162 | 100% | 3524 | 570888 | 750 | 121500 |  | 121500 |  |  | Peltophorum Inerme |  |  |  |  | 750 | 162 | 121500 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 162 | 162 |  | 162 | [7 empty] | 0 | 01 | Peltophorum Inerme |  | Ea | 750 |  | 750 | 162 | 121500 | 0 | 0 | 0 | 0 | 0
[21 empty] | 01 |  | SC | Ea | 750 | 1 | 750 | 162 | 121500
LS 15 |  | A 50 mm thick layer of gravel for green areas | m³ | 297.6892 | 139 | 41378.7988 | 95 | 28280.474 | 297.6892 | 297.6892 |  | 297.6892 | 100% | 139 | 41378.7988 | 95 | 28280.474 |  | 28280.474 |  |  | A 50 mm thick layer of gravel for green areas |  |  |  |  | 95 | 297.6892 | 28280.474 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 297.6892 | 297.6892 |  | 297.6892 | [7 empty] | 0 | 01 | A 50 mm thick layer of gravel for green areas |  | M³ | 95 |  | 95 | 297.6892 | 28280.474 | 0 | 0 | 0 | 0 | 0
[21 empty] | 01 |  | SC | m³ | 95 | 1 | 95 | 297.6892 | 28280.474
LS 15 |  | Ref. Planting Specifications |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
LS 15 |  | Gravel bed with a thickness of 150 mm for the drainage network | m³ | 144.235 | 139 | 20048.665 | 95 | 13702.325 | 144.235 | 144.235 |  | 144.235 | 100% | 139 | 20048.665 | 95 | 13702.325 |  | 13702.325 |  |  | Gravel bed with a thickness of 150 mm |  |  |  |  | 95 | 144.235 | 13702.325 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 144.235 | 144.235 |  | 144.235 | [7 empty] | 0 | 01 | Gravel bed with a thickness of 150 mm |  | M³ | 95 |  | 95 | 144.235 | 13702.325 | 0 | 0 | 0 | 0 | 0
[21 empty] | 01 |  | SC | M³ | 95 | 1 | 95 | 144.235 | 13702.325
LS 15 |  | Semi-porous membrane | m³ | 470 | 88 | 41360 | 50 | 23500 | 470 | 470 |  | 470 | 100% | 88 | 41360 | 50 | 23500 |  | 23500 |  |  | Semi-porous membrane |  |  |  |  | 50 | 470 | 23500 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 470 | 470 |  | 470 | [7 empty] | 0 | 01 | Semi-porous membrane |  | M³ | 50 |  | 50 | 470 | 23500 | 0 | 0 | 0 | 0 | 0
[21 empty] | 01 |  | SC | M³ | 50 | 1 | 50 | 470 | 23500
LS 15 |  | Sweet soil/sand | m³ |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
LS 15 |  | Cultivation soil | m³ | 239 | 164 | 39196 | 150 | 35850 | 239 | 239 |  | 239 | 100% | 164 | 39196 | 150 | 35850 |  | 35850 | [7 empty] | 150 | 239 | 35850 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 239 | 239 |  | 239 | [7 empty] | 0 | 01 | Cultivation soil |  | M³ | 150 |  | 150 | 239 | 35850 | 0 | 0 | 0 | 0 | 0
[21 empty] | 01 | Cultivation soil | SC | M³ | 150 | 1 | 150 | 239 | 35850
LS 15 |  | Irrigation system for agricultural coordination works |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
LS 15 |  | Design, supply and installation of an irrigation system for agricultural coordination works that works in an integrated manner in all aspects as approved by the owner in the following areas |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0
LS 15 |  | Arterial routes | m | 4194.735 | 642 | 2693019.87 | 450 | 1887630.75 | 4194.735 | 4194.735 |  | 4194.735 | 100% | 642 | 2693019.87 | 450 | 1887630.75 |  | 1887630.75 | [7 empty] | 450 | 4194.735 | 1887630.75 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 4194.735 | 4194.735 |  | 4194.735 | [7 empty] | 0 | 01 | Agricultural irrigation system |  | M | 450 |  | 450 | 4194.735 | 1887630.75 | 0 | 0 | 0 | 0 | 0
[21 empty] | 01 | Agricultural irrigation system | SC | M | 450 | 1 | 450 | 4194.735 | 1887630.75
LS 15 |  | Maintenance |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 1e-19
LS 15 |  | Integrated maintenance and preservation in all aspects | Days | 826 | 2266 | 1871716 | 1665 | 1375290 | 826 | 826 |  | 826 | 100% | 2266 | 1871716 | 1665 | 1375290 |  | 1375290 | [7 empty] | 1665 | 826 | 1375290 | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 826 | 826 |  | 826 | [7 empty] | 0 | 01 | Integrated maintenance and preservation |  | Days | 1665 |  | 1665 | 826 | 1375290 | 0 | 0 | 0 | 0 | 0
[21 empty] | 01 | Integrated maintenance and preservation | SC | Days | 1665 | 1 | 1665 | 826 | 1375290
[6 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 |  | 5 | Original Pay item
[9 empty] | 0 | 0 |  | 0 | [17 empty] | 0 | 0 | 0 | 0 | 0

## Sheet2
Resources | UOM | Rate | Type
Fuel | Ltre | 1.76
Unskilled Labour | HR | 13
Skilled Labor | HR | 17
Bulldozer CAT D9 | HR | 132.304
Bulldozer CAT D8 | HR | 111.568
Bulldozer CAT D4 | HR | 105
Wheel Excavator 20T With Bucket/Hock | HR | 68
Excavator with Bucket 20T | HR | 56
Excavator with Hydraulic Hammer 20T | HR | 58.4
Excavator with Bucket 50T | HR | 131.2
Excavator with Hydraulic Hammer 50T | HR | 150.4
Excavator 75T with Bucket | HR | 236
Excavator 95T with Bucket | HR | 271.2
Backhoe loader | HR | 44
Skid steer Loader with bucket | HR | 36
Grader | HR | 90.4
Wheel Loader | HR | 65.6
Flat Bed Trailer 20T | HR | 52
Trailer LowBed (Hydraulic) | HR | 140
Trailer LowBed (Normal) | HR | 88
Trailer LowBed (Normal)+Flat Bed | HR | 88
Trailer Dump Truck 24 m³ | HR | 56
Dump Truck 16 m³ | HR | 48
Articulated Dumper 24 m³ | HR | 172
Boom Truck 8T | HR | 63.0769
Boom Truck 10T | HR | 67.6923
Mobile Crane 50 ton | HR | 80
Hand Roller 1 Ton | HR | 23.3846
Roller Compactor 2.5 Ton | HR | 25.5385
Roller Compactor 10 Ton | HR | 40
Vibratory Roller Compactor 20 Ton | HR | 134.62
Water Tank Trailer 32,000 Litre | HR | 52
Diesel Tank Trailer 32,000 Litre | HR | 71.2
Water Tanker 12,000 Litre | HR | 36
Water Tanker 18,000 Litre (6x4) | HR | 44
Water Tanker 18,000 Litre (6x6) | HR | 48
Diesel Tanker 18,000 Litre (6x4) | HR | 52
Diesel Tanker 18,000 Litre (6x6) | HR | 65.2308
Store Diesel Tank Trailer 32,000 Litre | HR | 9.6
Plate Compactor | HR | 23
Concrete Cutter | HR | 40
Blasting | M³ | 15
Compaction Water | M³ | 2.8
Screening | M³ | 2
Rock Crushing | M³ | 7
Sand Supply | M³ | 30
Supply Filter backfilling material | M³ | 15
Backfilling Material | M³ | 10
Granular bedding backfilling material | M³ | 70
Filter fabric sheets arround the Gravel | M² | 8
Supply Basecourse Type 1&2 | M³ | 25
Supply bituminous concrete 50 mm | Ton | 250
Supply Asphalt Binder Course | Ton | 200
Supply MC1 | Ton | 2450
Supply RC2 | Ton | 2550
Apply Asphalt Binder Course 3-5 CM | M² | 4
Apply Asphalt Binder Course 7 CM | M² | 4.2
Apply Asphalt Wearing Course 3-5 CM | M² | 4
Apply Asphalt Wearing Course 7 CM | M² | 4.2
Spray MC1 | M² | 1
Spray RC2 | M² | 1
Subbase Transportation 0-60 KM | Ton | 17
Asphalt Transportation 0-60 KM | Ton | 19
Apply Basecourse 16-20 cm (1 Layer) | M² | 5.4
Screed mortar | M³ | 200
Supply Plain Concrete C15 | M³ | 240
Supply Plain Concrete C25 | M³ | 250
Concrete Ready-mix C35 SRC | M³ | 350
Curing, Repairing & Accessories | M³ | 5
Workmanship plain concrete | M³ | 150
Workmanship RC concrete | M³ | 450
Workmanship Thrust Block | M³ | 350
Trench Concrete workmanship | M³ | 150
Trench RC Concrete workmanship | M³ | 300
Screed workmanship | M³ | 200
Supply of steel rebar | Ton | 2500
Supply of steel rebar epoxy coated | Ton | 3500
Supply of bending wire | Kg | 5
Precast Box Conduit Supply | M³ | 2200
Curbstone Supply | m | 18
Curbstone Installation | m | 27
Interlock tiles Supply | M² | 25
Interlock tiles Installation | M² | 20
Supply & apply Chamber Cover, frames | Ea | 3500
Concrete manhole Cover, frames | Ea | 1250
Chamber Pipes Pieces | LS | 150
Supply and apply chamber ladder | Ea | 400
Supply concrete bricks 40*20*20 | M | 150
Masonry mortar | M | 90
Apply masonary works | M | 120
Supply & apply sliding door | LS | 18500
Supply & apply single door | LS | 4750
8 nos Flood Lights with single stand, 250 watts | LS | 219500
Pit for grounding work | LS | 1137.4
Cable pulling pit measuring 600x600 mm | LS | 1447
Supply Floor Surface Channel with grating | M | 150
Supply Pipes Connections | M | 20
Supply & apply external waterproofing | M² | 40
2 Layers Bituminous Application | M² | 10
Supply & apply internal coating | M² | 30
Supply& apply painting for toilets & Chloride | LS | 20000
Supply & apply Steel ladders | LS | 40000
Supply & Install doors and windows | LS | 35500
Reinforced Concrete Tank (Remining Works) | LS | 5251800
Supply and apply construction joints | LS | 1500
Supply & apply HDPE geotextile | M² | 5
Non-woven Geotextile 400gsm Supply | M² | 3.8
Non-woven Geotextile Installation | M² | 0.9
Orange warning Mesh | M² | 0.6
125 mm solid HDPE Pipe DR 11 | M | 35
160 mm solid HDPE Pipe DR 11 | M | 39
200 mm solid HDPE Pipe DR 11 | M | 50
225 mm solid HDPE Pipe DR 11 | M | 75
250 mm solid HDPE Pipe DR 11 | M | 95
280 mm solid HDPE Pipe DR 11 | M | 110
315 mm solid HDPE Pipe DR 11 | M | 145
355 mm solid HDPE Pipe DR 11 | M | 190
400 mm solid HDPE Pipe DR 11 | M | 229.9
500 mm solid HDPE Pipe DR 11 | M | 345
560 mm solid HDPE Pipe DR 11 | M | 510
630 mm solid HDPE Pipe DR 11 | M | 610
710 mm solid HDPE Pipe DR 11 | M | 1222
125 mm HDPE Pipe Installation | M | 18
160 mm HDPE Pipe Installation | M | 20
200 mm HDPE Pipe Installation | M | 25
225 mm HDPE Pipe Installation | M | 28
250 mm HDPE Pipe Installation | M | 30
280 mm HDPE Pipe Installation | M | 33 |  | 160 mm HDPE Fittings & Accessories | M | 25
315 mm HDPE Pipe Installation | M | 38 |  | 200 mm HDPE Fittings & Accessories | M | 30
355 mm HDPE Pipe Installation | M | 44 |  | 315 mm HDPE Fittings & Accessories | M | 130
400 mm HDPE Pipe Installation | M | 50 |  | 400 mm HDPE Fittings & Accessories | M | 180
500 mm HDPE Pipe Installation | M | 55 |  | 630 mm HDPE Fittings & Accessories | M | 250
560 mm HDPE Pipe Installation | M | 60
630 mm HDPE Pipe Installation | M | 60
710 mm HDPE Pipe Installation | M | 120
Supply Elbow 11.5°, diameter 125mm | Ea | 205
Supply Elbow 45°, diameter 125mm | Ea | 215
Supply Elbow 90°, diameter 125mm | Ea | 227.5
Supply Elbow 11.5°, diameter 160mm | Ea | 224.5
Supply Elbow 45°, diameter 160mm | Ea | 229
Supply Elbow 45°, diameter 200 mm | Ea | 260
Supply Elbow 11.25°, diameter 250 mm | Ea | 300
Supply Elbow 22.5°, diameter 250 mm | Ea | 312
Supply Elbow 45°, diameter 250 mm | Ea | 335.4
Supply 90° elbow, diameter 250 mm | Ea | 355
Supply Elbow 11.5°, diameter 280mm | Ea | 791
Supply Elbow 45°, diameter 280mm | Ea | 820
Supply Elbow 90°, diameter 280mm | Ea | 861
Supply 90° elbow, diameter 315 mm | Ea | 830
Supply Elbow 45°, diameter 355 mm | Ea | 835
Supply 90° elbow, diameter 355 mm | Ea | 920
Supply Elbow 11.5°, diameter 500mm | Ea | 1844
Supply Elbow 45°, diameter 500mm | Ea | 1857
Supply Elbow 90°, diameter 500mm | Ea | 1900
Supply Elbow 45°, diameter 560 mm | Ea | 1950
Supply Elbow 90°, diameter 630mm | Ea | 2370
Supply Elbow 45°, diameter 710 mm | Ea | 3472
Supply Elbow 90°, diameter 710 mm | Ea | 4200
M diff 710 mm elbow 22.5 & elbow 45 | Ea | 3325
Supply Tee size mm 125x125x125 | Ea | 288
Supply Tee size mm 160x160x125 | Ea | 307
Supply Tee size mm 160x160x160 | Ea | 345
Supply Tee size mm 280x280x125 | Ea | 935
Supply Tee size mm 280x280x160 | Ea | 958
Supply Tee size mm 280x280x280 | Ea | 1190
Supply Tee size mm 500x500x125 | Ea | 2150
Supply Tee size mm 500x500x280 | Ea | 2459
Supply Tee size mm 500x500x500 | Ea | 2578
Supply Tee size mm 630x630x630 | Ea | 3255
Supply Tee size 200x200x200 mm | Ea | 387
Supply Tee size 225x225x200 mm | Ea | 400
Supply Tee size 225x225x225 mm | Ea | 429
SupplyTee size 250x250x200 mm | Ea | 537
SupplyTee size 250x250x225 mm | Ea | 555
SupplyTee size 250x250x250 mm | Ea | 570
SupplyTee size 355x355x200 mm | Ea | 1065
SupplyTee size 355x355x225 mm | Ea | 1190
SupplyTee size 355x355x250 mm | Ea | 1215
SupplyTee size 355x355x355 mm | Ea | 1350
Supply Tee size 560x560x200 mm | Ea | 2725
Supply Tee size 560x560x250 mm | Ea | 2725
Supply Tee size 560x560x355 mm | Ea | 3200
Supply Tee size 560x560x560 mm | Ea | 3550
Supply Tee size 710x710x200 mm | Ea | 4200
Supply Tee size 710x710x250 mm | Ea | 4650
Supply Tee size 710x710x560 mm | Ea | 5100
Supply Tee size 710x710x710 mm | Ea | 5500
Supply 125 mm closed tube | Ea | 45
Supply 160 mm closed tube | Ea | 55
Supply 200 mm closed tube | Ea | 65
Supply 225 mm closed tube | Ea | 72
Supply 250 mm closed tube | Ea | 89
Supply 280 mm closed tube | Ea | 89
Supply 355 mm closed tube | Ea | 310
Supply 500 mm closed tube | Ea | 640
Supply 560 mm closed tube | Ea | 810
Supply 630 mm closed tube | Ea | 810
Supply Reducer size 125x160 mm | Ea | 285
Supply Reducer size 280*125 mm | Ea | 320
Supply Reducer size 125x500 mm | Ea | 1600
Supply Reducer size 280x500 mm | Ea | 2200
Supply Reducer size 500x630 mm | Ea | 2750
Supply Gate Valve 125 mm | Ea | 750
Fitting and Accessories 125 | Ea | 75
Installation Valve 125mm | Ea | 100
Supply Gate Valve 160 mm | Ea | 915
Fitting and Accessories 160 | Ea | 91.5
Installation Valve 160mm | Ea | 100
Supply Gate Valve 200 mm | Ea | 1268
Fitting and Accessories 200 | Ea | 126.8
Installation Valve 200mm | Ea | 150
Supply Gate Valve 225 mm | Ea | 1552
Fitting and Accessories 225 | Ea | 155.2
Installation Valve 225mm | Ea | 150
Supply Gate Valve 250 MM | Ea | 1700
Supply Air Valve 250 MM | Ea | 1870
Fitting and Accessories 250 | Ea | 170
Installation Valve 250mm | Ea | 150
Supply Gate Valve 280 MM | Ea | 1870
Supply Air Valve 280 MM | Ea | 2160
Fitting and Accessories 280 | Ea | 170
Installation Valve 280mm | Ea | 200
Supply Gate Valve 315 MM | Ea | 2200
Supply Air Valve 315 MM | Ea | 2825
Fitting and Accessories 315 | Ea | 220
Installation Valve 315mm | Ea | 200
Butterfly Valve for 355mm | Ea | 4550
Fitting and Accessories 355 | Ea | 455
Installation Valve 355mm | Ea | 200
Supply Butterfly Valve 500 MM | Ea | 7210
Supply Air Valve 500 MM | Ea | 7750
Fitting and Accessories 500 | Ea | 721
Installation Valve 500mm | Ea | 1500
Supply Butterfly Valve 560 MM | Ea | 8250
Fitting and Accessories 560 | Ea | 825
Installation Valve 560mm | Ea | 250
Supply Butterfly Valve 630 MM | Ea | 9750
Supply Air Valve 630 MM | Ea | 10150
Fitting and Accessories 630 | Ea | 975
Installation Valve 630mm | Ea | 1500
Supply Butterfly Valve 710 MM | Ea | 10250
Fitting and Accessories 710 | Ea | 1025
Installation Valve 710mm | Ea | 400
Supply & Install 3-outlet fire nozzle | LS | 8531
Supply & apply Flow Meter 125 mm | Ea | 11757.36
Supply & apply Flow Meter 280 mm | Ea | 13616.99
Supply & apply Flow Meter 355 mm | Ea | 16328.61
Supply & apply Flow Meter 500 mm | Ea | 26328.61
Supply & apply Flow Meter 560 mm | Ea | 35250
Supply & apply Flow Meter 710 mm | Ea | 48500
Supply & apply Flow Meter 800 mm | Ea | 175250
Supply & apply KW250 elec water pump 295 l/s | Ea | 630093.75
Supply & apply elec fire water pump 64 l/s | Ea | 193875
Supply & apply Diesel fire water pump 64 l/s | Ea | 174487.5
Supply & apply Jockey elec fire pump 64 l/s | Ea | 69937.5
Supply & apply Submersible fire pump 10 l/s | Ea | 49115
Surge vessel and pipe work | Ea | 28500
500 KVA generator with umbrella tank | LS | 1181727.9412
Supply and apply Chlorination device | LS | 323462.5
Supply & apply lighting Poles with laminars | LS | 9500
Supply & apply Poles Foundations | LS | 750
Electric source (Junction Boxes, cables, .. Etc) | LS | 1500
Sewage pumping station 428 l/s | LS | 2820451.1194
2 pumps discarge 86 l/s & 325 l/s head 25 m | LS | 3601579.3478
2 pumps discarge 55 l/s head 35 m | LS | 1153556.25
2 pumps discarge 30 l/s & 115 l/s head 17 m | LS | 2563458.3333
3 pumps discarge 100 l/s head 22 m | LS | 1047355.8333
Odor Control Unit & Connection | LS | 145500
In-line Booster Station | LS | 164793.75
In-line Booster Station V | LS | 1812500
In-line Booster Station K | LS | 715000
Grid mesh 35mm raked bar SS 316 | LS | 21972.5
100 KVA generator with umbrella tank | LS | 345270
2 wells internal dimensions 12m, depth 11m | LS | 662420.3793
2 wells internal dimensions 3m, depth 9m | LS | 157093.517
2 wells internal dimensions 5m, depth 11m | LS | 438304.67
1 wells internal dimensions 4m, depth 11m | LS | 272802.6305
Valve chamber | LS | 214682.1916
Flow meter room | LS | 104088.4115
Engine Control Center Building | LS | 77660.2699
Engine Control Center Building | LS | 754820
Valves, fittings and flow meters different sizes | LS | 65500
Pump station inc connect pipes, fittings, valves | LS | 131835
UPVC Pipe 50 mm | M | 4
UPVC Pipe 150 mm | M | 33.5
UPVC Pipe 160 mm | M | 33.5
UPVC Pipe 200 mm | M | 40
UPVC Pipe 250 mm | M | 52
UPVC Pipe 300 mm | M | 80
UPVC Pipe 315 mm | M | 95
UPVC Pipe 400 mm | M | 135
UPVC Pipe 600 mm | M | 275
UPVC Fitting 50 mm | M | 2
UPVC Fitting 150 mm | M | 2
UPVC Fitting 160 mm | M | 2
UPVC Fitting 200 mm | M | 4
UPVC Fitting 250 mm | M | 5
UPVC Fitting 300 mm | M | 8
UPVC Fitting 315 mm | M | 10
UPVC Fitting 400 mm | M | 14
UPVC Fitting 600 mm | M | 28
GRP Pipe 350 mm | M | 105
GRP Pipe 400 mm | M | 144
GRP Pipe 450 mm | M | 180
GRP Pipe 500 mm | M | 250
GRP Pipe 600 mm | M | 290
GRP Pipe 700 mm | M | 350
GRP Pipe 800 mm | M | 430
GRP Pipe 1000 mm | M | 557
GRP Fitting 350 mm | M | 10
GRP Fitting 400 mm | M | 15
GRP Fitting 450 mm | M | 18
GRP Fitting 500 mm | M | 25
GRP Fitting 600 mm | M | 29
GRP Fitting 700 mm | M | 35
GRP Fitting 800 mm | M | 43
GRP Fitting 1000 mm | M | 60
Workmanship GRP pipe 350 mm | M | 40
Workmanship GRP pipe 400 mm | M | 50
Workmanship GRP pipe 450 mm | M | 52
Workmanship GRP pipe 500 mm | M | 55
Workmanship GRP pipe 600 mm | M | 60
Workmanship GRP pipe 700 mm | M | 65
Workmanship GRP pipe 800 mm | M | 72
Workmanship GRP pipe 1000 mm | M | 80
Warning Tape 250 mic 305 m roll | Roll | 175
Pipe Testing and Commissioning | M | 5
Steel Shoring D=2.5 M | M | 35
Steel Shoring D>3.0 M | M | 60
Precast Insulated Manhole 2*1*1 | Ea | 7450
GRP manhole Dia 1200 mm D=1.5 m W Cover | Ea | 2590
GRP manhole Dia 1200 mm D=2.0 m W Cover | Ea | 3100
GRP manhole Dia 1200 mm D=2.5 m W Cover | Ea | 3600
GRP manhole Dia 1200 mm D=3.0 m W Cover | Ea | 4500
GRP manhole Dia 1200 mm D=3.5 m W Cover | Ea | 5350
GRP manhole Dia 1200 mm D=4.0 m W Cover | Ea | 6300
GRP manhole Dia 1200 mm D=4.5 m W Cover | Ea | 7200
GRP manhole Dia 1200 mm D=5.0 m W Cover | Ea | 8000
GRP manhole Dia 1200 mm D=5.5 m W Cover | Ea | 8850
GRP manhole Dia 1200 mm D=6.0 m W Cover | Ea | 9650
GRP manhole Dia 1500 mm D=1.5 m W Cover | Ea | 3470
GRP manhole Dia 1500 mm D=2.0 m W Cover | Ea | 4230
GRP manhole Dia 1500 mm D=2.5 m W Cover | Ea | 4710
GRP manhole Dia 1500 mm D=3.0 m W Cover | Ea | 5150
GRP manhole Dia 1500 mm D=3.5 m W Cover | Ea | 5800
GRP manhole Dia 1500 mm D=4.0 m W Cover | Ea | 6550
GRP manhole Dia 1500 mm D=4.5 m W Cover | Ea | 7350
GRP manhole Dia 1500 mm D=5.0 m W Cover | Ea | 8150
GRP manhole Dia 1500 mm D=5.5 m W Cover | Ea | 8950
GRP manhole Dia 1500 mm D=6.0 m W Cover | Ea | 9800
GRP manhole Dia 1500 mm D=6.5 m W Cover | Ea | 10650
GRP manhole Dia 1500 mm D=7.0 m W Cover | Ea | 11600
GRP manhole Dia 1800 mm D=2.0 m W Cover | Ea | 5085
GRP manhole Dia 1800 mm D=2.5 m W Cover | Ea | 5895
GRP manhole Dia 1800 mm D=3.0 m W Cover | Ea | 6705
GRP manhole Dia 1800 mm D=3.5 m W Cover | Ea | 7515
GRP manhole Dia 1800 mm D=4.0 m W Cover | Ea | 8500
GRP manhole Dia 1800 mm D=4.5 m W Cover | Ea | 9450
GRP manhole Dia 1800 mm D=5.0 m W Cover | Ea | 10500
GRP manhole Dia 1800 mm D=5.5 m W Cover | Ea | 11450
GRP manhole Dia 1800 mm D=6.0 m W Cover | Ea | 12550
GRP manhole Dia 2000 mm D=6.0 m W Cover | Ea | 14350
GRP manhole Dia 2000 mm D=7.0 m W Cover | Ea | 17850
Brick & Masonery for Manhole Neck | LS | 1500
Manhole Back drop PCs | LS | 3500
Supply Siphon Tubes | M | 275
Supply precast NJB | Ea | 450
Supply & apply grouted riprap 30 cm | M² | 80
Supply & apply grouted riprap 25 cm | M² | 70
2 layers 4mm bituminous waterproofing membrane | M² | 80
Polyethylene sheet | M² | 2
Subgrade Layer | M³ | 40
Crushed Aggregate Base Course | M³ | 80
Bituminous Prime Coat | M² | 3
Polyprime SB, 200ltr/drum | Litre | 2
Supply and applying Electric connections | LS | 25000
Supply and applying Mechnical connections | LS | 35000
Supply and Apply Plants with the Soil Mix | LS | 10000
Supply AC Unit | LS | 13000
Supply cabines Doors | LS | 6500
Maintaining the Offices Floor and slabs | LS | 25000
Maintaining the Offices Wall Paints | LS | 11000
Supply and apply furnitures | LS | 9000
Soil testing equipment | LS | 94000
Asphalt testing equipment | LS | 112800
Concrete testing equipment | LS | 94000
Hiring Two Technicians with Vechicle | Months | 25000
Computers and surveying devices | LS | 100000

## Level 3 (hidden)
|  | PAY ITEM No. (Refer Attach "D" Article 2-03) | DESCRIPTION OF ITEMS | Budget Amount | Subcontractor | Material | Manpower | Machinery
ENVIRONMENTAL WORKS | STORM DRAINAGE NETWORK |  | Direct Budget | 121000231.7286
ENVIRONMENTAL WORKS | STORM DRAINAGE NETWORK |  | Material | 219500
ENVIRONMENTAL WORKS | STORM DRAINAGE NETWORK | 15.4 | Manpower | 219500
ENVIRONMENTAL WORKS | STORM DRAINAGE NETWORK | 15.4.1 | Machinery | 219500 | #REF! | #REF! | #REF! | #REF! | #REF!
ENVIRONMENTAL WORKS | STORM DRAINAGE NETWORK |  | Subcontractor | 219500
[5 empty] | 1658389.6035 | 16442314.458 | 2825018.0948 | 5795428.3859
ENVIRONMENTAL WORKS | STORM DRAINAGE NETWORK |  | Indirect Budget | 37202526.9595
ENVIRONMENTAL WORKS | STORM DRAINAGE NETWORK |  | Total Project Budget | 158202758.6881

## Summary (hidden)
overall BUDGET Summary
PROJECT NAME: | MODON 3rd Industrial City Phase 1D – Part 2 – Dammam | REV. DATE.: | 2025-08-05
SITE LOCATION: | Eastern Region | REV. NO.: | 0
START DATE: | 2025-05-01 | PROJECT CODE: | S1-CNS-EP-MOD-2025.3
DURATION: | 16 MTH | CONTRACT PRICE : | 233776076.7635
FINISH DATE: | 2027-05-31 | BU Number: | 0
REV. FINISH DATE: | 0
No. | Description | Budget | Remark
1 | Direct Cost | 121000231.7286
2 | Indirect Cost | 37202526.9595
3 | Contingency Reserve | 23377607.6764 | 10%
| Total Amount | 181580366.3645
| Items | Amount | %
A | Contract Price | 233776076.7635 | 100%
B | Direct Cost | -121000231.7286 | 51.76%
C | Indirect Cost | -37202526.9595 | 15.91%
D | Contingency Reserve | -23377607.6764 | 10%
E= (B+C+D) | Sub-Total | -181580366.3645 | 77.67%
F=(A+E) | Gross Margin | 52195710.399 | 22.33%
G | Advance Payment Fees | -175332.0576 | 0.075%
H | Performance Bond Fees | -70017 | 0.02995%
I | LC Fees | 0 | 0%
J | CAR Insurance | -338506.86 | 0.1448%
K | Management Reserve | -1168880.3838 | 0.5%
L | General and Administrative Expenses (G&A) | -11688803.8382 | 5%
K=(F+G+H+I+J+K+L) | Net Profit Margin | 38754170.2595 | 16.58%